## DATA
ASSET REF | ASSET NAME | PO NUMBER | ACC REF | CONTRACTOR / CONSULTANTS | INITIAL | CONTRACTOR / CONSULTANT / DIRECT ACTUAL | PACKAGE | CODE 1 | CODE 2 | CODE 3 | CODE 4 | ACC 1 | ACC 2 | ACC 3
1.TB.01.003.01 | AMAALAYachtClub | 2210224 | 003C13 | Soil Improvement Contracting | SOIL IMPROVE | Contractor | Triple Bay Wide Ground Improvement | CN | 01 | CN.003C13 | Soil Improvement Contracting - 2210224 | 1TB01006.01.CN.003C13.00 | 1TB01006.01.CN.003C13.01 | 1TB01006.01.CN.003C13.02
1.TB.01.003.01 | AMAALAYachtClub | 2210167 | 003D04 | Applied Technology and Management Inc (Dubai BR) | APPLIED TECH | Consultant | Rapid Peer Review of AMAALA Existing Design of Yachting and Marina Facilities | PS | 01 | PS.003D04 | Applied Technology and Management Inc (Dubai BR) - 2210167 | 1TB01006.01.PS.003D04.00 | 1TB01006.01.PS.003D04.01 | 1TB01006.01.PS.003D04.02
1.TB.01.003.01 | AMAALAYachtClub | 2200445 | 003D01 | Dewan Architects & Engineers | DEWAN | Consultant | Triple Bay Hijaz Yacht Club - Lead Consultant Services | PS | 01 | PS.003D01 | Dewan Architects & Engineers - 2200445 | 1TB01006.01.PS.003D01.00 | 1TB01006.01.PS.003D01.01 | 1TB01006.01.PS.003D01.02
1.TB.01.003.01 | AMAALAYachtClub | 2200375 | 003D03 | HKS Architects Limited | HKS | Consultant | Triple Bay Marine Yacht Club - Design Architect Consultancy Services | PS | 01 | PS.003D03 | HKS Architects Limited - 2200375 | 1TB01006.01.PS.003D03.00 | 1TB01006.01.PS.003D03.01 | 1TB01006.01.PS.003D03.02
1.TB.01.003.01 | AMAALAYachtClub | 2200010 | 003D02 | HKS Architects Limited | HKS | Consultant | Design Competition | PS | 01 | PS.003D02 | HKS Architects Limited - 2200010 | 1TB01006.01.PS.003D02.00 | 1TB01006.01.PS.003D02.01 | 1TB01006.01.PS.003D02.02
1.TB.01.003.01 | AMAALAYachtClub | 2220032 | 003C14 | NSCC International Saudi Contracting | NSCC | Contractor | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | CN | 01 | CN.003C14 | NSCC International Saudi Contracting - 2220032 | 1TB01006.01.CN.003C14.00 | 1TB01006.01.CN.003C14.01 | 1TB01006.01.CN.003C14.02
1.TB.01.003.01 | AMAALAYachtClub | 2220038 | 003C20 | Green Business Certification Inc | GREEN BUSSINESS | Direct Actuals | Sustainability Accreditation, third party technical reviews and verification of LEED-registered AMAALA Projects | CN | 01 | CN.003C20 | Green Business Certification Inc - 2220038 | 1TB01006.01.CN.003C20.00 | 1TB01006.01.CN.003C20.01 | 1TB01006.01.CN.003C20.02
1.TB.01.003.01 | AMAALAYachtClub | 2230023 | 003C03 | Saudi Arabian Baytur Construction Company | BAYTUR | Contractor | Construction Contract - Site Enabling, Civil Works, Structural Concrete, Structural Steel, BOH Finishes, Building Envelope, MEP Including Tertiary Infrastructure & ICT/ELV | CN | 01 | CN.003C03 | Saudi Arabian Baytur Construction Company - 2230023 | 1TB01006.01.CN.003C03.00 | 1TB01006.01.CN.003C03.01 | 1TB01006.01.CN.003C03.02
1.TB.01.003.01 | AMAALAYachtClub | 2230042 | 003D05 | LANGAN International UK, LTD | LANGAN INNTERNATIONAL | Consultant | Geotechnical Consultancy Services (Yacht Club) - Peer Review | PS | 01 | PS.003D05 | LANGAN International UK, LTD - 2230042 | 1TB01006.01.PS.003D05.00 | 1TB01006.01.PS.003D05.01 | 1TB01006.01.PS.003D05.02
1.TB.01.003.01 | AMAALAYachtClub | 2230075 | 003C21 | Medtel - W.N | MEDTEL | Contractor | Sto Façade Mock-Up | CN | 01 | CN.003C21 | Medtel - W.N - 2230075 | 1TB01006.01.CN.003C21.00 | 1TB01006.01.CN.003C21.01 | 1TB01006.01.CN.003C21.02
1.TB.01.003.01 | AMAALAYachtClub | 2230031 | 003F02 | Saudi Consolidated Engineering Company - Khatib & Alami | KHATIB & ALAMI | Consultant | Construction Supervision Services - AMAALA Yacht Club (Call off Order No: 003) | MS | 01 | MS.003F02 | Saudi Consolidated Engineering Company - Khatib & Alami - 2230031 | 1TB01006.01.MS.003F02.00 | 1TB01006.01.MS.003F02.01 | 1TB01006.01.MS.003F02.02
1.TB.01.003.01 | AMAALAYachtClub | 699226 | 003D06 | Ministry of Municipality and Rural Affairs | MINISTRY | Direct Actuals | Permit Fees | PS | 01 | PS.003D06 | Ministry of Municipality and Rural Affairs - 699226 | 1TB01006.01.PS.003D06.00 | 1TB01006.01.PS.003D06.01 | 1TB01006.01.PS.003D06.02
1.TB.01.003.01 | AMAALAYachtClub | 2230041 | 003F01 | Zuhair Fayez Partnership Consultants (ZFP) | ZUHAIR | Consultant | Third Party Authority for Multidisciplinary Review & Certification Endorsement (Call off Order No: 004) | PS | 01 | PS.003F01 | Zuhair Fayez Partnership Consultants (ZFP) - 2230041 | 1TB01006.01.PS.003F01.00 | 1TB01006.01.PS.003F01.01 | 1TB01006.01.PS.003F01.02
1.TB.01.003.01 | AMAALAYachtClub | 2230178 | 003F03 | Elevator Systems Contracting Company (ESCCO) | ESCCO | Contractor | Supply and Installation of the Vertical Transportation System Works (Call Off Order No.001) | CN | 01 | CN.003F03 | Elevator Systems Contracting Company (ESCCO) - 2230178 | 1TB01006.01.CN.003F03.00 | 1TB01006.01.CN.003F03.01 | 1TB01006.01.CN.003F03.02
1.TB.01.003.01 | AMAALAYachtClub | 2230180 | 003F04 | Jensen Hughes Saudi Arabia, LLC | JENSEN | Consultant | Third-Party Authority for Fire and Life Safety Review & Certification Endorsement (Call off Order No: 007) | PS | 01 | PS.003F04 | Jensen Hughes Saudi Arabia, LLC - 2230180 | 1TB01006.01.PS.003F04.00 | 1TB01006.01.PS.003F04.01 | 1TB01006.01.PS.003F04.02
1.TB.01.003.01 | AMAALAYachtClub | 2230205 | 003C08 | Abdulaziz Al Raqtan and Partners Company for Trading and Industry Company | ABDULAZIZ | Contractor | Kitchen & Laundry Works | CN | 01 | CN.003C08 | Abdulaziz Al Raqtan and Partners Company for Trading and Industry Company - 2230205 | 1TB01006.01.CN.003C08.00 | 1TB01006.01.CN.003C08.01 | 1TB01006.01.CN.003C08.02
1.TB.01.003.01 | AMAALAYachtClub | 2230416 | 003C09 | DEPA Saudi Arabia for Contracting and Interior Decoration Co. Ltd | DEPA | Contractor | Fit-out works for Amaala Yacht Club | CN | 01 | CN.003C09 | DEPA Saudi Arabia for Contracting and Interior Decoration Co. Ltd - 2230416 | 1TB01006.01.CN.003C09.00 | 1TB01006.01.CN.003C09.01 | 1TB01006.01.CN.003C09.02
1.TB.01.003.01 | AMAALAYachtClub | 2240110 | 003C27 | Aluminium Technology Auxiliary Industries (Alutec) WLL | ALUTEC | Contractor | Aluminium & Glazing Works for the AMAALA Yacht Club | CN | 01 | CN.003C27 | Aluminium Technology Auxiliary Industries (Alutec) WLL - 2240110 | 1TB01006.01.CN.003C27.00 | 1TB01006.01.CN.003C27.01 | 1TB01006.01.CN.003C27.02
1.TB.01.003.01 | AMAALAYachtClub | 2240357 | 003F07 | Euro Consult For Engineering Consultancy | EURO | Consultant | Statutory Compliance Consultancy Services (Call Off Order No: 006) -AMAALA Yacht Club | PS | 01 | PS.003F07 | Euro Consult For Engineering Consultancy - 2240357 | 1TB01006.01.PS.003F07.00 | 1TB01006.01.PS.003F07.01 | 1TB01006.01.PS.003F07.02
1.TB.01.003.01 | AMAALAYachtClub | 2240202 | 003F06 | Areen Design Limited | AREEN | Consultant | FF&E Procurement Services | FFEOSE | 01 | FFEOSE.003F06 | Areen Design Limited - 2240202 | 1TB01006.01.FFEOSE.003F06.00 | 1TB01006.01.FFEOSE.003F06.01 | 1TB01006.01.FFEOSE.003F06.02
1.TB.01.003.01 | AMAALAYachtClub | 2240377 | 003F08 | CML International Saudi LLC | CML | Consultant | Independent Commissioning Agent Services (ICA) (Call off Order No: 007) - AMAALA Yacht Club | PS | 01 | PS.003F08 | CML International Saudi LLC - 2240377 | 1TB01006.01.PS.003F08.00 | 1TB01006.01.PS.003F08.01 | 1TB01006.01.PS.003F08.02
1.TB.01.003.01 | AMAALAYachtClub | 2240427 | 003C31 | MAS Engineering & Construction Company LTD | MAS | Contractor | Provision of construction manpower | CN | 01 | CN.003C31 | MAS Engineering & Construction Company LTD - 2240427 | 1TB01006.01.CN.003C31.00 | 1TB01006.01.CN.003C31.01 | 1TB01006.01.CN.003C31.02
1.TB.01.003.01 | AMAALAYachtClub | 2240461 | 003C32 | MAS Engineering & Construction Company LTD | MAS | Contractor | Ampitheatre Concrete Works | CN | 01 | CN.003C32 | MAS Engineering & Construction Company LTD - 2240461 | 1TB01006.01.CN.003C32.00 | 1TB01006.01.CN.003C32.01 | 1TB01006.01.CN.003C32.02
1.TB.01.003.01 | AMAALAYachtClub | 2250012 | 003C34 | Alfanar Company | ALFANAR | Contractor | Construction Manpower Services | CN | 01 | CN.003C34 | Alfanar Company - 2250012 | 1TB01006.01.CN.003C34.00 | 1TB01006.01.CN.003C34.01 | 1TB01006.01.CN.003C34.02
1.TB.01.003.01 | AMAALAYachtClub | 2250084 | 003C33 | Armetal Metal Industries Co. Ltd | ARMETAL | Contractor | Stainless Steel Reflecting Ceiling Works | CN | 01 | CN.003C33 | Armetal Metal Industries Co. Ltd - 2250084 | 1TB01006.01.CN.003C33.00 | 1TB01006.01.CN.003C33.01 | 1TB01006.01.CN.003C33.02
1.TB.01.003.01 | AMAALAYachtClub | 2250010 | 003C36 | Al Rajhi Company For Cooperative Insurance | AL RAJHI | Contractor | OCIP Insurance Premium (P0123­CAR­TCRO­00076041/E16) | CN | 01 | CN.003C36 | Al Rajhi Company For Cooperative Insurance - 2250010 | 1TB01006.01.CN.003C36.00 | 1TB01006.01.CN.003C36.01 | 1TB01006.01.CN.003C36.02
1.TB.01.003.01 | AMAALAYachtClub | 2250069 | 003C35 | Abu Dhabi Precast LLC | PRECAST | Contractor | Amaala Triple Bay – Marina Hotel 3 - Building Envelope GRC Works Package_CONTRACT CANCELLED_CONTRACT VALUE AED 7,640,027.22 (SAR 7,850,127.97) | CN | 01 | CN.003C35 | Abu Dhabi Precast LLC - 2250069 | 1TB01006.01.CN.003C35.00 | 1TB01006.01.CN.003C35.01 | 1TB01006.01.CN.003C35.02
1.TB.01.003.01 | AMAALAYachtClub | 2250063 | 003F09 | Euro Consult For Engineering Consultancy | EURO | Consultant | Statutory Compliance Consultancy Services (Call Off Order No: 027) | PS | 01 | PS.003F09 | Euro Consult For Engineering Consultancy - 2250063 | 1TB01006.01.PS.003F09.00 | 1TB01006.01.PS.003F09.01 | 1TB01006.01.PS.003F09.02
1.TB.01.003.01 | AMAALAYachtClub | 2250145 | 003C37 | Hassan Allam Construction Saudi Limited | HASSAN ALLAM | Contractor | Scaffolding Services | CN | 01 | CN.003C37 | Hassan Allam Construction Saudi Limited - 2250145 | 1TB01006.01.CN.003C37.00 | 1TB01006.01.CN.003C37.01 | 1TB01006.01.CN.003C37.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C66 | Sami General Contracting Est. | SAMI GENEERAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C66 | Sami General Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C66.00 | 1TB01006.01.CN.003C66.01 | 1TB01006.01.CN.003C66.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C42 | Saad Al Easa - Metal Industry | SAAD | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C42 | Saad Al Easa - Metal Industry - BAYTUR_PAYMENT | 1TB01006.01.CN.003C42.00 | 1TB01006.01.CN.003C42.01 | 1TB01006.01.CN.003C42.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C70 | Aldrees Petroleum and Transport Services Company | ALDREES | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C70 | Aldrees Petroleum and Transport Services Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C70.00 | 1TB01006.01.CN.003C70.01 | 1TB01006.01.CN.003C70.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C69 | Salim Hamed Cleaning | SALIM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C69 | Salim Hamed Cleaning - BAYTUR_PAYMENT | 1TB01006.01.CN.003C69.00 | 1TB01006.01.CN.003C69.01 | 1TB01006.01.CN.003C69.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C65 | Eastern Horizon Foundation Transportation Comp. | EASTERN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C65 | Eastern Horizon Foundation Transportation Comp. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C65.00 | 1TB01006.01.CN.003C65.01 | 1TB01006.01.CN.003C65.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C64 | JAK Generation Cont. Co. LLC | JAK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C64 | JAK Generation Cont. Co. LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C64.00 | 1TB01006.01.CN.003C64.01 | 1TB01006.01.CN.003C64.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C67 | Clean Coast For Contracting | CLEAN COAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C67 | Clean Coast For Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C67.00 | 1TB01006.01.CN.003C67.01 | 1TB01006.01.CN.003C67.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C61 | Al Rai Modern Water Factory | AL RAI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C61 | Al Rai Modern Water Factory - BAYTUR_PAYMENT | 1TB01006.01.CN.003C61.00 | 1TB01006.01.CN.003C61.01 | 1TB01006.01.CN.003C61.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C57 | Juffali Technical Equipment Company | JUFFALI TTECHNICAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C57 | Juffali Technical Equipment Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C57.00 | 1TB01006.01.CN.003C57.01 | 1TB01006.01.CN.003C57.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C63 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton | INTELLIGENT | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C63 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton - BAYTUR_PAYMENT | 1TB01006.01.CN.003C63.00 | 1TB01006.01.CN.003C63.01 | 1TB01006.01.CN.003C63.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C71 | Al-Anan Travels and Tours | AL ANAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C71 | Al-Anan Travels and Tours - BAYTUR_PAYMENT | 1TB01006.01.CN.003C71.00 | 1TB01006.01.CN.003C71.01 | 1TB01006.01.CN.003C71.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C58 | Madar Building Material Co. | MADAR BUIILDING | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C58 | Madar Building Material Co. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C58.00 | 1TB01006.01.CN.003C58.01 | 1TB01006.01.CN.003C58.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C53 | Factory Of USG Middle East Ltd. Co. | FACTORY | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C53 | Factory Of USG Middle East Ltd. Co. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C53.00 | 1TB01006.01.CN.003C53.01 | 1TB01006.01.CN.003C53.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C73 | M Mohammad Alharbi Medical Company | AL HARBI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C73 | M Mohammad Alharbi Medical Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C73.00 | 1TB01006.01.CN.003C73.01 | 1TB01006.01.CN.003C73.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C39 | Issam Kabani and Partners | ISSAM KABBANI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C39 | Issam Kabani and Partners - BAYTUR_PAYMENT | 1TB01006.01.CN.003C39.00 | 1TB01006.01.CN.003C39.01 | 1TB01006.01.CN.003C39.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C43 | Abu Dhabi Precast LLC | PRECAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C43 | Abu Dhabi Precast LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C43.00 | 1TB01006.01.CN.003C43.01 | 1TB01006.01.CN.003C43.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C115 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. | AHMED BIN SALEM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C115 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C115.00 | 1TB01006.01.CN.003C115.01 | 1TB01006.01.CN.003C115.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C87 | Bahamdoon Trading Co | BAHAMDOON | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C87 | Bahamdoon Trading Co - BAYTUR_PAYMENT | 1TB01006.01.CN.003C87.00 | 1TB01006.01.CN.003C87.01 | 1TB01006.01.CN.003C87.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C84 | Energy & Building Masters | ENERGY | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C84 | Energy & Building Masters - BAYTUR_PAYMENT | 1TB01006.01.CN.003C84.00 | 1TB01006.01.CN.003C84.01 | 1TB01006.01.CN.003C84.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C59 | Fosam Company LTD | FOSAM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C59 | Fosam Company LTD - BAYTUR_PAYMENT | 1TB01006.01.CN.003C59.00 | 1TB01006.01.CN.003C59.01 | 1TB01006.01.CN.003C59.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C56 | Glow Arabia Trading | GLOW | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C56 | Glow Arabia Trading - BAYTUR_PAYMENT | 1TB01006.01.CN.003C56.00 | 1TB01006.01.CN.003C56.01 | 1TB01006.01.CN.003C56.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C54 | Nextware International Supply | NEXTWARE | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C54 | Nextware International Supply - BAYTUR_PAYMENT | 1TB01006.01.CN.003C54.00 | 1TB01006.01.CN.003C54.01 | 1TB01006.01.CN.003C54.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C86 | Wood Expert | WOOD | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C86 | Wood Expert - BAYTUR_PAYMENT | 1TB01006.01.CN.003C86.00 | 1TB01006.01.CN.003C86.01 | 1TB01006.01.CN.003C86.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C85 | Lumi Rental Co. | LUMI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C85 | Lumi Rental Co. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C85.00 | 1TB01006.01.CN.003C85.01 | 1TB01006.01.CN.003C85.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C40 | Noreom Company Limited | NOREOM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C40 | Noreom Company Limited - BAYTUR_PAYMENT | 1TB01006.01.CN.003C40.00 | 1TB01006.01.CN.003C40.01 | 1TB01006.01.CN.003C40.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C41 | Raddad Al Madinah for General Contracting | RADDAD | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C41 | Raddad Al Madinah for General Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C41.00 | 1TB01006.01.CN.003C41.01 | 1TB01006.01.CN.003C41.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C44 | Medtel - W.N | MEDTEL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C44 | Medtel - W.N - BAYTUR_PAYMENT | 1TB01006.01.CN.003C44.00 | 1TB01006.01.CN.003C44.01 | 1TB01006.01.CN.003C44.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C45 | Virtual Projects DMCC | VIRTUAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C45 | Virtual Projects DMCC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C45.00 | 1TB01006.01.CN.003C45.01 | 1TB01006.01.CN.003C45.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C46 | Jameel Mohammed Hussain Alqatafa Cont.Est. | JAMEEL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C46 | Jameel Mohammed Hussain Alqatafa Cont.Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C46.00 | 1TB01006.01.CN.003C46.01 | 1TB01006.01.CN.003C46.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C47 | Gesr Alarab | GESR | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C47 | Gesr Alarab - BAYTUR_PAYMENT | 1TB01006.01.CN.003C47.00 | 1TB01006.01.CN.003C47.01 | 1TB01006.01.CN.003C47.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C48 | National Fire Fighting Manufacturing Company - NAFFCO | NAFFCO | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C48 | National Fire Fighting Manufacturing Company - NAFFCO - BAYTUR_PAYMENT | 1TB01006.01.CN.003C48.00 | 1TB01006.01.CN.003C48.01 | 1TB01006.01.CN.003C48.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C49 | Yaz Development Contracting | YAZ | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C49 | Yaz Development Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C49.00 | 1TB01006.01.CN.003C49.01 | 1TB01006.01.CN.003C49.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C50 | Abeer Manawer Al-Shamari Contracting Est. | ABEER | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C50 | Abeer Manawer Al-Shamari Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C50.00 | 1TB01006.01.CN.003C50.01 | 1TB01006.01.CN.003C50.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C51 | Brooq Alamaan Trading Company | BROOQ ALAAMAAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C51 | Brooq Alamaan Trading Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C51.00 | 1TB01006.01.CN.003C51.01 | 1TB01006.01.CN.003C51.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C83 | Yaz Development Contracting | YAZ | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C83 | Yaz Development Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C83.00 | 1TB01006.01.CN.003C83.01 | 1TB01006.01.CN.003C83.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C116 | Arabian Testing Evolution Company | ARABIAN TTESTING | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C116 | Arabian Testing Evolution Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C116.00 | 1TB01006.01.CN.003C116.01 | 1TB01006.01.CN.003C116.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C74 | Abu Nayyan Trading | ABU NAYYAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C74 | Abu Nayyan Trading - BAYTUR_PAYMENT | 1TB01006.01.CN.003C74.00 | 1TB01006.01.CN.003C74.01 | 1TB01006.01.CN.003C74.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C75 | Filter Expert Trading | FILTER | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C75 | Filter Expert Trading - BAYTUR_PAYMENT | 1TB01006.01.CN.003C75.00 | 1TB01006.01.CN.003C75.01 | 1TB01006.01.CN.003C75.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C77 | Arab Company for Laboratories and Soil Branch (ACES) | ACES | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan/Feb) | CN | 01 | CN.003C77 | Arab Company for Laboratories and Soil Branch (ACES) - BAYTUR_PAYMENT | 1TB01006.01.CN.003C77.00 | 1TB01006.01.CN.003C77.01 | 1TB01006.01.CN.003C77.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C92 | Al Hayat Investment | AL HAYAT | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C92 | Al Hayat Investment - BAYTUR_PAYMENT | 1TB01006.01.CN.003C92.00 | 1TB01006.01.CN.003C92.01 | 1TB01006.01.CN.003C92.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C93 | Gesr Alarab | GESR | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C93 | Gesr Alarab - BAYTUR_PAYMENT | 1TB01006.01.CN.003C93.00 | 1TB01006.01.CN.003C93.01 | 1TB01006.01.CN.003C93.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C94 | National Fire Fighting Manufacturing Company - NAFFCO | NAFFCO | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C94 | National Fire Fighting Manufacturing Company - NAFFCO - BAYTUR_PAYMENT | 1TB01006.01.CN.003C94.00 | 1TB01006.01.CN.003C94.01 | 1TB01006.01.CN.003C94.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C95 | Yaz Development Contracting | YAZ | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C95 | Yaz Development Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C95.00 | 1TB01006.01.CN.003C95.01 | 1TB01006.01.CN.003C95.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C96 | Factory Of USG Middle East Ltd. Co. | FACTORY | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C96 | Factory Of USG Middle East Ltd. Co. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C96.00 | 1TB01006.01.CN.003C96.01 | 1TB01006.01.CN.003C96.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C97 | Glow Arabia Trading | GLOW | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C97 | Glow Arabia Trading - BAYTUR_PAYMENT | 1TB01006.01.CN.003C97.00 | 1TB01006.01.CN.003C97.01 | 1TB01006.01.CN.003C97.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C98 | Juffali Technical Equipment Company | JUFFALI TTECHNICAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C98 | Juffali Technical Equipment Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C98.00 | 1TB01006.01.CN.003C98.01 | 1TB01006.01.CN.003C98.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C99 | The International Company For Building Materials LTD Binex | INT COMPANY | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C99 | The International Company For Building Materials LTD Binex - BAYTUR_PAYMENT | 1TB01006.01.CN.003C99.00 | 1TB01006.01.CN.003C99.01 | 1TB01006.01.CN.003C99.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C100 | Fosam Company LTD | FOSAM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C100 | Fosam Company LTD - BAYTUR_PAYMENT | 1TB01006.01.CN.003C100.00 | 1TB01006.01.CN.003C100.01 | 1TB01006.01.CN.003C100.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C101 | Al Rai Modern Water Factory | AL RAI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C101 | Al Rai Modern Water Factory - BAYTUR_PAYMENT | 1TB01006.01.CN.003C101.00 | 1TB01006.01.CN.003C101.01 | 1TB01006.01.CN.003C101.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C102 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton | INTELLIGENT | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C102 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton - BAYTUR_PAYMENT | 1TB01006.01.CN.003C102.00 | 1TB01006.01.CN.003C102.01 | 1TB01006.01.CN.003C102.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C103 | JAK Generation Cont. Co. LLC | JAK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C103 | JAK Generation Cont. Co. LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C103.00 | 1TB01006.01.CN.003C103.01 | 1TB01006.01.CN.003C103.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C104 | Sami General Contracting Est. | SAMI GENEERAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C104 | Sami General Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C104.00 | 1TB01006.01.CN.003C104.01 | 1TB01006.01.CN.003C104.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C105 | Clean Coast For Contracting | CLEAN COAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C105 | Clean Coast For Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C105.00 | 1TB01006.01.CN.003C105.01 | 1TB01006.01.CN.003C105.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C108 | M Mohammad Alharbi Medical Company | AL HARBI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C108 | M Mohammad Alharbi Medical Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C108.00 | 1TB01006.01.CN.003C108.01 | 1TB01006.01.CN.003C108.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C110 | AAMTAC Company LTD | AAMTAC | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C110 | AAMTAC Company LTD - BAYTUR_PAYMENT | 1TB01006.01.CN.003C110.00 | 1TB01006.01.CN.003C110.01 | 1TB01006.01.CN.003C110.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C111 | Ramzi Abbas Mohd Sayed Est | RAMZI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C111 | Ramzi Abbas Mohd Sayed Est - BAYTUR_PAYMENT | 1TB01006.01.CN.003C111.00 | 1TB01006.01.CN.003C111.01 | 1TB01006.01.CN.003C111.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C112 | Ihsan Muhammed Thakir Idress Trading | IHSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C112 | Ihsan Muhammed Thakir Idress Trading - BAYTUR_PAYMENT | 1TB01006.01.CN.003C112.00 | 1TB01006.01.CN.003C112.01 | 1TB01006.01.CN.003C112.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C113 | Saint Gobain - Sodamco Industrial | SAINT GOBAIN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C113 | Saint Gobain - Sodamco Industrial - BAYTUR_PAYMENT | 1TB01006.01.CN.003C113.00 | 1TB01006.01.CN.003C113.01 | 1TB01006.01.CN.003C113.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C79 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C79 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C79.00 | 1TB01006.01.CN.003C79.01 | 1TB01006.01.CN.003C79.02
1.TB.01.003.01 | AMAALAYachtClub | 2250184 | 003F10 | Jensen Hughes Saudi Arabia, LLC | JENSEN | Consultant | Third-Party Authority for Fire and Life Safety Review & Certification Endorsement (Call off Order No: 031) | PS | 01 | PS.003F10 | Jensen Hughes Saudi Arabia, LLC - 2250184 | 1TB01006.01.PS.003F10.00 | 1TB01006.01.PS.003F10.01 | 1TB01006.01.PS.003F10.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C81 | Jameel Mohammed Hussain Alqatafa Cont.Est. | JAMEEL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C81 | Jameel Mohammed Hussain Alqatafa Cont.Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C81.00 | 1TB01006.01.CN.003C81.01 | 1TB01006.01.CN.003C81.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C89 | Issam Kabani and Partners | ISSAM KABBANI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C89 | Issam Kabani and Partners - BAYTUR_PAYMENT | 1TB01006.01.CN.003C89.00 | 1TB01006.01.CN.003C89.01 | 1TB01006.01.CN.003C89.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C90 | Saad Al Easa - Metal Industry | SAAD | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C90 | Saad Al Easa - Metal Industry - BAYTUR_PAYMENT | 1TB01006.01.CN.003C90.00 | 1TB01006.01.CN.003C90.01 | 1TB01006.01.CN.003C90.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C91 | Medtel - W.N | MEDTEL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C91 | Medtel - W.N - BAYTUR_PAYMENT | 1TB01006.01.CN.003C91.00 | 1TB01006.01.CN.003C91.01 | 1TB01006.01.CN.003C91.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C82 | Gesr Alarab | GESR | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C82 | Gesr Alarab - BAYTUR_PAYMENT | 1TB01006.01.CN.003C82.00 | 1TB01006.01.CN.003C82.01 | 1TB01006.01.CN.003C82.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C80 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C80 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C80.00 | 1TB01006.01.CN.003C80.01 | 1TB01006.01.CN.003C80.02
1.TB.01.003.01 | AMAALAYachtClub | N/A | 003CXX | Ahmed Bin Salem Bin Dagher Al-Balawi Est. | AHMED BIN SALEM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar)_CONTRACT CANCELLED_CONTRACT VALUE SAR 22,058.81 | CN | 01 | CN.003CXX | Ahmed Bin Salem Bin Dagher Al-Balawi Est. - N/A | 1TB01006.01.CN.003CXX.00 | 1TB01006.01.CN.003CXX.01 | 1TB01006.01.CN.003CXX.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C149 | Clean Coast For Contracting | CLEAN COAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Mar) | CN | 01 | CN.003C149 | Clean Coast For Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C149.00 | 1TB01006.01.CN.003C149.01 | 1TB01006.01.CN.003C149.02
1.TB.01.003.01 | AMAALAYachtClub | 2250196 | 003C150 | Al Rajhi Company For Cooperative Insurance | AL RAJHI | Contractor | OCIP Insurance Premium - Declaration 9 | CN | 01 | CN.003C150 | Al Rajhi Company For Cooperative Insurance - 2250196 | 1TB01006.01.CN.003C150.00 | 1TB01006.01.CN.003C150.01 | 1TB01006.01.CN.003C150.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C125 | Yaz Development Contracting | YAZ | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C125 | Yaz Development Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C125.00 | 1TB01006.01.CN.003C125.01 | 1TB01006.01.CN.003C125.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C124 | Gesr Alarab | GESR | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C124 | Gesr Alarab - BAYTUR_PAYMENT | 1TB01006.01.CN.003C124.00 | 1TB01006.01.CN.003C124.01 | 1TB01006.01.CN.003C124.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C117 | Abeer Manawer Al-Shamari Contracting Est. | ABEER | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C117 | Abeer Manawer Al-Shamari Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C117.00 | 1TB01006.01.CN.003C117.01 | 1TB01006.01.CN.003C117.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C109 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C109 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C109.00 | 1TB01006.01.CN.003C109.01 | 1TB01006.01.CN.003C109.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C76 | Wood Expert | WOOD | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C76 | Wood Expert - BAYTUR_PAYMENT | 1TB01006.01.CN.003C76.00 | 1TB01006.01.CN.003C76.01 | 1TB01006.01.CN.003C76.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C146 | Al Tala'a International Transportation Co. | AL TALA'A | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C146 | Al Tala'a International Transportation Co. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C146.00 | 1TB01006.01.CN.003C146.01 | 1TB01006.01.CN.003C146.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C144 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C144 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C144.00 | 1TB01006.01.CN.003C144.01 | 1TB01006.01.CN.003C144.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C143 | M Mohammad Alharbi Medical Company | AL HARBI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C143 | M Mohammad Alharbi Medical Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C143.00 | 1TB01006.01.CN.003C143.01 | 1TB01006.01.CN.003C143.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C139 | Clean Coast For Contracting | CLEAN COAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C139 | Clean Coast For Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C139.00 | 1TB01006.01.CN.003C139.01 | 1TB01006.01.CN.003C139.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C137 | JAK Generation Cont. Co. LLC | JAK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C137 | JAK Generation Cont. Co. LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C137.00 | 1TB01006.01.CN.003C137.01 | 1TB01006.01.CN.003C137.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C138 | Sami General Contracting Est. | SAMI GENEERAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C138 | Sami General Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C138.00 | 1TB01006.01.CN.003C138.01 | 1TB01006.01.CN.003C138.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C135 | Al Rai Modern Water Factory | AL RAI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C135 | Al Rai Modern Water Factory - BAYTUR_PAYMENT | 1TB01006.01.CN.003C135.00 | 1TB01006.01.CN.003C135.01 | 1TB01006.01.CN.003C135.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C134 | The International Company For Building Materials LTD Binex | INT COMPANY | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C134 | The International Company For Building Materials LTD Binex - BAYTUR_PAYMENT | 1TB01006.01.CN.003C134.00 | 1TB01006.01.CN.003C134.01 | 1TB01006.01.CN.003C134.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C133 | Madar Building Material Co. | MADAR BUIILDING | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C133 | Madar Building Material Co. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C133.00 | 1TB01006.01.CN.003C133.01 | 1TB01006.01.CN.003C133.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C132 | Glow Arabia Trading | GLOW | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C132 | Glow Arabia Trading - BAYTUR_PAYMENT | 1TB01006.01.CN.003C132.00 | 1TB01006.01.CN.003C132.01 | 1TB01006.01.CN.003C132.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C131 | Masa Equipments Est | MASA | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C131 | Masa Equipments Est - BAYTUR_PAYMENT | 1TB01006.01.CN.003C131.00 | 1TB01006.01.CN.003C131.01 | 1TB01006.01.CN.003C131.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C127 | Brooq Alamaan Trading Company | BROOQ ALAAMAAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C127 | Brooq Alamaan Trading Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C127.00 | 1TB01006.01.CN.003C127.01 | 1TB01006.01.CN.003C127.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C145 | Saint Gobain - Sodamco Industrial | SAINT GOBAIN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C145 | Saint Gobain - Sodamco Industrial - BAYTUR_PAYMENT | 1TB01006.01.CN.003C145.00 | 1TB01006.01.CN.003C145.01 | 1TB01006.01.CN.003C145.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C120 | Issam Kabani and Partners | ISSAM KABBANI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C120 | Issam Kabani and Partners - BAYTUR_PAYMENT | 1TB01006.01.CN.003C120.00 | 1TB01006.01.CN.003C120.01 | 1TB01006.01.CN.003C120.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C123 | Medtel - W.N | MEDTEL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C123 | Medtel - W.N - BAYTUR_PAYMENT | 1TB01006.01.CN.003C123.00 | 1TB01006.01.CN.003C123.01 | 1TB01006.01.CN.003C123.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C121 | Abu Dhabi Precast LLC | PRECAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C121 | Abu Dhabi Precast LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C121.00 | 1TB01006.01.CN.003C121.01 | 1TB01006.01.CN.003C121.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C136 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton | INTELLIGENT | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C136 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton - BAYTUR_PAYMENT | 1TB01006.01.CN.003C136.00 | 1TB01006.01.CN.003C136.01 | 1TB01006.01.CN.003C136.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C148 | Top Construction Co. Ltd. | TOP CONST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C148 | Top Construction Co. Ltd. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C148.00 | 1TB01006.01.CN.003C148.01 | 1TB01006.01.CN.003C148.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C119 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C119 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C119.00 | 1TB01006.01.CN.003C119.01 | 1TB01006.01.CN.003C119.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C140 | Aldrees Petroleum and Transport Services Company | ALDREES | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C140 | Aldrees Petroleum and Transport Services Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C140.00 | 1TB01006.01.CN.003C140.01 | 1TB01006.01.CN.003C140.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C130 | Aknan Al Bena - ABECO | AKNAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C130 | Aknan Al Bena - ABECO - BAYTUR_PAYMENT | 1TB01006.01.CN.003C130.00 | 1TB01006.01.CN.003C130.01 | 1TB01006.01.CN.003C130.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C126 | TBK Metal | TBK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C126 | TBK Metal - BAYTUR_PAYMENT | 1TB01006.01.CN.003C126.00 | 1TB01006.01.CN.003C126.01 | 1TB01006.01.CN.003C126.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C141 | Al-Anan Travels and Tours | AL ANAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C141 | Al-Anan Travels and Tours - BAYTUR_PAYMENT | 1TB01006.01.CN.003C141.00 | 1TB01006.01.CN.003C141.01 | 1TB01006.01.CN.003C141.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C122 | Alcatop International Company for Building Material | ALCATOP | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C122 | Alcatop International Company for Building Material - BAYTUR_PAYMENT | 1TB01006.01.CN.003C122.00 | 1TB01006.01.CN.003C122.01 | 1TB01006.01.CN.003C122.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C147 | Saudi Brokers | SAUDI BROKERS | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C147 | Saudi Brokers - BAYTUR_PAYMENT | 1TB01006.01.CN.003C147.00 | 1TB01006.01.CN.003C147.01 | 1TB01006.01.CN.003C147.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C128 | Saveto Saudi Vetonit Co Ltd | SAVETO | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C128 | Saveto Saudi Vetonit Co Ltd - BAYTUR_PAYMENT | 1TB01006.01.CN.003C128.00 | 1TB01006.01.CN.003C128.01 | 1TB01006.01.CN.003C128.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C152 | Lakeside Flood Solutions | LAKESIDE | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C152 | Lakeside Flood Solutions - BAYTUR_PAYMENT | 1TB01006.01.CN.003C152.00 | 1TB01006.01.CN.003C152.01 | 1TB01006.01.CN.003C152.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C174 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jul) | CN | 01 | CN.003C174 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C174.00 | 1TB01006.01.CN.003C174.01 | 1TB01006.01.CN.003C174.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C118 | Dosar Al Najd | DOSAR | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C118 | Dosar Al Najd - BAYTUR_PAYMENT | 1TB01006.01.CN.003C118.00 | 1TB01006.01.CN.003C118.01 | 1TB01006.01.CN.003C118.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C106 | Aldrees Petroleum and Transport Services Company | ALDREES | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C106 | Aldrees Petroleum and Transport Services Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C106.00 | 1TB01006.01.CN.003C106.01 | 1TB01006.01.CN.003C106.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C154 | Saad Al Easa - Metal Industry | SAAD | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Apr) | CN | 01 | CN.003C154 | Saad Al Easa - Metal Industry - BAYTUR_PAYMENT | 1TB01006.01.CN.003C154.00 | 1TB01006.01.CN.003C154.01 | 1TB01006.01.CN.003C154.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C180 | Abu Dhabi Precast LLC | PRECAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C180 | Abu Dhabi Precast LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C180.00 | 1TB01006.01.CN.003C180.01 | 1TB01006.01.CN.003C180.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C181 | Medtel - W.N | MEDTEL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C181 | Medtel - W.N - BAYTUR_PAYMENT | 1TB01006.01.CN.003C181.00 | 1TB01006.01.CN.003C181.01 | 1TB01006.01.CN.003C181.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C183 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C183 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C183.00 | 1TB01006.01.CN.003C183.01 | 1TB01006.01.CN.003C183.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C178 | Issam Kabani and Partners | ISSAM KABBANI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C178 | Issam Kabani and Partners - BAYTUR_PAYMENT | 1TB01006.01.CN.003C178.00 | 1TB01006.01.CN.003C178.01 | 1TB01006.01.CN.003C178.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C179 | Saad Al Easa - Metal Industry | SAAD | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C179 | Saad Al Easa - Metal Industry - BAYTUR_PAYMENT | 1TB01006.01.CN.003C179.00 | 1TB01006.01.CN.003C179.01 | 1TB01006.01.CN.003C179.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C190 | Juffali Technical Equipment company | JUFFALI TTECHNICAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C190 | Juffali Technical Equipment company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C190.00 | 1TB01006.01.CN.003C190.01 | 1TB01006.01.CN.003C190.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C189 | Glow Arabia Trading | GLOW | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C189 | Glow Arabia Trading - BAYTUR_PAYMENT | 1TB01006.01.CN.003C189.00 | 1TB01006.01.CN.003C189.01 | 1TB01006.01.CN.003C189.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C187 | Brooq Alamaan Trading Company | BROOQ ALAAMAAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C187 | Brooq Alamaan Trading Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C187.00 | 1TB01006.01.CN.003C187.01 | 1TB01006.01.CN.003C187.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C186 | TBK Metal | TBK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C186 | TBK Metal - BAYTUR_PAYMENT | 1TB01006.01.CN.003C186.00 | 1TB01006.01.CN.003C186.01 | 1TB01006.01.CN.003C186.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C185 | Yaz Development Contracting | YAZ | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C185 | Yaz Development Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C185.00 | 1TB01006.01.CN.003C185.01 | 1TB01006.01.CN.003C185.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C184 | Gesr Alarab | GESR | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C184 | Gesr Alarab - BAYTUR_PAYMENT | 1TB01006.01.CN.003C184.00 | 1TB01006.01.CN.003C184.01 | 1TB01006.01.CN.003C184.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C204 | Fast Steps | FAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C204 | Fast Steps - BAYTUR_PAYMENT | 1TB01006.01.CN.003C204.00 | 1TB01006.01.CN.003C204.01 | 1TB01006.01.CN.003C204.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C203 | Tanseeq LLC | TANSEEQ | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C203 | Tanseeq LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C203.00 | 1TB01006.01.CN.003C203.01 | 1TB01006.01.CN.003C203.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C202 | Top Construction Co. Ltd. | TOP CONST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C202 | Top Construction Co. Ltd. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C202.00 | 1TB01006.01.CN.003C202.01 | 1TB01006.01.CN.003C202.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C201 | Saint Gobain - Sodamco Industrial | SAINT GOBAIN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C201 | Saint Gobain - Sodamco Industrial - BAYTUR_PAYMENT | 1TB01006.01.CN.003C201.00 | 1TB01006.01.CN.003C201.01 | 1TB01006.01.CN.003C201.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C200 | Ihsan Muhammed Thakir Idress Trading | IHSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C200 | Ihsan Muhammed Thakir Idress Trading - BAYTUR_PAYMENT | 1TB01006.01.CN.003C200.00 | 1TB01006.01.CN.003C200.01 | 1TB01006.01.CN.003C200.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C199 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C199 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C199.00 | 1TB01006.01.CN.003C199.01 | 1TB01006.01.CN.003C199.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C198 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C198 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C198.00 | 1TB01006.01.CN.003C198.01 | 1TB01006.01.CN.003C198.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C197 | M Mohammad Alharbi Medical Company | AL HARBI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C197 | M Mohammad Alharbi Medical Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C197.00 | 1TB01006.01.CN.003C197.01 | 1TB01006.01.CN.003C197.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C196 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. | AHMED BIN SALEM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C196 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C196.00 | 1TB01006.01.CN.003C196.01 | 1TB01006.01.CN.003C196.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C195 | Sami General Contracting Est. | SAMI GENEERAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C195 | Sami General Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C195.00 | 1TB01006.01.CN.003C195.01 | 1TB01006.01.CN.003C195.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C193 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton | INTELLIGENT | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C193 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton - BAYTUR_PAYMENT | 1TB01006.01.CN.003C193.00 | 1TB01006.01.CN.003C193.01 | 1TB01006.01.CN.003C193.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C194 | JAK Generation Cont. Co. LLC | JAK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C194 | JAK Generation Cont. Co. LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C194.00 | 1TB01006.01.CN.003C194.01 | 1TB01006.01.CN.003C194.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C192 | Al Rai Modern Water Factory | AL RAI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C192 | Al Rai Modern Water Factory - BAYTUR_PAYMENT | 1TB01006.01.CN.003C192.00 | 1TB01006.01.CN.003C192.01 | 1TB01006.01.CN.003C192.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C191 | Energy & Building Masters | ENERGY | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C191 | Energy & Building Masters - BAYTUR_PAYMENT | 1TB01006.01.CN.003C191.00 | 1TB01006.01.CN.003C191.01 | 1TB01006.01.CN.003C191.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C205 | Issam Kabani and Partners | ISSAM KABBANI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C205 | Issam Kabani and Partners - BAYTUR_PAYMENT | 1TB01006.01.CN.003C205.00 | 1TB01006.01.CN.003C205.01 | 1TB01006.01.CN.003C205.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C206 | Abu Dhabi Precast LLC | PRECAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C206 | Abu Dhabi Precast LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C206.00 | 1TB01006.01.CN.003C206.01 | 1TB01006.01.CN.003C206.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C207 | Alcatop International Company for Building Material | ALCATOP | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C207 | Alcatop International Company for Building Material - BAYTUR_PAYMENT | 1TB01006.01.CN.003C207.00 | 1TB01006.01.CN.003C207.01 | 1TB01006.01.CN.003C207.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C208 | Medtel - W.N | MEDTEL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C208 | Medtel - W.N - BAYTUR_PAYMENT | 1TB01006.01.CN.003C208.00 | 1TB01006.01.CN.003C208.01 | 1TB01006.01.CN.003C208.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C211 | Gesr Alarab | GESR | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C211 | Gesr Alarab - BAYTUR_PAYMENT | 1TB01006.01.CN.003C211.00 | 1TB01006.01.CN.003C211.01 | 1TB01006.01.CN.003C211.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C212 | National Fire Fighting Manufacturing Company - NAFFCO | NAFFCO | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C212 | National Fire Fighting Manufacturing Company - NAFFCO - BAYTUR_PAYMENT | 1TB01006.01.CN.003C212.00 | 1TB01006.01.CN.003C212.01 | 1TB01006.01.CN.003C212.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C213 | Yaz Development Contracting | YAZ | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C213 | Yaz Development Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C213.00 | 1TB01006.01.CN.003C213.01 | 1TB01006.01.CN.003C213.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C214 | TBK Metal | TBK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C214 | TBK Metal - BAYTUR_PAYMENT | 1TB01006.01.CN.003C214.00 | 1TB01006.01.CN.003C214.01 | 1TB01006.01.CN.003C214.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C215 | Abeer Manawer Al-Shamari Contracting Est. | ABEER | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C215 | Abeer Manawer Al-Shamari Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C215.00 | 1TB01006.01.CN.003C215.01 | 1TB01006.01.CN.003C215.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C216 | Masa Equipments Est | MASA | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C216 | Masa Equipments Est - BAYTUR_PAYMENT | 1TB01006.01.CN.003C216.00 | 1TB01006.01.CN.003C216.01 | 1TB01006.01.CN.003C216.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C217 | Madar Building Material Co. | MADAR BUIILDING | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C217 | Madar Building Material Co. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C217.00 | 1TB01006.01.CN.003C217.01 | 1TB01006.01.CN.003C217.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C218 | Energy & Building Masters | ENERGY | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C218 | Energy & Building Masters - BAYTUR_PAYMENT | 1TB01006.01.CN.003C218.00 | 1TB01006.01.CN.003C218.01 | 1TB01006.01.CN.003C218.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C219 | Al Rai Modern Water Factory | AL RAI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C219 | Al Rai Modern Water Factory - BAYTUR_PAYMENT | 1TB01006.01.CN.003C219.00 | 1TB01006.01.CN.003C219.01 | 1TB01006.01.CN.003C219.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C220 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton | INTELLIGENT | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C220 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton - BAYTUR_PAYMENT | 1TB01006.01.CN.003C220.00 | 1TB01006.01.CN.003C220.01 | 1TB01006.01.CN.003C220.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C221 | JAK Generation Cont. Co. LLC | JAK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C221 | JAK Generation Cont. Co. LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C221.00 | 1TB01006.01.CN.003C221.01 | 1TB01006.01.CN.003C221.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C222 | Sami General Contracting Est. | SAMI GENEERAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C222 | Sami General Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C222.00 | 1TB01006.01.CN.003C222.01 | 1TB01006.01.CN.003C222.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C223 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. | AHMED BIN SALEM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C223 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C223.00 | 1TB01006.01.CN.003C223.01 | 1TB01006.01.CN.003C223.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C224 | Salim Hamed Cleaning | SALIM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C224 | Salim Hamed Cleaning - BAYTUR_PAYMENT | 1TB01006.01.CN.003C224.00 | 1TB01006.01.CN.003C224.01 | 1TB01006.01.CN.003C224.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C225 | M Mohammad Alharbi Medical Company | AL HARBI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C225 | M Mohammad Alharbi Medical Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C225.00 | 1TB01006.01.CN.003C225.01 | 1TB01006.01.CN.003C225.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C226 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C226 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C226.00 | 1TB01006.01.CN.003C226.01 | 1TB01006.01.CN.003C226.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C227 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C227 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C227.00 | 1TB01006.01.CN.003C227.01 | 1TB01006.01.CN.003C227.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C228 | Ihsan Muhammed Thakir Idress Trading | IHSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C228 | Ihsan Muhammed Thakir Idress Trading - BAYTUR_PAYMENT | 1TB01006.01.CN.003C228.00 | 1TB01006.01.CN.003C228.01 | 1TB01006.01.CN.003C228.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C229 | Top Construction Co. Ltd. | TOP CONST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C229 | Top Construction Co. Ltd. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C229.00 | 1TB01006.01.CN.003C229.01 | 1TB01006.01.CN.003C229.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C230 | Fast Steps | FAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (July) | CN | 01 | CN.003C230 | Fast Steps - BAYTUR_PAYMENT | 1TB01006.01.CN.003C230.00 | 1TB01006.01.CN.003C230.01 | 1TB01006.01.CN.003C230.02
1.TB.01.003.01 | AMAALAYachtClub | TBC 1 | 003F12 | GST Building Energy Efficiency Services | GST BUILDING | Consultant | LEED Performance Testing (BECx & IAQ) (Call off Order No: 024) | PS | 01 | PS.003F12 | GST Building Energy Efficiency Services - TBC 1 | 1TB01006.01.PS.003F12.00 | 1TB01006.01.PS.003F12.01 | 1TB01006.01.PS.003F12.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C153 | Issam Kabani and Partners | ISSAM KABBANI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C153 | Issam Kabani and Partners - BAYTUR_PAYMENT | 1TB01006.01.CN.003C153.00 | 1TB01006.01.CN.003C153.01 | 1TB01006.01.CN.003C153.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C155 | Abu Dhabi Precast LLC | PRECAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C155 | Abu Dhabi Precast LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C155.00 | 1TB01006.01.CN.003C155.01 | 1TB01006.01.CN.003C155.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C157 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C157 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C157.00 | 1TB01006.01.CN.003C157.01 | 1TB01006.01.CN.003C157.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C158 | Gesr Alarab | GESR | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C158 | Gesr Alarab - BAYTUR_PAYMENT | 1TB01006.01.CN.003C158.00 | 1TB01006.01.CN.003C158.01 | 1TB01006.01.CN.003C158.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C159 | Yaz Development Contracting | YAZ | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C159 | Yaz Development Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C159.00 | 1TB01006.01.CN.003C159.01 | 1TB01006.01.CN.003C159.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C160 | TBK Metal | TBK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C160 | TBK Metal - BAYTUR_PAYMENT | 1TB01006.01.CN.003C160.00 | 1TB01006.01.CN.003C160.01 | 1TB01006.01.CN.003C160.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C162 | Al Rai Modern Water Factory | AL RAI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C162 | Al Rai Modern Water Factory - BAYTUR_PAYMENT | 1TB01006.01.CN.003C162.00 | 1TB01006.01.CN.003C162.01 | 1TB01006.01.CN.003C162.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C163 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton | INTELLIGENT | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C163 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton - BAYTUR_PAYMENT | 1TB01006.01.CN.003C163.00 | 1TB01006.01.CN.003C163.01 | 1TB01006.01.CN.003C163.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C164 | JAK Generation Cont. Co. LLC | JAK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C164 | JAK Generation Cont. Co. LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C164.00 | 1TB01006.01.CN.003C164.01 | 1TB01006.01.CN.003C164.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C165 | Sami General Contracting Est. | SAMI GENEERAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C165 | Sami General Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C165.00 | 1TB01006.01.CN.003C165.01 | 1TB01006.01.CN.003C165.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C166 | Clean Coast For Contracting | CLEAN COAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C166 | Clean Coast For Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C166.00 | 1TB01006.01.CN.003C166.01 | 1TB01006.01.CN.003C166.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C167 | Salim Hamed Cleaning | SALIM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C167 | Salim Hamed Cleaning - BAYTUR_PAYMENT | 1TB01006.01.CN.003C167.00 | 1TB01006.01.CN.003C167.01 | 1TB01006.01.CN.003C167.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C168 | Al-Anan Travels and Tours | AL ANAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C168 | Al-Anan Travels and Tours - BAYTUR_PAYMENT | 1TB01006.01.CN.003C168.00 | 1TB01006.01.CN.003C168.01 | 1TB01006.01.CN.003C168.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C170 | M Mohammad Alharbi Medical Company | AL HARBI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C170 | M Mohammad Alharbi Medical Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C170.00 | 1TB01006.01.CN.003C170.01 | 1TB01006.01.CN.003C170.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C171 | Wood Expert | WOOD | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C171 | Wood Expert - BAYTUR_PAYMENT | 1TB01006.01.CN.003C171.00 | 1TB01006.01.CN.003C171.01 | 1TB01006.01.CN.003C171.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C172 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C172 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C172.00 | 1TB01006.01.CN.003C172.01 | 1TB01006.01.CN.003C172.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C173 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C173 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C173.00 | 1TB01006.01.CN.003C173.01 | 1TB01006.01.CN.003C173.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C175 | Ihsan Muhammed Thakir Idress Trading | IHSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C175 | Ihsan Muhammed Thakir Idress Trading - BAYTUR_PAYMENT | 1TB01006.01.CN.003C175.00 | 1TB01006.01.CN.003C175.01 | 1TB01006.01.CN.003C175.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C177 | Top Construction Co. Ltd. | TOP CONST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C177 | Top Construction Co. Ltd. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C177.00 | 1TB01006.01.CN.003C177.01 | 1TB01006.01.CN.003C177.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C210 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C210 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C210.00 | 1TB01006.01.CN.003C210.01 | 1TB01006.01.CN.003C210.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C156 | Medtel - W.N | MEDTEL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (June) | CN | 01 | CN.003C156 | Medtel - W.N - BAYTUR_PAYMENT | 1TB01006.01.CN.003C156.00 | 1TB01006.01.CN.003C156.01 | 1TB01006.01.CN.003C156.02
1.TB.01.003.01 | AMAALAYachtClub | TBC 18 | 003F13 | Tabuk Investment and Tourism Company (Enviro Facility Management) | TABUK INVEST | Contractor | Deep Cleaning Services (Call off Order No: 005) | CN | 01 | CN.003F13 | Tabuk Investment and Tourism Company (Enviro Facility Management) - TBC 18 | 1TB01006.01.CN.003F13.00 | 1TB01006.01.CN.003F13.01 | 1TB01006.01.CN.003F13.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C250 | Ihsan Muhammed Thakir Idress Trading | IHSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C250 | Ihsan Muhammed Thakir Idress Trading - BAYTUR_PAYMENT | 1TB01006.01.CN.003C250.00 | 1TB01006.01.CN.003C250.01 | 1TB01006.01.CN.003C250.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C232 | Issam Kabani and Partners | ISSAM KABBANI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C232 | Issam Kabani and Partners - BAYTUR_PAYMENT | 1TB01006.01.CN.003C232.00 | 1TB01006.01.CN.003C232.01 | 1TB01006.01.CN.003C232.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C233 | Saad Al Easa - Metal Industry | SAAD | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C233 | Saad Al Easa - Metal Industry - BAYTUR_PAYMENT | 1TB01006.01.CN.003C233.00 | 1TB01006.01.CN.003C233.01 | 1TB01006.01.CN.003C233.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C234 | Abu Dhabi Precast LLC | PRECAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C234 | Abu Dhabi Precast LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C234.00 | 1TB01006.01.CN.003C234.01 | 1TB01006.01.CN.003C234.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C235 | Alcatop International Company for Building Material | ALCATOP | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C235 | Alcatop International Company for Building Material - BAYTUR_PAYMENT | 1TB01006.01.CN.003C235.00 | 1TB01006.01.CN.003C235.01 | 1TB01006.01.CN.003C235.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C238 | National Fire Fighting Manufacturing Company - NAFFCO | NAFFCO | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C238 | National Fire Fighting Manufacturing Company - NAFFCO - BAYTUR_PAYMENT | 1TB01006.01.CN.003C238.00 | 1TB01006.01.CN.003C238.01 | 1TB01006.01.CN.003C238.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C237 | Gesr Alarab | GESR | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C237 | Gesr Alarab - BAYTUR_PAYMENT | 1TB01006.01.CN.003C237.00 | 1TB01006.01.CN.003C237.01 | 1TB01006.01.CN.003C237.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C239 | Yaz Development Contracting | YAZ | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C239 | Yaz Development Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C239.00 | 1TB01006.01.CN.003C239.01 | 1TB01006.01.CN.003C239.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C240 | TBK Metal | TBK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C240 | TBK Metal - BAYTUR_PAYMENT | 1TB01006.01.CN.003C240.00 | 1TB01006.01.CN.003C240.01 | 1TB01006.01.CN.003C240.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C241 | Al Rai Modern Water Factory | AL RAI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C241 | Al Rai Modern Water Factory - BAYTUR_PAYMENT | 1TB01006.01.CN.003C241.00 | 1TB01006.01.CN.003C241.01 | 1TB01006.01.CN.003C241.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C242 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton | INTELLIGENT | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C242 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton - BAYTUR_PAYMENT | 1TB01006.01.CN.003C242.00 | 1TB01006.01.CN.003C242.01 | 1TB01006.01.CN.003C242.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C243 | JAK Generation Cont. Co. LLC | JAK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C243 | JAK Generation Cont. Co. LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C243.00 | 1TB01006.01.CN.003C243.01 | 1TB01006.01.CN.003C243.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C244 | Sami General Contracting Est. | SAMI GENEERAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C244 | Sami General Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C244.00 | 1TB01006.01.CN.003C244.01 | 1TB01006.01.CN.003C244.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C245 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. | AHMED BIN SALEM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C245 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C245.00 | 1TB01006.01.CN.003C245.01 | 1TB01006.01.CN.003C245.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C246 | Salim Hamed Cleaning | SALIM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C246 | Salim Hamed Cleaning - BAYTUR_PAYMENT | 1TB01006.01.CN.003C246.00 | 1TB01006.01.CN.003C246.01 | 1TB01006.01.CN.003C246.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C247 | M Mohammad Alharbi Medical Company | AL HARBI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C247 | M Mohammad Alharbi Medical Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C247.00 | 1TB01006.01.CN.003C247.01 | 1TB01006.01.CN.003C247.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C248 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C248 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C248.00 | 1TB01006.01.CN.003C248.01 | 1TB01006.01.CN.003C248.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C249 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C249 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C249.00 | 1TB01006.01.CN.003C249.01 | 1TB01006.01.CN.003C249.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C251 | Top Construction Co. Ltd. | TOP CONST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C251 | Top Construction Co. Ltd. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C251.00 | 1TB01006.01.CN.003C251.01 | 1TB01006.01.CN.003C251.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C252 | HRFA Special Skills Co | HRFA | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C252 | HRFA Special Skills Co - BAYTUR_PAYMENT | 1TB01006.01.CN.003C252.00 | 1TB01006.01.CN.003C252.01 | 1TB01006.01.CN.003C252.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C253 | Nesma United Industries Co. Ltd. | NESMA | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Aug) | CN | 01 | CN.003C253 | Nesma United Industries Co. Ltd. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C253.00 | 1TB01006.01.CN.003C253.01 | 1TB01006.01.CN.003C253.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C182 | Al Hayat Investment | AL HAYAT | Contractor | Payment On Behalf Of Saudi Arabian Baytur | CN | 01 | CN.003C182 | Al Hayat Investment - BAYTUR_PAYMENT | 1TB01006.01.CN.003C182.00 | 1TB01006.01.CN.003C182.01 | 1TB01006.01.CN.003C182.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C236 | Medtel - W.N | MEDTEL | Contractor | Payment On Behalf Of Saudi Arabian Baytur | CN | 01 | CN.003C236 | Medtel - W.N - BAYTUR_PAYMENT | 1TB01006.01.CN.003C236.00 | 1TB01006.01.CN.003C236.01 | 1TB01006.01.CN.003C236.02
1.TB.01.003.01 | AMAALAYachtClub | TBC 42 | 003F11 | Extraordinary Cart | EXTRAORDINARY | Contractor | Supply and Delivery Of Buggies | FFEOSE | 01 | FFEOSE.003F11 | Extraordinary Cart - TBC 42 | 1TB01006.01.FFEOSE.003F11.00 | 1TB01006.01.FFEOSE.003F11.01 | 1TB01006.01.FFEOSE.003F11.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C272 | Top Construction Co. Ltd. | TOP CONST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C272 | Top Construction Co. Ltd. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C272.00 | 1TB01006.01.CN.003C272.01 | 1TB01006.01.CN.003C272.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C270 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C270 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C270.00 | 1TB01006.01.CN.003C270.01 | 1TB01006.01.CN.003C270.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C271 | Ihsan Muhammed Thakir Idress Trading | IHSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C271 | Ihsan Muhammed Thakir Idress Trading - BAYTUR_PAYMENT | 1TB01006.01.CN.003C271.00 | 1TB01006.01.CN.003C271.01 | 1TB01006.01.CN.003C271.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C269 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C269 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C269.00 | 1TB01006.01.CN.003C269.01 | 1TB01006.01.CN.003C269.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C268 | M Mohammad Alharbi Medical Company | AL HARBI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C268 | M Mohammad Alharbi Medical Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C268.00 | 1TB01006.01.CN.003C268.01 | 1TB01006.01.CN.003C268.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C267 | Salim Hamed Cleaning | SALIM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C267 | Salim Hamed Cleaning - BAYTUR_PAYMENT | 1TB01006.01.CN.003C267.00 | 1TB01006.01.CN.003C267.01 | 1TB01006.01.CN.003C267.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C266 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. | AHMED BIN SALEM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C266 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C266.00 | 1TB01006.01.CN.003C266.01 | 1TB01006.01.CN.003C266.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C265 | Sami General Contracting Est. | SAMI GENEERAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C265 | Sami General Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C265.00 | 1TB01006.01.CN.003C265.01 | 1TB01006.01.CN.003C265.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C263 | JAK Generation Cont. Co. LLC | JAK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C263 | JAK Generation Cont. Co. LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C263.00 | 1TB01006.01.CN.003C263.01 | 1TB01006.01.CN.003C263.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C262 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton | INTELLIGENT | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C262 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton - BAYTUR_PAYMENT | 1TB01006.01.CN.003C262.00 | 1TB01006.01.CN.003C262.01 | 1TB01006.01.CN.003C262.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C261 | Al Rai Modern Water Factory | AL RAI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C261 | Al Rai Modern Water Factory - BAYTUR_PAYMENT | 1TB01006.01.CN.003C261.00 | 1TB01006.01.CN.003C261.01 | 1TB01006.01.CN.003C261.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C260 | Abeer Manawer Al-Shamari Contracting Est. | ABEER | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C260 | Abeer Manawer Al-Shamari Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C260.00 | 1TB01006.01.CN.003C260.01 | 1TB01006.01.CN.003C260.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C259 | Yaz Development Contracting | YAZ | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C259 | Yaz Development Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C259.00 | 1TB01006.01.CN.003C259.01 | 1TB01006.01.CN.003C259.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C258 | National Fire Fighting Manufacturing Company - NAFFCO | NAFFCO | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C258 | National Fire Fighting Manufacturing Company - NAFFCO - BAYTUR_PAYMENT | 1TB01006.01.CN.003C258.00 | 1TB01006.01.CN.003C258.01 | 1TB01006.01.CN.003C258.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C257 | Gesr Alarab | GESR | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C257 | Gesr Alarab - BAYTUR_PAYMENT | 1TB01006.01.CN.003C257.00 | 1TB01006.01.CN.003C257.01 | 1TB01006.01.CN.003C257.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C256 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C256 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C256.00 | 1TB01006.01.CN.003C256.01 | 1TB01006.01.CN.003C256.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C255 | Medtel - W.N | MEDTEL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C255 | Medtel - W.N - BAYTUR_PAYMENT | 1TB01006.01.CN.003C255.00 | 1TB01006.01.CN.003C255.01 | 1TB01006.01.CN.003C255.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C254 | Issam Kabani and Partners | ISSAM KABBANI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Sep) | CN | 01 | CN.003C254 | Issam Kabani and Partners - BAYTUR_PAYMENT | 1TB01006.01.CN.003C254.00 | 1TB01006.01.CN.003C254.01 | 1TB01006.01.CN.003C254.02
1.TB.01.003.01 | AMAALAYachtClub | TBC 60 | 003D09 | SaudiCo Electronic Systems | SAUDI ELEC | Consultant | Supply, Installation Of Oracle Hospitality Simphony Cloud POS Solutions for Yacht Club | FFEOSE | 01 | FFEOSE.003D09 | SaudiCo Electronic Systems - TBC 60 | 1TB01006.01.FFEOSE.003D09.00 | 1TB01006.01.FFEOSE.003D09.01 | 1TB01006.01.FFEOSE.003D09.02
1.TB.01.003.01 | AMAALAYachtClub | TBC 72 | 003D07 | Birchstreet Systems, LLC | BIRCHSTREET | Consultant | Procurement, Inventory, & Receipt Management System for Yacht Club | FFEOSE | 01 | FFEOSE.003D07 | Birchstreet Systems, LLC - TBC 72 | 1TB01006.01.FFEOSE.003D07.00 | 1TB01006.01.FFEOSE.003D07.01 | 1TB01006.01.FFEOSE.003D07.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C292 | Emaar Suhail Engineering Consultant | EMAAR | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C292 | Emaar Suhail Engineering Consultant - BAYTUR_PAYMENT | 1TB01006.01.CN.003C292.00 | 1TB01006.01.CN.003C292.01 | 1TB01006.01.CN.003C292.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C291 | HRFA Special Skills Co | HRFA | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C291 | HRFA Special Skills Co - BAYTUR_PAYMENT | 1TB01006.01.CN.003C291.00 | 1TB01006.01.CN.003C291.01 | 1TB01006.01.CN.003C291.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C290 | Top Construction Co. Ltd. | TOP CONST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C290 | Top Construction Co. Ltd. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C290.00 | 1TB01006.01.CN.003C290.01 | 1TB01006.01.CN.003C290.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C289 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C289 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C289.00 | 1TB01006.01.CN.003C289.01 | 1TB01006.01.CN.003C289.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C288 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C288 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C288.00 | 1TB01006.01.CN.003C288.01 | 1TB01006.01.CN.003C288.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C287 | M Mohammad Alharbi Medical Company | AL HARBI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C287 | M Mohammad Alharbi Medical Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C287.00 | 1TB01006.01.CN.003C287.01 | 1TB01006.01.CN.003C287.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C286 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. | AHMED BIN SALEM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C286 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C286.00 | 1TB01006.01.CN.003C286.01 | 1TB01006.01.CN.003C286.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C285 | Sami General Contracting Est. | SAMI GENEERAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C285 | Sami General Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C285.00 | 1TB01006.01.CN.003C285.01 | 1TB01006.01.CN.003C285.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C284 | JAK Generation Cont. Co. LLC | JAK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C284 | JAK Generation Cont. Co. LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C284.00 | 1TB01006.01.CN.003C284.01 | 1TB01006.01.CN.003C284.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C283 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton | INTELLIGENT | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C283 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton - BAYTUR_PAYMENT | 1TB01006.01.CN.003C283.00 | 1TB01006.01.CN.003C283.01 | 1TB01006.01.CN.003C283.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C282 | Al Rai Modern Water Factory | AL RAI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C282 | Al Rai Modern Water Factory - BAYTUR_PAYMENT | 1TB01006.01.CN.003C282.00 | 1TB01006.01.CN.003C282.01 | 1TB01006.01.CN.003C282.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C281 | Masa Equipments Est | MASA | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C281 | Masa Equipments Est - BAYTUR_PAYMENT | 1TB01006.01.CN.003C281.00 | 1TB01006.01.CN.003C281.01 | 1TB01006.01.CN.003C281.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C280 | Yaz Development Contracting | YAZ | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C280 | Yaz Development Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C280.00 | 1TB01006.01.CN.003C280.01 | 1TB01006.01.CN.003C280.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C279 | National Fire Fighting Manufacturing Company - NAFFCO | NAFFCO | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C279 | National Fire Fighting Manufacturing Company - NAFFCO - BAYTUR_PAYMENT | 1TB01006.01.CN.003C279.00 | 1TB01006.01.CN.003C279.01 | 1TB01006.01.CN.003C279.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C278 | Gesr Alarab | GESR | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C278 | Gesr Alarab - BAYTUR_PAYMENT | 1TB01006.01.CN.003C278.00 | 1TB01006.01.CN.003C278.01 | 1TB01006.01.CN.003C278.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C277 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C277 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C277.00 | 1TB01006.01.CN.003C277.01 | 1TB01006.01.CN.003C277.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C276 | Medtel WN Contracting Co. | MEDTEL_CON | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C276 | Medtel WN Contracting Co. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C276.00 | 1TB01006.01.CN.003C276.01 | 1TB01006.01.CN.003C276.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C275 | Alcatop International Company for Building Material | ALCATOP | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C275 | Alcatop International Company for Building Material - BAYTUR_PAYMENT | 1TB01006.01.CN.003C275.00 | 1TB01006.01.CN.003C275.01 | 1TB01006.01.CN.003C275.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C274 | Saad Al Easa - Metal Industry | SAAD | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C274 | Saad Al Easa - Metal Industry - BAYTUR_PAYMENT | 1TB01006.01.CN.003C274.00 | 1TB01006.01.CN.003C274.01 | 1TB01006.01.CN.003C274.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C273 | Issam Kabani and Partners | ISSAM KABBANI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Oct) | CN | 01 | CN.003C273 | Issam Kabani and Partners - BAYTUR_PAYMENT | 1TB01006.01.CN.003C273.00 | 1TB01006.01.CN.003C273.01 | 1TB01006.01.CN.003C273.02
1.TB.01.003.01 | AMAALAYachtClub | TBC 143 | 003D15 | Saudico Electronic Systems | SAUDI ELEC | Consultant | Supply, Implementation Of Infor SunSystems for AMAALA Yacht Club | FFEOSE | 01 | FFEOSE.003D15 | Saudico Electronic Systems - TBC 143 | 1TB01006.01.FFEOSE.003D15.00 | 1TB01006.01.FFEOSE.003D15.01 | 1TB01006.01.FFEOSE.003D15.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C293 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov) | CN | 01 | CN.003C293 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C293.00 | 1TB01006.01.CN.003C293.01 | 1TB01006.01.CN.003C293.02
1.TB.01.003.01 | AMAALAYachtClub | TBC 154 | 003D10 | Al Falak Electronic Equipment & Supplies Co | AL FALAK | Consultant | Providing HPE Servers | FFEOSE | 01 | FFEOSE.003D10 | Al Falak Electronic Equipment & Supplies Co - TBC 154 | 1TB01006.01.FFEOSE.003D10.00 | 1TB01006.01.FFEOSE.003D10.01 | 1TB01006.01.FFEOSE.003D10.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C299 | National Fire Fighting Manufacturing Company - NAFFCO | NAFFCO | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C299 | National Fire Fighting Manufacturing Company - NAFFCO - BAYTUR_PAYMENT | 1TB01006.01.CN.003C299.00 | 1TB01006.01.CN.003C299.01 | 1TB01006.01.CN.003C299.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C302 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton | INTELLIGENT | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C302 | Intelligent General Cont. Co - Equipment - Industrial Forklift & 5ton - BAYTUR_PAYMENT | 1TB01006.01.CN.003C302.00 | 1TB01006.01.CN.003C302.01 | 1TB01006.01.CN.003C302.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C303 | JAK Generation Cont. Co. LLC | JAK | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C303 | JAK Generation Cont. Co. LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C303.00 | 1TB01006.01.CN.003C303.01 | 1TB01006.01.CN.003C303.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C301 | Al Rai Modern Water Factory | AL RAI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C301 | Al Rai Modern Water Factory - BAYTUR_PAYMENT | 1TB01006.01.CN.003C301.00 | 1TB01006.01.CN.003C301.01 | 1TB01006.01.CN.003C301.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C300 | Yaz Development Contracting | YAZ | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C300 | Yaz Development Contracting - BAYTUR_PAYMENT | 1TB01006.01.CN.003C300.00 | 1TB01006.01.CN.003C300.01 | 1TB01006.01.CN.003C300.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C309 | Top Construction Co. Ltd. | TOP CONST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C309 | Top Construction Co. Ltd. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C309.00 | 1TB01006.01.CN.003C309.01 | 1TB01006.01.CN.003C309.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C310 | Nesma United Industries Co. Ltd. | NESMA | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C310 | Nesma United Industries Co. Ltd. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C310.00 | 1TB01006.01.CN.003C310.01 | 1TB01006.01.CN.003C310.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C294 | Issam Kabani and Partners | ISSAM KABBANI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C294 | Issam Kabani and Partners - BAYTUR_PAYMENT | 1TB01006.01.CN.003C294.00 | 1TB01006.01.CN.003C294.01 | 1TB01006.01.CN.003C294.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C308 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C308 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C308.00 | 1TB01006.01.CN.003C308.01 | 1TB01006.01.CN.003C308.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C306 | M Mohammad Alharbi Medical Company | AL HARBI | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C306 | M Mohammad Alharbi Medical Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C306.00 | 1TB01006.01.CN.003C306.01 | 1TB01006.01.CN.003C306.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C305 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. | AHMED BIN SALEM | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C305 | Ahmed Bin Salem Bin Dagher Al-Balawi Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C305.00 | 1TB01006.01.CN.003C305.01 | 1TB01006.01.CN.003C305.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C304 | Sami General Contracting Est. | SAMI GENEERAL | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C304 | Sami General Contracting Est. - BAYTUR_PAYMENT | 1TB01006.01.CN.003C304.00 | 1TB01006.01.CN.003C304.01 | 1TB01006.01.CN.003C304.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C297 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C297 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C297.00 | 1TB01006.01.CN.003C297.01 | 1TB01006.01.CN.003C297.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C295 | Abu Dhabi Precast LLC | PRECAST | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C295 | Abu Dhabi Precast LLC - BAYTUR_PAYMENT | 1TB01006.01.CN.003C295.00 | 1TB01006.01.CN.003C295.01 | 1TB01006.01.CN.003C295.02
1.TB.01.003.01 | AMAALAYachtClub | TBC 165 | 003D12 | Infor (Saudi Arabia Limited) | INFOR | Consultant | Supply,Setup and Implementation Of Infor Financial Software (SunSystems) | FFEOSE | 01 | FFEOSE.003D12 | Infor (Saudi Arabia Limited) - TBC 165 | 1TB01006.01.FFEOSE.003D12.00 | 1TB01006.01.FFEOSE.003D12.01 | 1TB01006.01.FFEOSE.003D12.02
1.TB.01.003.01 | AMAALAYachtClub | TBC 167 | 003D11 | Sevenrooms Inc. | SEVEN | Consultant | Supply,Setup and Implementation Of Reservation System | FFEOSE | 01 | FFEOSE.003D11 | Sevenrooms Inc. - TBC 167 | 1TB01006.01.FFEOSE.003D11.00 | 1TB01006.01.FFEOSE.003D11.01 | 1TB01006.01.FFEOSE.003D11.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C312 | National Fire Fighting Manufacturing Company - NAFFCO | NAFFCO | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Jan) | CN | 01 | CN.003C312 | National Fire Fighting Manufacturing Company - NAFFCO - BAYTUR_PAYMENT | 1TB01006.01.CN.003C312.00 | 1TB01006.01.CN.003C312.01 | 1TB01006.01.CN.003C312.02
1.TB.01.003.01 | AMAALAYachtClub | BAYTUR_PAYMENT | 003C307 | Glsan Contracting Company | GLSAN | Contractor | Payment On Behalf Of Saudi Arabian Baytur (Nov/Dec) | CN | 01 | CN.003C307 | Glsan Contracting Company - BAYTUR_PAYMENT | 1TB01006.01.CN.003C307.00 | 1TB01006.01.CN.003C307.01 | 1TB01006.01.CN.003C307.02
1.TB.01.009.01 | MH3 | KORTEK | 009C05 | KTH - MEP Works Package - 2240072 | KORTEK | Contractor |  | CN | 01 | CN.009C05 | KTH - MEP Works Package - 2240072 - KORTEK | 1TB01006.01.CN.009C05.00 | 1TB01006.01.CN.009C05.01 | 1TB01006.01.CN.009C05.02
1.TB.01.012.01 | Four Seasons | Alcatop | 012C33 | ALC - Alcatop Package - Fourseasons | ALCATOP | Contractor |  | CN | 01 | CN.012C33 | ALC - Alcatop Package - Fourseasons - Alcatop | 1TB01006.01.CN.012C33.00 | 1TB01006.01.CN.012C33.01 | 1TB01006.01.CN.012C33.02
1.TB.01.003.01 | AMAALAYachtClub | Al Futtaim Pioneer | 003C328 | Al Futtaim Pioneer Elevators | Al Futtaim | Contractor |  | CN | 01 | CN.003C328 | Al Futtaim Pioneer Elevators - Al Futtaim Pioneer | 1TB01006.01.CN.003C328.00 | 1TB01006.01.CN.003C328.01 | 1TB01006.01.CN.003C328.02
1.TB.01.003.01 | AMAALAYachtClub |  | 003D14 | TRA - Zatca Integration with Reachware | TRA | Consultant | Reachware installation | FFEOSE | 01 | FFEOSE.003D14 | TRA - Zatca Integration with Reachware - | 1TB01006.01.FFEOSE.003D14.00 | 1TB01006.01.FFEOSE.003D14.01 | 1TB01006.01.FFEOSE.003D14.02
1.TB.01.003.01 | AMAALAYachtClub |  | 003D14 | TRA - Zatca Integration with Reachware | TRA | Consultant | Reachware installation | FFEOSE | 01 | FFEOSE.003D14 | TRA - Zatca Integration with Reachware - | 1TB01006.01.FFEOSE.003D14.00 | 1TB01006.01.FFEOSE.003D14.01 | 1TB01006.01.FFEOSE.003D14.02
1.TB.01.006.99 | VBH_PROJECT WIDE | 2230277 | 006C22 | Shandong Tiejun Electric Power Engineering Co. LTD. Branch | SHANDONG | Contractor |  | CN | 99 | CN.006C22 | Shandong Tiejun Electric Power Engineering Co. LTD. Branch - 2230277 | 1TB01006.99.CN.006C22.00 | 1TB01006.99.CN.006C22.01 | 1TB01006.99.CN.006C22.02
1.TB.01.009.99 | MH3 | IMAR MH3 | 009C09 | IMAR Overseas Saudi Arabia Co. W.L.L. | IMAR | Contractor |  | CN | 99 | CN.009C09 | IMAR Overseas Saudi Arabia Co. W.L.L. - IMAR MH3 | 1TB01006.99.CN.009C09.00 | 1TB01006.99.CN.009C09.01 | 1TB01006.99.CN.009C09.02
1.TB.01.009.99 | MH3 | FIBREX LLC | 009C35 | Fibrex LLC | FIBREX | Contractor |  | CN | 99 | CN.009C35 | Fibrex LLC - FIBREX LLC | 1TB01006.99.CN.009C35.00 | 1TB01006.99.CN.009C35.01 | 1TB01006.99.CN.009C35.02
1.TB.01.009.99 | AMAALAYachtClub | OCIP Insurance | 003C314 | RJT- OCIP Insurance Premium - Declaration 11 | OCIP Insurance | Contractor |  | CN | 99 | CN.003C314 | RJT- OCIP Insurance Premium - Declaration 11 - OCIP Insurance | 1TB01006.99.CN.003C314.00 | 1TB01006.99.CN.003C314.01 | 1TB01006.99.CN.003C314.02
1.TB.01.003.01 | AMAALAYachtClub | Operation Systems | 003D20 | Samtiah Arabis Ltd - Operation systems | Samtiah Arabia - Operations systems | Contractor |  | FFEOSE | 01 | FFEOSE.003D20 | Samtiah Arabis Ltd - Operation systems - Operation Systems | 1TB01006.01.FFEOSE.003D20.00 | 1TB01006.01.FFEOSE.003D20.01 | 1TB01006.01.FFEOSE.003D20.02
Village Boutique Branded Condos
Village Boutique Residence
Village Boutique Hotel
Village Boutique Hotel-Project Wide

## Data Input
PROGRAMME: | MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: | 1TB01003
ASSET NAME: | AMAALA YACHT CLUB |  | UPDATE INFORMATION IN RED EACH MONTH
ASSET CODE: | 1TB01003.01
Client: | AMAALA
Location: | AL WAJH SAUDI ARABIA
REPORT NO: | MONTHLY REPORT NO. 49
REPORTING PERIOD: | OCTOBER 2026
AMAALA Ref | AMAALA/AYC/MONTHLY REPORT 01
AMAALA Ref | AMAALA/AYC/MONTHLY REPORT 01
Report No Short: | NO. 49
|  |  | Done | Not Done
TO DO |  |  | √ | X
MOM | MINUTES OF MEETINGS | X | √
EXECUTIVE SUMMARY | EXECUTIVE SUMMARY DASHBOARD | X | √
EXECUTIVE SUMMARY | STAKEHOLDER EXECUTIVE REVIEW | X | √
EXECUTIVE SUMMARY | EARLY WARNINGS | X | √
EXECUTIVE SUMMARY | ACC | X | √
SCHEDULE A | LEVEL 1 - EXECUTIVE SUMMARY | X | √
SCHEDULE B | LEVEL 2 - DETAILED SUMMARY | X | √
SCHEDULE C | CHANGE MANAGEMENT TRACKER | X | √
SCHEDULE D | RISK AND OPPORTUNITIES | X | √
SCHEDULE E | CLAIMS AND DISPUTES | X | √
SCHEDULE F | PROVISIONAL SUMS | X | √
SCHEDULE G | BONDS AND INSURANCE TRACKING LOG | X | √
SCHEDULE H | INVOICE AND PAYMENT TRACKING LOG | X | √
SCHEDULE I | CASH FLOW
SCHEDULE J | BUDGET TRANSFER TRACKER
SCHEDULE K | PROCUREMENT STATUS
Distribution
Head of Commercial: |  | Paul Donaghy
Executive Commercial Director: |  | Shane Fairfield
Senior Commercial Director: |  | Michael Hansen
Associate Commercial Director: |  | Blake Lombard
Senior Project Director: |  | Christopher Burke
Project Team
Executive Project Director:
Senior Project Director: |  | Christopher Burke
Planning Director |  | Sudhakaran Kodicheth
Senior Design Director:
Senior Commercial Director: |  | Michael Hansen
Associate Commercial Director |  | Blake Lombard
Procurement Lead (Red Sea): |  | Joe Honeine
Asst. Manager - Quantity Surveying: |  | Jose Chavenia

## dropdowns
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Initiated By: | Approval Status | Yes/No: | VE | Change Initiated by | Approval Status Claims: | Contractor or Sub Contractor | Packages | Contractor Details |  | PS Drop down | Insurances | COST REPORT EFFECTIVE FIGURE | Reporting Period | REFF PO Ref | VENDOR TYPE
Design Development | APPROVED | YES | Contract | Consultant | Rejected | ALS - Early Works | DAE -Prf Fees | DEWAN ARCHI |  | PENDING | Professional Indemnity | ACTIVE | Monthly Report No 1 - Oct'22 | 2200340 | Contractor
Scope Gap | REJECTED | NO | Consultant | Contractor | Approved | JVD - Early Works | HKL (Design Comp Fees)-Prf Fees | HKS Design Consultant |  | EXPENDED | Third Party Liability | NOT ACTIVE | Monthly Report No 2 - Nov'22 | 2200317 | Contractor
Scope Overlap | PENDING |  | Contractor | Employer | Pending | ALS - Main Works | HKL (Design Architect)-Prf Fees | HKS Design Consultant |  | PARTIALLY EXPENDED | Workmens Compensation |  | Monthly Report No 3 - Dec'22 | 2200571 | Contractor
Provisional Sum | REVISED & RE-SUBMIT |  |  |  | Approved inc. in Lump Sum | Five Oceans Marine Survey | ATM-Prf Fees | ATM |  |  | Contractors all Risk |  | Monthly Report No 4 - Jan'23 | 2200571 | Contractor
Final Account | SUPERSEDED |  |  |  | Approved (Authority) | Becon Development Co | T&T-Prf Fees | 1: Turner & Townsend; 4: Advance Payment Bond; 6: Monthly Report No 5 - Feb'23
Operator's Change | CANCELLED |  |  |  | Approved (proceed to ERI) | WSP Consultants | LUI-Prf Fees | 1: SIC; 4: Performance Bond; 6: Monthly Report No 6 - Mar'23
Contractor's Performance | TRANSFERRED |  |  |  |  | Five Oceans Coral Relocation | ZFP-Prf Fees | 1: NSCC; 4: Retention Bond; 6: Monthly Report No 7 - Apr'23
EOT - Contractor's Performance | REVIEW COMPLETE | [5 empty] | KAA-Mgt Fees | 1: KAA; 4: Marine and Hull; 6: Monthly Report No 8 - May'23
Extension of Time (EOT) | [6 empty] | ECC-Mgt Fees | 1: GBC; 4: Plant and Equipment; 6: Monthly Report No 9 - Jun'23
Omission | [6 empty] | ECC-Mgt Fees (Accom & Transpo) | 1: CML; 4: Vehicle; 6: Monthly Report No 10 - Jul'23
Omission - Contractor Performance | [6 empty] | CML-Mgt Fees | 1: Foster + Partners; 4: Trade License; 6: Monthly Report No 11 - Aug'23
Scope transfer - Contractor's Performance | [6 empty] | SOI TB Ground Improvement Works | 1: Langan; 6: Monthly Report No 12 - Sep'23
Contractor's Performance | [6 empty] | SOI TB Ground Improvement Works (PS) | 1: Areen; 6: Monthly Report No 13 - Oct'23
Prelims |  |  | Initiated By Amaala Representative |  | Status |  | GST-LEED Fees | 1: Al Rahji Takaful; 6: Monthly Report No 14 - Nov'23
Back Charge |  |  | BLAKE |  | RFC - Pending from Contractor / Consultant |  | NSCC - Piling | 1: Baytur; 6: Monthly Report No 15 - Dec'23
|  |  | FOWZULLAH |  | RFC - Pending from Engineer |  | GBC - Sustainability Accreditation | 1: DEPA; 6: Monthly Report No 16 - Jan'24
Project Stage |  |  | HANEEF |  | RFC - Pending to Upload on Aconex |  | Jensen Hughes-Prf Fees COO 30 | 1: Medtel; 6: Monthly Report No 17 - Feb'24
Pre Contract Variation |  |  | JOSE |  | RFC - Pending for Approval on Aconex |  | Langan-Prf Fees | 1: New Contractor; 6: Monthly Report No 18 - Mar'24
Post Contract Variation |  |  | MIKE . H |  | RFC - Approved |  | Langan-Prf Fees (Provisional) | 1: ESCCO; 6: Monthly Report No 19 - Apr'24
Consultant Variation |  |  | SHIHAM |  | RFC - Rejected |  | Jensen Hughes-Prf Fees | 1: RAQTAN; 6: Monthly Report No 20 - May'24
Pre Contract - Consultant Variation |  |  | VASEEF |  | RFC - Cancelled |  | Executive Architect Services | 1: ARMETAL; 6: Monthly Report No 21 - Jun'24
Post Contract - Consultant Variation |  |  | VEDHAKUMAR |  | PVO - Pending from Contractor / Consultant |  | MOM - Building Permit Fee | 1: ALUTEC; 6: Monthly Report No 22 - Jul'24
|  |  | CLOSED |  | PVO - Pending from Engineer |  | Saudi Baytur - Main Works | 1: Al Fanar; 6: Monthly Report No 23 - Aug'24
|  |  | OTHER |  | PVO - Pending to Upload on Aconex |  | SAB - Civil and Arch Works, MEPD & ICT/ELV | 1: Abu Dhabi Precast; 6: Monthly Report No 24 - Sep'24
[5 empty] | PVO - Pending for Approval on Aconex |  | New Contract - Civil and Arch Works, MEPD & ICT/ELV | 1: HAS; 6: Monthly Report No 25 - Oct'24
[5 empty] | PVO - Rejected |  | SAB - Civil and Arch Works | 1: MASS - GRC Works; 6: Monthly Report No 26 - Nov'24
[5 empty] | VO - Pending from Contractor / Consultant |  | SAB - MEPD | 1: Tamimi; 6: Monthly Report No 27 - Dec'24
[5 empty] | VO - Pending from Engineer |  | SAB - ICT / ELV | 1: MAS; 6: Monthly Report No 28 - Jan'25
ACTIONEE |  |  |  |  | VO - Pending to Upload on Aconex |  | Medtel - STO Façade Mock-up | 1: KORTEC; 6: Monthly Report No 29 - Feb'25
CLIENT |  |  |  |  | VO - Pending for Approval on Aconex |  | ESCCO - Vertical Transport | 1: ALCATOP; 6: Monthly Report No 30 - March'25
ENGINEER |  |  |  |  | VO - Rejected |  | Hard and Soft Landscaping | 1: AL FUTTAIM
CONSULTANT |  |  |  |  | DVO - Pending from Contractor / Consultant |  | DEPA Interior Fitout | 1: EURO CONSULT
DESIGN CONSULTANT |  |  |  |  | DVO - Pending from Engineer |  | FF&E and OSE Procurement Agent | 1: JensenHuges
CONTRACTOR |  |  |  |  | DVO - Pending to Upload on Aconex |  | Façade & Glazing Works | 1: TEIJUN
[5 empty] | DVO - Pending for Approval on Aconex |  | RAQTAN - Kitchen and Laundry | 1: IMAR MH3
[5 empty] | DVO - Accepted |  | Loose FF&E items (FOH) | 1: FIBREX MH3
[5 empty] | DVO - Rejected |  | Loose FF&E items (BOH)
Areen - FF&E OS&E Items
Art Work
Al Rahji Takaful - Owner Controlled Insurance Program
| PROGRAM NAME | PROGRAM CODE | PROJECT NAME | PROJECT CODE | ASSET | ASSET CODE | ARMETAL - Reflective ceiling
ABU DHABI PRECAST - GRC Cladding
| MARINA VILLAGE | 1.TB.01.100 | MARINA LIFESTYLE HOTEL & VILLAGE | 1.TB.01.002 | MARINA LIFESTYLE BRANDED CONDOS | 1.TB.01.002.02 | Al Fanar - MEP Labour Supply
SR.NO. | TRIPLE BAY CENTRAL | 1.TB.02.200 | AMAALA YATCH CLUB | 1.TB.01.003 | MARINA LIFESTYLE HOTEL | 1.TB.01.002.03 | MAS - Amphitheatre
| WELLNESS CORE | 1.TB.03.300 | RED SEA MARINE LIFE INSTITUTE | 1.TB.01.005 | LUXURY VILLAGE DISTRICT | 1.TB.01.002.01 | MAS - Labour Supply - Wet Works
1 | TRIPLE BAY WIDE | 1.TB.04.400 | VILLAGE BOUTIQUE HOTEL | 1.TB.01.006 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MAS - Various Works
2 | OCEAN GOLF | 1.TB.05.500 | MARINA HOTEL 3 | 1.TB.01.009 | RED SEA MARINE LIFE INSTITUTE | 1.TB.01.005.01 | Marina Village Wide - MS Budget Hold
3 | TRIPLE BAY EAST | 1.TB.06.600 | FLOATING DIVING CLUB | 1.TB.01.001 | VILLAGE BOUTIQUE BRANDED CONDOS | 1.TB.01.006.01 | Marina Village Wide - CN Budget Hold
4 | TRIPLE BAY SOUTH | 1.TB.07.700 | THE MARINA | 1.TB.01.031 | VILLAGE BOUTIQUE BRANDED VILLAS | 1.TB.01.006.02 | HAS - External Scaffolding Works
5 | CIVIC ASSETS | 1.TB.09.035 |  |  | VILLAGE BOUTIQUE HOTEL | 1.TB.01.006.03 | MASS - GRC Repair Works
6 | FOURSEASON | 1.TB.12.100 | FOURSEASONS | 1.TB.01.012 | MARINA HOTEL 3 | 1.TB.01.009.01 | GST- Sustainability Accreditation Services
7 |  |  |  |  | FLOATING DIVING CLUB | 1.TB.01.001.01 | Enviro - Deep Cleaning
8 |  |  |  |  | THE MARINA | 1.TB.01.031.01 | Extraordinary Cart - Buggy Cart | 6: Monthly Report No 13 - Oct'23
9 | FOURSEASON | 1.TB.12.100 | FOURSEASONS | 1.TB.01.012 | FOURSEASONS | 1.TB.01.012.01 | Alutec - Aluminum and Glazing Works
10 | [6 empty] | AlFalak Electronic - HPE Servers | 5: External Factors – Authorities led change
11 | [6 empty] | Sevenrooms Inc | 5: External Factors – BoD instructed change
[7 empty] | Infor Co | 5: External Factors – Operator’s change
[7 empty] | Reachware Integration | 5: External Factors – Third party damage
Logistics – Accommodation constraints
[7 empty] | Prelims - Emaar Suhali | 5: Logistics – Constructability reasons
[7 empty] | Prelims - Mohammad Alharbi Medical Company | 5: Project Management – Cost reduction
[7 empty] | Prelims - Al Anan Travels and Tours | 5: Project Management – Late appointment – Consultant
[7 empty] | Prelims - Al drees Petroleum | 5: Project Management – Late appointment – Contractor
[7 empty] | Prelims - Salim Hamed Cleaning | 5: Project Management – Late appointment – Operator
[7 empty] | Prelims - Clean Coast for Contracting | 5: Project Management – Scope – gap / omission
[7 empty] | Prelims - Sami General Contracting | 5: Project Management – Scope – new
[7 empty] | Prelims - Eastern Horizons Foundation Transportation Comp | 5: Project Management – Scope – overlap
[7 empty] | Prelims - Jak Generation Cont Co LLC | 5: Provisional Sums
[7 empty] | Prelims - Intelligent General Cont Co Equipment | 5: Revenue related – Aesthetic enhancement
[7 empty] | Prelims - Al Rai Modern Water Factory | 5: Revenue related – Guest experience
[7 empty] | Direct Works - Madar Building material Co | 5: Revenue related – Revenue enhancement
[7 empty] | Direct Works - Juffali Technical Equipment Company | 5: Supply chain – Consultant performance
[7 empty] | Direct Works - USG Middle East Ltd. Co | 5: Supply chain – Contractor cashflow
[7 empty] | Direct Works - Abu Dhabi Precast | 5: Supply chain – Contractor performance
Direct Works - SAMIF
[7 empty] | Direct Works - SAUDI MANPOWER SOLUTIONS CO | 5: Design Development/Improvement
[7 empty] | Direct Works - Fosam Company LTD | 5: Scope Gap
[7 empty] | Direct Works - Glow Arabia Trading | 5: Scope Overlap
[7 empty] | Direct Works - HRFA | 5: Provisional Sum
[7 empty] | Direct Works - NESMA | 5: Final Account
Operator's Change
[7 empty] | Prelims - NEXTWARE INTERNATIONAL SUPPLY | 5: Contractor's Performance
[7 empty] | Direct Works - BROOQ ALAMAAN TRAD COMPANY | 5: EOT due to Contractor's Performance
[7 empty] | Direct Works - Abeer Munawer Al Shamari | 5: Extension of Time (EOT)
[7 empty] | Direct Works - Yaz Development Contracting | 5: Back Charge
Direct Works - Naffco
Direct Works - GESR Alarab
Direct Works - Jameel Mohamed Hussain Alqatafa Cont Est
Prelims - Virtual Projects DMCC
Direct Works - MEDTEL
Prelims - Raddad Al adinah
Direct Works - Noreom
Direct Works - Isam Kabani & Partners
Direct Works - ARABIAN TESTING EVOLUTION COMPANY
Prelims - Ahmed Bin Salem Bin Dagher
Prelims - Bahamdoon Trading
Direct Works - Wood Expert
Prelims - Lumi Rentals
Direct Works - Energy & Building Master
Direct Works - ACES
Prelims - Filter Expert Trading
Prelims - Abu Nayyan
Direct Works - International Company for Building Materials LTD
Direct Works - Al Hayat
Direct Works -Saint Gobain
Prelims - Ihsan Muhammed Thakir Idress Trading
Prelims - Ramzi Abbas Mohd. Sayed Est.
Direct Works- AAMTAC Company LTD
Prelims - Al Rayi Water
Direct Works - DOSAR Al Najd
Prelims - GLSAN Contracting Company
Prelims - GLSAN Contracting Company (Red Sea)
Direct Works - Fast Steps
Direct Works - TANSEEQ
Prelims - Masa Equipment Est
Prelims - Al Tala'a International Transportation Co
Direct Works - Alcatop
Direct Works - Saveto Saudi Vetonit Co Ltd
Prelims - Saudi Brokers
Direct Works - Top Construction Co Ltd
Direct Works - TBK Metal
Prelims - Aknan Al Bena
Direct Works - Lakeshore
Tamimi (SAB Accommodation Payment)
Birch Street
Saudico Electronic Systems
Remaining budget - Professional Fees
Remaining budget - Management Supervision
Remaining budget - Commercial Management
Remaining budget - Construction Works
Remaining budget - FF&E and OSE
External - Budget for Approval
External - Pre Approved
External - Approved - Revised Asset Budget Allocation (02/02/2023)
IDC98998.98 (20-Jan-2025)
Marina Hotel 3 - CN Hold
Marina Hotel 3 - PS Hold
MS - Budget Hold
PS - Budget Hold
CN - Budget Hold
FF&E OSE - Budget Hold
CM - Budget Hold
Jensen Hughes
KTH - MEP Works Package - 2240072 - KORTEK
ALC - Alcatop Package - Fourseasons
PeopleVine Implementation
Al Futtaim Pioneer Elevators - Al Futtaim Pioneer
TEIJUN VBH
IMAR MH3
FIBREX MH3
RJT- OCIP Insurance Premium - Declaration 11
Samtiah Arabis Ltd - Operation systems

## MoM
TRIPLE BAY - MARINA VILLAGE - AYC - MONTHLY REPORT
MINUTES OF MEETING
FINANCIAL OVERVIEW | [5 empty] | * PROCUREMENT STATUS (CONSTRUCTION RELATED WORKS ONLY) |  |  |  | KEY PERFORMANCE INDICATORS (KPI)
Description |  |  | Date Reported | Action | Resolved | Description | Date Reported | Action | Resolved | Description | Date | Action | Resolved
PVO related to NSCC : 1. Savings indicated in the NSCC's PVO to be revisited/reevaluated 2. Since it is a D&B Contract and NSCC proposed design is fit for the purpose, then AMAALA may not be entitled to savings. 3. Notice to NSCC to be issued to proceed with the works to expedite the progress at site 4. Ben advised the changes to be evaluated fairly/ reasonably to pay provided they continue with the works . (For info, BL/MH confirmed Soil investigation report and bore hole (3 No) reports issued to NSCC during RFP stage) |  |  | 2022-11-09 | Commercial | In Process |  |  |  |  | Currently 2 No of claims are under review, to be evaluated fairly. | 2022-11-09 | Commercial | In Process
2452499.72
* PROVISIONAL SUMS STATUS (CONSTRUCTION RELATED WORKS ONLY)
KEY PERIOD MOVEMENTS | [5 empty] | Description | Date Reported | Action | Resolved
Description |  |  | Date Reported | Action | Resolved
PACKAGE PROGRAMME STATUS
[10 empty] | Description | Date | Action | Resolved
CHANGE MANAGEMENT OVERVIEW
[6 empty] | Description | Date Reported | Action | Resolved
CURRENT COMMITTED VALUE VS WORKS COMPLETE
Description |  |  | Date Reported | Action | Resolved
Dewan fees to be merged in NSCC's final account settlement |  |  | 2022-11-09 | Commercial | In Process
GENERAL COMMENTS
[10 empty] | Description | Date | Action | Resolved
| Condemned | 0% - 20%
| Poor | 21% - 39%
| Fair | 40% - 59%
| Good | 60% - 75%
| As New | 76% - 100%
Option 1 |  | AED
Option 2 |  | OMR
Option 3 |  | 1
2
0
BUA ft² | #REF! | #REF! | #REF! |  | #REF!
GFA ft² | #REF! | #REF! | #REF! |  | #REF!
BUA m² | #REF! | #REF! | #REF! |  | #REF!
GFA m² | #REF! | #REF! | #REF! |  | #REF!
Efficiency | #REF! | #REF! | #REF! |  | #REF!

## Cover
33
35
2025-01-18
TRIPLE BAY - MARINA VILLAGE - AMAALA YACHT CLUB - MONTHLY REPORT
October 2026 Report
Commercial
REPORTING NOTES
Data Cut-off Date: 30 September 2026
Reporting Date: 31st of the Month
Data projected from cut-off date until 31st of month

## Index
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
INDEX
PAGE NO
EXECUTIVE SUMMARY - EXECUTIVE SUMMARY DASHBOARD |  | 2
EXECUTIVE SUMMARY - STAKEHOLDER EXECUTIVE REVIEW |  | 3
EXECUTIVE SUMMARY - EARLY WARNINGS |  | 5 | 5,6
EXECUTIVE SUMMARY - ACC |  | 8 | 7,12
COST REPORT EXECUTIVE SUMMARY - LEVEL 1 |  | 16
COST REPORT EXECUTIVE SUMMARY - LEVEL 2 |  | 17
SCHEDULE A - LEVEL 1 - EXECUTIVE SUMMARY |  | 18
SCHEDULE B - LEVEL 2 - DETAILED SUMMARY |  | 19 | 16,19
SCHEDULE C - CHANGE MANAGEMENT TRACKER |  | 23 | 20,26
SCHEDULE D - RISK AND OPPORTUNITIES |  | 31
SCHEDULE E - CLAIMS AND DISPUTES |  | 32
SCHEDULE F - PROVISIONAL SUMS |  | 33
SCHEDULE G - BONDS AND INSURANCE TRACKING LOG |  | 34 | 30,32
SCHEDULE H - INVOICE AND PAYMENT TRACKING LOG |  | 37
SCHEDULE I - CASH FLOW |  | 65
SCHEDULE J - BUDGET TRANSFER TRACKER |  | 66
SCHEDULE K - PROCUREMENT STATUS |  | 85
Distribution
Head of Commercial: - Paul Donaghy
Executive Commercial Director: - Shane Fairfield
Senior Commercial Director: - Michael Hansen
Associate Commercial Director: - Blake Lombard
Senior Project Director: - Christopher Burke
PREPARED BY : | REVIEWED BY : | APPROVED BY :
Asst. Manager - Quantity Surveying: - Jose Chavenia | Associate Commercial Director - Blake Lombard | Senior Commercial Director: - Michael Hansen

## Executive Summary
TRIPLE BAY - MARINA VILLAGE - AMAALA YACHT CLUB - MONTHLY REPORT
| FINANCIAL OVERVIEW | [5 empty] | * PROCUREMENT STATUS (CONSTRUCTION RELATED WORKS ONLY) | [5 empty] | KEY PERFORMANCE INDICATORS (KPI)
|  | October 2026 |  | September 2026 |  | Period Movement | Contractor / Consultant Package | Original pkg Budget | Revised Package Budget | Variance | Contract Award | (Saving) / Additional | DETERMINED VARIATION ORDERS (DVO)
| Approved / Current Budget | 583847550.86 |  | 584492905.6 |  | -645354.74 | Construction Works | [6 empty] | Total | Previous | Current
[7 empty] | PS.003D01 - Dewan Architect | 5973808 | 5973808 | 0 | 5973808 | 0 | Value of PVO (Planned) | 33878350.355 | 33878350.355 | 0
| Contracts Awarded | 553452418.18 |  | 553452418.18 |  | 0 | PS.003D02 - HKS Architect - Competition | 555960.36 | 555960.36 | 0 | 555960.36 | 0 | Value of DVO (Actual) | 6873283.775 | 6873283.775 | 0
[7 empty] | PS.003D03 - HKS Architect - Design | 10891204 | 10891204 | 0 | 10891204 | 0 | Variance % PVO vs DVO | -392.9% | -392.9% | 0%
| Committed Procurement Packages | 0 |  | 0 |  | 0 | PS.003D04 - Applied Technology | 93750 | 93750 | 0 | 93750 | 0 | Count of DVO Closed | 118 | 118 | 0
[7 empty] | MS.003F02 - Khatib & Alami 2230031 | 17975993 | 17975993 | 0 | 13059930 | -4916063 | DVO Pending < 30 days | 2 | 0 | 2
| Determined Variation Orders (DVO) | 6820135.48 |  | 6820135.48 |  | 0 | PS.003D05 - Langan International UK Limited 2230042 | 172368.42 | 172368.42 | 0 | 172368.42 | 0 | DVO Pending > 30 < 60 days | 1 | 1 | 0
[7 empty] | PS.003D06 - Ministry of Municipality and Rural Affairs (Tabuk) | 45677.6 | 45677.6 | 0 | 45677.6 | 0 | DVO Pending < 60 > 90 days | 4 | 4 | 0
| Committed Costs | 560272553.66 |  | 560272553.66 |  | 0 | PS.003F01 - Zuhair Fayez and Partners 2230041 | 106231.5 | 106231.5 | 0 | 106231.5 | 0 | DVO Overdue (>90 days) | 13 | 15 | -2
[7 empty] | PS.003F04 - Jensen Hughes Saudi Arabia Co 2230180 | 127291.9 | 127291.9 | 0 | 127291.9 | 0
| Potential Variation Orders (PVO) | -16136787.47 |  | -16136787.47 |  | 0 | PS.003F10 - Langan-Prf Fees COO 30 |  | 38103.2 | 38103.2 | 38103.2 | 38103.2 | 90 DAY CASH FLOWS | MARCH | 2026 |  | FORECAST
[7 empty] | CN.003C20 - Green Business Cert | 4500 | 23094.49 | 18594.49 | 23094.49 | 18594.49 | VARIANCE | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30
| Request for Change (RFC) | 3585562.5 |  | 3801447.69 |  | -215885.19 | CN.003C13 - SOI TB Gr Improvement | 3082688.7 | 3082689 | 0.3 | 3082689 | 0.3 | NSCC - Triple Bay Piling (AYC only) | 0 | 0 | 0 | 0 | 0
[7 empty] | CN.003C13 - NSCC - Piling - AYC Only | 18698534 | 18698534 | 0 | 18698534 | 0 | DEWAN Architecture | 0 | 0 | 0 | 0 | 0
| Approved Claims | 0 |  | 0 |  | 0 | CN.003C03 - SAB - Civil and Arch Works, MEPD & ICT/ELV | 169752875.4261 | 273501320 | 103748444.5739 | 260955414.4 | 91202538.9739 | SIC TB Ground Improvement Works | 0 | 0 | 0 | 0 | 0
[7 empty] | Direct Payments for SAB's Subcontractors and Suppliers | 0 | 0 | 0 | 42594259.73 | 42594259.73 | GBC - Sustainability Accreditation | 0 | 0 | 0 | 0 | 0 |  |  |  |  | -215885.19
| Early Warnings | 32891648.893 |  | 32891648.893 |  | 0 | CN.003C21 - STO Façade Mock-up -(MWN) 2230075 | 0 | 0 | 0 | 834298.55 | 834298.55 | HKS - Design Competition | 0 | 0 | 0 | 0 | 0
[7 empty] | CN.003F03 - Vertical Transportation (ESCCO) 2230178 | 2153850.9655 | 2675472.9955 | 521622.03 | 2675473 | 521622.0345 | HKS - Design Architect | 0 | 0 | 0 | 0 | 0
| Uncommitted Cost | 20340423.923 |  | 20556309.113 |  | -215885.19 | CN.003C08 - Kitchen & Laundry Works (Al Raqtan) 2230205 | 5907720 | 4695209 | -1212511 | 4695209 | -1212511 | ATM - Rapid review | 0 | 0 | 0 | 0 | 0
[7 empty] | CN.003C09 - Fitout Works (DEPA) | 27478729.2618 | 62092796 | 34614066.7382 | 75969227 | 48490497.7382 | SAB - AMAALA Yacht Club Construction Contract | 5755976.9 | -2856041.1304 | -3483605.7739 | 0 | 1787346
| Current Budget Hold | 0 |  | 0 |  | 0 | CN.003C27 - Façade & Glazing Works (Alutec) | 0 | 0 | 0 | 29899670.55 | 29899670.55 | LANGAN International UK, LTD | 0 | 0 | 0 | 0 | 0
[7 empty] | MS.003F07 - Euro Consult (COO 6) | 0 | 182184.38 | 182184.38 | 182184.38 | 182184.38 | Medtel - W.N. WLL | 0 | 0 | 0 | 0 | 0
| Projected Cost to Complete | 580612977.583 |  | 580828862.773 |  | -215885.19 | MS.003F09 - Euro Consult (COO 27) | 0 | 54000 | 54000 | 54000 | 54000 | Raqtan (Kitchen & Laundry) | 0 | 0 | 0 | 159337 | 0
[7 empty] | FFEOSE.003F06 - FF&E and OSE Procurement Agent (Areen Design Ltd) | 0 | 1107465.88 | 1107465.88 | 1107465.88 | 1107465.88 | ESCCO (Vertical Transportation) | 0 | 0 | 0 | 334075.28 | 52335.24 |  |  |  |  | 27005066.58
| KEY PERIOD MOVEMENTS | [5 empty] | PS.003F08 - CML (Independent Commissioning Agent) COO 7 | 0 | 2406500 | 2406500 | 2406500 | 2406500 | Khatib & Alami (Management Supervison) | 0 | 0 | 0 | 0 | 78720
| Description |  |  |  | Amount |  | CN.003C31 - MAS - Wet Works | 0 | 4004000 | 4004000 | 4004000 | 4004000 | DEPA (Interior Fitout) | 0 | 0 | 0 | 1737945 | 3226545.62
| DVO High Level Overview |  |  |  | 0 |  | CN.003C32 - MAS - Amphitheatre Works | 0 | 1078892.27 | 1078892.27 | 1078892.27 | 1078892.27 | ALUTEC | 0 | 0 | 0 | 0 | 49611.16
[7 empty] | CN.003C34 - Al Fanar - MEP Labour Supply | 0 | 23125000 | 23125000 | 23125000 | 23125000 | Areen Design | 0 | 0 | 0 | 0 | 4331572.5
| PVO High Level Overview |  |  |  | 0 |  | CN.003C34 - ARMETAL - Reflective ceiling | 0 | 7129950 | 7129950 | 7129950 | 7129950 | MAS Labour | 0 | 0 | 0 | 0 | 1016402.21
[7 empty] | CN.003C34 - Al Rahji Takaful - Owner Controlled Insurance Program | 0 | 89047.06 | 89047.06 | 73970.78 | 73970.78 | MAS Amphitheatre | 0 | 0 | 0 | 0 | 0
[7 empty] | CN.003C35 - HASSAN ALLAM - External Scaffoldings | 0 | 3096124.9 | 3096124.9 | 3096124.9 | 3096124.9 | Al Fanar Labour | 0 | 0 | 0 | 1972028 | 0
| RFC High Level Overview |  |  |  | -215885.19 |  | PS.003F12 - GST - Sustainability Accreditation Services | 0 | 133000 | 133000 | 133000 | 133000 | CML | 0 | 0 | 0 | 241100 | 164253.85
[7 empty] | CN.003CF13 - Enviro - Deep Cleaning | 0 | 799625.31 | 799625.31 | 799625.31 | 799625.31 | EuroConsult | 0 | 0 | 0 | 15762.54 | 0
[7 empty] | FFEOSE.003F02 - Loose FF&E Items (FOH) | 12800000 | 25558750 | 12758750 | Included in the SEED Fund issued as VO to Areen | 0 | EuroConsult (Accom and Transport) | 0 | 0 | 0 | 0 | 0
| Early Warnings/Contract Award |  |  |  | 0 |  | Included in FF&E FOH - Loose FF&E Items (BOH) | 340000 | 470000 | 130000 |  | 0 | Hassan Allam | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 224
[7 empty] | FFEOSE.003F02 - OS&E Items | 3543829 | 8681174.56 | 5137345.56 |  | 0 | ARMetal | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 8
[7 empty] | Included in OS&E - Art Works | 2400000 | 2874723 | 474723 |  | 0 | Total | 5755976.9 | -2856041.1304 | -3483605.7739 | 4460247.82 | 10706786.58 |  |  |  |  | 232
[7 empty] | FFEOSE.003F11 - Extraordinary Cart | 0 | 397876 | 397876 | 397876 | 397876
| Current Budget Hold Movement for this Month |  |  |  | 0 |  | FFEOSE.003D09 - Saudico Electronic Systems | 0 | 353487.06 | 353487.06 | 353487.06 | 353487.06 | FORMAL NOTICE OF CLAIM
[7 empty] | FFEOSE.003D07 - Birch Street | 0 | 115998.98 | 115998.98 | 115998.98 | 115998.98 |  | Total | Previous | Current |  |  | Claims Pending < 120 > 180 days | 0 | 1 | -1
| Total |  |  |  | -215885.19 |  | FFEOSE.003D10 - AlFalak Electronic - HPE Servers | 0 | 16655 | 16655 | 16655 | 16655 | Amount Claimed | 6747085.3268 | 6747085.3268 | 0
| CURRENT COMMITTED VALUE VS WORKS COMPLETE | [5 empty] | FFEOSE.003D15 - Saudico Electronic Systems | 0 | 34719 | 34719 | 34719 | 34719 | Amount Granted | 0 | 0 | 0
[7 empty] | FFEOSE.003D11 - Sevenrooms Inc | 0 | 3633.9 | 3633.9 | 3633.9 | 3633.9 | EOT Claimed (Time only) | 668 | 668 | 0
| Contractor / Consultant Package | Current Committed Value (Incl PS) | Application Received to date (incl Accrual) | Certified Works to Date | Works to Complete | % Certified | FFEOSE.003D12 - Saudico Electronic Systems | 0 | 58307.19 | 58307.19 | 58307.19 | 58307.19 | EOT Granted (Time only) | 378 | 378 | 0
| Professional Services | 25075830.1 | 24713374.87 | 24672062.58 | 403767.52 | 98.39% | FFEOSE.003D14 - Reachware Integration | 0 | 57135 | 57135 | 57135 | 57135 | Claims Pending < 60 days | 0 | 0 | 0
| PS.003D01 - Dewan Architects & Engineers 2200445 | 9290526.1 | 9068064.5 | 9026746.1 | 263780 | 97.16% | Total | 282105012.1334 | 482577752.9555 | 200472740.8221 | 514720720.35 | 251699537.2166 | Claims Pending > 60 < 120 days | 0 | 0 | 0
| PS.003D02 - HKS Architects Ltd - Design Competition Fees 2200010 | 555960.36 | 555960 | 555960 | 0.36 | 100% | [6 empty] | Claims Overdue (>180 days) | 3 | 3 | 0
| PS.003D03 - HKS Architects Ltd - Design Architect Fees 2200375 | 10801429 | 10801428.46 | 10801428.46 | 0.54 | 100% | CN.100C01 (MVW) - Hard and Soft Landscaping | 13329115.5849 | 0 | -13329115.5849 | 19746260.64 | 6417145.0551
| PS.003D04 - Applied Technology and Management Inc (Dubai BR)s 2210167 | 93750 | 93750 | 93750 | 0 | 100%
| PS.003D05 - Langan International UK Limited 2230042 | 170469.9 | 168421.05 | 168421.05 | 2048.85 | 98.8% | * PROVISIONAL SUMS STATUS (CONSTRUCTION RELATED WORKS ONLY) | [5 empty] | PACKAGE PROGRAMME STATUS
| PS.003F01 - Zuhair Fayez and Partners 2230041 | 106231.5 | 106231.5 | 106231.5 | 0 | 100%
| PS.003F04 - Jensen Hughes Saudi Arabia Co 2230180 | 70591.9 | 0 | 0 | 70591.9 | 0% | Contractor / Consultant Package | Number of PS packages | PS Budget | No expended PS pkg's | PS Award | Remaining to Spend | Contractor / Consultant Package | Commencement Date | Original Completion Date | EOT Received | EOT Granted | Revised Comp Date
| PS.003F10 - Langan-Prf Fees COO 30 | 14303.2 | 0 | 0 | 14303.2 | 0% | Construction Works | [5 empty] | Professional Services
| PS.003D06 - Ministry of Municipality and Rural Affairs (Tabuk) | 45677.6 | 45677.6 | 45677.6 | 0 | 100% | CN.003C13 - SOI TB Ground Improvement Works | 1 | 282972 | 0 | 0 | 282972 | PS.003D01 - Dewan Architects & Engineers 2200445
| PS.003F08 - CML (Independent Commissioning Agent) COO 7 | 3926890.54 | 3873841.76 | 3873847.87 | 53042.67 | 98.65% | PS.003D05 - Langan International UK Limited 2230042 | 1 | 3947.37 | 0 | 0 | 3947.37 | PS.003D02 - HKS Architects Ltd - Design Competition Fees 2200010 | Completed | Completed
| Management Supervision | 14368091.38 | 14261136.64 | 14265377.64 | 102713.74 | 99.29% | [6 empty] | PS.003D04 - Applied Technology and Management Inc (Dubai BR)s 2210167 | Completed | Completed
| MS.003F02 - Khatib & Alami 2230031 | 14131907 | 14078459 | 14082700 | 49207 | 99.65% | PROPOSED VARIATION ORDER (PVO) | [5 empty] | PS.003D05 - Langan International UK Limited 2230042 | Completed | Completed
| MS.003F07 - Euro Consult (COO 6) | 182184.38 | 128677.64 | 128677.64 | 53506.74 | 70.63% |  | Total | Previous | Period |  |  | PS.003F01 - Zuhair Fayez and Partners 2230041 | Completed | Completed
| MS.003F09 - Euro Consult (COO 27) | 54000 | 54000 | 54000 | 0 | 100% | Total PVO's | 184 | 182 | 2 |  |  | PS.003F04 - Jensen Hughes Saudi Arabia Co 2230180
| Commercial Management | 0 | 0 | 0 | 0 |  | PVO Approved | 144 | 144 | 0 |  |  | PS.003F10 - Langan-Prf Fees COO 30
| No Awarded Contracts | 0 | 0 | 0 | 0 | 0% | PVO Pending | 24 | 22 | 2 |  |  | PS.003F08 - CML (Independent Commissioning Agent) COO 7
| Construction Works | 475028212.42 | 650023801.2637 | 454057160.8315 | 20971051.5885 | 95.59% | Cancelled (Not to Proceed) | 16 | 16 | 0 |  |  | Management Supervision
| CN.003C20 - Green Business Certification Inc.2220038 | 22585.01 | 18000.1125 | 18000.1125 | 4584.8975 | 79.7% | Superseded (PVO Replaced) | 0 | 0 | 0 |  |  | MS.003F02 - Khatib & Alami 2230031 | 2023-02-12 | 2025-02-28 |  |  | 2025-02-28
| CN.003C13 - SOI TB Ground Improvement Works 2210224 | 3082689 | 1748735.938 | 1748735.938 | 1333953.062 | 56.73% | [6 empty] | MS.003F07 - Euro Consult (COO 6)
| CN.003C13 - NSCC - Triple Bay Piling (AYC only) 2220032 | 16458381.51 | 23335059.096 | 16458381.54 | -0.03 | 100% | VARIATIONS (VO) | [5 empty] | MS.003F09 - Euro Consult (COO 27)
| CN.003C03 - Structural Concrete, Wet Trades, BOH Fit out, Pools and Water Features, Structural Steel, Glazing, Glass Balustrades, Aluminum Soffits, SFS and GRC, Render Façade, Roof Waterproofing, MEP, ICT/ELV - (SAB) 2230023 | 169939906.7 | 274254987.5851 | 170592084.657 | -652177.957 | 100.4% |  | Total | Previous | Period |  |  | Commercial Management
| Direct Payments for SAB's Subcontractors and Suppliers | 42594259.73 | 42594259.73 | 42594259.73 | 0 | 100% | Total VO's | 166 | 164 | 2 |  |  | No Awarded Contracts
| CN.003C21 - STO Façade Mock-up -(MWN) 2230075 | 819298.55 | 819298.55 | 819298.55 | 0 | 100% | VO's Issued / Approved | 139 | 137 | 2 |  |  | Construction Works
| CN.003C27 - Façade & Glazing Works (Alutec) | 30474501.58 | 48279532.9045 | 29131817.318 | 1342684.262 | 95.59% | VO Pending | 14 | 14 | 0 |  |  | CN.003C20 - Green Business Certification Inc.2220038 | Completed | Completed
| CN.003F03 - Vertical Transportation (ESCCO) 2230178 | 2773546 | 1990337.824 | 1982337.664 | 791208.336 | 71.47% | Superseded (VO Replaced) | 0 | 0 | 0 |  |  | CN.003C13 - SOI TB Ground Improvement Works 2210224 | 2021-10-05 | 2021-12-27 | 30 | 30 | 2022-01-26
| CN.003C09 - Interior Fitout Works (DEPA) | 80210582.25 | 91261011.175 | 65072967.4665 | 15137614.7835 | 81.13% | Cancelled (Not to Proceed) | 13 | 13 | 0 |  |  | CN.003C13 - NSCC - Triple Bay Piling (AYC only) 2220032 | 2022-03-24 | 2023-05-20 | 156 | 96 | 2023-08-24
| CN.003C31 - MAS - Wet Works | 22360118 | 23384183.21 | 22345856.21 | 14261.79 | 99.94% | [6 empty] | CN.003C03 - Structural Concrete, Wet Trades, BOH Fit out, Pools and Water Features, Structural Steel, Glazing, Glass Balustrades, Aluminum Soffits, SFS and GRC, Render Façade, Roof Waterproofing, MEP, ICT/ELV - (SAB) 2230023 | 2023-01-12 | 2025-02-28 |  | 0 | 2025-02-28
| CN.003C32 - MAS - Amphitheatre Works | 1284550.35 | 1395241.184 | 1211278.835 | 73271.515 | 94.3%
| CN.003C34 - Al Fanar - MEP Labour Supply | 94625593.23 | 131213586.2341 | 92352575.09 | 2273018.14 | 97.6% | DETERMINED VARIATION ORDERS (DVO) | [5 empty] | CN.003F03 - Vertical Transportation (ESCCO) 2230178
| CN.003C34 - ARMETAL - Reflective ceiling | 7197028.55 | 6633442.8205 | 6633442.8205 | 563585.7295 | 92.17% |  | Total | Previous | Period |  |  | CN.003C09 - Interior Fitout Works (DEPA) | 2023-10-24 | 2024-12-13 |  | 0 | 2024-12-13
| CN.003C34 - Al Rahji Takaful - Owner Controlled Insurance Program | 89047.06 | 0 | 0 | 89047.06 | 0% | Total DVO's | 146 | 146 | 0 |  |  | CN.003C27 - Façade & Glazing Works (Alutec) | 2024-12-30 | 2024-12-30 |  |  | 2024-12-30
| CN.003C35 - HASSAN ALLAM - External Scaffoldings | 3096124.9 | 3096124.9 | 3096124.9 | 0 | 100% | DVO Approved | 118 | 118 | 0 |  |  | CN.003C31 - MAS - Wet Works | 2024-10-16 | 2024-12-15 |  |  | 2024-12-15
| Client Cost | 0 | 0 | 0 | 0 |  | DVO Pending | 20 | 20 | 0 |  |  | CN.003C32 - MAS - Amphitheatre Works | 64 Calendar days from Commencement Date
| No Awarded Contracts | 0 | 0 | 0 | 0 | 0% | Cancelled (Not to Proceed) | 8 | 8 | 0 |  |  | CN.003C34 - Al Fanar - MEP Labour Supply
| FF&E AND OS&E | 44435277.57 | 31470987.905 | 29205220.99 | 15230056.58 |  | Superseded (DVO Replaced) | 0 | 0 | 0 |  |  | CN.003C34 - ARMETAL - Reflective ceiling
| CN.003C08 - Kitchen & Laundry Works (Al Raqtan) 2230205 | 4705352 | 6151689.085 | 3837547.3 | 867804.7 | 81.56% | DETERMINED VARIATION ORDERS (DVO) | [5 empty] | CN.003C35 - HASSAN ALLAM - External Scaffoldings
| FFEOSE.003F06 - FF&E and OSE Procurement Agent (Areen Design Ltd) | 1107465.88 | 25319298.82 | 25367673.69 | 13324439.75 | 65.56% |  | Total | Contractor value | PVO Value |  |  | FF&E AND OS&E
| FFEOSE.003F06.02 - FF&E and OSE (VO to Areen Design Ltd) | 37584647.56 |  |  |  |  | Total DVO's | 138 |  |  |  |  | CN.003C08 - Kitchen & Laundry Works (Al Raqtan) 2230205 | 2023-05-25 | 2024-12-20 |  |  | 2024-12-20
| FFEOSE.003F11 - Extraordinary Cart | 397876 | 0 | 0 | 397876 | 0% | [6 empty] | FFEOSE.003F06 - FF&E and OSE Procurement Agent (Areen Design Ltd) | 2024-01-16 | 2025-01-16 |  |  | 2025-01-16
| FFEOSE.003D09 - Saudico Electronic Systems | 353487.06 | 0 | 0 | 353487.06 | 0% | C-Sub pending Amaala review | 15 | 0 | 0 |  |  | FFEOSE.003F11 - Extraordinary Cart
| FFEOSE.003D07 - Birch Street | 115998.98 | 0 | 0 | 115998.98 | 0% | C-Sub outstanding | 5 | 0 | 0 |  |  | FFEOSE.003D09 - Saudico Electronic Systems
| FFEOSE.003D10 - AlFalak Electronic - HPE Servers | 16655 | 0 | 0 | 16655 | 0% | [6 empty] | FFEOSE.003D07 - Birch Street
| FFEOSE.003D15 - Saudico Electronic Systems | 34719 | 0 | 0 | 34719 | 0% | DVO's Approved | 118 | 3174007.175 | 33878350.355 |  |  | FFEOSE.003D10 - AlFalak Electronic - HPE Servers
| FFEOSE.003D11 - Sevenrooms Inc | 3633.9 | 0 | 0 | 3633.9 | 0% | [6 empty] | FFEOSE.003D15 - Saudico Electronic Systems
| FFEOSE.003D12 - Saudico Electronic Systems | 58307.19 | 0 | 0 | 58307.19 | 0% | [6 empty] | FFEOSE.003D11 - Sevenrooms Inc
| FFEOSE.003D14 - Reachware Integration | 57135 | 0 | 0 | 57135 | 0% | [6 empty] | FFEOSE.003D12 - Saudico Electronic Systems
| Total | 558907411.47 | 720469300.6787 | 522199822.0415 | 36707589.4285 | 93.43% | [6 empty] | FFEOSE.003D12 - Saudico Electronic Systems
| -213967.975 | 522413790.0165 | -559121379.445 | 522199822.0415 | 0 | Check Payment Certified at Zero: |  | -522199822.0415
213967.975
| KEY PERIOD MOVEMENTS |  |  |  | -215885.19 |  |  | CHECK:
| Description |  |  |  | Amount
| DVO High Level Overview |  |  |  | 0 |  | 0 | CHECK:
Item No. - 239 - Extension of Areen services - 31 May 2026
a
a
a
a
a
| PVO High Level Overview |  |  |  | 0 |  | 0 | CHECK:
Item No. - 157 - Notice of Backcharge to SAB - Altenative Labour Support to Abu Dhabi Precast (IMAR & Fibrex)
Moved back error to ;ast report - PVO only raised now
| RFC High Level Overview |  |  |  | -215885.19 |  | -4.6566e-10 | CHECK
| Item No. - 273 - Payment of SAB's Sub-Contractors through DEPA – GLSAN, Blue Wellness and BMC |  |  |  | 1196461.25
| Item No. - 274 - Back-charge to SAB – Payment of SAB's Sub-Contractors through DEPA and Nesma |  |  |  | -1412346.44
| Early Warnings |  |  |  | 0 |  | 0 | CHECK
| Item No. - 173 - Replacement of External Doors - requested by the Operator (Cluster Manager - Back of House) | [5 empty] | 0 | Contract Awards
[7 empty] | 0 | Check |  |  | 15939 | -15939
[11 empty] | 312470.43 | -312470.43
[11 empty] | 34680 | -34680
[11 empty] | 850370.6 | -850370.6
[11 empty] | 765844.0218 | -765844.0218
[11 empty] | 856801.79 | -856801.79
[11 empty] | 87285 | -87285
[11 empty] | 666280 | -666280
[11 empty] | -1173602.39 | 1173602.39
[11 empty] | -581464.2 | 581464.2
[11 empty] | 9510310.37 | -9510310.37
[11 empty] | -9510310.37 | 9510310.37
[11 empty] | -7850127.97 | 7850127.97
[11 empty] | 4045112.76 | -4045112.76
[11 empty] | 2232198 | -2232198
[11 empty] | -478548 | 478548
[8 empty] | 0 | CHECK
| BUDGET HOLD Movement |  |  |  | 0
-215885.19
-4.6566e-10
550000
| Option 1 |  | AED
| Option 2 |  | OMR
| Option 3 |  | 1
2
0
| BUA ft² | #REF! | #REF! | #REF! |  | #REF!
| GFA ft² | #REF! | #REF! | #REF! |  | #REF!
| BUA m² | #REF! | #REF! | #REF! |  | #REF!
| GFA m² | #REF! | #REF! | #REF! |  | #REF!
| Efficiency | #REF! | #REF! | #REF! |  | #REF!
View from Red Sea Marine Life Institute
Core Walls Under Construction
Level 3 Pool Deck
Aerial Photo
West Elevation
Site Overview - Dec 2023
Site Overview - Dec 2023
Note on D30: NOTE: Update Manually
Note on D32: NOTE: Update manually

## Stakeholder Executive Review (hidden)
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
|  |  |  | COMMITTED |  |  | UNCOMITTED | [8 empty] | PERIOD MOVEMENT
| Approved Baseline Budget | Approved Budget Transfers | Current Approved Budget | Approved Contracts + Direct Actual | Approved Contract Changes (DVOs+PVOs) | Total Approved Commitments | Pending Contracts | Pending Contract Changes (PVOs) | Total Commitments (Approved & Pending) | Early Warnings & RFC | EAC Based on Awarded Packages | Remaining Budget Before EW | Remaining Budget after EW | To Procure (Forecasted Contract Award Value) | Forecasted EAC Including all awards | SEPTEMBER 2026 | Variance | Comments |  | MH3 Aconex - CN Budget Hold | Variance | MVW | Other Prog 1 Assets | BTR under Process
| A | B | C = (A + B) | D | E | F = (D + E) | G | H | I = (F + G + H) | J | K = (I + J) | L = (F - I) | M = (F - (I+J)) | N | O = (K + N) | P | Q = (O - P)
|  |  | To match with "Approved Budget" in Aconex |  |  | To match with "Current Commitments" in Aconex |  |  | To match with "All Commitments" in Aconex
Professional Services | 28761589.23 | -6705327.73 | 22056261.5 | 22056261.5 | 3171766.92 | 25228028.42 | 0 | 101675.08 | 25329703.5 | 0 | 25310505.18 | 82398.52 | 101596.84 | 0 | 25310505.18 | 25310505.18 | 0 |  |  | 118356935.08 | -93046429.9
Dewan Architects & Engineers 2200445 | 5973808 | 0 | 5973808 | 5973808 | 3316718.1 | 9290526.1 |  | 0 | 9290526.1 | 0 | 9290526.1 | 0 | 0 |  | 9290526.1 | 9290526.1 | 0
HKS Architects Ltd - Design Competition Fees 2200010 | 555960.36 | 0 | 555960.36 | 555960.36 | 0 | 555960.36 |  | 0 | 555960.36 | 0 | 555960.36 | 0 | 0 |  | 555960.36 | 555960.36 | 0 | Closed - Final account executed.
HKS Architects Ltd - Design Architect Fees 2200375 | 10891204 | 0 | 10891204 | 10891204 | -89775 | 10801429 |  | 0 | 10801429 | 0 | 10801429 | 0 | 0 |  | 10801429 | 10801429 | 0 | Closed - Final account executed.
Applied Technology and Management Inc (Dubai BR)s 2210167 | 93750 | 0 | 93750 | 93750 | 0 | 93750 |  | 0 | 93750 | 0 | 93750 | 0 | 0 |  | 93750 | 93750 | 0 | Closed - Final account executed.
Langan International UK Limited 2230042 | 0 | 172368.42 | 172368.42 | 172368.42 | -1898.52 | 170469.9 |  | 0 | 170469.9 | 0 | 170469.9 | 1898.52 | 1898.52 |  | 170469.9 | 170469.9 | 0 | Closed - Final account executed.
Zuhair Fayez and Partners 2230041 | 0 | 106231.5 | 106231.5 | 106231.5 | 0 | 106231.5 |  | 0 | 106231.5 | 0 | 106231.5 | 0 | 0 |  | 106231.5 | 106231.5 | 0 | Closed - Final account executed.
Ministry of Municipality and Rural Affairs (Tabuk) | 0 | 45677.6 | 45677.6 | 45677.6 | 0 | 45677.6 |  | 0 | 45677.6 | 0 | 45677.6 | 0 | 0 |  | 45677.6 | 45677.6 | 0 | Closed - Payment to Tabuk Municipality
Jensen Hughes Saudi Arabia Co 2230180 | 0 | 127291.9 | 127291.9 | 127291.9 | -56700 | 70591.9 |  | 0 | 70591.9 | 0 | 70591.9 | 56700 | 56700 |  | 70591.9 | 70591.9 | 0
Jensen Hughes Saudi Arabia Co 2250184 | 0 | 38103.2 | 38103.2 | 38103.2 | -23800 | 14303.2 |  |  | 14303.2 | 0 | 14303.2 | 23800 | 23800 |  | 14303.2 | 14303.2 | 0
CML (Independent Commissioning Agent) COO 7 | 0 | 2406500 | 2406500 | 2406500 | 1520390.54 | 3926890.54 |  | 101675.08 | 4028565.62 | 0 | 4028565.62 | 0 | 0 |  | 4028565.62 | 4028565.62 | 0
GST - Sustainability Accreditation Services | 0 | 133000 | 133000 | 133000 | 0 | 133000 |  | 0 | 133000 | 0 | 133000 | 0 | 0 |  | 133000 | 133000 | 0
Remaining budget - Professional Fees | 11246866.87 | -9734500.35 | 1512366.52 | 1512366.52 | -1493168.2 | 19198.32 | 0 | 0 | 19198.32 | 0 | 0 | 0 | 19198.32 |  | 0 | 0 | 0 | [8 empty] | 19198.32
Management Supervision | 17975993.27 | -4937063.27 | 13038930 | 13038930 | 1329161.38 | 14368091.38 | 0 | -53507 | 14314584.38 | 0 | 14265377.38 | 53507 | 102714 | 0 | 14265377.38 | 14265377.38 | 0
Khatib & Alami 2230031 | 0 | 13059930 | 13059930 | 13059930 | 1071977 | 14131907 |  | 0 | 14131907 | -49207 | 14082700 | 0 | 0 |  | 14082700 | 14082700 | 0
Euro Consult (COO 6) | 0 | 182184.38 | 182184.38 | 182184.38 | 0 | 182184.38 |  | -53507 | 128677.38 | 0 | 128677.38 | 53507 | 53507 |  | 128677.38 | 128677.38 | 0
Euro Consult (COO 27) | 0 | 54000 | 54000 | 54000 | 0 | 54000 |  | 0 | 54000 |  | 54000 | 0 | 0 |  | 54000 | 54000 | 0
Remaining budget - Management Supervision | 17975993.27 | -18233177.65 | -257184.38 | -257184.38 | 257184.38 | 1.0477e-09 | 0 | 0 | 1.0477e-09 | 49207 | 0 | 0 | 49207 |  | 0 | 0 | 0
Commercial Management | 1198399.55 | -1198399.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 210052126.0368
Remaining budget - Commercial Management | 1198399.55 | -1198399.55 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction | 243418954.2 | 265160325.49 | 508579279.69 | 508579279.69 | -5794907.3 | 502784372.39 | 0 | -164010 | 502620362.39 | -1115864.7 | 497864140.763 | 18178901.14 | 94389834.9839 | 0 | 497864140.763 | 498080025.953 | -215885.19 |  | -10715138.927 | 229543628 | #REF! | #REF! | #REF! | 189345.67
SOI TB Ground Improvement Works 2210224 | 2799717 | 0 | 2799717 | 2799717 | 0 | 2799717 |  | 0 | 2799717 | -500000 | 2299717 | 0 | 500000 |  | 2299717 | 2299717 | 0 |  | #REF!
SOI TB Ground Improvement Works 2210224 PROVISIONAL SUMS | 282972 | 0 | 282972 | 282972 | 0 | 282972 |  | 0 | 282972 | -282972 | 0 | 0 | 282972 |  | 0 | 0 | 0 |  | #REF!
Green Business Certification Inc.2220038 | 4500 | 18594.49 | 23094.49 | 23094.49 | -509.48 | 22585.01 |  | 0 | 22585.01 | 0 | 22585.01 | 509.48 | 509.48 |  | 22585.01 | 22585.01 | 0 |  | #REF!
|  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | #REF!
NSCC - Triple Bay Piling (AYC only) 2220032 | 18698534 | 0 | 18698534 | 18698534 | -2240152.49 | 16458381.51 |  | 0 | 16458381.51 | 0 | 16458381.51 | 0 | 0 |  | 16458381.51 | 16458381.51 | 0 | Closed - Final account executed.
Structural Concrete, Wet Trades, BOH Fit out, Pools and Water Features, Structural Steel, Glazing, Glass Balustrades, Aluminum Soffits, SFS and GRC, Render Façade, Roof Waterproofing, MEP, ICT/ELV - (SAB) 2230023 | 0 | 260955414.4 | 260955414.4 | 260955414.4 | -91015507.7 | 169939906.7 |  | -19683045.7 | 150256861 | 20732556.823 | 170989417.823 | 0 | 89965996.577 |  | 170989417.823 | 172401764.263 | -1412346.44
Direct Payment to SAB's Subcontractors and Suppliers
Prelims - Mohammad Alharbi Medical Company | 0 | 134895.4 | 134895.4 | 134895.4 | 0 | 134895.4 |  | 0 | 134895.4 | 0 | 134895.4 | 0 | 0 |  | 134895.4 | 134895.4 | 0
Prelims - Al Anan Travels and Tours | 0 | 103373.74 | 103373.74 | 103373.74 | 0 | 103373.74 |  | 0 | 103373.74 | 0 | 103373.74 | 0 | 0 |  | 103373.74 | 103373.74 | 0
Prelims - Al drees Petroleum | 0 | 34782.61 | 34782.61 | 34782.61 | 0 | 34782.61 |  | 0 | 34782.61 | 0 | 34782.61 | 0 | 0 |  | 34782.61 | 34782.61 | 0
Prelims - Salim Hamed Cleaning | 0 | 31306.1 | 31306.1 | 31306.1 | 0 | 31306.1 |  | 0 | 31306.1 | 0 | 31306.1 | 0 | 0 |  | 31306.1 | 31306.1 | 0
Prelims - Clean Coast for Contracting | 0 | 252583.81 | 252583.81 | 252583.81 | 0 | 252583.81 |  | 0 | 252583.81 | 0 | 252583.81 | 0 | 0 |  | 252583.81 | 252583.81 | 0
Prelims - Sami General Contracting | 0 | 273350 | 273350 | 273350 | 0 | 273350 |  | 0 | 273350 | 0 | 273350 | 0 | 0 |  | 273350 | 273350 | 0
Prelims - Eastern Horizons Foundation Transportation Comp | 0 | 14349 | 14349 | 14349 | 0 | 14349 |  | 0 | 14349 | 0 | 14349 | 0 | 0 |  | 14349 | 14349 | 0
Prelims - Jak Generation Cont Co LLC | 0 | 369751.45 | 369751.45 | 369751.45 | 0 | 369751.45 |  | 0 | 369751.45 | 0 | 369751.45 | 0 | 0 |  | 369751.45 | 369751.45 | 0
Prelims - Intelligent General Cont Co Equipment | 0 | 758870.17 | 758870.17 | 758870.17 | 0 | 758870.17 |  | 0 | 758870.17 | 0 | 758870.17 | 0 | 0 |  | 758870.17 | 758870.17 | 0
Prelims - Al Rai Modern Water Factory | 0 | 318320.5 | 318320.5 | 318320.5 | 0 | 318320.5 |  | 0 | 318320.5 | 0 | 318320.5 | 0 | 0 |  | 318320.5 | 318320.5 | 0
Prelims - NEXTWARE INTERNATIONAL SUPPLY | 0 | 1845 | 1845 | 1845 | 0 | 1845 |  | 0 | 1845 | 0 | 1845 | 0 | 0 |  | 1845 | 1845 | 0
Prelims - Virtual Projects DMCC | 0 | 51948.13 | 51948.13 | 51948.13 | 0 | 51948.13 |  | 0 | 51948.13 | 0 | 51948.13 | 0 | 0 |  | 51948.13 | 51948.13 | 0
Prelims - Raddad Al adinah | 0 | 142131.61 | 142131.61 | 142131.61 | 0 | 142131.61 |  | 0 | 142131.61 | 0 | 142131.61 | 0 | 0 |  | 142131.61 | 142131.61 | 0
Prelims - Ahmed Bin Salem Bin Dagher | 0 | 348199.81 | 348199.81 | 348199.81 | 0 | 348199.81 |  | 0 | 348199.81 | 0 | 348199.81 | 0 | 0 |  | 348199.81 | 348199.81 | 0
Prelims - Bahamdoon Trading | 0 | 1535 | 1535 | 1535 | 0 | 1535 |  | 0 | 1535 | 0 | 1535 | 0 | 0 |  | 1535 | 1535 | 0
Prelims - Lumi Rentals | 0 | 6142.43 | 6142.43 | 6142.43 | 0 | 6142.43 |  | 0 | 6142.43 | 0 | 6142.43 | 0 | 0 |  | 6142.43 | 6142.43 | 0
Prelims - Filter Expert Trading | 0 | 8565 | 8565 | 8565 | 0 | 8565 |  | 0 | 8565 | 0 | 8565 | 0 | 0 |  | 8565 | 8565 | 0
Prelims - Abu Nayyan | 0 | 17800 | 17800 | 17800 | 0 | 17800 |  | 0 | 17800 | 0 | 17800 | 0 | 0 |  | 17800 | 17800 | 0
Prelims - Ihsan Muhammed Thakir Idress Trading | 0 | 99000 | 99000 | 99000 | 0 | 99000 |  | 0 | 99000 | 0 | 99000 | 0 | 0 |  | 99000 | 99000 | 0
Prelims - Ramzi Abbas Mohd. Sayed Est. | 0 | 48767 | 48767 | 48767 | 0 | 48767 |  | 0 | 48767 | 0 | 48767 | 0 | 0 |  | 48767 | 48767 | 0
Prelims - Al Rayi Water | 0 | 46655 | 46655 | 46655 | 0 | 46655 |  | 0 | 46655 | 0 | 46655 | 0 | 0 |  | 46655 | 46655 | 0
Prelims - GLSAN Contracting Company | 0 | 8291108.14 | 8291108.14 | 8291108.14 | 0 | 8291108.14 |  | 0 | 8291108.14 | 0 | 8291108.14 | 0 | 0 |  | 8291108.14 | 8291108.14 | 0
Prelims - GLSAN Contracting Company (Red Sea) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Prelims - Masa Equipment Est | 0 | 287000 | 287000 | 287000 | 0 | 287000 |  | 0 | 287000 | 0 | 287000 | 0 | 0 |  | 287000 | 287000 | 0
Prelims - Al Tala'a International Transportation Co | 0 | 6608.7 | 6608.7 | 6608.7 | 0 | 6608.7 |  | 0 | 6608.7 | 0 | 6608.7 | 0 | 0 |  | 6608.7 | 6608.7 | 0
Prelims - Saudi Brokers | 0 | 59606.12 | 59606.12 | 59606.12 | 0 | 59606.12 |  | 0 | 59606.12 | 0 | 59606.12 | 0 | 0 |  | 59606.12 | 59606.12 | 0
Prelims - Aknan Al Bena | 0 | 75000 | 75000 | 75000 | 0 | 75000 |  | 0 | 75000 | 0 | 75000 | 0 | 0 |  | 75000 | 75000 | 0
Prelims - Emaar Suhali | 0 | 90000 | 90000 | 90000 | 0 | 90000 |  | 0 | 90000 | 0 | 90000 | 0 | 0 |  | 90000 | 90000 | 0
Direct Works - Madar Building material Co | 0 | 14320 | 14320 | 14320 | 0 | 14320 |  | 0 | 14320 | 0 | 14320 | 0 | 0 |  | 14320 | 14320 | 0
Direct Works - Juffali Technical Equipment Company | 0 | 12113.6 | 12113.6 | 12113.6 | 0 | 12113.6 |  | 0 | 12113.6 | 0 | 12113.6 | 0 | 0 |  | 12113.6 | 12113.6 | 0
Direct Works - USG Middle East Ltd. Co | 0 | 39954.82 | 39954.82 | 39954.82 | 0 | 39954.82 |  | 0 | 39954.82 | 0 | 39954.82 | 0 | 0 |  | 39954.82 | 39954.82 | 0
Direct Works - Abu Dhabi Precast | 0 | 3619680.62 | 3619680.62 | 3619680.62 | 0 | 3619680.62 |  | 0 | 3619680.62 | 0 | 3619680.62 | 0 | 0 |  | 3619680.62 | 3619680.62 | 0
Direct Works - SAMIF | 0 | 6340696.9 | 6340696.9 | 6340696.9 | 0 | 6340696.9 |  | 0 | 6340696.9 | 0 | 6340696.9 | 0 | 0 |  | 6340696.9 | 6340696.9 | 0
Direct Works - SAUDI MANPOWER SOLUTIONS CO | 0 | 377764.03 | 377764.03 | 377764.03 | 0 | 377764.03 |  | 0 | 377764.03 | 0 | 377764.03 | 0 | 0 |  | 377764.03 | 377764.03 | 0
Direct Works - Fosam Company LTD | 0 | 40570 | 40570 | 40570 | 0 | 40570 |  | 0 | 40570 | 0 | 40570 | 0 | 0 |  | 40570 | 40570 | 0
Direct Works - Glow Arabia Trading | 0 | 49460.5 | 49460.5 | 49460.5 | 0 | 49460.5 |  | 0 | 49460.5 | 0 | 49460.5 | 0 | 0 |  | 49460.5 | 49460.5 | 0
Direct Works - BROOQ ALAMAAN TRAD COMPANY | 0 | 130305.72 | 130305.72 | 130305.72 | 0 | 130305.72 |  | 0 | 130305.72 | 0 | 130305.72 | 0 | 0 |  | 130305.72 | 130305.72 | 0
Direct Works - Abeer Munawer Al Shamari | 0 | 1059365.93 | 1059365.93 | 1059365.93 | 0 | 1059365.93 |  | 0 | 1059365.93 | 0 | 1059365.93 | 0 | 0 |  | 1059365.93 | 1059365.93 | 0
Direct Works - Yaz Development Contracting | 0 | 1036210 | 1036210 | 1036210 | 0 | 1036210 |  | 0 | 1036210 | 0 | 1036210 | 0 | 0 |  | 1036210 | 1036210 | 0
Direct Works - Naffco | 0 | 936325.93 | 936325.93 | 936325.93 | 0 | 936325.93 |  | 0 | 936325.93 | 0 | 936325.93 | 0 | 0 |  | 936325.93 | 936325.93 | 0
Direct Works - GESR Alarab | 0 | 2444255.5 | 2444255.5 | 2444255.5 | 0 | 2444255.5 |  | 0 | 2444255.5 | 0 | 2444255.5 | 0 | 0 |  | 2444255.5 | 2444255.5 | 0
Direct Works - Jameel Mohamed Hussain Alqatafa Cont Est | 0 | 127257.78 | 127257.78 | 127257.78 | 0 | 127257.78 |  | 0 | 127257.78 | 0 | 127257.78 | 0 | 0 |  | 127257.78 | 127257.78 | 0
Direct Works - MEDTEL | 0 | 5913785.58 | 5913785.58 | 5913785.58 | 0 | 5913785.58 |  | 0 | 5913785.58 | 0 | 5913785.58 | 0 | 0 |  | 5913785.58 | 5913785.58 | 0
Direct Works - Noreom | 0 | 100641.6 | 100641.6 | 100641.6 | 0 | 100641.6 |  | 0 | 100641.6 | 0 | 100641.6 | 0 | 0 |  | 100641.6 | 100641.6 | 0
Direct Works - Isam Kabani & Partners | 0 | 2267626.88 | 2267626.88 | 2267626.88 | 0 | 2267626.88 |  | 0 | 2267626.88 | 0 | 2267626.88 | 0 | 0 |  | 2267626.88 | 2267626.88 | 0
Direct Works - ARABIAN TESTING EVOLUTION COMPANY | 0 | 425440 | 425440 | 425440 | 0 | 425440 |  | 0 | 425440 | 0 | 425440 | 0 | 0 |  | 425440 | 425440 | 0
Direct Works - Wood Expert | 0 | 22475 | 22475 | 22475 | 0 | 22475 |  | 0 | 22475 | 0 | 22475 | 0 | 0 |  | 22475 | 22475 | 0
Direct Works - Energy & Building Master | 0 | 117720 | 117720 | 117720 | 0 | 117720 |  | 0 | 117720 | 0 | 117720 | 0 | 0 |  | 117720 | 117720 | 0
Direct Works - ACES | 0 | 4401.3 | 4401.3 | 4401.3 | 0 | 4401.3 |  | 0 | 4401.3 | 0 | 4401.3 | 0 | 0 |  | 4401.3 | 4401.3 | 0
Direct Works - International Company for Building Materials LTD | 0 | 60486.9 | 60486.9 | 60486.9 | 0 | 60486.9 |  | 0 | 60486.9 | 0 | 60486.9 | 0 | 0 |  | 60486.9 | 60486.9 | 0
Direct Works - Al Hayat | 0 | 846817.39 | 846817.39 | 846817.39 | 0 | 846817.39 |  | 0 | 846817.39 | 0 | 846817.39 | 0 | 0 |  | 846817.39 | 846817.39 | 0
Direct Works -Saint Gobain | 0 | 122301.47 | 122301.47 | 122301.47 | 0 | 122301.47 |  | 0 | 122301.47 | 0 | 122301.47 | 0 | 0 |  | 122301.47 | 122301.47 | 0
Direct Works- AAMTAC Company LTD | 0 | 22553 | 22553 | 22553 | 0 | 22553 |  | 0 | 22553 | 0 | 22553 | 0 | 0 |  | 22553 | 22553 | 0
Direct Works - DOSAR Al Najd | 0 | 123937.39 | 123937.39 | 123937.39 | 0 | 123937.39 |  | 0 | 123937.39 | 0 | 123937.39 | 0 | 0 |  | 123937.39 | 123937.39 | 0
Direct Works - Alcatop | 0 | 1139399.11 | 1139399.11 | 1139399.11 | 0 | 1139399.11 |  | 0 | 1139399.11 | 0 | 1139399.11 | 0 | 0 |  | 1139399.11 | 1139399.11 | 0
Direct Works - Saveto Saudi Vetonit Co Ltd | 0 | 2730 | 2730 | 2730 | 0 | 2730 |  | 0 | 2730 | 0 | 2730 | 0 | 0 |  | 2730 | 2730 | 0
Direct Works - Top Construction Co Ltd | 0 | 326341.06 | 326341.06 | 326341.06 | 0 | 326341.06 |  | 0 | 326341.06 | 0 | 326341.06 | 0 | 0 |  | 326341.06 | 326341.06 | 0
Direct Works - TBK Metal | 0 | 200069 | 200069 | 200069 | 0 | 200069 |  | 0 | 200069 | 0 | 200069 | 0 | 0 |  | 200069 | 200069 | 0
Direct Works - Lakeshore | 0 | 624120.15 | 624120.15 | 624120.15 | 0 | 624120.15 |  | 0 | 624120.15 | 0 | 624120.15 | 0 | 0 |  | 624120.15 | 624120.15 | 0
Direct Works - Fast Steps | 0 | 22250 | 22250 | 22250 | 0 | 22250 |  | 0 | 22250 | 0 | 22250 | 0 | 0 |  | 22250 | 22250 | 0
Direct Works - HRFA | 0 | 196505.68 | 196505.68 | 196505.68 | 0 | 196505.68 |  | 0 | 196505.68 | 0 | 196505.68 | 0 | 0 |  | 196505.68 | 196505.68 | 0
Direct Works - NESMA | 0 | 1942966.8 | 1942966.8 | 1942966.8 | 0 | 1942966.8 |  | 0 | 1942966.8 | 0 | 1942966.8 | 0 | 0 |  | 1942966.8 | 1942966.8 | 0
Direct Works - TANSEEQ | 0 | 9915.37 | 9915.37 | 9915.37 | 0 | 9915.37 |  | 0 | 9915.37 | 0 | 9915.37 | 0 | 0 |  | 9915.37 | 9915.37 | 0
Tamimi (SAB Accommodation Payment) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
STO Façade Mock-up -(MWN) 2230075 | 0 | 834298.55 | 834298.55 | 834298.55 | -15000 | 819298.55 |  | 0 | 819298.55 | 0 | 819298.55 | 0 | 0 |  | 819298.55 | 819298.55 | 0 | Closed - Final account executed.
Vertical Transportation (ESCCO) 2230178 | 0 | 2675473 | 2675473 | 2675473 | 98073 | 2773546 |  | 765046.05 | 3538592.05 | -215675 | 3322917.05 | 0 | 0 |  | 3322917.05 | 3322917.05 | 0
Kitchen & Laundry Works (Al Raqtan) 2230205 | 0 | 4695209 | 4695209 | 4695209 | 10143 | 4705352 |  | 0 | 4705352 | 1365246.45 | 6070598.45 | 0 | 0 |  | 6070598.45 | 6070598.45 | 0 |  |  | Total Commitment | Balance Budget | To Procure | EW
Fitout Works (DEPA) | 0 | 75969227 | 75969227 | 75969227 | 4241355.25 | 80210582.25 |  | -842054.38 | 79368527.87 | 12754372.42 | 92122900.29 | 0 | 0 |  | 92122900.29 | 90926439.04 | 1196461.25
Façade & Glazing Works (Alutec) | 0 | 29899670.55 | 29899670.55 | 29899670.55 | 574831.03 | 30474501.58 |  | -112821 | 30361680.58 | 491334 | 30853014.58 | 0 | 0 |  | 30853014.58 | 30853014.58 | 0
Hard and Soft Landscaping | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | Package Awarded under MVW - Budget transfer has not taken place - Request to Remove from EW | #REF!
MAS - Wet Works | 0 | 4004000 | 4004000 | 4004000 | 18356118 | 22360118 |  | 160876.21 | 22520994.21 | 0 | 22520994.21 | 0 | 0 |  | 22520994.21 | 22520994.21 | 0
MAS - Amphitheatre Works | 0 | 1078892.27 | 1078892.27 | 1078892.27 | 205658.08 | 1284550.35 |  | 0 | 1284550.35 | -9520 | 1275030.35 | 0 | 0 |  | 1275030.35 | 1275030.35 | 0
Al Fanar - MEP Labour Supply | 0 | 23125000 | 23125000 | 23125000 | 71500593.23 | 94625593.23 |  | 786453.46 | 95412046.69 | 128285 | 95540331.69 | 0 | 0 |  | 95540331.69 | 95540331.69 | 0
ARMETAL - Reflective ceiling | 0 | 7129950 | 7129950 | 7129950 | 67078.55 | 7197028.55 |  | 0 | 7197028.55 | 0 | 7197028.55 | 0 | 0 |  | 7197028.55 | 7197028.55 | 0
Al Rahji Takaful - Owner Controlled Insurance Program | 0 | 89047.06 | 89047.06 | 89047.06 | 0 | 89047.06 |  | 0 | 89047.06 | 0 | 89047.06 | 0 | 0 |  | 89047.06 | 89047.06 | 0
ABU DHABI PRECAST - GRC Cladding | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | GRC Cladding to Abu Dhabi Precast (Withdrawn)
HASSAN ALLAM - External Scaffoldings | 0 | 3096124.9 | 3096124.9 | 3096124.9 | 0 | 3096124.9 |  | 0 | 3096124.9 | 0 | 3096124.9 | 0 | 0 |  | 3096124.9 | 3096124.9 | 0
Enviro - Deep Cleaning | 0 | 799625.31 | 799625.31 | 799625.31 | 0 | 799625.31 |  | 0 | 799625.31 | 0 | 799625.31 | 0 | 0 |  | 799625.31 | 799625.31 | 0 | New Contract Award
KTH - MEP Works Package - 2240072 - KORTEK | 0 | 0 | 0 | 0 | 0 | 0 |  | 583143.7 | 583143.7 | 367770 | 950913.7 | 0 | 0 |  | 950913.7 | 950913.7 | 0 | New Contract Award
ALC - Alcatop Package - Fourseasons - Alcatop | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 150000 | 150000 | 0 | 0 |  | 150000 | 150000 | 0 | New Contract Award
Al Futtaim Pioneer Elevators - Al Futtaim Pioneer | 0 | 691955 | 691955 | 691955 | 0 | 691955 |  | 0 | 691955 | 0 | 691955 | 0 | 0 |  | 691955 | 691955 | 0 | New Contract Award
|  |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | #REF!
Remaining budget - Construction Works | 221633231.2 | -192496415.77 | 29136815.43 | 29136815.43 | -7577587.77 | 21559227.66 | 0 | 18178391.66 | 39737619.32 | -36097262.393 | 0 | 18178391.66 | 3640356.927 |  | 0 | 0 | 0 |  | 1115864.7 | [6 empty] | 17918870.733 |  | 17791405.42
FF&E | 24991549 | 15106816.84 | 40098365.84 | 40098365.84 | 851779 | 40950144.84 | 0 | 0 | 40950144.84 | 0 | 41376165.73 | 0 | 0 | 0 | 41376165.73 | 41376165.73 | 0 |  |  |  |  | 128910137.11
FF&E and OSE Procurement Agent (Areen Design Ltd) | 0 | 1107465.88 | 1107465.88 | 1107465.88 | 851779 | 1959244.88 |  | 0 | 1959244.88 | 0 | 1959244.88 | 0 | 0 |  | 1959244.88 | 1959244.88 | 0
Loose FF&E Items (FOH) | 0 | 22998647.56 | 22998647.56 | 22998647.56 | 0 | 22998647.56 |  | 0 | 22998647.56 | 0 | 22998647.56 | 0 | 0 |  | 22998647.56 | 22998647.56 | 0
Loose FF&E Items (BOH) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
OS&E Items | 0 | 14586000 | 14586000 | 14586000 | 0 | 14586000 |  | 0 | 14586000 | 429156 | 15015156 | 0 | 0 |  | 15015156 | 15015156 | 0
Art Works | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Extraordinary Cart | 0 | 397876 | 397876 | 397876 | 0 | 397876 |  | 0 | 397876 | 0 | 397876 | 0 | 0 |  | 397876 | 397876 | 0
Saudico Electronic Systems | 0 | 353487.06 | 353487.06 | 353487.06 | 0 | 353487.06 |  | 0 | 353487.06 | 0 | 353487.06 | 0 | 0 |  | 353487.06 | 353487.06 | 0
Birch Street | 0 | 115998.98 | 115998.98 | 115998.98 | 0 | 115998.98 |  | 0 | 115998.98 | 0 | 115998.98 | 0 | 0 |  | 115998.98 | 115998.98 | 0
AlFalak Electronic - HPE Servers | 0 | 16655 | 16655 | 16655 | 0 | 16655 |  | 0 | 16655 | 0 | 16655 | 0 | 0 |  | 16655 | 16655 | 0
Saudico Electronic Systems | 0 | 34719 | 34719 | 34719 | 0 | 34719 |  | 0 | 34719 | 0 | 34719 | 0 | 0 |  | 34719 | 34719 | 0
Sevenrooms Inc | 0 | 32751.56 | 32751.56 | 32751.56 | 0 | 32751.56 |  | 0 | 32751.56 | 0 | 32751.56 | 0 | 0 |  | 32751.56 | 32751.56 | 0
Infor Saudi Arabia Limited | 0 | 58307.19 | 58307.19 | 58307.19 | 0 | 58307.19 |  | 0 | 58307.19 | 0 | 58307.19 | 0 | 0 |  | 58307.19 | 58307.19 | 0
TRA - Zatca Integration with Reachware | 0 | 57135 | 57135 | 57135 | 0 | 57135 |  | 0 | 57135 | 0 | 57135 | 0 | 0 |  | 57135 | 57135 | 0
PeopleVine Implementation | 0 | 336187.5 | 336187.5 | 336187.5 | 0 | 336187.5 |  | 0 | 336187.5 | 0 | 336187.5 | 0 | 0 |  | 336187.5 | 336187.5 | 0
|  |  | 0 | [7 empty] | 0 |  |  |  | 0
Remaining budget - FF&E and OSE | 24991549 | -24988413.89 | 3135.11 | 3135.11 | 0 | 3135.11 | 0 | 0 | 3135.11 | -429156 | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0
Total Development Budget | 316346485.25 | 267426351.78 | 583772837.03 | 583772837.03 | -442200 | 583330637.03 | 0 | -115841.92 | 583214795.11 | -1115864.7 | 578816189.053 | 18314806.66 | 94594145.8239 | 0 | 578816189.053 | 579032074.243 | -215885.19 |  | -10715138.927 | [6 empty] | 0 | -215885.19 | Check Zero | -215885.19 | -215885.19
Early Warning / Budget Overrun | [14 empty] | -4956647.977 | [10 empty] | 3234573.277 | -1722074.7 | Check Zero | -3234573.277 | 0
[15 empty] | -3234573.277 |  | 215885.19 | -215885.19
[6 empty] | -442200 |  |  |  |  | 580612977.583 |  |  |  | 1722074.7 |  |  | 0 | [6 empty] | Check:
[6 empty] | 583847550.86 |  |  |  |  | 1796788.53 |  |  |  | 347793.9 |  | -215885.19
[6 empty] | 516913.83 | [8 empty] | 569838.42 |  | 0
[15 empty] | -4039015.657 | 101258508.083 | 105297523.74
[10 empty] | #REF! |  |  |  |  | 580612977.583
[10 empty] | #REF! |  |  |  |  | 1796788.53
#REF!

## Level 01
Triple Bay Portfolio Cost Report Executive Summary Programme 1 - Amaala Yacht Club
OCTOBER 2026
Program 1 - AMAALA Yacht Club | Professional Services | Management supervision | Commercial Management | Early Works Constructions | Construction Works | FF&E | Total AMAALA Yacht Club
| SAR | SAR | SAR | SAR | SAR | SAR | SAR | -7993697.557
Development Budget | 22056261.5 | 13038930 | 0 | 3105783.49 | 505488572.48 | 40158003.39 | 583847550.86 | 583847550.86 | 0 | ZERO CHECK:
Commitments
Contract Awards | 20543894.98 | 13296114.38 | 0 | 3105783.49 | 476351757.05 | 40154868.28 | 553452418.18 | 553452418.18 | 0 | ZERO CHECK:
DVO's | 4664935.12 | 1071977 | 0 | -509.48 | 231953.84 | 851779 | 6820135.48 | 6820135.48 | 0 | ZERO CHECK:
PVO's | 0 | 0 | 0 | 0 | 1993436.11 | 0 | 1993436.11 | 1993436.11 | 0 | ZERO CHECK:
Less: Remaining - Budget Hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ZERO CHECK:
Potential Out-Turn Costs
PVO's (uncommitted) | 101675.08 | -53507 | 0 | 0 | -18178391.66 | 0 | -18130223.58 | -18130223.58 | 0 | ZERO CHECK:
Early Warnings | 0 | 0 | 0 | -782972 | 33674620.893 | 0 | 32891648.893 | 32891648.893 | 0 | ZERO CHECK:
Balance to Procure
CTC - Site | 0 | -49207 | 0 | 0 | 3205613.5 | 429156 | 3585562.5 | 3585562.5 | 0 | ZERO CHECK:
CTC - Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uncommitted Packages | 0 | 0 | 0 | 0 | 0 | 0 | 0
Anticipated Final Account | 25310505.18 | 14265377.38 | 0 | 2322302.01 | 497278989.733 | 41435803.28 | 580612977.583 | 580612977.583 | 0 | ZERO: CHECK
Variance to Budget | 3254243.68 | 1226447.38 | 0 | -783481.48 | -8209582.747 | 1277799.89 | -3234573.277 | -3234573.277 | 0 | ZERO CHECK:
Last Month Anticipated Final Account | 25310505.18 | 14265377.38 | 0 | 2322302.01 | 497494874.923 | 41435803.28 | 580828862.773
Variance to Last Month | 0 | 0 | 0 | 0 | -215885.19 | 0 | -215885.19
Reasons for Variance - from last month | Al Futtaim elevator contract awarded (SAR 691,955 against RFC SAR 850,000); Alutec external doors EW cancelled (SAR 780,000); Al Fanar manpower extension PVO 012 (SAR 842,550); KAA final account saving (SAR 49,207).

## Early Warnings
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
Location: - AL WAJH SAUDI ARABIA
REPORT NO: - MONTHLY REPORT NO. 49
Item No. | Package | Early Warning Description | Impact | Change Status | Remarks
| PROFESSIONAL SERVICES |  | 0
| MANAGEMENT SUPERVISION |  | 0
| COMMERCIAL MANAGEMENT |  | 0
| CONSTRUCTION WORKS |  | 32891648.893
SOI TB Ground Improvement Works (SIC)
EW 058 | SOI TB Ground Improvement Works | SIC Contract (Works not Done) | -500000 | Awaiting confirmation from Programme 2 Commercial. | This will be incorporated in the SIC Final Account. Awaiting confirmation from Prog 2 Commercial.
EW 059 | SOI TB Ground Improvement Works (PS) | SIC Contract (PS - Not done) | -282972 | Awaiting confirmation from Programme 2 Commercial. | This will be incorporated in the SIC Final Account. Awaiting confirmation from Prog 2 Commercial.
SUB-TOTAL |  |  | -782972
SAB - Civil and Arch Works, MEPD & ICT/ELV (Baytur)
EW 15 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Omission of Surveying Equipment from SAB Contract | -7890 | Early Warning | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 17 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Omission of food and welfare provision to AMAALA Staff from SAB Contract. | -90000 | Early Warning | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 17 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Cost saving to Site Office Monthly Running Cost due to late installation of the Office Establishment by SAB. | -200000 | Early Warning | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 029 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Cancellation of Amphitheatre Works issued to MAS - Process not followed | -1108000 | RFA appoved | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 031 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Recovery of Remaining Block work, Plaster work and Paint Work to be carried out by MAS - Process not followed | -4004000 | RFA appoved | This EI was drafted and issued by delivery on the 15th September 2024, Processes were not followed. No need for PVO/VO. This will be dealt with in the Final Account.
EW 034 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Deployment of Seven (7) Surveyors | 201600 | EI issued | SAB has not been notified of submitting a variation cost for this. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 037 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Scaffolding works for Secondary Steel and Façade (Design) | 75000 | EI issued | SAB has not been notified of submitting a variation cost for this. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 043 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Column Dry Wall Cladding and Partitions (Blockworks Omission) | -9180 | Early Warning | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 045 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Replace the existing FOH electrical faceplates in designated areas of the Project with upgraded units meeting specifications. (Omission from SAB) | -68541 | Early Warning | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 047 | SAB - Civil and Arch Works, MEPD & ICT/ELV | LPG Works (Omission from SAB) | -582220 | Early Warning | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 050 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Allowance for SAB (Grankraft) works on mockup (same as advance payment amount) | 852173.913 | Early Warning | Included in the approved RFA for Cost to Complete (Grankraft). This amount is being used to make direct payments to SAB's suppliers and subcontractors. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 051 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Additional Costs related to Aluminium Soffits & Cladding - Alcatop | 1026091 | Early Warning | Included in the approved RFA for Cost to Complete (Alcatop). This amount is being used to make direct payments to SAB's suppliers and subcontractors. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 052 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Additional Costs related to Abu Dhabi Precast - GRC Cladding | 3761897 | Early Warning | Included in the approved RFA for Cost to Complete (Abu Dhabi Precast). This amount is being used to make direct payments to SAB's suppliers and subcontractors. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 053 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Additional Costs related to Structural Metal Work - SAMIF | 4647142 | Early Warning | Included in the approved RFA for Cost to Complete (SAMIF). This amount is being used to make direct payments to SAB's suppliers and subcontractors. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 055 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Dismantling and Reinstatement of Cold Rooms (Chiller 1, Chiller 2, and Chiller 3) including coordination - Backcharge | -22250 | Early Warning | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 062 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Omission of Limestone from SAB | -133949.24 | RFA appoved | Included in the approved RFA for SAB Cost to Complete (Limestone). This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 063 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Cost to Complete (SAB Amount) - Including Contingencies | 53011624.83 | RFA appoved | Included in the approved RFA for SAB Cost to Complete (SAB Cost). This amount is being used to make direct payments to SAB's suppliers and subcontractors. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 065 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Back-of-House Finishes (EI 006)_SAB | -701856.29 | EI issued | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 077 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Omission of Interior Designer Selected Light Fittings (included in the FF&E) | -1173602.39 | Early Warning | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 078 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Omission of Swimming Pool Lights (supplied by Al Fanar) | -581464.2 | Early Warning | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 095 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Omission of Accommodation Budget from SAB (Payment for Tamimi) - to be deducted from SAB Contract Adjustment EW 063. | -10718725 | Early Warning | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 096 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Overrun on SAB's Accommodation Budget (Payment for Tamimi) - to be deducted from SAB Contract Adjustment EW 063. | -9279215.75 | Early Warning | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 100 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Direct Payments to SAB's Subcontractors and Suppliers (August 2025). | -5277917.79 | Payment Release | 0
EW 101 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Direct Payments to SAB's Subcontractors and Suppliers (September 2025). | -3192741.9 | Payment Release | 0
EW 102 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Direct Payments to SAB's Subcontractors and Suppliers (October 2025). | -3189139.87 | Payment Release | Direct Payment
EW 103 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Direct Payments to SAB's Subcontractors and Suppliers (Nov and Dec 2025). | -4203149.6 |  | 0
EW 112 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Balance Works for ICT System (NESMA) | 2674938 | EI issued | This will be part of the direct payments negative PVO. Therefore, there is no need to process a separate PVO/VO for this item.
EW 114 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Omission of Internal Windows (Kitchen Service Hatches) from SAB - Supply and install by RAQTAN | -8078.16 | RFA appoved | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO.
EW 123 | SAB - Civil and Arch Works, MEPD & ICT/ELV | EI-18 : Amendment of Secondary Steel Structure vs Honeycomb Limestone Cladding | 54000 | Early Warning | PVO to prepare
EW 137 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Employer's Instruction No. 020 – Replacement of the Aluminium Ceiling Panels | 282122.46 | EI issued | PVO to prepare
EW 139 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Backcharge Notification: Marvel System for Ecology Unit provided by Raqtan on behalf of SAB | -233351.85 | EI issued | PVO to prepare
EW 141 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Employer’s Instruction No. 025 – Aluminum Cladding Panel Replacement at Various Locations (Discrepancy between the model and actual site conditions (construction tolerances).) | 269447.1 | BC issued | PVO to prepare
EW 151 | SAB - Civil and Arch Works, MEPD & ICT/ELV | EVO No. 005 - Supply of Alutec Manpower to Install the External Glass Balustrade on Behalf of Alcatop (BC to Alcatop) | -332640 | EI issued | 0
EW 156 | SAB - Civil and Arch Works, MEPD & ICT/ELV | EVO 29 Rectification of damaged waterproofing at Water Features | 60000 |  | PVO to prepare
SUB-TOTAL |  |  | 21798123.263
ESCCO - Vertical Transport
EW 080 | ESCCO - Vertical Transport | Clause 11.11 (Backcharging by Employer) - Supply of Electricians by Al Fanar for ESCCO’s Vertical Transportation Installations | -15675 | BC issued | This will be dealt with in the final account reconciliation with RAQTAN; therefore, there is no need to process a PVO/VO.
SUB-TOTAL |  |  | -15675
Special Kitchen (Al Raqtan)
EW 054 | Special Kitchen | Dismantling and Reinstatement of Cold Rooms (Chiller 1, Chiller 2, and Chiller 3) including coordination | 22250 | Early Warning | Works completed. RAQTAN has not been notified of submitting a variation cost for this. This will be dealt with in the final account reconciliation with RAQTAN; therefore, there is no need to process a PVO/VO.
EW 140 | Special Kitchen | Marvel System for Ecology Unit provided by Raqtan on behalf of SAB | 233351.85 | Completed at Site | PVO to prepare
SUB-TOTAL |  |  | 255601.85
DEPA Interior Fitout
EW 032 | DEPA Interior Fitout | Alteration to finishes due to Façade Layout Changes - Process not Followed | 69000 | Ei Issued | Works completed. DEPA has not been notified of submitting a variation cost for this. This will be dealt with in the final account reconciliation with DEPA; therefore, there is no need to process a PVO/VO.
EW 060 | DEPA Interior Fitout | DEPA EOT 01 Prolongation Cost (Estimated) | 8100000 | Time assessment issued. Awaiting DEPA's submission of prolongation cost. | DEPA to submit the actual cost upon agreement of the time imact for EOT 001.
EW 115 | DEPA Interior Fitout | EI-17: Road Markings Paint Application | 8000 | EI issued | 0
EW 121 | DEPA Interior Fitout | EI-20: Rectification of the Damaged Ceilings Based on the Various Damage Reports | 100000 | EI issued | 0
EW 127 | DEPA Interior Fitout | Adjustment for DEPA PVO 008, PVO 015 and PVO 013 (expected DVOs to be agreed) | 1936178.33 | Anticipated adjustment for DVOs value to be agreed. | 0
EW 128 | DEPA Interior Fitout | Allow for rectification of damaged ceiling and other finishes. | 900000 | PVO to prepare upon receipt of Final Cost | PVO to prepare
EW 144 | DEPA Interior Fitout | Employer’s Instruction No. 030 – Changes in the Aluminum Panels Design (Accommodation of Actual Site Conditions: Adjustments are required to align with on-site realities resulting from changes within adjacent or interfacing work packages. • Aesthetic Enhancements: Revisions have been introduced to improve the visual outcome of the façade elements.) | 131987.45 | EI issued | PVO to prepare. This is SAB
EW 157 | DEPA Interior Fitout | EVO 29 Rectification of damaged waterproofing at Water Features (BC) | -60000 | BC issued | PVO to prepare
SUB-TOTAL |  |  | 11185165.78
Façade & Glazing Works (Alutec)
EW 126 | Façade & Glazing Works | Replacement of External Doors - requested by the Operator (Cluster Manager - Back of House) | 0 | RFC to prepare | No action has been taken in 5 months, hence cancelled
EW 150 | Façade & Glazing Works | EVO No. 005 - Supply of Alutec Manpower to Install the External Glass Balustrade on Behalf of Alcatop | 332640 | EVO issued | Emergency Variation order was issued on the 18th Feb 2026. PVO, DVO to be processed
SUB-TOTAL |  |  | 332640
Al Fanar - MEP Labour Supply
EW 073 | Al Fanar - MEP Labour Supply | Employer’s Instruction for Variation – Panic Alarm System for ADA toilets | 87285 | EI issued | This will be included in the material supply DVO with Al Fanar; therefore, there is no need to process a PVO/VO.
EW 089 | Al Fanar - MEP Labour Supply | Powder coating of wiring accessories (to suit ID requirements) | 20000 | EI issued | This will be included in the material supply DVO with Al Fanar; therefore, there is no need to process a PVO/VO.
EW 105 | Al Fanar - MEP Labour Supply | EI 05: Powder coating of ID light fittings (to suit ID requirements) | 21000 | EI issued | This will be included in the material supply DVO with Al Fanar; therefore, there is no need to process a PVO/VO.
SUB-TOTAL |  |  | 128285
MAS - Amphitheatre & Labour Supply Works
EW 01 - MAS | MAS - Amphitheatre | Amphitheatre Construction Works - Final Account | -9520 | 0 | P Donaghy: Please confirm if they owe us accommodation charges P Donaghy: So is there outstanding accommodation on the other contract? Yes or No?
SUB-TOTAL |  |  | -9520
| FF&E AND OS&E |  | 0
EARLY WARNING TOTAL |  |  | 32891648.893
|  | Check EW (from Schedule A) | 32891648.893
|  | Should Be Zero | 0

## Early Warning (2) (hidden)
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
Location: - AL WAJH SAUDI ARABIA
REPORT NO: - MONTHLY REPORT NO. 49
Item No. | Package | Early Warning Description | Impact | Change Status | Remarks
| Professional Services |  | 0
| Management Supervision |  | 0
| Commercial Management |  | 0
| Construction |  | -22201579.41
RFC 26 | SAB - Civil and Arch Works, MEPD & ICT/ELV | AYC ¦ Grand Stair Structure Backfill | 166610 | PVO rejected | To be discussed if this still be pursued. SAB currently not put forward a variation cost submission for this.
48 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Additional Primary side CHW Valve Arrangement, Flushing Bypass and BTU Meter | 223236 |  |  | Not yet in ACC | 49699225.44
39 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Provision of New IBS Infra. Requirements for Indoor GSM | 1017433 |  |  | Not yet in ACC
RFC 32 | Special Kitchen | Relocation Marina Offices and Regeneration Kitchen (Kitchen) | 1109644.6 | Approved RFC | PVO will be submitted upon receipt of completed IFC drawings from Dewan. |  | -24440698.01 | SAB
RFC 32 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Relocation Marina Offices and Regeneration Kitchen (Construction plus abortive Works) | 2230142.99 | Approved RFC | PVO will be submitted upon receipt of completed IFC drawings from Dewan. |  | 74139923.45
RFC 41 | DEPA Interior Fitout | AYC Guest Lobby Staircase Geometry & Finish Revisions (Construction) | 0 | Approved RFC | PVO will be submitted upon receipt of completed IFC drawings from Dewan.
RFC 43 | DEPA Interior Fitout | Changes to Members Lobby and Guest Lobby Staircase Ballustrades | 27201.54 | Approved RFC | PVO will be submitted upon receipt of completed IFC drawings from Dewan.
RFC 44 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Grand Stair Balustrade Revision to Avoid Fall Hazard (Construction) | 180170 | Approved RFC | PVO will be submitted upon receipt of completed IFC drawings from Dewan.
RFA | SAB - Civil and Arch Works, MEPD & ICT/ELV | MEP Manpower Supply to AYC Project on behalf of SAB. | -23125000 | Approved RFA | PVO 026 in WF for Approval
|  | Adjustment to PVO 005 per Approved DVO 005 - DEPA | -52635
|  | Adjustment to PVO 006 per Approved DVO 006 - DEPA | -198642.89
EW 15 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Omission of Surveying Equipment from SAB Contract | -7890 | Early Warning | RFC to be initiated upon receipt of submission from SAB.
EW 17 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Omission of food and welfare provision to AMAALA Staff from SAB Contract. | -90000 | Early Warning | RFC to be initiated upon receipt of submission from SAB.
EW 17 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Cost saving to Site Office Monthly Running Cost due to late installation of the Office Establishment by SAB. | -200000 | Early Warning | RFC to be initiated upon receipt of submission from SAB.
EW 26 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Potential Contract Cost Adjustment | 0 | Early Warning | Under review - Awaiting SAB Submission of Supporting Documents
EW 29 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Cancellation of Amphitheatre Works issued to MAS - Process not followed | -1108000 | RFA appoved | PVO to be processed.
EW 31 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Recovery of Remaining Block work, Plaster work and Paint Work to be carried out by MAS - Process not followed | -4004000 | RFA appoved | PVO to be processed.
EW 32 | DEPA Interior Fitout | Alteration to finishes due to Façade Layout Changes - Process not Followed | 69000 | EI issued to DEPA | EI issued and awaiting DEPA to submit the cost proposal before we initiate the PVO.
|  | MAS Amphitheatre Works | 1284550.35 |  | Pending Downstream Contracts - Not yet approved in ACC.
EW 33 | MAS - Amphitheatre | Additional Porte Cochere Works to be carried out by MAS | 0 | EI issued to MAS | EI issued to MAS. PVO and VO will be prepared.
EW 34 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Deployment of Seven (7) Surveyors | 201600 | EI issued to SAB | EI issued to SAB. PVO and VO will be prepared.
EW 35 | DEPA Interior Fitout | Employer’s instruction for ID Finishes on Vertical Transportation Fixture Elements | 0 | EI to DEPA drafted | EI to DEPA drafted. Awaiting approval before issue to DEPA.
EW 36 | ESCCO - Vertical Transport | AYC – Disassembly and Reassembly of electronic items from VT fixtures | 0 | EI to ESCCO drafted | EI to ESCCO drafted. Awaiting approval before issue to ESCCO.
EW 37 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Scaffolding works for Secondary Steel and Façade (Design) | 75000 | EI issued to SAB | EI issued to SAB. PVO and VO will be prepared.
EW 38 | ARMETAL - Reflective ceiling | Reflective Ceiling (Award to Armetal) | 0 | RFA under Approval | RFA to award the reflective ceiling to ARMETAL in WF for approval.
EW 39 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Reflective Ceiling (Omission from SAB) | 0 | RFA under Approval | PVO and VO will be prepared.
EW 40 | Al Fanar MEP Manpower Supply to AYC Project on behalf of SAB. | Al Fanar MEP Manpower Supply to AYC Project on behalf of SAB. | 0 | Approved RFA | Contract for Al Fanar under process.
| FF&E |  | 429156
RFC 45 | OS&E Items | Addition of Accessories to Existing Artwork Proposal - Change Decision Pack_Artwork Package | 429156 |  | PVO will be submitted upon receipt of completed details from Dewan/Art Consultant.
EARLY WARNING TOTAL |  |  | -21772423.41
|  |  | 3585562.5 | -18982074.87 | -22567637.37
|  |  | 32891648.893 | -5064290 | -37955938.893
36477211.393
58249634.803
3585562.5
32891648.893
36477211.393

## ACC (hidden)
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
Client: - AMAALA
Location: - AL WAJH SAUDI ARABIA
REPORT NO: - MONTHLY REPORT NO. 49

## Movement (hidden)
October 2025 - Report
October 2025 Cost Report
| Al Fanar Manpower from Jul to Oct25 | 14.56 | 14557384.22 | 14.5574
| Direct Payment for NESMA for ICT System | 2.67 | 2674938 | 2.6749 |  |  | Al Fanar Mapower Services to Dec 2025, & DLP (Jan to Mar25). | 8136064 | 8.14
| Al Fanar Mapower Services to Dec 2025, & DLP (Jan to Mar25). | 8.14 | 8136064 | 8.1361 |  |  | Al Fanar further MEP Matls. (excluded in DVO 002) | 4300000 | 4.3 | RFA for October 2025 Direct Payment:
| MAS Manpower Services (Nov to Dec 25) | 3.05 | 3050936 | 3.0509 |  |  | MAS Manpower Services (Nov to Dec 25) | 3050936 | 3.05 | SAB Position:
| Contract Award for GST (Sustainability) | 0.13 | 133000 | 0.133 |  |  | Contract Award for GST (Sustainability) | 133000 | 0.13 | Payment Made to Date | 208249044.947 | 208249044.947 | copied value
| Contract Award for Enviro (Deep Cleaning) | 0.8 | 799625.31 | 0.79963 |  |  | Contract Award for Enviro (Deep Cleaning) | 799625.31 | 0.8 | AP and PB Recovery | -37656960.29
| Al Fanar further MEP Matls. (excluded in DVO 002) | 4.3 | 4300000 | 4.3 |  |  | Replacement of External Doors - requested by the Operator | 780000 | 0.78 |  | 170592084.657
| Replacement of External Doors - requested by the Operator | 0.78 |  |  |  |  | Various EIs | 402710.72 | 0.4
[7 empty] | Omission Kitchen Service Hatches from SAB | -8078.16 | -0.01 | SAB FFA, Oct 25 Cost Report | 170989417.823 | 228362520.883 | copied value
|  | 34.43 |  |  |  |  | Adj. to SAB's EW cost to cover the various EIs | -402710.72 | -0.4 | August 2025 Direct Payment | 4790313.1478 | 4790313.1478 | copied value
[7 empty] | Adj. to SAB's EW cost to cover the previous Alcatop VOs and SAMIF's VOs. | -1168628.13 | -1.17 | September 2025 Direct Payment | 3198424.1565 | 3198424.1565 | copied value
[7 empty] | Adj. due to the approved DVOs value vs PVOs | -52726 | -0.05 |  | 163000680.5187
[8 empty] | 15970193.02 | 15.97 | Remaining for October 2025 Report | -45248364.4283
This is based on SAB approved EAC.
205264982.63
222783157
193724484.3478
17518174.37
222783157.57
14534122.58
208249034.99
| DVO High Level Overview |  |  |  | 238213
| Item No. - 112 - Employer’s Instruction No.01 - Supply of additional Kitchen Shelf Opening Hatch (Servery Hatches) |  |  |  | 10143 | -5796 | Adjustment due to the approved DVO value vs PVO | -52726 |  | Al Fanar Manpower from July to October 2025 (per the approved DVO 003) | 14557384.22
| Item No. - 111 - Metal Mesh Grating as per CML requirements in MEP shafts |  |  |  | 228070 | -46930 |  |  |  |  | -59805748.6483
[10 empty] | Remaining budget for SAB, based on approved EAC | -45248364.4283
[10 empty] | Alfanar DVO 003 (Jul to Oct25), no BTR yet | -14557384.22
[10 empty] | NET Budget Hold | -59805748.6483
| PVO High Level Overview |  |  |  | -290939
| Item No. - 112 - Employer’s Instruction No.01 - Supply of additional Kitchen Shelf Opening Hatch (Servery Hatches) |  |  |  | -15939
| Item No. - 111 - Metal Mesh Grating as per CML requirements in MEP shafts |  |  |  | -275000
| RFC High Level Overview |  |  |  | 0
| Early Warnings |  |  |  | 16022919.02
| Item No. - 161 - Omission of Internal Windows (Kitchen Service Hatches) from SAB - Supply and install by RAQTAN |  |  | EW 114 | -8078.16 |  | Omission Kitchen Service Hatches from SAB | -8078.16
| Item No. - 162 - EI-17: Road Markings Paint Application |  |  | EW 115 | 8000 |  | Various EIs | 402710.72
| Item No. - 163 - Extension of Al Fanar Mapower Services to AMAALA Yacht Club Project through to December 2025, and DLP Contingency (January to March 2025). |  |  | EW 116 | 8136064 |  | Al Fanar Mapower Services to Dec 2025, & DLP (Jan to Mar25). | 8136064
| Item No. - 164 - Extension of MAS Manpower Services (Nov to Dec 2025) - TB01003-003C31-AMA-RFA-CM-0002 |  |  | EW 117 | 3050936 |  | MAS Manpower Services (Nov to Dec 25) | 3050936
| Item No. - 158 - EI 16: Change in Aged Mirror finish to members' bar & Signature Restaurant |  |  | EW 111 | -204382
| Item No. - 160 - EI-15: Removing and replace tiling around faulty Urinal Sensors |  |  | EW 113 | 72092.72
| Item No. - 166 - EI-18: Consolidated Fit-Out Instructions (Ceiling, LPG, Capping, Beech Ovens & Hood Cladding) |  |  | EW 119 | 232000
| Item No. - 167 - EI-19: Replacement of Vanity Top Soap Dispensers and Rectification of Existing Vanity Units |  |  | EW 120 | 90000
| Item No. - 168 - EI-20: Rectification of the Damaged Ceilings Based on the Various Damage Reports |  |  | EW 121 | 100000
| Item No. - 169 - EI-03: Cooled Glass Display Case at Café (CPD10). |  |  | EW 122 | 0
| Item No. - 170 - EI-18 : Amendment of Secondary Steel Structure vs Honeycomb Limestone Cladding |  |  | EW 123 | 54000
| Item No. - 171 - EI-03: External Glass Door Application at Chart Model Room Staircase |  |  | EW 124 | 51000
| Item No. - 102 - Cost to Complete (SAB Amount) - Including Contingencies |  |  | EW 063 - Adjustment | -402710.72 |  | Adjustment to SAB's EW cost to cover the various EIs | -402710.72
| Contract Award to GST for Sustainability Accreditations Services |  |  |  | 133000 |  | Contract Award for GST (Sustainability) | 133000
| Contract Award to Enviro Facility Management for Deep Cleaning |  |  |  | 799625.31 |  | Contract Award for Enviro (Deep Cleaning) | 799625.31
| SAB - Metal Mesh Grating as per CML requirements in MEP shafts - deducted from SAB's Cost to Complete Early Warning Cost |  |  |  | -228070 |  | Adjustment to SAB's EW cost to cover the Alcatop VOs on handrail changes and SAMIF's VO Metal Mesh Gratings | -1168628.13
| SAB - Employer's Instruction No. 017 - Grand Stair Handrail (Alcatop) - deducted from SAB's Cost to Complete Early Warning Cost |  |  |  | -677313.67
| Item No. - 102 - Cost to Complete (SAB Amount) - Including Contingencies |  |  | Further adjustment to align with the requested additional budget | -263244.46
| Item No. - 172 - Further MEP Material Supply by Al Fanar (excluded in the previous DVO) - Al Fanar letter 1TB01003-003C34-ACY-LTR-0057 |  |  |  | 4300000 |  | Al Fanar further MEP Matls. (excluded in DVO 002) | 4300000
| Item No. - 173 - Replacement of External Doors - requested by the Operator (Cluster Manager - Back of House) |  |  |  | 780000 |  | Replacement of External Doors - requested by the Operator | 780000
15970193.02
| BUDGET HOLD Movement |  |  |  | 0
15970193.02
13.28 | a) 13.28M – approved PVO for Al Fanar Manpower Extension up to 31 Oct 25.
1.28 | b) 1.28M – adjustment due to variance in PVO and DVO approval regarding Al Fanar Manpower Extension up to 31 Oct 25.
1.02 | c) 1.02M – adjustment due to the variance in Early Warning and PVO approval regarding the direct payment to SAB’s subcontractors and suppliers for April and May 2025 Invoices.
2.67 | d) 2.67M – ICT system by NESMA.
0.25 | e) 0.21M – adjustments due to various approved DVOs values compared to PVOs.
18.5
12.06 |  |  |  | 250000
30.5119
|  |  |  | -0.052726 | -52726 | Adjustment due to approved DVO value compared to PVO.
-0.05 | a) -0.05M - Adj due to variance in PVO and DVO 001 of RAQTAN and PVO and DVO 018 of SAB
0.3 | f) 0.30M - EI-15, EI-16, EI-17, EI-18, EI-19 and EI-20 to DEPA
0.05 | g) 0.50M - EI-18 to SAB/SAMIF
0.05 | h) 0.05M - EI-09 to Alutec
3.05 | i) 3.05M - RFA - MAS labour up to Dec-25 |  |  | -0.0080782 | -8078.16 | Item No. - 161 - Omission of Internal Windows (Kitchen Service Hatches) from SAB - Supply and install by RAQTAN |  | EW 114 | -8078.16
5.54 | j) 5.54M - RFA - Al Fanar labour up to Dec-25 |  |  | 0.008 | 8000 | Item No. - 162 - EI-17: Road Markings Paint Application |  | EW 115 | 8000
3.49 | k) 3.49M - RFA - Al Fanar labour DLP/contingency |  |  | 5.5361 | 5536063.63 | Item No. - 163 - Extension of Al Fanar Manpower Services (Nov to Dec 2025) |  | EW 116 | 5536063.63
-0.4 | l) -0.40M - Adjustment to SAB's Contract Adjustment allowance (covering all EIs issued to DEPA, Alutec and SAB/SAMIF) |  |  | 3.0509 | 3050936 | Item No. - 164 - Extension of MAS Manpower Services (Nov to Dec 2025) - TB01003-003C31-AMA-RFA-CM-0002 |  | EW 117 | 3050936
-0.01 | m) -0.01M - Omission of Service Hatches from SAB (install by RAQTAN) |  |  | -0.20438 | -204382 | Item No. - 158 - EI 16: Change in Aged Mirror finish to members' bar & Signature Restaurant |  | EW 111 | -204382
|  |  |  | 0.072093 | 72092.72 | Item No. - 160 - EI-15: Removing and replace tiling around faulty Urinal Sensors |  | EW 113 | 72092.72
12.02 |  |  |  | 0.232 | 232000 | Item No. - 166 - EI-18: Consolidated Fit-Out Instructions (Ceiling, LPG, Capping, Beech Ovens & Hood Cladding) |  | EW 119 | 232000
30.52 |  |  |  | 0.09 | 90000 | Item No. - 167 - EI-19: Replacement of Vanity Top Soap Dispensers and Rectification of Existing Vanity Units |  | EW 120 | 90000
30.57 |  |  |  | 0.1 | 100000 | Item No. - 168 - EI-20: Rectification of the Damaged Ceilings Based on the Various Damage Reports |  | EW 121 | 100000
30.61 |  |  |  | 0 | 0 | Item No. - 169 - EI-03: Cooled Glass Display Case at Café (CPD10). |  | EW 122 | 0
0.04 |  |  |  | 0.054 | 54000 | Item No. - 170 - EI-18 : Amendment of Secondary Steel Structure vs Honeycomb Limestone Cladding |  | EW 123 | 54000
|  |  |  | 0.051 | 51000 | Item No. - 171 - EI-03: External Glass Door Application at Chart Model Room Staircase |  | EW 124 | 51000
|  |  |  | 3.4928 | 3492825.22 | Item No. - 172 - Additional Budget Approval for Al Fanar Manpower Services (Dec 2025 Completion and DLP Contingency) - 1TB01003-003C34-AMA-RFA-CM-0003 |  | EW 125 | 3492825.22
|  |  |  | -0.40271 | -402710.72 | Item No. - 102 - Cost to Complete (SAB Amount) - Including Contingencies |  | EW 063 - Adjustment | -402710.72
297710.72
|  |  |  | 12.0717 | 402710.72
14.56 | a) 14.56M – DVO for Al Fanar Manpower up to 31 Oct 25. |  |  |  | 12071746.69
1.02 | b) 1.02M – adj due to the variance in EW and PVO regarding SAB's direct payment (Apr & May 25). |  |  |  | 12019020.69
2.67 | c) 2.67M – direct payment for the ICT system by NESMA.
0.29 | d) 0.25M – adj due to various approved DVOs compared to PVOs.
0.3 | e) 0.30M - EI-15, EI-16, EI-17, EI-18, EI-19 and EI-20 to DEPA
0.05 | f) 0.05M - EI-18 to SAB/SAMIF
0.05 | g) 0.05M - EI-09 to Alutec
3.05 | h) 3.05M - RFA - MAS labour up to Dec-25
5.54 | i) 5.54M - RFA - Al Fanar labour up to Dec-25
3.49 | j) 3.49M - RFA - Al Fanar labour DLP/contingency
-0.4 | k) -0.40M - reduction of SAB's CP Adjustment allowance (cost of all EIs issued to DEPA, Alutec and SAB/SAMIF).
-0.01 | l) -0.01M - Omission of Service Hatches from SAB.
30.61
0

## 75.7M SAB EW (hidden)
=75,660,633.83-(13,737,620)-(760,869.57+612,731.57)-4,055,764.55-(1,655,399.8-569838*0)-82,2640.54-519,230.25-(158,817.97)-(104,000)+666,280-(21,000)-(115,000)-(50,000)
53713839.58
| Early Warning | Cost to Complete (SAB Amount) - Including Contingencies | 75723856.83
Adjustment for DEPA
| 2024-10-01 | No change | 0 | [5 empty] | Employer’s instruction for ID Finishes on Vertical Transportation Fixture Elements | 684836.5 | 313961.5 | 370875
| 2024-11-01 | No change | 0 | [5 empty] | Back-of-House Finishes (EI 006)_DEPA | 3351000 | 2521135.52 | 829864.48
| 2024-12-01 | Removed | 0 | [5 empty] | Employers Instruction No. 07 – Supply and Installation of Millworks to Show Kitchens |  |  | 0
| 2025-01-01 | Owner Controlled Insurance Program | -63223 | [5 empty] | Employers Instruction No. 09 – Honeycomb Limestone System and External Doors | 1585809.45 | 850370.6 | 735438.85
| 2025-02-01 | MAS Manpower and Supervision PVO | -13737620 | [5 empty] | Employer's Instruction No. 10 - Changes In the Balustrade Materials at the Member's Lobby and Guest Foyer
| 2025-02-01 | Scaffolding Material in CTC | -760869.57 | The Scaffolding Contract Awarded to HAS at |  |  | SAR 3,096,124.9 |  | Descope FF12.04 Millwork & Procure Globe via Depa
| 2025-02-01 | ??? | -612731.57 | [5 empty] | Total |  |  | 1936178.33
| 2025-03-03 | No change
| 2025-04-03 | No change
| 2025-05-01 | Negative adjustment to maintain the SAR 584.59M EAC | -4055764.55
| 2025-06-03 | No change |  | =-(1655399.8-569838*0)-822640.54-519230.25-(158817.97)
| 2025-07-03 | K&A Extension | -1655399.8 | =-(1655399.8-569838*0)-822640.54-519230.25-(158817.97) |  |  |  | -3156088.56
| 2025-07-03 | CML Extension | -822640.54
| 2025-07-03 | Areen's Extension | -519230.25 |  | -158817.97
| 2025-07-03 | Negative adjustment to maintain the previous EAC Report in Jul 2025 of SAR 594.03M (however, this is deducted with SAB's PB and APB amount of SAR 37.66 = SAR 556.37M EAC in Jul 2025). | -158817.97 |  | 106917.56 |  | 0 | 0
| 2025-08-03 | Modification to Members Lobby & Guest Foyer Staircase Finishes | -104000 |  | -51900.41 |  | 0 | 0
|  | Powder coating of ID light fittings (to suit ID requirements) | -21000 |  |  |  | -158817.97
|  | Installation of Decorative Lights | -115000
|  | Supply and Install Access Doors | -50000
|  | ??? | 666280
| 2025-09-25 | No change
| 2025-10-03 | Item No. - 162 - EI-17: Road Markings Paint Application | -8000 |  |  |  |  | 8000
|  | Item No. - 158 - EI 16: Change in Aged Mirror finish to members' bar & Signature Restaurant | 204382
|  | Item No. - 160 - EI-15: Removing and replace tiling around faulty Urinal Sensors | -72092.72
|  | Item No. - 166 - EI-18: Consolidated Fit-Out Instructions (Ceiling, LPG, Capping, Beech Ovens & Hood Cladding) | -232000
|  | Item No. - 167 - EI-19: Replacement of Vanity Top Soap Dispensers and Rectification of Existing Vanity Units | -90000
|  | Item No. - 168 - EI-20: Rectification of the Damaged Ceilings Based on the Various Damage Reports | -100000
|  | Item No. - 169 - EI-03: Cooled Glass Display Case at Café (CPD10). | 0
|  | Item No. - 170 - EI-18 : Amendment of Secondary Steel Structure vs Honeycomb Limestone Cladding | -54000
|  | Item No. - 171 - EI-03: External Glass Door Application at Chart Model Room Staircase | -51000 | -402710.72
|  | Metal Mesh Grating as per CML requirements in MEP shafts | -228070
|  | Employer's Instruction No. 017 - Grand Stair Handrail (Alcatop) | -677313.67
|  | Further adjustment (for balancing of requested budget) | -263244.46
| 2025-11-25 | Adjustment due to DEPA PVO 019 increased by 10K from EW | -10000
|  | Adjustment due variance in EW and PVO 033 (Jun and Jul 25 Direct Payment) | 838114.1
|  | Adjustment due to variance in PVO and DVO (SAB Road Studs from Railing) | 41010
|  | TOTAL | 53011624.83 |  | 0 | 0
|  |  | -702214.75 |  | 0 | 0
0
-569838.42
|  |  | 53548.43 |  | 1655399.8
1085561.38
Direct Payments
|  | Direct Payment - Jan to Mar 25 | -8870230.27
|  | Direct Payment - Apr to May 25 | -7235632.79
|  | Direct Payment - Jun to Jul 25 | -8703634.56
-24809497.62
28202127.21
|  | Contigencies | 0
|  |  | 28202127.21 |  | 2024-05-29
2024-07-02
34
0.29
0.25

## Level 02
Triple Bay Portfolio
Cost Report Executive Summary
Programme 1 - Amaala Yacht Club
OCTOBER 2026
Program | Asset | Sub-category | Name | Previous Approved Budget | Approved Budget Transfers | Currently Approved Budget | Contracts | DVO's | Committed PVOs | Committed | Uncommitted | PVO's | CTC - Site | CTC - Procurement | Early Warnings | Final Account | Variance
Program 1 - AYC | Professional Services | Professional Services | Dewan Architects & Engineers 2200445 | 5973808 | 0 | 5973808 | 5973808 | 3316718.1 | 0 | 9290526.1 |  | 0 | 0 |  | 0 | 9290526.1 | 3316718.1
Program 1-AYC | Professional Services | Professional Services | HKS Architects Ltd - Design Competition Fees 2200010 | 555960.36 | 0 | 555960.36 | 555960.36 | 0 | 0 | 555960.36 |  | 0 | 0 |  | 0 | 555960.36 | 0
Program 1-AYC | Professional Services | Professional Services | HKS Architects Ltd - Design Architect Fees 2200375 | 10891204 | 0 | 10891204 | 10891204 | -89775 | 0 | 10801429 |  | 0 | 0 |  | 0 | 10801429 | -89775
Program 1-AYC | Professional Services | Professional Services | Applied Technology and Management Inc (Dubai BR)s 2210167 | 93750 | 0 | 93750 | 93750 | 0 | 0 | 93750 |  | 0 | 0 |  | 0 | 93750 | 0
Program 1-AYC | Professional Services | Professional Services | Langan International UK Limited 2230042 | 0 | 172368.42 | 172368.42 | 172368.42 | -1898.52 | 0 | 170469.9 |  | 0 | 0 |  | 0 | 170469.9 | -1898.52
Program 1-AYC | Professional Services | Professional Services | Zuhair Fayez and Partners 2230041 | 0 | 106231.5 | 106231.5 | 106231.5 | 0 | 0 | 106231.5 |  | 0 | 0 |  | 0 | 106231.5 | 0
Program 1-AYC | Professional Services | Professional Services | Ministry of Municipality and Rural Affairs (Tabuk) | 0 | 45677.6 | 45677.6 | 45677.6 | 0 | 0 | 45677.6 |  | 0 | 0 |  | 0 | 45677.6 | 0
Program 1-AYC | Professional Services | Professional Services | Jensen Hughes Saudi Arabia Co 2230180 | 0 | 127291.9 | 127291.9 | 127291.9 | -56700 | 0 | 70591.9 |  | 0 | 0 |  | 0 | 70591.9 | -56700
Program 1-AYC | Professional Services | Professional Services | Jensen Hughes Saudi Arabia Co 2250184 | 0 | 38103.2 | 38103.2 | 38103.2 | -23800 | 0 | 14303.2 |  | 0 | 0 |  | 0 | 14303.2 | -23800
Program 1-AYC | Professional Services | Professional Services | CML (Independent Commissioning Agent) COO 7 | 0 | 2406500 | 2406500 | 2406500 | 1520390.54 | 0 | 3926890.54 |  | 101675.08 | 0 |  | 0 | 4028565.62 | 1622065.62
Program 1-AYC | Professional Services | Professional Services | GST - Sustainability Accreditation Services | 0 | 133000 | 133000 | 133000 | 0 | 0 | 133000 |  | 0 | 0 |  | 0 | 133000 | 0
Program 1-AYC | Professional Services | Professional Services | Remaining budget - Professional Fees | 11246866.87 | -9734500.35 | 1512366.52 | 0 | 0 |  | 0 |  | 0 |  |  | 0 | 0 | -1512366.52
Sub-Total | Professional Services |  | Sub-Total Professional Fees | 28761589.23 | -6705327.73 | 22056261.5 | 20543894.98 | 4664935.12 | 0 | 25208830.1 | 0 | 101675.08 | 0 | 0 | 0 | 25310505.18 | 3254243.68
Program 1-AYC | Management supervision | Management Services | MS.003F02 - Khatib & Alami 2230031 | 0 | 13059930 | 13059930 | 13059930 | 1071977 | 0 | 14131907 |  | 0 | -49207 |  | 0 | 14082700 | 1022770
Program 1-AYC | Management supervision | Management Services | PS.003F07 - Euro Consult (COO 6) | 0 | 182184.38 | 182184.38 | 182184.38 | 0 | 0 | 182184.38 |  | -53507 | 0 |  | 0 | 128677.38 | -53507
Program 1-AYC | Management supervision | Management Services | PS.003F09 - Euro Consult (COO 27) | 0 | 54000 | 54000 | 54000 | 0 | 0 | 54000 |  | 0 | 0 |  | 0 | 54000 | 0
Program 1-AYC | Management supervision | Management Services | Remaining budget - Management Supervision | 17975993.27 | -18233177.65 | -257184.38 | 0 | 0 | 0 | 1.0477e-09 |  | 0 | 0 |  | 0 | 0 | 257184.38
Sub-Total | Management supervision |  | Sub-Total Management Services | 17975993.27 | -4937063.27 | 13038930 | 13296114.38 | 1071977 | 0 | 14368091.38 | 0 | -53507 | -49207 | 0 | 0 | 14265377.38 | 1226447.38
Program 1-AYC | Commercial Management | Commercial Management | Nothing to Report |  |  | 0 |  |  |  | 0 | [5 empty] | 0 | 0
Program 1-AYC | Commercial Management | Commercial Management | Remaining budget - Commercial Management | 1198399.55 | -1198399.55 | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0
Sub-Total | Commercial Management |  | Sub-Total Commercial Management | 1198399.55 | -1198399.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Program 1-AYC | Early Works Constructions | Early Works Construction | SOI TB Ground Improvement Works 2210224 | 2799717 | 0 | 2799717 | 2799717 | 0 | 0 | 2799717 |  | 0 | 0 |  | -500000 | 2299717 | -500000
Program 1-AYC | Early Works Constructions | Early Works Construction | SOI TB Ground Improvement Works 2210224 PROVISIONAL SUMS | 282972 | 0 | 282972 | 282972 | 0 | 0 | 282972 |  | 0 | 0 |  | -282972 | 0 | -282972
Program 1-AYC | Construction Works | Construction Works | Green Business Certification Inc.2220038 | 4500 | 18594.49 | 23094.49 | 23094.49 | -509.48 | 0 | 22585.01 |  | 0 | 0 |  | 0 | 22585.01 | -509.48
Sub-Total | Early Works Constructions |  | Sub-Total Early Works | 3087189 | 18594.49 | 3105783.49 | 3105783.49 | -509.48 | 0 | 3105274.01 | 0 | 0 | 0 | 0 | -782972 | 2322302.01 | -783481.48
Program 1-AYC | Construction Works | Construction Works | NSCC - Triple Bay Piling (AYC only) 2220032 | 18698534 | 0 | 18698534 | 18698534 | -2240152.49 | 0 | 16458381.51 |  | 0 | 0 |  | 0 | 16458381.51 | -2240152.49
Program 1-AYC | Construction Works | Construction Works | Civil and Mechanical Works - (SAB) 2230023 | 0 | 260955414.4 | 260955414.4 | 260955414.4 | -91015507.7 | 0 | 169939906.7 |  | -19683045.7 | -1065566.44 |  | 21798123.263 | 170989417.823 | -89965996.577
Program 1-AYC | Construction Works | Direct Payments | Prelims - Mohammad Alharbi Medical Company | 0 | 134895.4 | 134895.4 | 134895.4 | 0 | 0 | 134895.4 |  | 0 | 0 |  | 0 | 134895.4 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Al Anan Travels and Tours | 0 | 103373.74 | 103373.74 | 103373.74 | 0 | 0 | 103373.74 |  | 0 | 0 |  | 0 | 103373.74 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Al drees Petroleum | 0 | 34782.61 | 34782.61 | 34782.61 | 0 | 0 | 34782.61 |  | 0 | 0 |  | 0 | 34782.61 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Salim Hamed Cleaning | 0 | 31306.1 | 31306.1 | 31306.1 | 0 | 0 | 31306.1 |  | 0 | 0 |  | 0 | 31306.1 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Clean Coast for Contracting | 0 | 252583.81 | 252583.81 | 252583.81 | 0 | 0 | 252583.81 |  | 0 | 0 |  | 0 | 252583.81 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Sami General Contracting | 0 | 273350 | 273350 | 273350 | 0 | 0 | 273350 |  | 0 | 0 |  | 0 | 273350 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Eastern Horizons Foundation Transportation Comp | 0 | 14349 | 14349 | 14349 | 0 | 0 | 14349 |  | 0 | 0 |  | 0 | 14349 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Jak Generation Cont Co LLC | 0 | 369751.45 | 369751.45 | 369751.45 | 0 | 0 | 369751.45 |  | 0 | 0 |  | 0 | 369751.45 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Intelligent General Cont Co Equipment | 0 | 758870.17 | 758870.17 | 758870.17 | 0 | 0 | 758870.17 |  | 0 | 0 |  | 0 | 758870.17 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Al Rai Modern Water Factory | 0 | 318320.5 | 318320.5 | 318320.5 | 0 | 0 | 318320.5 |  | 0 | 0 |  | 0 | 318320.5 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - NEXTWARE INTERNATIONAL SUPPLY | 0 | 1845 | 1845 | 1845 | 0 | 0 | 1845 |  | 0 | 0 |  | 0 | 1845 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Virtual Projects DMCC | 0 | 51948.13 | 51948.13 | 51948.13 | 0 | 0 | 51948.13 |  | 0 | 0 |  | 0 | 51948.13 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Raddad Al adinah | 0 | 142131.61 | 142131.61 | 142131.61 | 0 | 0 | 142131.61 |  | 0 | 0 |  | 0 | 142131.61 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Ahmed Bin Salem Bin Dagher | 0 | 348199.81 | 348199.81 | 348199.81 | 0 | 0 | 348199.81 |  | 0 | 0 |  | 0 | 348199.81 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Bahamdoon Trading | 0 | 1535 | 1535 | 1535 | 0 | 0 | 1535 |  | 0 | 0 |  | 0 | 1535 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Lumi Rentals | 0 | 6142.43 | 6142.43 | 6142.43 | 0 | 0 | 6142.43 |  | 0 | 0 |  | 0 | 6142.43 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Filter Expert Trading | 0 | 8565 | 8565 | 8565 | 0 | 0 | 8565 |  | 0 | 0 |  | 0 | 8565 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Abu Nayyan | 0 | 17800 | 17800 | 17800 | 0 | 0 | 17800 |  | 0 | 0 |  | 0 | 17800 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Ihsan Muhammed Thakir Idress Trading | 0 | 99000 | 99000 | 99000 | 0 | 0 | 99000 |  | 0 | 0 |  | 0 | 99000 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Ramzi Abbas Mohd. Sayed Est. | 0 | 48767 | 48767 | 48767 | 0 | 0 | 48767 |  | 0 | 0 |  | 0 | 48767 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Al Rayi Water | 0 | 46655 | 46655 | 46655 | 0 | 0 | 46655 |  | 0 | 0 |  | 0 | 46655 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - GLSAN Contracting Company | 0 | 8291108.14 | 8291108.14 | 8291108.14 | 0 | 0 | 8291108.14 |  | 0 | 0 |  | 0 | 8291108.14 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - GLSAN Contracting Company (Red Sea) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Masa Equipment Est | 0 | 287000 | 287000 | 287000 | 0 | 0 | 287000 |  | 0 | 0 |  | 0 | 287000 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Al Tala'a International Transportation Co | 0 | 6608.7 | 6608.7 | 6608.7 | 0 | 0 | 6608.7 |  | 0 | 0 |  | 0 | 6608.7 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Saudi Brokers | 0 | 59606.12 | 59606.12 | 59606.12 | 0 | 0 | 59606.12 |  | 0 | 0 |  | 0 | 59606.12 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Aknan Al Bena | 0 | 75000 | 75000 | 75000 | 0 | 0 | 75000 |  | 0 | 0 |  | 0 | 75000 | 0
Program 1-AYC | Construction Works | Direct Payments | Prelims - Emaar Suhali | 0 | 90000 | 90000 | 90000 | 0 | 0 | 90000 |  | 0 | 0 |  | 0 | 90000 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Madar Building material Co | 0 | 14320 | 14320 | 14320 | 0 | 0 | 14320 |  | 0 | 0 |  | 0 | 14320 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Juffali Technical Equipment Company | 0 | 12113.6 | 12113.6 | 12113.6 | 0 | 0 | 12113.6 |  | 0 | 0 |  | 0 | 12113.6 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - USG Middle East Ltd. Co | 0 | 39954.82 | 39954.82 | 39954.82 | 0 | 0 | 39954.82 |  | 0 | 0 |  | 0 | 39954.82 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Abu Dhabi Precast | 0 | 3619680.62 | 3619680.62 | 3619680.62 | 0 | 0 | 3619680.62 |  | 0 | 0 |  | 0 | 3619680.62 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - SAMIF | 0 | 6340696.9 | 6340696.9 | 6340696.9 | 0 | 0 | 6340696.9 |  | 0 | 0 |  | 0 | 6340696.9 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - SAUDI MANPOWER SOLUTIONS CO | 0 | 377764.03 | 377764.03 | 377764.03 | 0 | 0 | 377764.03 |  | 0 | 0 |  | 0 | 377764.03 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Fosam Company LTD | 0 | 40570 | 40570 | 40570 | 0 | 0 | 40570 |  | 0 | 0 |  | 0 | 40570 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Glow Arabia Trading | 0 | 49460.5 | 49460.5 | 49460.5 | 0 | 0 | 49460.5 |  | 0 | 0 |  | 0 | 49460.5 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - BROOQ ALAMAAN TRAD COMPANY | 0 | 130305.72 | 130305.72 | 130305.72 | 0 | 0 | 130305.72 |  | 0 | 0 |  | 0 | 130305.72 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Abeer Munawer Al Shamari | 0 | 1059365.93 | 1059365.93 | 1059365.93 | 0 | 0 | 1059365.93 |  | 0 | 0 |  | 0 | 1059365.93 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Yaz Development Contracting | 0 | 1036210 | 1036210 | 1036210 | 0 | 0 | 1036210 |  | 0 | 0 |  | 0 | 1036210 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Naffco | 0 | 936325.93 | 936325.93 | 936325.93 | 0 | 0 | 936325.93 |  | 0 | 0 |  | 0 | 936325.93 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - GESR Alarab | 0 | 2444255.5 | 2444255.5 | 2444255.5 | 0 | 0 | 2444255.5 |  | 0 | 0 |  | 0 | 2444255.5 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Jameel Mohamed Hussain Alqatafa Cont Est | 0 | 127257.78 | 127257.78 | 127257.78 | 0 | 0 | 127257.78 |  | 0 | 0 |  | 0 | 127257.78 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - MEDTEL | 0 | 5913785.58 | 5913785.58 | 5913785.58 | 0 | 0 | 5913785.58 |  | 0 | 0 |  | 0 | 5913785.58 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Noreom | 0 | 100641.6 | 100641.6 | 100641.6 | 0 | 0 | 100641.6 |  | 0 | 0 |  | 0 | 100641.6 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Isam Kabani & Partners | 0 | 2267626.88 | 2267626.88 | 2267626.88 | 0 | 0 | 2267626.88 |  | 0 | 0 |  | 0 | 2267626.88 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - ARABIAN TESTING EVOLUTION COMPANY | 0 | 425440 | 425440 | 425440 | 0 | 0 | 425440 |  | 0 | 0 |  | 0 | 425440 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Wood Expert | 0 | 22475 | 22475 | 22475 | 0 | 0 | 22475 |  | 0 | 0 |  | 0 | 22475 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Energy & Building Master | 0 | 117720 | 117720 | 117720 | 0 | 0 | 117720 |  | 0 | 0 |  | 0 | 117720 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - ACES | 0 | 4401.3 | 4401.3 | 4401.3 | 0 | 0 | 4401.3 |  | 0 | 0 |  | 0 | 4401.3 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - International Company for Building Materials LTD | 0 | 60486.9 | 60486.9 | 60486.9 | 0 | 0 | 60486.9 |  | 0 | 0 |  | 0 | 60486.9 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Al Hayat | 0 | 846817.39 | 846817.39 | 846817.39 | 0 | 0 | 846817.39 |  | 0 | 0 |  | 0 | 846817.39 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works -Saint Gobain | 0 | 122301.47 | 122301.47 | 122301.47 | 0 | 0 | 122301.47 |  | 0 | 0 |  | 0 | 122301.47 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works- AAMTAC Company LTD | 0 | 22553 | 22553 | 22553 | 0 | 0 | 22553 |  | 0 | 0 |  | 0 | 22553 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - DOSAR Al Najd | 0 | 123937.39 | 123937.39 | 123937.39 | 0 | 0 | 123937.39 |  | 0 | 0 |  | 0 | 123937.39 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Alcatop | 0 | 1139399.11 | 1139399.11 | 1139399.11 | 0 | 0 | 1139399.11 |  | 0 | 0 |  | 0 | 1139399.11 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Saveto Saudi Vetonit Co Ltd | 0 | 2730 | 2730 | 2730 | 0 | 0 | 2730 |  | 0 | 0 |  | 0 | 2730 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Top Construction Co Ltd | 0 | 326341.06 | 326341.06 | 326341.06 | 0 | 0 | 326341.06 |  | 0 | 0 |  | 0 | 326341.06 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - TBK Metal | 0 | 200069 | 200069 | 200069 | 0 | 0 | 200069 |  | 0 | 0 |  | 0 | 200069 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Lakeshore | 0 | 624120.15 | 624120.15 | 624120.15 | 0 | 0 | 624120.15 |  | 0 | 0 |  | 0 | 624120.15 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - Fast Steps | 0 | 22250 | 22250 | 22250 | 0 | 0 | 22250 |  | 0 | 0 |  | 0 | 22250 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - HRFA | 0 | 196505.68 | 196505.68 | 196505.68 | 0 | 0 | 196505.68 |  | 0 | 0 |  | 0 | 196505.68 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - NESMA | 0 | 1942966.8 | 1942966.8 | 1942966.8 | 0 | 0 | 1942966.8 |  | 0 | 0 |  | 0 | 1942966.8 | 0
Program 1-AYC | Construction Works | Direct Payments | Direct Works - TANSEEQ | 0 | 9915.37 | 9915.37 | 9915.37 | 0 | 0 | 9915.37 |  | 0 | 0 |  | 0 | 9915.37 | 0
Program 1-AYC | Construction Works | Direct Payments | Tamimi (SAB Accommodation Payment) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
Program 1-AYC | Construction Works | Construction Works | STO Façade Mock-up -(MWN) 2230075 | 0 | 834298.55 | 834298.55 | 834298.55 | -15000 | 0 | 819298.55 |  | 0 | 0 |  | 0 | 819298.55 | -15000
Program 1-AYC | Construction Works | Construction Works | Vertical Transportation (ESCCO) 2230178 | 0 | 2675473 | 2675473 | 2675473 | 98073 | 0 | 2773546 |  | 765046.05 | -200000 |  | -15675 | 3322917.05 | 647444.05
Program 1-AYC | Construction Works | Construction Works | Kitchen & Laundry Works (Al Raqtan) 2230205 | 0 | 4695209 | 4695209 | 4695209 | 10143 | 0 | 4705352 |  | 0 | 1109644.6 |  | 255601.85 | 6070598.45 | 1375389.45
Program 1-AYC | Construction Works | Construction Works | Fitout Works (DEPA) | 0 | 75969227 | 75969227 | 75969227 | 2312919.14 | 1928436.11 | 80210582.25 |  | -842054.38 | 1569206.64 |  | 11185165.78 | 92122900.29 | 16153673.29
Program 1-AYC | Construction Works | Construction Works | Façade & Glazing Works (Alutec) | 0 | 29899670.55 | 29899670.55 | 29899670.55 | 574831.03 | 0 | 30474501.58 |  | -112821 | 158694 |  | 332640 | 30853014.58 | 953344.03
Program 1-AYC | Construction Works | Construction Works | MAS - Wet Works | 0 | 4004000 | 4004000 | 4004000 | 18356118 | 0 | 22360118 |  | 160876.21 | 0 |  | 0 | 22520994.21 | 18516994.21
Program 1-AYC | Construction Works | Construction Works | MAS - Amphitheatre Works | 0 | 1078892.27 | 1078892.27 | 1078892.27 | 205658.08 | 0 | 1284550.35 |  | 0 | 0 |  | -9520 | 1275030.35 | 196138.08
Program 1-AYC | Construction Works | Construction Works | Al Fanar - MEP Labour Supply | 0 | 23125000 | 23125000 | 23125000 | 71435593.23 | 65000 | 94625593.23 |  | 786453.46 | 0 |  | 128285 | 95540331.69 | 72415331.69
Program 1-AYC | Construction Works | Construction Works | Hard and Soft Landscaping | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
Program 1-AYC | Construction Works | Construction Works | ARMETAL - Reflective ceiling | 0 | 7129950 | 7129950 | 7129950 | 67078.55 | 0 | 7197028.55 |  | 0 | 0 |  | 0 | 7197028.55 | 67078.55
Program 1-AYC | Construction Works | Construction Works | Al Rahji Takaful - Owner Controlled Insurance Program | 0 | 89047.06 | 89047.06 | 89047.06 | 0 | 0 | 89047.06 |  | 0 | 0 |  | 0 | 89047.06 | 0
Program 1-AYC | Construction Works | Construction Works | ABU DHABI PRECAST - GRC Cladding | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
Program 1-AYC | Construction Works | Construction Works | HASSAN ALLAM - External Scaffoldings | 0 | 3096124.9 | 3096124.9 | 3096124.9 | 0 | 0 | 3096124.9 |  | 0 | 0 |  | 0 | 3096124.9 | 0
Program 1-AYC | Construction Works | Construction Works | Enviro - Deep Cleaning | 0 | 799625.31 | 799625.31 | 799625.31 | 0 | 0 | 799625.31 |  | 0 | 0 |  | 0 | 799625.31 | 0
Program 1-AYC | Construction Works | Construction Works | KTH - MEP Works Package - 2240072 - KORTEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 583143.7 | 367770 |  | 0 | 950913.7 | 950913.7
Program 1-AYC | Construction Works | Construction Works | ALC - Alcatop Package - Fourseasons - Alcatop | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 150000 |  | 0 | 150000 | 150000
Program 1-AYC | Construction Works | Construction Works | Al Futtaim Pioneer Elevators - Al Futtaim Pioneer | 0 | 691955 | 691955 | 691955 | 0 | 0 | 691955 |  | 0 | 0 |  | 0 | 691955 | 0
Program 1-AYC | Construction Works | Construction Works | Shandong Tiejun Electric Power Engineering Co. LTD. Branch - 2230277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1079464.7 |  | 0 | 1079464.7 | 1079464.7
Program 1-AYC | Construction Works | Construction Works | IMAR Overseas Saudi Arabia Co. W.L.L. - IMAR MH3 | 0 | 0 | 0 | 0 | 442200 | 0 | 442200 |  | 0 | 36400 |  | 0 | 478600 | 478600
Program 1-AYC | Construction Works | Construction Works | Fibrex LLC - FIBREX LLC | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 164010 | 0 |  | 0 | 164010 | 164010
Program 1-AYC | Construction Works | Construction Works | RJT- OCIP Insurance Premium - Declaration 11 - OCIP Insurance | 0 | 15076.28 | 15076.28 | 15076.28 | 0 | 0 | 15076.28 |  | 0 | 0 |  | 0 | 15076.28 | 0
Program 1-AYC | Construction Works | Construction Works | Remaining budget - Construction Works | 221633231.2 | -192496415.77 | 29136815.43 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | -29136815.43
Sub-Total | Construction Works |  | Sub-Total Construction Works | 240331765.2 | 265156807.28 | 505488572.48 | 476351757.05 | 231953.84 | 1993436.11 | 478577147 | 0 | -18178391.66 | 3205613.5 | 0 | 33674620.893 | 497278989.733 | -8209582.747
Program 1-AYC | FF&E | FF&E | FF&E and OSE Procurement Agent (Areen Design Ltd) | 0 | 1107465.88 | 1107465.88 | 1107465.88 | 851779 | 0 | 1959244.88 |  | 0 | 0 |  | 0 | 1959244.88 | 851779
Program 1-AYC | FF&E | FF&E | Loose FF&E Items (FOH & BOH) - Areen Design Ltd | 0 | 22998647.56 | 22998647.56 | 22998647.56 | 0 | 0 | 22998647.56 |  | 0 | 0 |  | 0 | 22998647.56 | 0
Program 1-AYC | FF&E | FF&E | OS&E Items - Areen Design Ltd | 0 | 14586000 | 14586000 | 14586000 | 0 | 0 | 14586000 |  | 0 | 429156 |  | 0 | 15015156 | 429156
Program 1-AYC | FF&E | FF&E | Extraordinary Cart | 0 | 397876 | 397876 | 397876 | 0 | 0 | 397876 |  | 0 | 0 |  | 0 | 397876 | 0
Program 1-AYC | FF&E | FF&E | Saudico Electronic Systems | 0 | 353487.06 | 353487.06 | 353487.06 | 0 | 0 | 353487.06 |  | 0 | 0 |  | 0 | 353487.06 | 0
Program 1-AYC | FF&E | FF&E | Birch Street | 0 | 115998.98 | 115998.98 | 115998.98 | 0 | 0 | 115998.98 |  | 0 | 0 |  | 0 | 115998.98 | 0
Program 1-AYC | FF&E | FF&E | AlFalak Electronic - HPE Servers | 0 | 16655 | 16655 | 16655 | 0 | 0 | 16655 |  | 0 | 0 |  | 0 | 16655 | 0
Program 1-AYC | FF&E | FF&E | Saudico Electronic Systems | 0 | 34719 | 34719 | 34719 | 0 | 0 | 34719 |  | 0 | 0 |  | 0 | 34719 | 0
Program 1-AYC | FF&E | FF&E | Sevenrooms Inc | 0 | 32751.56 | 32751.56 | 32751.56 | 0 | 0 | 32751.56 |  | 0 | 0 |  | 0 | 32751.56 | 0
Program 1-AYC | FF&E | FF&E | Infor Saudi Arabia Limited | 0 | 58307.19 | 58307.19 | 58307.19 | 0 | 0 | 58307.19 |  | 0 | 0 |  | 0 | 58307.19 | 0
Program 1-AYC | FF&E | FF&E | TRA - Zatca Integration with Reachware | 0 | 57135 | 57135 | 57135 | 0 | 0 | 57135 |  | 0 | 0 |  | 0 | 57135 | 0
Program 1-AYC | FF&E | FF&E | PeopleVine Implementation | 0 | 336187.5 | 336187.5 | 336187.5 | 0 | 0 | 336187.5 |  | 0 | 0 |  | 0 | 336187.5 | 0
Program 1-AYC | FF&E | FF&E | Samtiah Arabis Ltd - Operation systems | 0 | 59637.55 | 59637.55 | 59637.55 | 0 | 0 | 59637.55 |  | 0 | 0 |  | 0 | 59637.55 | 0
Program 1-AYC | FF&E | FF&E | Remaining budget - FF&E and OSE | 24991549 | -24988413.89 | 3135.11 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | -3135.11
Sub-Total | FF&E |  | Sub-Total FF&E | 24991549 | 15166454.39 | 40158003.39 | 40154868.28 | 851779 | 0 | 41006647.28 | 0 | 0 | 429156 | 0 | 0 | 41435803.28 | 1277799.89
|  |  | GRAND TOTAL | 316346485.25 | 267501065.61 | 583847550.86 | 553452418.18 | 6820135.48 | 1993436.11 | 562265989.77 | 0 | -18130223.58 | 3585562.5 | 0 | 32891648.893 | 580612977.583 | -3234573.277
|  |  |  | 316346485.25 | 267501065.61 | 583847550.86 | 553452418.18 | 6820135.48 | 1993436.11 | 562265989.77 |  | -18130223.58 | 3585562.5 |  | 32891648.893 | 580612977.583 | -3234573.277
|  |  | CHECK ZERO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## FA Status
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
OPEN |  |  | CLOSED |  |  | NOT REQUIRED |  |  | TOTAL PACKAGES
17 |  |  | 18 |  |  | 10 |  |  | 45
VALUE – OPEN (SAR) |  |  | VALUE – CLOSED (SAR) |  |  | VALUE – NOT REQ. (SAR) |  |  | TOTAL ANTICIPATED FA (SAR)
497616623.113 |  |  | 36070673.9 |  |  | 1448794.89 |  |  | 535136091.903
No. | ACC Code | Package / Description | Contractor / Consultant | Type | Committed Cost (Schedule B – Col K) | Uncommitted Cost (AFA – Committed) | Anticipated Final Account (Sch B – Q) | Responsible | Forecast Date (FA Closure) | Days Remaining to Close | Status | Comments
1 | PS.003D01 | Triple Bay Hijaz Yacht Club - Lead Consultant Services | Dewan Architects & Engineers | Consultant | 9290526.1 | 0 | 9290526.1 | Jose Chavenia | 2026-07-30 | -66 | Open | Works Ongoing
2 | PS.003D02 | Design Competition | HKS Architects Limited | Consultant | 555960.36 | 0 | 555960.36 | Blake Lombard | N/A | - | Closed | FAS Signed (Closed)
3 | PS.003D03 | Triple Bay Marine Yacht Club - Design Architect Consultancy Services | HKS Architects Limited | Consultant | 10801429 | 0 | 10801429 | Blake Lombard | N/A | - | Closed | FAS Signed (Closed)
4 | PS.003D04 | Rapid Peer Review of AMAALA Existing Design of Yachting and Marina Facilities | Applied Technology and Management Inc (Dubai BR) | Consultant | 93750 | 0 | 93750 | Blake Lombard | N/A | - | Closed | FAS Signed (Closed)
5 | PS.003D05 | Geotechnical Consultancy Services (Yacht Club) - Peer Review | LANGAN International UK, LTD | Consultant | 170469.9 | 0 | 170469.9 | Blake Lombard | N/A | - | Closed | FAS Signed (Closed)
6 | PS.003F01 | Third Party Authority for Multidisciplinary Review & Certification Endorsement (Call off Order No: 004) | Zuhair Fayez Partnership Consultants (ZFP) | Consultant | 106231.5 | 0 | 106231.5 | Blake Lombard | N/A | - | Closed | FAS Signed (Closed)
7 | PS.003D06 | Permit Fees | Ministry of Municipality and Rural Affairs | Direct Actuals | 45677.6 | 0 | 45677.6 | Mike H | TBC | - | Not Required | No FAS Required (PO)
8 | PS.003F04 | Third-Party Authority for Fire and Life Safety Review & Certification Endorsement (Call off Order No: 007) | Jensen Hughes Saudi Arabia, LLC | Consultant | 70591.9 | 0 | 70591.9 | Abdulrahman | N/A | - | Closed | FAS Signed (Closed)
9 | PS.003F07 | Statutory Compliance Consultancy Services (Call Off Order No: 006) -AMAALA Yacht Club | Euro Consult For Engineering Consultancy | Consultant | 182184.38 | -53507 | 128677.38 | Abdulrahman | 2026-07-07 | - | Closed | FAS Signed (Closed) - With HQ action
10 | PS.003F08 | Independent Commissioning Agent Services (ICA) (Call off Order No: 007) - AMAALA Yacht Club | CML International Saudi LLC | Consultant | 3926890.54 | 101675.08 | 4028565.62 | Jose Chavenia | 2026-08-30 | -35 | Open | Works Ongoing
11 | PS.003F09 | Statutory Compliance Consultancy Services (Call Off Order No: 027) | Euro Consult For Engineering Consultancy | Consultant | 54000 | 0 | 54000 | Abdulrahman | N/A | - | Closed | FAS Signed (Closed)
12 | PS.003F10 | Third-Party Authority for Fire and Life Safety Review & Certification Endorsement (Call off Order No: 031) | Jensen Hughes Saudi Arabia, LLC | Consultant | 14303.2 | 0 | 14303.2 | Abdulrahman | N/A | - | Closed | FAS Signed (Closed)
13 | PS.003F12 | LEED Performance Testing (BECx & IAQ) (Call off Order No: 024) | GST Building Energy Efficiency Services | Consultant | 133000 | 0 | 133000 | Abdulrahman | 2026-10-30 | 26 | Open | Works Ongoing
14 | MS.003F02 | Construction Supervision Services - AMAALA Yacht Club (Call off Order No: 003) | Saudi Consolidated Engineering Company - Khatib & Alami | Consultant | 14131907 | -49207 | 14082700 | Jose Chavenia | 2026-10-30 | 26 | Open | Works Ongoing
15 | CN.003C13 | Triple Bay Wide Ground Improvement | Soil Improvement Contracting | Contractor | 2799717 | -500000 | 2299717 | Azam Shaikh | N/A | - | Closed | FAS Signed (Closed)
16 | CN.003C14 | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting | Contractor | 16458381.51 | 0 | 16458381.51 | Blake Lombard | N/A | - | Closed | FAS Signed (Closed)
17 | CN.003C20 | Sustainability Accreditation, third party technical reviews and verification of LEED-registered AMAALA Projects | Green Business Certification Inc | Direct Actuals | 22585.01 | 0 | 22585.01 | Abdulrahman | 2026-07-07 | - | Closed | No FAS requried
18 | CN.003C03 | Construction Contract - Site Enabling, Civil Works, Structural Concrete, Structural Steel, BOH Finishes, Building Envelope, MEP Including Tertiary Infrastructure & ICT/ELV | Saudi Arabian Baytur Construction Company | Contractor | 169939906.7 | 1049511.123 | 170989417.823 | Jose Chavenia | 2026-12-30 | 87 | Open | Works Ongoing - FAS highly unlikely - SAB non exisistant
19 | CN.003C21 | Sto Façade Mock-Up | Medtel - W.N | Contractor | 819298.55 | 0 | 819298.55 | Blake Lombard | N/A | - | Closed | FAS Signed (Closed)
20 | CN.003F03 | Supply and Installation of the Vertical Transportation System Works (Call Off Order No.001) | Elevator Systems Contracting Company (ESCCO) | Contractor | 2773546 | 549371.05 | 3322917.05 | Blake Lombard | 2026-10-30 | 26 | Open | Works Ongoing and back charges
21 | CN.003C08 | Kitchen & Laundry Works | Abdulaziz Al Raqtan and Partners Company for Trading and Industry Company | Contractor | 4705352 | 1365246.45 | 6070598.45 | Blake Lombard | 2026-08-30 | -35 | Open | Works Ongoing - F&B changes
22 | CN.003C09 | Fit-out works for Amaala Yacht Club | DEPA Saudi Arabia for Contracting and Interior Decoration Co. Ltd | Contractor | 80210582.25 | 11912318.04 | 92122900.29 | Jose Chavenia | 2027-01-30 | 118 | Open | Works Ongoing - Provision allowed for EOT's
23 | CN.003C27 | Aluminium & Glazing Works for the AMAALA Yacht Club | Aluminium Technology Auxiliary Industries (Alutec) WLL | Contractor | 30474501.58 | 378513 | 30853014.58 | Blake Lombard | 2026-09-30 | -4 | Open | Works Ongoing + Provision for EOT's
24 | CN.003C31 | Provision of construction manpower | MAS Engineering & Construction Company LTD | Contractor | 22360118 | 160876.21 | 22520994.21 | Fayez Aldosari | 2026-10-30 | 26 | Open | Works Ongoing further extension provided.
25 | CN.003C32 | Ampitheatre Concrete Works | MAS Engineering & Construction Company LTD | Contractor | 1284550.35 | -9520 | 1275030.35 | Fayez Aldosari | 2026-07-15 | - | Closed | FAS under WF Approval
26 | CN.003C34 | Construction Manpower Services | Alfanar Company | Contractor | 94625593.23 | 914738.46 | 95540331.69 | Fayez Aldosari | 2026-10-30 | 26 | Open | Works Ongoing
27 | CN.003C33 | Stainless Steel Reflecting Ceiling Works | Armetal Metal Industries Co. Ltd | Contractor | 7197028.55 | 0 | 7197028.55 | Fayez Aldosari | 2026-07-30 | -66 | Open | Works Ongoing
28 | CN.003C36 | OCIP Insurance Premium (P0123­CAR­TCRO­00076041/E16) | Al Rajhi Company For Cooperative Insurance | Contractor | 89047.06 | 0 | 89047.06 | TBC | N/A | - | Closed | No FAS Required (PO)
29 | CN.003C35 | Amaala Triple Bay – Marina Hotel 3 - Building Envelope GRC Works Package_CONTRACT CANCELLED_CONTRACT VALUE AED 7,640,027.22 (SAR 7,850,127.97) | Abu Dhabi Precast LLC | Contractor | 0 | 0 | 0 | Blake Lombard | TBC | - | Closed | Contract Cancelled
30 | CN.003C37 | Scaffolding Services | Hassan Allam Construction Saudi Limited | Contractor | 3096124.9 | 0 | 3096124.9 | Fayez Aldosari | 2026-03-30 | - | Closed | FAS Signed (Closed)
31 | CN.003C314 | RJT- OCIP Insurance Premium - Declaration 11 | RJT- OCIP Insurance Premium - Declaration 11 | Contractor | 15076.28 | 0 | 15076.28 | TBC | N/A | - | Closed | No FAS Required (Direct Payment)
32 | CN.003F13 | Deep Cleaning Services (Call off Order No: 005) | Tabuk Investment and Tourism Company (Enviro Facility Management) | Contractor | 799625.31 | 0 | 799625.31 | Jose Chavenia | 2026-07-30 | -66 | Open | Works Ongoing
33 | FFEOSE.003F06 | FF&E Procurement Services | Areen Design Limited | Consultant | 1959244.88 | 0 | 1959244.88 | Malik / Hazem Ali | 2026-09-30 | -4 | Open | Works ongoing
34 | FFEOSE.003F11 | Supply and Delivery Of Buggies | Extraordinary Cart | Contractor | 397876 | 0 | 397876 | Fayez Aldosari | N/A | - | Not Required | No FAS Required (PO)
35 | FFEOSE.003D09 | Supply, Installation Of Oracle Hospitality Simphony Cloud POS Solutions for Yacht Club | SaudiCo Electronic Systems | Consultant | 353487.06 | 0 | 353487.06 | Fayez Aldosari | N/A | - | Not Required | No FAS Required (PO)
36 | FFEOSE.003D07 | Procurement, Inventory, & Receipt Management System for Yacht Club | Birchstreet Systems, LLC | Consultant | 115998.98 | 0 | 115998.98 | Fayez Aldosari | N/A | - | Not Required | No FAS Required (PO)
37 | FFEOSE.003D10 | Providing HPE Servers | Al Falak Electronic Equipment & Supplies Co | Consultant | 16655 | 0 | 16655 | Fayez Aldosari | N/A | - | Not Required | No FAS Required (PO)
38 | CN.003C328 | Al Futtaim Pioneer Elevators - Al Futtaim Pioneer | Al Futtaim Pioneer Elevators - Al Futtaim Pioneer | Contractor | 691955 | 0 | 691955 | Fayez Aldosari | 2026-09-30 | -4 | Open | Al Futtaim Pioneer Elevators – ongoing.
39 | FFEOSE.003F02 | Loose FF&E Items (FOH) | Loose FF&E Items (FOH) | Consultant | 22998647.56 | 0 | 22998647.56 | Malik / Hazem Ali | 2026-09-30 | -4 | Open | Procurement team to close Final Account
40 | FFEOSE.003F02 | OS&E Items | OS&E Items | Consultant | 14586000 | 429156 | 15015156 | Malik / Hazem Ali | 2026-09-30 | -4 | Open | Procurement team to close Final Account
41 | FFEOSE.003D15 | Supply,Setup and Implementation Of Infor Financial Software (SunSystems) | Infor (Saudi Arabia Limited) | Consultant | 34719 | 0 | 34719 | Fayez Aldosari | N/A | - | Not Required | No final account required
42 | FFEOSE.003D11 | Sevenrooms Inc | Sevenrooms Inc |  | 32751.56 | 0 | 32751.56 | Fayez Aldosari | N/A | - | Not Required | No final account required
43 | FFEOSE.003D12 | Infor Co | Infor Saudi Arabia Limited |  | 58307.19 | 0 | 58307.19 | Fayez Aldosari | N/A | - | Not Required | No final account required
44 | FFEOSE.003D14 | Reachware Integration | TRA - Zatca Integration with Reachware |  | 57135 | 0 | 57135 | Fayez Aldosari | N/A | - | Not Required | No final account required
45 | FFEOSE.003D16 | PeopleVine Implementation | PeopleVine Implementation |  | 336187.5 | 0 | 336187.5 | Fayez Aldosari | N/A | - | Not Required | No final account required
|  | TOTAL – AMAALA YACHT CLUB FINAL ACCOUNTS |  |  | 518886920.49 | 16249171.413 | 535136091.903
INTERPROJECT / BUDGET TRANSFER PACKAGES — NO AYC FINAL ACCOUNT REQUIRED
Input received from other contractors; budget to be transferred back to the originating package. No final account to be completed under AYC.
1 | CN.009C05 | KTH - MEP Works Package - 2240072 - KORTEK | KTH - MEP Works Package - 2240072 - KORTEK | Contractor | 0 | 950913.7 | 950913.7 | Ved Kumar | TBC | - | No FA Req. | Works done under MH3
2 | CN.012C33 | ALC - Alcatop Package - Fourseasons | ALC - Alcatop Package - Fourseasons - Alcatop |  | 0 | 150000 | 150000 | Christopher Lewis | TBC | - | No FA Req. | Alcatop Package (Four Seasons) – ongoing.
|  | SUB-TOTAL – BUDGET TRANSFER (NO FA) |  |  | 0 | 1100913.7 | 1100913.7
DIRECT PAYMENTS ON BEHALF OF SAB (CN.003C03) — NO FINAL ACCOUNT REQUIRED
Payments made by the Client on behalf of SAB; recovered through the SAB main contract account. No separate final account required.
1 | CN.003C03 | Direct Payments on behalf of SAB (Jan–Aug) — consolidated | Various subcontractors / suppliers (paid on behalf of SAB) | Direct Actual | 42594259.73 | 0 | 42594259.73 | – | N/A | - | No FA Req. | Consolidated total of 196 direct-payment lines (Jan–Aug), paid on behalf of SAB. Recovered through SAB; no separate final account required.
|  | SUB-TOTAL – DIRECT PAYMENTS (NO FA) |  |  | 42594259.73 | 0 | 42594259.73
Note: Items below the line require no AYC final account, but form part of total asset cost and are added back below to reconcile to Schedule B.
|  | Sub-total – AYC Final Accounts (real packages, excl. below-the-line & Budget Hold) |  |  | 518886920.49 | 16249171.413 | 535136091.903
|  | Add: Interproject / Budget Transfer packages (no FA) |  |  | 0 | 1100913.7 | 1100913.7
|  | Add: Direct Payments on behalf of SAB (no FA) |  |  | 42594259.73 | 0 | 42594259.73
|  | Add: Remaining Budget Hold (PS+MS+CM+CN) — per Schedule B |  |  | 21581561.09 | -21581561.09 | 0 |  |  |  |  | Unallocated budget hold retained in Schedule B grand total (incl. budget hold).
|  | GRAND TOTAL — ties to Schedule B Grand Total Asset Costs (incl. Budget Hold) |  |  | 583062741.31 | -4231475.977 | 578831265.333
Formulas:
Days Remaining to Close = IF([Status]="Closed","-",[TOTAL PACKAGES]-TODAY())

## Schedule A
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01 | [18 empty] | X-CHECK
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
|  |  |  | COMMITTED |  |  |  | UNCOMMITTED | [7 empty] | Period Movement |  | From LEVEL 2 | MUST BE ZERO
|  | A | B | C | D.1 |  | E = (C+D) | F | G | H | I | J = (Sum E to I) | (J-C) | K | L = (J- K) | M | N = (J-M)
CODE | NAME | APPROVED BASELINE BUDGET | BUDGET TRANSFERS | AWARDED CONTRACTS / BUDGET | DETERMINED VARIATION ORDERS (DVO) | COMMITTED PVO (CPVO) | COMMITTED COSTS | POTENTIAL VARIATION ORDERS (PVO) | REQUEST FOR CHANGE (RFC) | EARLY WARNING | CLAIMS | ANTICIPATED FINAL ACCOUNT | VARIANCE TO LATEST BUDGET | CERTIFIED TO DATE | WORKS TO COMPLETE | SEPTEMBER 2026 | VARIANCE | #REF! | #REF! |  | 1066798 | -4301371.277
|  | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | -215885.19
PS | PROFESSIONAL SERVICES | 17514722.36 | 3029172.62 | 20543894.98 | 4664935.12 | 0 | 25208830.1 | 101675.08 | 0 | 0 | 0 | 25310505.18 | 4766610.2 | 24735312.58 | 575192.6 | 25310505.18 | 0 | 120.4% | 20543894.98 | 0
MS | MANAGEMENT SUPERVISION | 0 | 13296114.38 | 13296114.38 | 1071977 | 0 | 14368091.38 | -53507 | -49207 | 0 | 0 | 14265377.38 | 969263 | 14265377.64 | -0.26 | 14265377.38 | 0 | 107.3% |  | 0
0
CM | COMMERCIAL MANAGEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  | 0
0
CN | CONSTRUCTION WORKS | 21785723 | 457671817.54 | 479457540.54 | 231444.36 | 1993436.11 | 481682421.01 | -18178391.66 | 3205613.5 | 32891648.893 | 0 | 499601291.743 | 20143751.203 | 457894708.1315 | 41706583.6115 | 499817176.933 | -215885.19 | 95.5% | 215885.19 | 215885.19
| TOTAL (PS+MS+CM+CN) | 39300445.36 | 473997104.54 | 513297549.9 | 5968356.48 | 1993436.11 | 521259342.49 | -18130223.58 | 3156406.5 | 32891648.893 | 0 | 539177174.303 | 25879624.403 | 496895398.3515 | 42281775.9515 | 539393059.493 | -215885.19
CC | CLIENT COST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
FF&E & OS&E | FF&E AND OS&E | 0 | 40154868.28 | 40154868.28 | 851779 | 0 | 41006647.28 | 0 | 429156 | 0 | 0 | 41435803.28 | 1280935 | 25518391.665 | 15917411.615 | 41435803.28 | 0 | 63.55% | -215885.19
| TOTAL (CC+FF&E & OS&E) | 0 | 40154868.28 | 40154868.28 | 851779 | 0 | 41006647.28 | 0 | 429156 | 0 | 0 | 41435803.28 | 1280935 | 25518391.665 | 15917411.615 | 41435803.28 | 0 |  | -215885.19
#DIV/0!
1TB01031.01 | GRAND TOTAL ASSET COSTS (EXCL BUDGET HOLD) | 39300445.36 | 514151972.82 | 553452418.18 | 6820135.48 | 1993436.11 | 562265989.77 | -18130223.58 | 3585562.5 | 32891648.893 | 0 | 580612977.583 | 27160559.403 | 522413790.0165 | 58199187.5665 | 580828862.773 | -215885.19 | 215885.19 |  | -3234573.277 | 9826662 | -13061235.277
98 | BUDGET HOLD | 277046039.89 | -246650907.21 | 30395132.68 | 6830634.64 | -15644206.23 | 21581561.09 | 18178391.66 | -3585562.5 | -32891648.893 | 0 | 0 | -30395132.68 | 0 | 0 | 0 | 0 | 0% | -3234573.277
1TB01031.01 | GRAND TOTAL ASSET COSTS (INCL BUDGET HOLD) | 316346485.25 | 267501065.61 | 583847550.86 | 13650770.12 | -13650770.12 | 583847550.86 | 48168.08 | 0 | 0 | 0 | 580612977.583 | -3234573.277 | 522413790.0165 | 58199187.5665 | 580828862.773 | -215885.19 | -5.7742e-08 | 7193270 | 3018688.087 | 29277634
[18 empty] | -3234573.277 |  | -215885.19
NOTES (if any) | [17 empty] | 7193270 | -3018688.087 | -3234573.277
[18 empty] | -10427843.277 | -3234573.277 | 794838 | 59832671.43
1 - Note_The original budget for the AMAALA Yacht Club Project was SAR 316,346,485. In July 2023 an additional budget of SAR 139,440,201 was allocated, giving a revised budget of SAR 455,786,687. In January 2025, March 2025 and June 2025 further allocations of SAR 26,781,117, SAR 40,000,000 and SAR 62,089,112 respectively were received, bringing the approved budget to SAR 584,656,916. Inter-project transfers to Marina Hotel 3 of SAR 164,010 (Fibrex) and SAR 645,355 (IMAR façade installer), both BTRs under process, bring the current budget to SAR 583,847,551. | [17 empty] | #REF! | #REF! | 7193270
2 – Note_The anticipated final account for the Project is SAR 580,828,863, which is SAR 3,018,688 (0.52%) lower than the current budget of SAR 583,847,551. This is a reduction of SAR 862,445 against the previous month's anticipated final account of SAR 581,691,308. | [17 empty] | -3234573.277 | -215885.19 | -3234573.277
[18 empty] | 7193270 | #REF! | 0
927845
70854622
PREPARED BY: |  |  |  | REVIEWED BY: | [6 empty] | APPROVED BY: | [6 empty] | 18429499
[17 empty] | -3234573.277 | -21664072.277
Associate Commercial Director - Blake Lombard |  |  |  | Senior Commercial Director: - Michael Hansen | [6 empty] | Executive Commercial Director: - Shane Fairfield | [5 empty] | 89611679.78 |  | #REF!
3634769.5
| From Level 2 | #REF! |  | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| X-Check (MUST be ZERO) | #REF! |  | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
36477211.393
28761589.23
[7 empty] | -20274456 |  |  | -527572793.777
8487133.23
[7 empty] | 17975993.27 |  |  | 580612977.583 |  |  | 104270066
[7 empty] | -13059930 | [5 empty] | 101035492.723
[7 empty] | 4916063.27 | [5 empty] | 101035492.723
1198399.55
14601596.05
37902585
3 - Note_Additional budget has been allocated to AYC - SAR 104,270,066. Therefore the Actual Budget over run related to the AYC totals SAR 156,819,925 OR SAR 142,172,651 Utilizing all remianing budget
93913586.15
38306169
132219755.15
93913586.15
38306169
132219755.15
2 – Note_The anticipated final account value for the Project is SAR 593,900,457, which is higher than the approved budget of SAR 584,656,916 in ACC by SAR 9,243,541. There's a SAR 2,226,314 movement in the budget compared to the previous month's Anticipated Forecast Final Account of SAR 591,674,143.

## Schedule B
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
MUST BE ZERO
| -456925.8 |  |  |  |  | COMMITTED |  |  |  | UNCOMMITTED | [7 empty] | Period Movement
| 35325075.93 |  |  | A | B | C | D.1 | D.2 | E = (C+D) | F | G | H | I | J = (Sum E to I) | (J-C) | K | L = (J- K) | M | N = (J-M)
CODE | Package | NAME | CONTRACTOR / SUBCONTRACTOR | APPROVED BASELINE BUDGET | BUDGET TRANSFERS | AWARDED CONTRACTS / BUDGET | DETERMINED VARIATION ORDERS (DVO) | COMMITTED PVO (CPVO) | COMMITTED COSTS | POTENTIAL VARIATION ORDERS (PVO) | REQUEST FOR CHANGE (RFC) | EARLY WARNING | CLAIMS | ANTICIPATED FINAL ACCOUNT | VARIANCE TO LATEST BUDGET | CERTIFIED TO DATE | WORKS TO COMPLETE | SEPTEMBER 2026 | VARIANCE |  |  |  | COST REPORT NO 6 | MOVEMENT IN THE PERIOD | MATCHING INVOICE
|  |  |  | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR
PS |  | PROFESSIONAL SERVICES | [17 empty] | 0 | 0
[20 empty] | 0 | 0
PS.003D01 | DAE -Prf Fees | Dewan Architects & Engineers 2200445 |  | 5973808 |  | 5973808 | 3316718.1 |  | 9290526.1 | 0 | 0 | 0 | 0 | 9290526.1 | 3316718.1 | 9026746.1 | 263780 | 9290526.1 | 0 | -3316718.1 | 0 |  | #REF! | #REF! | #REF!
PS.003D02 | HKL (Design Comp Fees)-Prf Fees | HKS Architects Ltd - Design Competition Fees 2200010 |  | 555960.36 |  | 555960.36 | 0 |  | 555960.36 | 0 | 0 | 0 | 0 | 555960.36 | 0 | 555960 | 0.36 | 555960.36 | 0 | 0 | 0 |  | #REF! | #REF! | #REF!
PS.003D03 | HKL (Design Architect)-Prf Fees | HKS Architects Ltd - Design Architect Fees 2200375 |  | 10891204 |  | 10891204 | -89775 |  | 10801429 | 0 | 0 | 0 | 0 | 10801429 | -89775 | 10801428.46 | 0.54 | 10801429 | 0 | 89775 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
PS.003D04 | ATM-Prf Fees | Applied Technology and Management Inc (Dubai BR)s 2210167 |  | 93750 |  | 93750 | 0 |  | 93750 | 0 | 0 | 0 | 0 | 93750 | 0 | 93750 | 0 | 93750 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
PS.003D05 | LUI-Prf Fees | Langan International UK Limited 2230042 |  | 0 | 172368.42 | 172368.42 | -1898.52 |  | 170469.9 | 0 | 0 | 0 | 0 | 170469.9 | -1898.52 | 168421.05 | 2048.85 | 170469.9 | 0 | 1898.52 | 0
PS.003F01 | ZFP-Prf Fees | Zuhair Fayez and Partners 2230041 |  | 0 | 106231.5 | 106231.5 | 0 |  | 106231.5 | 0 | 0 | 0 | 0 | 106231.5 | 0 | 106231.5 | 0 | 106231.5 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
PS.003D06 | MOM - Building Permit Fee | Ministry of Municipality and Rural Affairs (Tabuk) |  | 0 | 45677.6 | 45677.6 | 0 |  | 45677.6 | 0 | 0 | 0 | 0 | 45677.6 | 0 | 45677.6 | 0 | 45677.6 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
PS.003F04 | Jensen Hughes-Prf Fees | Jensen Hughes Saudi Arabia Co 2230180 |  | 0 | 127291.9 | 127291.9 | -56700 |  | 70591.9 | 0 | 0 | 0 | 0 | 70591.9 | -56700 | 0 | 70591.9 | 70591.9 | 0 | 56700 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
PS.003F10 | Jensen Hughes-Prf Fees COO 30 | Jensen Hughes Saudi Arabia Co 2250184 |  | 0 | 38103.2 | 38103.2 | -23800 |  | 14303.2 | 0 | 0 | 0 | 0 | 14303.2 | -23800 | 0 | 14303.2 | 14303.2 | 0 | 23800 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
PS.003F08 | CML-Mgt Fees | CML (Independent Commissioning Agent) COO 7 |  | 0 | 2406500 | 2406500 | 1520390.54 |  | 3926890.54 | 101675.08 | 0 | 0 | 0 | 4028565.62 | 1622065.62 | 3873847.87 | 154717.75 | 4028565.62 | 0
PS.003F12 | GST-LEED Fees | GST - Sustainability Accreditation Services |  | 0 | 133000 | 133000 | 0 |  | 133000 | 0 | 0 | 0 | 0 | 133000 | 0 | 63250 | 69750 | 133000 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 | [7 empty] | 102
PS |  | SUB-TOTAL - PROFESSIONAL SERVICES |  | 17514722.36 | 3029172.62 | 20543894.98 | 4664935.12 | 0 | 25208830.1 | 101675.08 | 0 | 0 | 0 | 25310505.18 | 4766610.2 | 24735312.58 | 575192.6 | 25310505.18 | 0 | -4766610.2 | 0 |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0
MS |  | MANAGEMENT SUPERVISION | [17 empty] | 0 | 0
[20 empty] | 0 | 0
MS.003F02 | KAA-Mgt Fees | Khatib & Alami 2230031 |  |  | 13059930 | 13059930 | 1071977 |  | 14131907 | 0 | -49207 | 0 | 0 | 14082700 | 1022770 | 14082700 | 0 | 14082700 | 0 | -1022770 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
PS.003F07 | ECC-Mgt Fees | Euro Consult (COO 6) |  |  | 182184.38 | 182184.38 | 0 |  | 182184.38 | -53507 | 0 | 0 | 0 | 128677.38 | -53507 | 128677.64 | -0.26 | 128677.38 | 0 | 53507 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
PS.003F09 | ECC-Mgt Fees (Accom & Transpo) | Euro Consult (COO 27) |  |  | 54000 | 54000 | 0 |  | 54000 | 0 | 0 | 0 | 0 | 54000 | 0 | 54000 | 0 | 54000 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
|  | SUB TOTAL |  | 0 | 13296114.38 | 13296114.38 | 1071977 |  | 14368091.38 | -53507 | -49207 | 0 | 0 | 14265377.38 | 969263 | 14265377.64 | -0.26 | 14265377.38 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
|  | SUB TOTAL |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | [7 empty] | 102
MS |  | SUB-TOTAL - MANAGEMENT SUPERVISION |  | 0 | 13296114.38 | 13296114.38 | 1071977 | 0 | 14368091.38 | -53507 | -49207 | 0 | 0 | 14265377.38 | 969263 | 14265377.64 | -0.26 | 14265377.38 | 0 | -969263 | 0
CM |  | COMMERCIAL MANAGEMENT | [17 empty] | 0 | 0
[20 empty] | 0 | 0
[20 empty] | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
|  | SUB TOTAL |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
|  | SUB TOTAL |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 | [7 empty] | 102
CM |  | SUB-TOTAL - COMMERCIAL MANAGEMENT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN |  | CONSTRUCTION WORKS
CN - EW |  | EARLY WORKS
[20 empty] | 0 | 0 |  |  |  |  | LUMP SUM Value | CORRECTION DUE TO SPLIT | EARLY WARNING VALUE | Check | Check
CN.003C13 | SOI TB Ground Improvement Works | SOI TB Ground Improvement Works 2210224 |  | 2799717 |  | 2799717 | 0 |  | 2799717 | 0 | 0 | -500000 | 0 | 2299717 | -500000 | 1748735.938 | 550981.062 | 2299717 | 0 | 500000 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.003C13 | SOI TB Ground Improvement Works (PS) | SOI TB Ground Improvement Works 2210224 PROVISIONAL SUMS |  | 282972 |  | 282972 | 0 |  | 282972 | 0 | 0 | -282972 | 0 | 0 | -282972 | 0 | 0 | 0 | 0 | 282972 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.003C20 | GBC - Sustainability Accreditation | Green Business Certification Inc.2220038 |  | 4500 | 18594.49 | 23094.49 | -509.48 |  | 22585.01 | 0 | 0 | 0 | 0 | 22585.01 | -509.48 | 18000.1125 | 4584.8975 | 22585.01 | 0 | 509.48 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN - EW |  | SUB-TOTAL - EARLY WORKS |  | 3087189 | 18594.49 | 3105783.49 | -509.48 |  | 3105274.01 | 0 | 0 | -782972 | 0 | 2322302.01 | -783481.48 | 1766736.0505 | 555565.9595 | 2322302.01 | 0 | 783481.48 | 0
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN - MW |  | MAIN CONSTRUCTION WORKS
|  | Awarded Contracts | [17 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.003C13 | NSCC - Piling | NSCC - Triple Bay Piling (AYC only) 2220032 |  | 18698534 | 0 | 18698534 | -2240152.49 |  | 16458381.51 | 0 | 0 | 0 | 0 | 16458381.51 | -2240152.49 | 16458381.54 | -0.03 | 16458381.51 | 0 | 2240152.49 | 0 |  |  |  |  | #REF! | #REF! | 0 | #REF! | 0
0
CN.003C03 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Structural Concrete, Wet Trades, BOH Fit out, Pools and Water Features, Structural Steel, Glazing, Glass Balustrades, Aluminum Soffits, SFS and GRC, Render Façade, Roof Waterproofing, MEP, ICT/ELV - (SAB) 2230023 |  | 0 | 260955414.4 | 260955414.4 | -91015507.7 |  | 169939906.7 | -19683045.7 | -1065566.44 | 21798123.263 | 0 | 170989417.823 | -89965996.577 | 170592084.657 | 397333.166 | 172401764.263 | -1412346.44 | 89965996.577 | 0 |  | 189323001.68 | 19383094.98 |  | #REF! | #REF! | -1065566.44 | #REF! | 0
|  | Direct Payment to SAB's Subcontractors and Suppliers |  |  |  |  | 0
Direct Payment - Prelims | Prelims - Mohammad Alharbi Medical Company | Prelims - Mohammad Alharbi Medical Company |  | 0 | 134895.4 | 134895.4 | 0 |  | 134895.4 | 0 | 0 | 0 | 0 | 134895.4 | 0 | 134895.4 | 0 | 134895.4 | 0 | 0 | 0 |  | 189323001.68 | 189188106.28 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Al Anan Travels and Tours | Prelims - Al Anan Travels and Tours |  | 0 | 103373.74 | 103373.74 | 0 |  | 103373.74 | 0 | 0 | 0 | 0 | 103373.74 | 0 | 103373.74 | 0 | 103373.74 | 0 | 0 | 0 |  | 189323001.68 | 189219627.94 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Al drees Petroleum | Prelims - Al drees Petroleum |  | 0 | 34782.61 | 34782.61 | 0 |  | 34782.61 | 0 | 0 | 0 | 0 | 34782.61 | 0 | 34782.61 | 0 | 34782.61 | 0 | 0 | 0 |  | 189323001.68 | 189288219.07 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Salim Hamed Cleaning | Prelims - Salim Hamed Cleaning |  | 0 | 31306.1 | 31306.1 | 0 |  | 31306.1 | 0 | 0 | 0 | 0 | 31306.1 | 0 | 31306.1 | 0 | 31306.1 | 0 | 0 | 0 |  | 189323001.68 | 189291695.58 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Clean Coast for Contracting | Prelims - Clean Coast for Contracting |  | 0 | 252583.81 | 252583.81 | 0 |  | 252583.81 | 0 | 0 | 0 | 0 | 252583.81 | 0 | 252583.81 | 0 | 252583.81 | 0 | 0 | 0 |  | 189323001.68 | 189070417.87 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Sami General Contracting | Prelims - Sami General Contracting |  | 0 | 273350 | 273350 | 0 |  | 273350 | 0 | 0 | 0 | 0 | 273350 | 0 | 273350 | 0 | 273350 | 0 | 0 | 0 |  | 189323001.68 | 189049651.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Eastern Horizons Foundation Transportation Comp | Prelims - Eastern Horizons Foundation Transportation Comp |  | 0 | 14349 | 14349 | 0 |  | 14349 | 0 | 0 | 0 | 0 | 14349 | 0 | 14349 | 0 | 14349 | 0 | 0 | 0 |  | 189323001.68 | 189308652.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Jak Generation Cont Co LLC | Prelims - Jak Generation Cont Co LLC |  | 0 | 369751.45 | 369751.45 | 0 |  | 369751.45 | 0 | 0 | 0 | 0 | 369751.45 | 0 | 369751.45 | 0 | 369751.45 | 0 | 0 | 0 |  | 189323001.68 | 188953250.23 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Intelligent General Cont Co Equipment | Prelims - Intelligent General Cont Co Equipment |  | 0 | 758870.17 | 758870.17 | 0 |  | 758870.17 | 0 | 0 | 0 | 0 | 758870.17 | 0 | 758870.17 | 0 | 758870.17 | 0 | 0 | 0 |  | 189323001.68 | 188564131.51 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Al Rai Modern Water Factory | Prelims - Al Rai Modern Water Factory |  | 0 | 318320.5 | 318320.5 | 0 |  | 318320.5 | 0 | 0 | 0 | 0 | 318320.5 | 0 | 318320.5 | 0 | 318320.5 | 0 | 0 | 0 |  | 189323001.68 | 189004681.18 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - NEXTWARE INTERNATIONAL SUPPLY | Prelims - NEXTWARE INTERNATIONAL SUPPLY |  | 0 | 1845 | 1845 | 0 |  | 1845 | 0 | 0 | 0 | 0 | 1845 | 0 | 1845 | 0 | 1845 | 0 | 0 | 0 |  | 189323001.68 | 189321156.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Virtual Projects DMCC | Prelims - Virtual Projects DMCC |  | 0 | 51948.13 | 51948.13 | 0 |  | 51948.13 | 0 | 0 | 0 | 0 | 51948.13 | 0 | 51948.13 | 0 | 51948.13 | 0 | 0 | 0 |  | 189323001.68 | 189271053.55 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Raddad Al adinah | Prelims - Raddad Al adinah |  | 0 | 142131.61 | 142131.61 | 0 |  | 142131.61 | 0 | 0 | 0 | 0 | 142131.61 | 0 | 142131.61 | 0 | 142131.61 | 0 | 0 | 0 |  | 189323001.68 | 189180870.07 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Ahmed Bin Salem Bin Dagher | Prelims - Ahmed Bin Salem Bin Dagher |  | 0 | 348199.81 | 348199.81 | 0 |  | 348199.81 | 0 | 0 | 0 | 0 | 348199.81 | 0 | 348199.81 | 0 | 348199.81 | 0 | 0 | 0 |  | 189323001.68 | 188974801.87 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Bahamdoon Trading | Prelims - Bahamdoon Trading |  | 0 | 1535 | 1535 | 0 |  | 1535 | 0 | 0 | 0 | 0 | 1535 | 0 | 1535 | 0 | 1535 | 0
Direct Payment - Prelims | Prelims - Lumi Rentals | Prelims - Lumi Rentals |  | 0 | 6142.43 | 6142.43 | 0 |  | 6142.43 | 0 | 0 | 0 | 0 | 6142.43 | 0 | 6142.43 | 0 | 6142.43 | 0
Direct Payment - Prelims | Prelims - Filter Expert Trading | Prelims - Filter Expert Trading |  | 0 | 8565 | 8565 | 0 |  | 8565 | 0 | 0 | 0 | 0 | 8565 | 0 | 8565 | 0 | 8565 | 0
Direct Payment - Prelims | Prelims - Abu Nayyan | Prelims - Abu Nayyan |  | 0 | 17800 | 17800 | 0 |  | 17800 | 0 | 0 | 0 | 0 | 17800 | 0 | 17800 | 0 | 17800 | 0
Direct Payment - Prelims | Prelims - Ihsan Muhammed Thakir Idress Trading | Prelims - Ihsan Muhammed Thakir Idress Trading |  | 0 | 99000 | 99000 | 0 |  | 99000 | 0 | 0 | 0 | 0 | 99000 | 0 | 99000 | 0 | 99000 | 0
Direct Payment - Prelims | Prelims - Ramzi Abbas Mohd. Sayed Est. | Prelims - Ramzi Abbas Mohd. Sayed Est. |  | 0 | 48767 | 48767 | 0 |  | 48767 | 0 | 0 | 0 | 0 | 48767 | 0 | 48767 | 0 | 48767 | 0
Direct Payment - Prelims | Prelims - Al Rayi Water | Prelims - Al Rayi Water |  | 0 | 46655 | 46655 | 0 |  | 46655 | 0 | 0 | 0 | 0 | 46655 | 0 | 46655 | 0 | 46655 | 0
Direct Payment - Prelims | Prelims - GLSAN Contracting Company | Prelims - GLSAN Contracting Company |  | 0 | 8291108.14 | 8291108.14 | 0 |  | 8291108.14 | 0 | 0 | 0 | 0 | 8291108.14 | 0 | 8291108.14 | 0 | 8291108.14 | 0
Direct Payment - Prelims | Prelims - GLSAN Contracting Company (Red Sea) | Prelims - GLSAN Contracting Company (Red Sea) |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Direct Payment - Prelims | Prelims - Masa Equipment Est | Prelims - Masa Equipment Est |  | 0 | 287000 | 287000 | 0 |  | 287000 | 0 | 0 | 0 | 0 | 287000 | 0 | 287000 | 0 | 287000 | 0 | 0 | 0 |  | 189323001.68 | 189036001.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Prelims | Prelims - Al Tala'a International Transportation Co | Prelims - Al Tala'a International Transportation Co |  | 0 | 6608.7 | 6608.7 | 0 |  | 6608.7 | 0 | 0 | 0 | 0 | 6608.7 | 0 | 6608.7 | 0 | 6608.7 | 0
Direct Payment - Prelims | Prelims - Saudi Brokers | Prelims - Saudi Brokers |  | 0 | 59606.12 | 59606.12 | 0 |  | 59606.12 | 0 | 0 | 0 | 0 | 59606.12 | 0 | 59606.12 | 0 | 59606.12 | 0
Direct Payment - Prelims | Prelims - Aknan Al Bena | Prelims - Aknan Al Bena |  | 0 | 75000 | 75000 | 0 |  | 75000 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 75000 | 0
Direct Payment - Prelims | Prelims - Emaar Suhali | Prelims - Emaar Suhali |  | 0 | 90000 | 90000 | 0 |  | 90000 | 0 | 0 | 0 | 0 | 90000 | 0 | 90000 | 0 | 90000 | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0
Direct Payment - Works | Direct Works - Madar Building material Co | Direct Works - Madar Building material Co |  | 0 | 14320 | 14320 | 0 |  | 14320 | 0 | 0 | 0 | 0 | 14320 | 0 | 14320 | 0 | 14320 | 0 | 0 | 0 |  | 189323001.68 | 189308681.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Juffali Technical Equipment Company | Direct Works - Juffali Technical Equipment Company |  | 0 | 12113.6 | 12113.6 | 0 |  | 12113.6 | 0 | 0 | 0 | 0 | 12113.6 | 0 | 12113.6 | 0 | 12113.6 | 0 | 0 | 0 |  | 189323001.68 | 189310888.08 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - USG Middle East Ltd. Co | Direct Works - USG Middle East Ltd. Co |  | 0 | 39954.82 | 39954.82 | 0 |  | 39954.82 | 0 | 0 | 0 | 0 | 39954.82 | 0 | 39954.82 | 0 | 39954.82 | 0 | 0 | 0 |  | 189323001.68 | 189283046.86 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Abu Dhabi Precast | Direct Works - Abu Dhabi Precast |  | 0 | 3619680.62 | 3619680.62 | 0 |  | 3619680.62 | 0 | 0 | 0 | 0 | 3619680.62 | 0 | 3619680.62 | 0 | 3619680.62 | 0 | 0 | 0 |  | 189323001.68 | 185703321.06 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - SAMIF | Direct Works - SAMIF |  | 0 | 6340696.9 | 6340696.9 | 0 |  | 6340696.9 | 0 | 0 | 0 | 0 | 6340696.9 | 0 | 6340696.9 | 0 | 6340696.9 | 0 | 0 | 0 |  | 189323001.68 | 182982304.78 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - SAUDI MANPOWER SOLUTIONS CO | Direct Works - SAUDI MANPOWER SOLUTIONS CO |  | 0 | 377764.03 | 377764.03 | 0 |  | 377764.03 | 0 | 0 | 0 | 0 | 377764.03 | 0 | 377764.03 | 0 | 377764.03 | 0 | 0 | 0 |  | 189323001.68 | 188945237.65 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Fosam Company LTD | Direct Works - Fosam Company LTD |  | 0 | 40570 | 40570 | 0 |  | 40570 | 0 | 0 | 0 | 0 | 40570 | 0 | 40570 | 0 | 40570 | 0 | 0 | 0 |  | 189323001.68 | 189282431.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Glow Arabia Trading | Direct Works - Glow Arabia Trading |  | 0 | 49460.5 | 49460.5 | 0 |  | 49460.5 | 0 | 0 | 0 | 0 | 49460.5 | 0 | 49460.5 | 0 | 49460.5 | 0 | 0 | 0 |  | 189323001.68 | 189273541.18 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - BROOQ ALAMAAN TRAD COMPANY | Direct Works - BROOQ ALAMAAN TRAD COMPANY |  | 0 | 130305.72 | 130305.72 | 0 |  | 130305.72 | 0 | 0 | 0 | 0 | 130305.72 | 0 | 130305.72 | 0 | 130305.72 | 0 | 0 | 0 |  | 189323001.68 | 189192695.96 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Abeer Munawer Al Shamari | Direct Works - Abeer Munawer Al Shamari |  | 0 | 1059365.93 | 1059365.93 | 0 |  | 1059365.93 | 0 | 0 | 0 | 0 | 1059365.93 | 0 | 1059365.93 | 0 | 1059365.93 | 0 | 0 | 0 |  | 189323001.68 | 188263635.75 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Yaz Development Contracting | Direct Works - Yaz Development Contracting |  | 0 | 1036210 | 1036210 | 0 |  | 1036210 | 0 | 0 | 0 | 0 | 1036210 | 0 | 1036210 | 0 | 1036210 | 0 | 0 | 0 |  | 189323001.68 | 188286791.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Naffco | Direct Works - Naffco |  | 0 | 936325.93 | 936325.93 | 0 |  | 936325.93 | 0 | 0 | 0 | 0 | 936325.93 | 0 | 936325.93 | 0 | 936325.93 | 0 | 0 | 0 |  | 189323001.68 | 188386675.75 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - GESR Alarab | Direct Works - GESR Alarab |  | 0 | 2444255.5 | 2444255.5 | 0 |  | 2444255.5 | 0 | 0 | 0 | 0 | 2444255.5 | 0 | 2444255.5 | 0 | 2444255.5 | 0 | 0 | 0 |  | 189323001.68 | 186878746.18 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Jameel Mohamed Hussain Alqatafa Cont Est | Direct Works - Jameel Mohamed Hussain Alqatafa Cont Est |  | 0 | 127257.78 | 127257.78 | 0 |  | 127257.78 | 0 | 0 | 0 | 0 | 127257.78 | 0 | 127257.78 | 0 | 127257.78 | 0 | 0 | 0 |  | 189323001.68 | 189195743.9 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - MEDTEL | Direct Works - MEDTEL |  | 0 | 5913785.58 | 5913785.58 | 0 |  | 5913785.58 | 0 | 0 | 0 | 0 | 5913785.58 | 0 | 5913785.58 | 0 | 5913785.58 | 0 | 0 | 0 |  | 189323001.68 | 183409216.1 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Noreom | Direct Works - Noreom |  | 0 | 100641.6 | 100641.6 | 0 |  | 100641.6 | 0 | 0 | 0 | 0 | 100641.6 | 0 | 100641.6 | 0 | 100641.6 | 0 | 0 | 0 |  | 189323001.68 | 189222360.08 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Isam Kabani & Partners | Direct Works - Isam Kabani & Partners |  | 0 | 2267626.88 | 2267626.88 | 0 |  | 2267626.88 | 0 | 0 | 0 | 0 | 2267626.88 | 0 | 2267626.88 | 0 | 2267626.88 | 0 | 0 | 0 |  | 189323001.68 | 187055374.8 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - ARABIAN TESTING EVOLUTION COMPANY | Direct Works - ARABIAN TESTING EVOLUTION COMPANY |  | 0 | 425440 | 425440 | 0 |  | 425440 | 0 | 0 | 0 | 0 | 425440 | 0 | 425440 | 0 | 425440 | 0 | 0 | 0 |  | 189323001.68 | 188897561.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Wood Expert | Direct Works - Wood Expert |  | 0 | 22475 | 22475 | 0 |  | 22475 | 0 | 0 | 0 | 0 | 22475 | 0 | 22475 | 0 | 22475 | 0 | 0 | 0 |  | 189323001.68 | 189300526.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Energy & Building Master | Direct Works - Energy & Building Master |  | 0 | 117720 | 117720 | 0 |  | 117720 | 0 | 0 | 0 | 0 | 117720 | 0 | 117720 | 0 | 117720 | 0 | 0 | 0 |  | 189323001.68 | 189205281.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - ACES | Direct Works - ACES |  | 0 | 4401.3 | 4401.3 | 0 |  | 4401.3 | 0 | 0 | 0 | 0 | 4401.3 | 0 | 4401.3 | 0 | 4401.3 | 0 | 0 | 0 |  | 189323001.68 | 189318600.38 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - International Company for Building Materials LTD | Direct Works - International Company for Building Materials LTD |  | 0 | 60486.9 | 60486.9 | 0 |  | 60486.9 | 0 | 0 | 0 | 0 | 60486.9 | 0 | 60486.9 | 0 | 60486.9 | 0 | 0 | 0 |  | 189323001.68 | 189262514.78 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Al Hayat | Direct Works - Al Hayat |  | 0 | 846817.39 | 846817.39 | 0 |  | 846817.39 | 0 | 0 | 0 | 0 | 846817.39 | 0 | 846817.39 | 0 | 846817.39 | 0 | 0 | 0 |  | 189323001.68 | 188476184.29 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works -Saint Gobain | Direct Works -Saint Gobain |  | 0 | 122301.47 | 122301.47 | 0 |  | 122301.47 | 0 | 0 | 0 | 0 | 122301.47 | 0 | 122301.47 | 0 | 122301.47 | 0 | 0 | 0 |  | 189323001.68 | 189200700.21 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works- AAMTAC Company LTD | Direct Works- AAMTAC Company LTD |  | 0 | 22553 | 22553 | 0 |  | 22553 | 0 | 0 | 0 | 0 | 22553 | 0 | 22553 | 0 | 22553 | 0 | 0 | 0 |  | 189323001.68 | 189300448.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - DOSAR Al Najd | Direct Works - DOSAR Al Najd |  | 0 | 123937.39 | 123937.39 | 0 |  | 123937.39 | 0 | 0 | 0 | 0 | 123937.39 | 0 | 123937.39 | 0 | 123937.39 | 0
Direct Payment - Works | Direct Works - Alcatop | Direct Works - Alcatop |  | 0 | 1139399.11 | 1139399.11 | 0 |  | 1139399.11 | 0 | 0 | 0 | 0 | 1139399.11 | 0 | 1139399.11 | 0 | 1139399.11 | 0 | 0 | 0 |  | 189323001.68 | 188183602.57 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Saveto Saudi Vetonit Co Ltd | Direct Works - Saveto Saudi Vetonit Co Ltd |  | 0 | 2730 | 2730 | 0 |  | 2730 | 0 | 0 | 0 | 0 | 2730 | 0 | 2730 | 0 | 2730 | 0 | 0 | 0 |  | 189323001.68 | 189320271.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Top Construction Co Ltd | Direct Works - Top Construction Co Ltd |  | 0 | 326341.06 | 326341.06 | 0 |  | 326341.06 | 0 | 0 | 0 | 0 | 326341.06 | 0 | 326341.06 | 0 | 326341.06 | 0 | 0 | 0 |  | 189323001.68 | 188996660.62 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - TBK Metal | Direct Works - TBK Metal |  | 0 | 200069 | 200069 | 0 |  | 200069 | 0 | 0 | 0 | 0 | 200069 | 0 | 200069 | 0 | 200069 | 0 | 0 | 0 |  | 189323001.68 | 189122932.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Lakeshore | Direct Works - Lakeshore |  | 0 | 624120.15 | 624120.15 | 0 |  | 624120.15 | 0 | 0 | 0 | 0 | 624120.15 | 0 | 624120.15 | 0 | 624120.15 | 0 | 0 | 0 |  | 189323001.68 | 188698881.53 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - Fast Steps | Direct Works - Fast Steps |  | 0 | 22250 | 22250 | 0 |  | 22250 | 0 | 0 | 0 | 0 | 22250 | 0 | 22250 | 0 | 22250 | 0 | 0 | 0 |  | 189323001.68 | 189300751.68 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - HRFA | Direct Works - HRFA |  | 0 | 196505.68 | 196505.68 | 0 |  | 196505.68 | 0 | 0 | 0 | 0 | 196505.68 | 0 | 196505.68 | 0 | 196505.68 | 0 | 0 | 0 |  | 189323001.68 | 189126496 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - NESMA | Direct Works - NESMA |  | 0 | 1942966.8 | 1942966.8 | 0 |  | 1942966.8 | 0 | 0 | 0 | 0 | 1942966.8 | 0 | 1942966.8 | 0 | 1942966.8 | 0 | 0 | 0 |  | 189323001.68 | 187380034.88 |  | #REF! | #REF! | 0 | #REF! | 0
Direct Payment - Works | Direct Works - TANSEEQ | Direct Works - TANSEEQ |  | 0 | 9915.37 | 9915.37 | 0 |  | 9915.37 | 0 | 0 | 0 | 0 | 9915.37 | 0 | 9915.37 | 0 | 9915.37 | 0 | 0 | 0 |  | 189323001.68 | 189313086.31 |  | #REF! | #REF! | 0 | #REF! | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 189323001.68 | 189323001.68 |  | #REF! | #REF! | 0 | #REF! | 0
Tamimi | Tamimi (SAB Accommodation Payment) | Tamimi (SAB Accommodation Payment) |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.003C21 | Medtel - STO Façade Mock-up | STO Façade Mock-up -(MWN) 2230075 |  | 0 | 834298.55 | 834298.55 | -15000 |  | 819298.55 | 0 | 0 | 0 | 0 | 819298.55 | -15000 | 819298.55 | 0 | 819298.55 | 0 | 15000 | 0 |  | 12666084.31 | 11846785.76 |  | LUMP SUM Value | CORRECTION DUE TO SPLIT | EARLY WARNING VALUE | Check | Check
CN.003F03 | ESCCO - Vertical Transport | Vertical Transportation (ESCCO) 2230178 |  | 0 | 2675473 | 2675473 | 98073 |  | 2773546 | 765046.05 | -200000 | -15675 | 0 | 3322917.05 | 647444.05 | 1982337.664 | 1340579.386 | 3322917.05 | 0 | -647444.05 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.003C08 | Special Kitchen | Kitchen & Laundry Works (Al Raqtan) 2230205 |  | 0 | 4695209 | 4695209 | 10143 |  | 4705352 | 0 | 1109644.6 | 255601.85 | 0 | 6070598.45 | 1375389.45 | 3837547.3 | 2233051.15 | 6070598.45 | 0
CN.003C09 | DEPA Interior Fitout | Fitout Works (DEPA) |  | 0 | 75969227 | 75969227 | 2312919.14 | 1928436.11 | 80210582.25 | -842054.38 | 1569206.64 | 11185165.78 | 0 | 92122900.29 | 16153673.29 | 65072967.4665 | 27049932.8235 | 90926439.04 | 1196461.25 | -16153673.29 | 0 | 7622348.7768 |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.003C27 | Façade & Glazing Works | Façade & Glazing Works (Alutec) |  | 0 | 29899670.55 | 29899670.55 | 574831.03 |  | 30474501.58 | -112821 | 158694 | 332640 | 0 | 30853014.58 | 953344.03 | 29131817.318 | 1721197.262 | 30853014.58 | 0 | -953344.03 | 0 | 0 |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.003C31 | MAS - Labour Supply - Wet Works | MAS - Wet Works |  | 0 | 4004000 | 4004000 | 18356118 |  | 22360118 | 160876.21 | 0 | 0 | 0 | 22520994.21 | 18516994.21 | 22345856.21 | 175138 | 22520994.21 | 0 | -18516994.21 | 0 | 0 |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.003C32 | MAS - Amphitheatre | MAS - Amphitheatre Works |  | 0 | 1078892.27 | 1078892.27 | 205658.08 |  | 1284550.35 | 0 | 0 | -9520 | 0 | 1275030.35 | 196138.08 | 1211278.835 | 63751.515 | 1275030.35 | 0
CN.003C34 | Al Fanar - MEP Labour Supply | Al Fanar - MEP Labour Supply |  | 0 | 23125000 | 23125000 | 71435593.23 | 65000 | 94625593.23 | 786453.46 | 0 | 128285 | 0 | 95540331.69 | 72415331.69 | 92352575.09 | 3187756.6 | 95540331.69 | 0
CN.100C01 (MVW) | Hard and Soft Landscaping | Hard and Soft Landscaping |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 7622348.7768 |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.003C34 | ARMETAL - Reflective ceiling | ARMETAL - Reflective ceiling |  | 0 | 7129950 | 7129950 | 67078.55 |  | 7197028.55 | 0 | 0 | 0 | 0 | 7197028.55 | 67078.55 | 6633442.8205 | 563585.7295 | 7197028.55 | 0 | -67078.55 | 0 | 0 |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.003C34 | Al Rahji Takaful - Owner Controlled Insurance Program | Al Rahji Takaful - Owner Controlled Insurance Program |  | 0 | 89047.06 | 89047.06 | 0 |  | 89047.06 | 0 | 0 | 0 | 0 | 89047.06 | 0 |  | 89047.06 | 89047.06 | 0
CN.003C35 | ABU DHABI PRECAST - GRC Cladding | ABU DHABI PRECAST - GRC Cladding |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.003C35 | HAS - External Scaffolding Works | HASSAN ALLAM - External Scaffoldings |  | 0 | 3096124.9 | 3096124.9 | 0 |  | 3096124.9 | 0 | 0 | 0 | 0 | 3096124.9 | 0 | 3096124.9 | 0 | 3096124.9 | 0
CN.003F13 | Enviro - Deep Cleaning | Enviro - Deep Cleaning |  | 0 | 799625.31 | 799625.31 | 0 |  | 799625.31 | 0 | 0 | 0 | 0 | 799625.31 | 0 | 0 | 799625.31 | 799625.31 | 0
CN.009C05 | KTH - MEP Works Package - 2240072 - KORTEK | KTH - MEP Works Package - 2240072 - KORTEK |  | 0 | 0 | 0 | 0 |  | 0 | 583143.7 | 367770 | 0 | 0 | 950913.7 | 950913.7 |  | 950913.7 | 950913.7 | 0
CN.012C33 | ALC - Alcatop Package - Fourseasons | ALC - Alcatop Package - Fourseasons - Alcatop |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 150000 | 0 | 0 | 150000 | 150000 |  | 150000 | 150000 | 0
CN.003C328 | Al Futtaim Pioneer Elevators - Al Futtaim Pioneer | Al Futtaim Pioneer Elevators - Al Futtaim Pioneer |  | 0 | 691955 | 691955 | 0 |  | 691955 | 0 | 0 | 0 | 0 | 691955 | 0 |  | 691955 | 691955 | 0
CN.006C22 | TEIJUN VBH | Shandong Tiejun Electric Power Engineering Co. LTD. Branch - 2230277 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 1079464.7 | 0 | 0 | 1079464.7 | 1079464.7 |  | 1079464.7 | 1079464.7 | 0
CN.009C09 | IMAR MH3 | IMAR Overseas Saudi Arabia Co. W.L.L. - IMAR MH3 |  | 0 | 0 | 0 | 442200 |  | 442200 | 0 | 36400 | 0 | 0 | 478600 | 478600 |  | 478600 | 478600 | 0
CN.009C35 | FIBREX MH3 | Fibrex LLC - FIBREX LLC |  | 0 | 0 | 0 | 0 |  | 0 | 164010 | 0 | 0 | 0 | 164010 | 164010 |  | 164010 | 164010 | 0
CN.003C314 | RJT- OCIP Insurance Premium - Declaration 11 | RJT- OCIP Insurance Premium - Declaration 11 - OCIP Insurance |  | 0 | 15076.28 | 15076.28 | 0 |  | 15076.28 | 0 | 0 | 0 | 0 | 15076.28 | 0 |  | 15076.28 | 15076.28 | 0
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN-MW |  | SUB TOTAL MAIN CONTRACT WORKS |  | 18698534 | 457653223.05 | 476351757.05 | 231953.84 | 1993436.11 | 478577147 | -18178391.66 | 3205613.5 | 33674620.893 | 0 | 497278989.733 | 20927232.683 | 456127972.081 | 41151017.652 | 497494874.923 | -215885.19 | -20927232.683 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! | #REF! | 0 | #REF! | 0
CN.031C05 |  |  | Five Oceans Coral Relocation |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.031C05 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.031C05 |  | SUB TOTAL - |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! | #REF! | 0 | #REF! | 0
CN.031C05 |  |  | Five Oceans Coral Relocation |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
CN.031C05 |  | SUB TOTAL - |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! | #REF! | 0 | #REF! | 0
CN - MW |  | SUB-TOTAL - MAIN CONSTRUCTION WORKS |  | 21785723 | 457671817.54 | 479457540.54 | 231444.36 | 1993436.11 | 481682421.01 | -18178391.66 | 3205613.5 | 32891648.893 | 0 | 499601291.743 | 20143751.203 | 457894708.1315 | 41706583.6115 | 499817176.933 | -215885.19 | -20143751.203 | 0 | 215885.19 |  |  |  | -215885.19
[20 empty] | 0 | 0
|  | TOTAL (PS+MS+CM+CN) |  | 39300445.36 | 473997104.54 | 513297549.9 | 5968356.48 | 1993436.11 | 521259342.49 | -18130223.58 | 3156406.5 | 32891648.893 | 0 | 539177174.303 | 25879624.403 | 496895398.3515 | 42281775.9515 | 539393059.493 | -215885.19 | -25879624.403 | 0 |  | #REF! | #REF! |  | #REF!
[20 empty] | + | #VALUE!
CC |  | CLIENT COST | [17 empty] | 0 | 0
[20 empty] | 0 | 0
[20 empty] | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
|  | SUB TOTAL |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
|  | SUB TOTAL |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | [7 empty] | 102
CC |  | SUB-TOTAL - CLIENT COSTS |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0
FF&E & OS&E |  | FF&E AND OS&E | [17 empty] | 0 | 0
[20 empty] | 0 | 0
FFEOSE.003F06 | FF&E and OSE Procurement Agent | FF&E and OSE Procurement Agent (Areen Design Ltd) |  | 0 | 1107465.88 | 1107465.88 | 851779 |  | 1959244.88 | 0 | 0 | 0 | 0 | 1959244.88 | 851779 | 25367673.69 | 14605374.75 | 1959244.88 | 0 | -851779 | 0 | 0 |  |  |  | #REF! |  | #REF! | #REF! | #REF!
0
|  | Issued as a VO to Areen |  |  |  |  | 0
FFEOSE.003F02 | Loose FF&E items (FOH) | Loose FF&E Items (FOH) |  | 0 | 22998647.56 | 22998647.56 | 0 |  | 22998647.56 | 0 | 0 | 0 | 0 | 22998647.56 | 0 |  |  | 22998647.56 | 0 | 0 | 0
Included in FF&E FOH | Loose FF&E items (BOH) | Loose FF&E Items (BOH) |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
FFEOSE.003F02 | OS&E Items | OS&E Items |  | 0 | 14586000 | 14586000 | 0 |  | 14586000 | 0 | 429156 | 0 | 0 | 15015156 | 429156 |  |  | 15015156 | 0 | -429156 | 0
Included in OS&E | Art Work | Art Works |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0
FFEOSE.003F11 | Extraordinary Cart - Buggy Cart | Extraordinary Cart |  | 0 | 397876 | 397876 | 0 |  | 397876 | 0 | 0 | 0 | 0 | 397876 | 0 | 0 | 397876 | 397876 | 0 | 0 | 0 | 0 |  |  |  | #REF! |  | #REF! | #REF! | #REF!
FFEOSE.003D09 | Saudico Electronic Systems | Saudico Electronic Systems |  | 0 | 353487.06 | 353487.06 | 0 |  | 353487.06 | 0 | 0 | 0 | 0 | 353487.06 | 0 | 0 | 353487.06 | 353487.06 | 0
FFEOSE.003D07 | Birch Street | Birch Street |  | 0 | 115998.98 | 115998.98 | 0 |  | 115998.98 | 0 | 0 | 0 | 0 | 115998.98 | 0 | 115998.975 | 0.005 | 115998.98 | 0
FFEOSE.003D10 | AlFalak Electronic - HPE Servers | AlFalak Electronic - HPE Servers |  | 0 | 16655 | 16655 | 0 |  | 16655 | 0 | 0 | 0 | 0 | 16655 | 0 | 0 | 16655 | 16655 | 0
FFEOSE.003D15 | Saudico Electronic Systems | Saudico Electronic Systems |  | 0 | 34719 | 34719 | 0 |  | 34719 | 0 | 0 | 0 | 0 | 34719 | 0 | 34719 | 0 | 34719 | 0
FFEOSE.003D11 | Sevenrooms Inc | Sevenrooms Inc |  | 0 | 32751.56 | 32751.56 | 0 |  | 32751.56 | 0 | 0 | 0 | 0 | 32751.56 | 0 | 0 | 32751.56 | 32751.56 | 0
FFEOSE.003D12 | Infor Co | Infor Saudi Arabia Limited |  | 0 | 58307.19 | 58307.19 | 0 |  | 58307.19 | 0 | 0 | 0 | 0 | 58307.19 | 0 | 0 | 58307.19 | 58307.19 | 0
FFEOSE.003D14 | Reachware Integration | TRA - Zatca Integration with Reachware |  | 0 | 57135 | 57135 | 0 |  | 57135 | 0 | 0 | 0 | 0 | 57135 | 0 | 0 | 57135 | 57135 | 0
FFEOSE.003D16 | PeopleVine Implementation | PeopleVine Implementation |  | 0 | 336187.5 | 336187.5 | 0 |  | 336187.5 | 0 | 0 | 0 | 0 | 336187.5 | 0 | 0 | 336187.5 | 336187.5 | 0
FFEOSE.003D20 | Samtiah Arabis Ltd - Operation systems | Samtiah Arabis Ltd - Operation systems |  | 0 | 59637.55 | 59637.55 | 0 |  | 59637.55 | 0 | 0 | 0 | 0 | 59637.55 | 0 | 0 | 59637.55 | 59637.55 | 0
|  | SUB TOTAL |  | 0 | 40154868.28 | 40154868.28 | 851779 |  | 41006647.28 | 0 | 429156 | 0 | 0 | 41435803.28 | 1280935 | 25518391.665 | 15917411.615 | 41435803.28 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
|  | SUB TOTAL |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | #REF! |  | #REF! | #REF! | #REF!
[20 empty] | 0 | 0 | [7 empty] | 102
FF&E & OS&E |  | SUB-TOTAL - FF&E AND OS&E |  | 0 | 40154868.28 | 40154868.28 | 851779 | 0 | 41006647.28 | 0 | 429156 | 0 | 0 | 41435803.28 | 1280935 | 25518391.665 | 15917411.615 | 41435803.28 | 0 | -1280935 | 0
[20 empty] | 0 | 0
|  | TOTAL (CC+FF&E & OS&E) |  | 0 | 40154868.28 | 40154868.28 | 851779 | 0 | 41006647.28 | 0 | 429156 | 0 | 0 | 41435803.28 | 1280935 | 25518391.665 | 15917411.615 | 41435803.28 | 0 | -1280935 | 0 |  | #REF! | #REF! |  | #REF!
[20 empty] | 0 | 0
1TB01031.01 |  | GRAND TOTAL ASSET COSTS (EXCL BUDGET HOLD) |  | 39300445.36 | 514151972.82 | 553452418.18 | 6820135.48 | 1993436.11 | 562265989.77 | -18130223.58 | 3585562.5 | 32891648.893 | 0 | 580612977.583 | 27160559.403 | 522413790.0165 | 58199187.5665 | 580828862.773 | -215885.19 | -27160559.403 | 0 |  | #REF! | #REF! |  | #REF!
Check - to be zero before start of month
98 |  | BUDGET HOLD | [17 empty] | 0 | 0
[20 empty] | 0 | 0
|  | PROFESSIONAL SERVICES - BUDGET HOLD | [17 empty] | 0 | 0
PS.98 |  | Remaining budget - Professional Fees |  | 11246866.87 | -9734500.35 | 1512366.52 | -1493168.2 |  | 19198.32 | 0 | 0 | 0 | 0 | 0 | -1512366.52 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0
PS.98 |  | SUB TOTAL - BUDGET HOLD PS |  | 11246866.87 | -9734500.35 | 1512366.52 | -1493168.2 | 0 | 19198.32 | 0 | 0 | 0 | 0 | 0 | -1512366.52 | 0 | 0 | 0 | 0
|  | MANAGEMENT - BUDGET HOLD | [17 empty] | 0 | 0
MS.98 |  | Remaining budget - Management Supervision |  | 17975993.27 | -18233177.65 | -257184.38 | 827022.8 | -569838.42 | 1.0477e-09 | 0 | 49207 | 0 | 0 | 0 | 257184.38 | 0 | 0 | 0 | 0
CM.98 |  | Remaining budget - Commercial Management |  | 1198399.55 | -1198399.55 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0
MS.98 + CM.98 |  | SUB TOTAL - BUDGET HOLD MS & CM |  | 19174392.82 | -19431577.2 | -257184.38 | 827022.8 | -569838.42 | 1.0477e-09 | 0 | 49207 | 0 | 0 | 0 | 257184.38 | 0 | 0 | 0 | 0
|  | CONSTRUCTION WORKS RELATED FUNDS | [17 empty] | 0 | 0
CN.98 |  | Remaining budget - Construction Works |  | 221633231.2 | -192496415.77 | 29136815.43 | 7496780.04 | -15074367.81 | 21559227.66 | 18178391.66 | -3205613.5 | -32891648.893 | 0 | 0 | -29136815.43 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0
CN.98 |  | SUB TOTAL - BUDGET HOLD CN |  | 221633231.2 | -192496415.77 | 29136815.43 | 7496780.04 | -15074367.81 | 21559227.66 | 18178391.66 | -3205613.5 | -32891648.893 | 0 | 0 | -29136815.43 | 0 | 0 | 0 | 0
|  | FF&E & OSE WORKS RELATED FUNDS | [17 empty] | 0 | 0
CN.98 |  | Remaining budget - FF&E and OSE |  | 24991549 | -24988413.89 | 3135.11 |  |  | 3135.11 | 0 | -429156 | 0 | 0 | 0 | -3135.11 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0
CN.98 |  | SUB TOTAL - BUDGET HOLD CN |  | 24991549 | -24988413.89 | 3135.11 | 0 | 0 | 3135.11 | 0 | -429156 | 0 | 0 | 0 | -3135.11 | 0 | 0 | 0 | 0
[20 empty] | 0 | 0 | [7 empty] | 102
98 |  | TOTAL - BUDGET HOLD (PS+MS+CM+CN+FFE+OSE) |  | 277046039.89 | -246650907.21 | 30395132.68 | 6830634.64 | -15644206.23 | 21581561.09 | 18178391.66 | -3585562.5 | -32891648.893 | 0 | 0 | -30395132.68 | 0 | 0 | 0 | 0 | 30395132.68 | 0
[20 empty] | 0 | 0
1TB01031.01 | AYC | GRAND TOTAL ASSET COSTS (INCL BUDGET HOLD) |  | 316346485.25 | 267501065.61 | 583847550.86 | 13650770.12 | -13650770.12 | 583847550.86 | 48168.08 | 0 | 0 | 0 | 580612977.583 | -3234573.277 | 522413790.0165 | 58199187.5665 | 580828862.773 | -215885.19 | 3234573.277 | 0
[5 empty] | -4203149.6 | 583847550.86 |  |  | 0 |  |  |  |  | 0 | -3234573.277 | 522199822.0415 |  | 580828862.773 | 215885.19
| -707031.28 |  |  |  |  | 583847550.86 |  | -16136787.47 | 0 | -18130223.58 |  |  |  | 580612977.583 | -3234573.277 | -213967.975 | Check Zero: |  | -215885.19
| -707031.28 |  |  |  |  | 1086381.73 |  |  | 2044368.78 |  |  |  |  | 591674143.363 |  |  |  |  | -215885.19 | 0
|  |  |  | 796667539.81 | 16269412.54 | 584656915.6 |  |  | 21559227.66 |  |  |  | CHECK: | -11061165.78 | ZERO ALWAYS |  |  |  | -2.3283e-09
|  | X-CHECK (MUST BE ZERO) |  | -480321054.56 | 283770478.15 | 809364.74 |  |  | 23603596.44 | 2044368.78
[6 empty] | 0 |  |  |  | 461630.05
|  |  |  | 316346485.05 | 128593066.81 |  |  |  | 24403221.75 | -1582738.73 |  |  |  |  | -12734573.277
|  | 70608874 |  | -0.2 | 23779038 | [8 empty] | 580612977.583 |  |  |  | 215885.19
|  | 9826662 |  |  |  | 584492905.6 |  |  | 39281175.97
|  | 2.547% |  |  | 139742229.35 | 645354.74 |  |  | 17721948.31
|  | 60782212 |  | 13682040 | -127758836.26
|  | 60782212 |  | 28206303 |  |  |  |  | 39281175.97
|  | 1066798 | 11.6667 | [5 empty] | 17721948.31
|  | 69542076 |  |  | -224981609.7
|  |  |  | 12800000 | 2660039 |  |  |  | 584492905.6
|  |  |  | 340000 | -222321570.7 |  |  |  | -645354.74
3543829
2400000

## Overrun Summary (hidden)
Ref | Overrun Items Descriptions | Variance |  | Current BT Summary Breakdown | Estimated Commitment Date
Budget V Cost
|  | SAR | % | SAR
1 | Early Warning for Future Awards | -1457002 | 25.75% | 0
1.a | Item No. - 81 - Al Fanar MEP Manpower Supply to AYC Project on behalf of SAB. | 0 | 0% |  | 2024-11-17
1.b | Item No. - 79 - Reflective Ceiling (Award to Armetal) | -1457002 | 25.75% |  | 2024-11-17
1.c | Item No. - 73 - Additional Porte Cochere Works to be carried out by MAS | 0 | 0% |  | 2024-11-25
2 | Early Warning on Awarded Packages | -4201674 | 74.25% | 0
2.a | Item No. - 22 - Omission of Surveying Equipment from SAB Contract | -7890 | 0.1394% |  | Final Account
2.b | Item No. - 24 - Omission of food and welfare provision to AMAALA Staff from SAB Contract. | -90000 | 1.59% |  | Final Account
2.c | Item No.-25 - Cost saving to Site Office Monthly Running Cost due to late installation of the Office Establishment by SAB. | -200000 | 3.534% |  | Final Account
2.d | Item No. - 64 - Potential Contract Cost Adjustment | 0 | 0% |  | Management to Advise
2.e | Item No. - 70b - Cancellation of Amphitheatre Works issued to MAS - Process not followed | 0 | 0% |  | 2024-11-30
2.f | Item No. - 71b - Recovery of Remaining Block work, Plaster work and Paint Work to be carried out by MAS - Process not followed | -4004000 | 70.76% |  | 2024-11-30
2.g | Item No. - 72 - Alteration to finishes due to Façade Layout Changes - Process not Followed | 69000 | -1.219% |  | 2024-11-30
2.h | Item No. - 80 - Reflective Ceiling (Omission from SAB) | 0 | 0% |  | 2024-11-30
2.i | Item No. - 75 - Deployment of Seven (7) Surveyors | 0 | 0% |  | 2024-11-30
2.j | Item No. - 76 - Employer’s instruction for ID Finishes on Vertical Transportation Fixture Elements | 0 | 0% |  | 2024-11-30
2.k | Item No. - 77 - AYC – Disassembly and Reassembly of electronic items from VT fixtures | 0 | 0% |  | 2024-11-30
2.l | Item No. - 78 - Scaffolding works for Secondary Steel and Façade (Design) | 75000 | -1.325% |  | 2024-12-15
-43784
0
Total Overrun |  | -5658676 | 100% | 0
ERB_Rev 03_20240514
-5658676
0
#REF!
#REF!

## Schedule J
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
Budget Approved - UNOFFICIALLY
ITEM | BUDGET TRANSFER DESCRIPTION |  |  | FROM PACKAGE | TO PACKAGE | BUDGET TO PACKAGE | BUDGET FROM PACKAGE | BUDGET TO PACKAGE | DATE | REPORTING PERIOD
1 | INTER PROGRAMME TRANSFER - Site Logistics budget transfer 2.547% |  |  | All Construction Packages | Site Logistics | 0 | -6199291.02 | 0 | 2022-08-19 | Monthly Report No 1 - Oct'22
2 | INTER PACKAGE TRANSFER - Piling NSCC to Construction Budget Hold - Contract Award |  |  | NSCC - Piling | Remaining budget - Construction Works | #VALUE! | -2719369.0417 | 2719369.0417 | 2022-10-18 | Monthly Report No 1 - Oct'22 | 1
3 | ADDITIONAL BUDGET - Inline with EW Reported against PTE's to Civils package |  |  | External - Pre Approved | Civil and Arch Works | 70957643.397 |  | 70957643.397 | 2022-12-19 | Monthly Report No 3 - Dec'22
4 | ADDITIONAL BUDGET - Inline with EW Reported against PTE's to MEPD package |  |  | External - Pre Approved | MEPD | 27815335.598 |  | 27815335.598 | 2022-12-19 | Monthly Report No 3 - Dec'22
5 | ADDITIONAL BUDGET - Inline with EW Reported against PTE's to ICT / ELV package |  |  | External - Pre Approved | ICT / ELV | 4975465.6089 |  | 4975465.6089 | 2022-12-19 | Monthly Report No 3 - Dec'22
6 | INTER PACKAGE TRANSFER - MEPD to Civils and Arch Works - Contract Award (Baytur) |  |  | MEPD | Civil and Arch Works | #VALUE! | -12877723.65 | 12877723.65 | 2022-12-19 | Monthly Report No 3 - Dec'22
7 | INTER PACKAGE TRANSFER - MEPD to ICT / ELV - Contract Award (Baytur) |  |  | MEPD | ICT / ELV | #VALUE! | -2819592.31 | 2819592.31 | 2022-12-19 | Monthly Report No 3 - Dec'22
8 | INTER PACKAGE TRANSFER - MEPD to Budget Hold - Contract Award (Baytur) - Saving |  |  | MEPD | Remaining budget - Construction Works | #VALUE! | -12545905.62 | 12545905.62 | 2022-12-19 | Monthly Report No 3 - Dec'22 | 1
9 | INTER PACKAGE TRANSFER - MS Budget Hold to Khatib & Alami Contract Award (MS - AYC) |  |  | MS - Budget Hold | KAA-Mgt Fees | #VALUE! | -13059930 | 13059930 | 2023-01-26 | Monthly Report No 4 - Jan'23
10 | INTER PACKAGE TRANSFER - PS Budget Hold to Langan Contract Award |  |  | PS - Budget Hold | Langan-Prf Fees | 172368.42 | -172368.42 | 172368.42 | 2023-01-20 | Monthly Report No 4 - Jan'23
11 | INTER PACKAGE TRANSFER - PS Budget Hold to Zuhair Fayez Partnership Contract Award (PS - AYC) |  |  | PS - Budget Hold | ZFP-Prf Fees | 106231.5 | -106231.5 | 106231.5 | 2023-01-26 | Monthly Report No 4 - Jan'23
[6 empty] | 33 |  | 33
12 | INTER PACKAGE TRANSFER - CN Budget Hold to Medtel W.N. WLL Contract Award (CN - AYC) |  |  | CN - Budget Hold | Medtel - STO Façade Mock-up | 35 | -834298.55 | 35 | 2023-01-26 | Monthly Report No 5 - Feb'23
13 | ADDITIONAL BUDGET - EW No.4 Reported at SAR 2,675,473 against PTE's to Vertical Transport |  |  | External - Pre Approved | Vertical Transport | 521622.03 |  | 521622.03 | 2023-04-05 | Monthly Report No 7 - Apr'23
13 | INTER PACKAGE TRANSFER - PS Budget Hold to Jensen Hughes Contract Award |  |  | PS - Budget Hold | Jensen Hughes-Prf Fees | 127291.9 | -127291.9 | 127291.9 | 2023-05-06 | Monthly Report No 8 - May'23
14 | INTER PACKAGE TRANSFER - Kitchen & Laundry Works to Budget Hold - Contract Award (Al Raqtan) - Saving |  |  | Special Kitchen | Remaining budget - FF&E and OSE | #VALUE! | -1212511 | 1212511 | 2023-05-25 | Monthly Report No 8 - May'23
14 | INTER PACKAGE TRANSFER - PS Budget Hold to MOMRA (Tabuk) - Building Permit |  |  | PS - Budget Hold | MOM - Building Permit Fee | #VALUE! | -45677.6 | 45677.6 |  | Monthly Report No 10 |  |  |  | Recent transfer to CN Hold | BTR from MH3 | Transferred budget for Kitchen Package
15 | INTER PROJECT TRANSFERS (INCOMING) |  |  | Approved Additional Budget | CN - Budget Hold | 112330560.37 | -104270066.6339 | 112330560.37 | 2023-07-18 | Monthly Report No 10 - Jul'23 (incl. the previous External-Pre Approved Budget. Kitchen package budget transferred under CN in ACC). |  |  | 112330560.37 | 93913586.15 | 13721765.22 | 4695209
16 | INTER PROJECT TRANSFERS (INCOMING) |  |  | Approved Additional Budget | FF&E OSE - Budget Hold | 33610960 | 0 | 33610960 | 2023-07-18 | Monthly Report No 10 - Jul'23 (transferred the budget for Kitchen to CN-Budget Hold) |  |  | 33610960 | 38306169 | -4695209
| Transfer budget to Hard and Soft Landscaping |  |  | CN - Budget Hold | Hard and Soft Landscaping | #VALUE! | -12527902.4151 | 12527902.4151
| Transfer budget to Interior Fitout |  |  | CN - Budget Hold | Interior Fitout | #VALUE! | -29047396.4327 | 29047396.4327
[13 empty] | 145941520.37 | Recent transfer to FFEOSE Hold | Transferred budget for Kitchen Package to CN
| TOTALS |  |  |  |  | #VALUE! | -198565556.0935 | 337473554.8935
[6 empty] | #VALUE! |  | 138907998.8 |  |  | transfer to Logistics |  | -6199291.02 | 132219755.15
[6 empty] | 104270066.6339 |  | 104270066.6339 |  |  | Approved Budget Changes: |  | 139742229.35
[6 empty] | #VALUE! |  | 41575298.8479
| INTER PROJECT TRANSFERS (OUTGOING) |  |  | PS - Budget Hold | Marina Hotel 3 - PS Hold | 0 | -6277273.42 | 0
| INTER PROJECT TRANSFERS (OUTGOING) |  |  | CN - Budget Hold | Marina Hotel 3 - CN Hold | 0 | -834298.55 | 0
History - related to budget transfers to appoint Baytur - due to additional budget not formally being approved as of 1 Feb 2023
ITEM | BUDGET TRANSFER DESCRIPTION |  | BTR APPROVAL REFERENCE | FROM PACKAGE | TO PACKAGE | REMARKS | BUDGET FROM PACKAGE | BUDGET TO PACKAGE | DATE | REPORTING PERIOD
1 | INTER PROGRAMME TRANSFER - Site Logistics budget transfer 2.547% |  | 1TB04034-034000-AMA-BTR-CM-0001-02 | CN - Budget Hold | Site Logistics |  | -6199291.02 | 0 | 2022-08-10 |  | from Construction Budget |  | 243418954.2 | 221633231.5
2 | Appointment of Art Consultant for Design Services |  | AMA-RBTR-000006 | PS - Budget Hold | DAE -Prf Fees | DEWAN Variation DVO 001 | -261030 | 261030 | 2022-09-18
3 | Langan International UK, Ltd. for Geotechnical Consultancy Services - Peer Review. |  | AMA01003-RBTR-000018 | PS - Budget Hold | Langan-Prf Fees (Provisional) |  | -3947.37 | 3947.37 | 2023-01-22
4 | Langan International UK, Ltd. for Geotechnical Consultancy Services - Peer Review. |  | AMA01003-RBTR-000019 | PS - Budget Hold | Langan-Prf Fees |  | -168421.05 | 168421.05 | 2023-01-22
5 | Contract Award to Saudi Baytur |  | AMA01003-RBTR-000031 | MS - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV |  | -9614128.52 | 9614128.52 | 2023-01-24
6 | Contract Award to Saudi Baytur |  | AMA01003-RBTR-000034 | CM - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV |  | -1198399.55 | 1198399.55 | 2023-01-24
7 | Contract Award to Saudi Baytur |  | AMA01003-RBTR-000030 | PS - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV |  | -9717397.15 | 9717397.15 | 2023-01-24
8 | Contract Award to Saudi Baytur |  | AMA01003-RBTR-000032 | FF&E OSE - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV |  | -24991549 | 24991549 | 2023-01-24
9 | Contract Award to Saudi Baytur |  | AMA01003-RBTR-000033 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV |  | -215433940.18 | 215433940.18 | 2023-01-24
10 | MS to PS Hold to fund the Contract Award to Langan |  | AMA01003-RBTR-000038 | MS - Budget Hold | PS - Budget Hold |  | -172368.42 | 172368.42 | 2023-01-29
11 | Contract Award of KHATIB & ALAMI (KAA) for Supervision Consultancy Services |  | AMA01003-WTRAN-001673 | Marina Hotel 3 - PS Hold | KAA-Mgt Fees |  | 0 | 4870433.67 | 2023-02-08
12 | Contract Award of KHATIB & ALAMI (KAA) for Supervision Consultancy Services |  | AMA01003-WTRAN-001673 | MS - Budget Hold | KAA-Mgt Fees |  | -8189496.33 | 8189496.33 | 2023-02-08
13 | Contract Award to Zuhair Fayez (ZFP) |  | AMA01003-WTRAN-001674 | Marina Hotel 3 - PS Hold | ZFP-Prf Fees |  | 0 | 106231.5 | 2023-02-08
14 | DEWAN DVO 005 |  | AMA01003-WTRAN-001799 | Marina Hotel 3 - PS Hold | DAE -Prf Fees | Variation/to PS Hold | 0 | 16000 | 2023-02-14
15 | DEWAN DVO 006 |  | AMA01003-WTRAN-001799 | Marina Hotel 3 - PS Hold | DAE -Prf Fees | Variation/to PS Hold | 0 | 351150 | 2023-02-14
16 | Contract Award to Medtel |  | AMA01009-WTRAN-000645 | Marina Hotel 3 - CN Hold | Medtel - STO Façade Mock-up |  | 0 | 834298.55 | 2023-03-05
17 | Municipality Fees (Ministry of Municipalities and Rural Affairs - Tabuk) to obtain Building Permit |  | AMA01003-WTRAN-001952 | Marina Hotel 3 - PS Hold | MOM - Building Permit Fee |  | 0 | 45677.6 | 2023-03-01
18 | Contract Award to Jensen Hughes |  | AMA01003-WTRAN-000996 | Marina Hotel 3 - PS Hold | Jensen Hughes-Prf Fees |  | 0 | 127291.9 | 2023-04-09
19 | Contract Award to ESCCO |  | AMA01009-WTRAN-001073 | Marina Hotel 3 - PS Hold | ESCCO - Vertical Transport |  | 0 | 2675473 | 2023-04-07
20 | Contract Award to Raqtan |  | AMA01009-WTRAN-001188 | Marina Hotel 3 - PS Hold | RAQTAN - Kitchen and Laundry |  | 0 | 4695209 | 2023-05-31
21 | NSCC DVO 009 Changes in Piling Works Redesign |  | AMA01003-RBTR-000062 | NSCC - Piling | CN - Budget Hold | Variation | -3801279.3 | 3801279.3 | 2023-08-08
22 | Additional Budget (Budget Transfer Request for AMD Phase 1 Rev 3) |  | AMA99999-WTRAN-003032 | External - Approved - Revised Asset Budget Allocation (02/02/2023) | CN - Budget Hold | Additional Budget | 0 | 93913586.15 | 2023-07-18
23 | Additional Budget (Budget Transfer Request for AMD Phase 1 Rev 3) |  | AMA99999-WTRAN-003032 | External - Approved - Revised Asset Budget Allocation (02/02/2023) | FF&E OSE - Budget Hold | Additional Budget | 0 | 38306169 | 2023-07-18
24 | Payment of LEED Design Review fees under invoice #91671322 |  | AMA01003-RBTR-000046 | CN - Budget Hold | GBC - Sustainability Accreditation | Variation | -13500.11 | 13500.11 | 2023-08-03 |  | d
25 | DVO 004 (Changes in External and Internal Temporary Watertight Shoring System) from the SAB account to CN Budget Hold. |  | AMA01003-RBTR-000095 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -11545998.09 | 11545998.09 | 2023-12-04
26 | DEWAN DVO 007 - Staff Canteen Redesign |  | AMA01003-RBTR-000059 | CN - Budget Hold | DAE -Prf Fees | Variation | -413183 | 413183 | 2023-08-08 |  | d
27 | NSCC DVO 007 - Changes in Ready-Mix Concrete Supply Rates to Piling Works in AMAALA Yacht Club Project. |  | AMA01003-RBTR-000060 | CN - Budget Hold | NSCC - Piling | Variation | -70027.76 | 70027.76 | 2023-08-08
28 | SAB DVO 001 - Additional Mass Concrete Works |  | AMA01003-RBTR-000061 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV | Variation | -343524.99 | 343524.99 | 2023-08-08
29 | HKS - Final Settlement |  | AMA01003-RBTR-000136 | HKL (Design Architect)-Prf Fees | PS - Budget Hold | Variation / Final Account | -89775 | 89775 | 2024-03-21
30 | GBC - BTR for future GBCI invoices (Construction Review) |  | AMA01003-RBTR-000074 | CN - Budget Hold | GBC - Sustainability Accreditation | Variation | -5737.5 | 5737.5 | 2023-09-11
31 | SAB DVO 003 - Omission of Dewatering from SAB Contract |  | AMA01003-RBTR-000098 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -4902500 | 4902500 | 2023-12-07
32 | WSP COO 002 (Sustainability Accreditation LEED Consultancy Services) |  | AMA01100-WTRAN-003600 | CN - Budget Hold | Marina Village Wide - MS Budget Hold |  | -302028 | 0 | 2023-09-16
33 | DEWAN DVO 008 (Fire & Life Safety (FLS) Code Deviation - Additional FLS Documentation) |  | AMA01003-RBTR-000082 | CN - Budget Hold | DAE -Prf Fees | Variation | -193161.38 | 193161.38 | 2023-10-30
34 | SAB DVO 002 (Changes from IFT to IFC Documents) |  | AMA01003-RBTR-000080 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV | Variation | -2458484 | 2458484 | 2023-10-24
35 | Contract Award to Depa Saudi Arabia for Contracting and Interior Decoration Co. Ltd. |  | AMA01003-RBTR-000086 | CN - Budget Hold | Interior Fitout |  | -75969227 | 75969227 | 2023-10-09
36 | DEWAN PVO 004 (Design Fee - Relocation of Marina Operations Office to AMAALA Yacht Club) |  | AMA01003-RBTR-000090 | CN - Budget Hold | DAE -Prf Fees | Variation | -248219 | 248219 | 2023-11-21
37 | SAB DVO 006 (Omission of Service Vehicles from SAB Contract) |  | AMA01003-RBTR-000105 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -774075.97 | 774075.97 | 2023-12-24
38 | SAB DVO 005 (Omission of Sto Facade Mock-up scope from SAB) |  | AMA01003-RBTR-000106 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -848556 | 848556 | 2023-12-27
39 | Saudi Arabian Baytur (SAB) for AYC Site Offices Extension (PVO 004). |  | AMA01003-RBTR-000141 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV | Variation | -1518989 | 1518989 | 2024-04-21
40 | DEPA PVO – 01 amounting to Negative SAR 486,713.10 to DEPA Saudi Arabia for “Changes in the AYC Back-of-House (BOH) Finishes – Basement Level '' |  | AMA01003-RBTR-000134 | Interior Fitout | CN - Budget Hold | Variation | -486713.1 | 486713.1 | 2024-03-21
41 | SAB Changes in the Basement Level Back-of-House (BOH) Finishes to Amaala Yacht Club Project (PVO 009) |  | AMA01003-RBTR-000114 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV | Variation | -452337.15 | 452337.15 | 2024-02-20
42 | DEPA PVO – 02 amounting to Negative SAR 212,913.40 to DEPA Saudi Arabia for “Descope of Back of House Finishes - Ground Level |  | AMA01003-RBTR-000135 | Interior Fitout | CN - Budget Hold | Variation | -212913.4 | 212913.4 | 2024-03-21
43 | SAB Changes in the Ground Floor Level Back-of-House (BOH) Finishes to Amaala Yacht Club Project (PVO 010) |  | AMA01003-RBTR-000113 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV | Variation | -56240.63 | 56240.63 | 2024-02-20
44 | K&A DVO 001 (Removal of K&A's Sustainability LEED AP Resource) |  | AMA01003-RBTR-000123 | KAA-Mgt Fees | MS - Budget Hold | Variation | -977022.8 | 977022.8 | 2024-03-17
45 | Contract Award to Alutec |  | AMA01003-RBTR-000138 | CN - Budget Hold | Façade & Glazing Works |  | -29899670.55 | 29899670.55 | 2024-03-26
46 | SAB PVO 012 (Omission of Joinery LED Lights from SAB from SAB Contract) |  | AMA01003-RBTR-000144 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -139212.69 | 139212.69 | 2024-04-22
47 | MEDTEL Final Account Statement |  | AMA01003-RBTR-000148 | Medtel - STO Façade Mock-up | CN - Budget Hold | Variation | -15000 | 15000 | 2024-05-13
48 | SAB PVO 004 (DVO 07) AYC Site Office - Adjustment P3 |  | AMA01003-RBTR-000154 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -4062831 | 4062831 | 2024-06-05
49 | SAB PVO 004 (DVO 07) AYC Site Office - Adjustment P2 |  | AMA01003-RBTR-000160 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV | Variation | -2765566 | 2765566 | 2024-06-06
50 | SAB Cancellation PVO 10 "Changes to BOH Finishes to Ground Floor – SAB Adjustments" to Amaala Yacht Club Project (PVO 010) |  | AMA01003-RBTR-000180 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -56240.63 | 56240.63 | 2024-06-30
51 | SAB Cancellation PVO 09 "Changes in the AYC Back-of-House (BOH) Finishes -Basement Level" to Amaala Yacht Club Project (PVO 009) |  | AMA01003-RBTR-000177 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -452337.15 | 452337.15 | 2024-06-30
52 | DEPA PVO – 05 amounting to SAR 131,832.80to DEPA Saudi Arabia for “Changes in Skirting and Ceiling Finishes at Member's Lobby'' |  | AMA01003-RBTR-000159 | CN - Budget Hold | Interior Fitout | Variation | -131832.8 | 131832.8 | 2024-06-06
53 | Areen - Provisional Sum of Areen Design Ltd Contract (003F06) for FFE & OSE Procurement Agent Service |  | AMA01003-RBTR-000178 | FF&E OSE - Budget Hold | OS&E Items |  | -52736.47 | 52736.47 | 2024-06-30
54 | Areen Contract Award of Areen Design Ltd (003F06) - FFE & OSE Procurement Agent Services for AYC. |  | AMA01003-RBTR-000179 | FF&E OSE - Budget Hold | OS&E Items |  | -1054729.41 | 1054729.41 | 2024-06-30
55 | This Budget Transfer is raised for approval to transfer budget for the provisional Sum of Areen Design Ltd Contract (003F06) for FFE & OSE Procurement Agent Services. |  | AMA01003-RBTR-000186 | OS&E Items | OS&E Items | Areen Provisional Sums | 0 | 0 | 2024-07-14
56 | DEPA cancellation of the approved PVO - 01 (Changes in the AYC Back-of-House (BOH) Finishes – Basement Level) PVO 02 (Descope of Back of House Finishes - Ground Level) |  | AMA01003-RBTR-000176 | CN - Budget Hold | Interior Fitout | Variation | -699626.5 | 699626.5 | 2024-01-30
57 | This Budget Transfer is raised for approval RFA for Seed Funds for FFE & OSE Procurement Agent Services. |  | AMA01003-RBTR-000200 | FF&E OSE - Budget Hold | OS&E Items | Contract Award | -37198703.12 | 37198703.12 | 2024-07-23 |  | 37584647.56
58 | This Budget Transfer is raised for approval RFA for Seed Funds for FFE & OSE Procurement Agent Services. |  | AMA01003-RBTR-000201 | CN - Budget Hold | OS&E Items | Variation | -385944.44 | 385944.44 | 2024-07-23
59 | This Budget Transfer Request is raised for approval to transfer a budget for the approved PVO 013 (Riva Curved Banquet Support Wall & Porte Cochere Wall Panel Access) from the SAB account to CN Budget Hold. |  | AMA01003-RBTR-000206 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -12334.95 | 12334.95 | 2024-07-28
60 | This Budget Transfer is raised for approval to transfer the budget for the approved PVO – 06 amounting to SAR 1,021,958 DEPA Saudi Arabia for “BOH Doors & Fire Curtains at Basement Level'' |  | AMA01003-RBTR-000207 | CN - Budget Hold | Interior Fitout | Variation | -1021958 | 1021958 | 2024-07-28
61 | This BTR is raised based on the approved Final Account Statement - Langan |  | AMA01003-RBTR-000240 | LUI-Prf Fees | PS - Budget Hold | Variation | -1898.52 | 1898.52 | 2024-08-14
62 | DEWAN - This Budget Transfer Request is raised for approval to transfer a budget for the approved PVO 009 |  | AMA01003-RBTR-000234 | PS - Budget Hold | DAE -Prf Fees | Variation | -89775 | 89775 | 2024-08-14
63 | DEWAN PVO 07 - Members Lobby Staircase Balustrade & Finish Revisions |  | AMA01003-RBTR-000235 | MS - Budget Hold | DAE -Prf Fees | Variation | -75000 | 75000 | 2024-08-14
64 | DEWAN PVO 06 - Guest Lobby Staircase Geometry & Finish Revisions |  | AMA01003-RBTR-000236 | PS - Budget Hold | DAE -Prf Fees | Variation | -75000 | 75000 | 2024-08-14
65 | SAB PVO 11 -Site Office Levelling and Fencing |  | AMA01003-RBTR-000233 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV | Variation | -3013648.7 | 3013648.7 | 2024-08-14
66 | PVO 09 - Staff Canteen and Marina Operation Office (From CN) |  | AMA01003-RBTR-000232 | CN - Budget Hold | DAE -Prf Fees | Variation | -229813 | 229813 | 2024-08-14
67 | New Contract Award (F07) - ECC - Statutory Compliance Contract |  | AMA01003-RBTR-000242 | MS - Budget Hold | ECC-Mgt Fees |  | -182184.38 | 182184.38 | 2024-08-14
68 | DEWAN PVO 012 - Grand Stair Balustrade Redesign (Design Works) |  | AMA01003-RBTR-000241 | MS - Budget Hold | DAE -Prf Fees | Variation | -75000 | 75000 | 2024-08-14
69 | DEWAN PVO 06 - Guest Lobby Staircase Geometry & Finish Revisions |  | AMA01003-RBTR-000257 | MS - Budget Hold | PS - Budget Hold |  | -75000 | 75000 | 2024-08-22
70 | DEPA PVO 004 (DEPA) Riva Curved Banquet Support Wall & Porte Cochere Wall Panel Access |  | AMA01003-RBTR-000254 | CN - Budget Hold | Interior Fitout | Variation | -72215.12 | 72215.12 | 2024-08-22
71 | SAB PVO 018 - Changes in Floor Finish Type CSF-1 |  | AMA01003-RBTR-000255 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV | Variation | -140560.76 | 140560.76 | 2024-08-22
72 | SAB PVO 017 - Facade Glazing and Glazing Doors Omission from SAB Scope |  | AMA01003-RBTR-000256 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -10807729.2 | 10807729.2 | 2024-08-22 |  | Committed, no DVO Contract Change.
73 | Contract Award to CML (Provisional Sum) |  | AMA01003-RBTR-000277 | CN - Budget Hold | CML-Mgt Fees |  | -471500 | 471500 | 2024-09-10
74 | Contract Award to CML (Main Contract) |  | AMA01003-RBTR-000281 | CN - Budget Hold | CML-Mgt Fees |  | -1935000 | 1935000 | 2024-09-11
75 | DEPA PVO 02 - Descope of Back of House Finishes - Ground Level |  | AMA01003-RBTR-000270 | Interior Fitout | CN - Budget Hold | Variation | -122736.16 | 122736.16 | 2024-09-03
76 | DEPA PVO 07 - Accommodation Outside TB-Construction Village (Senior and Executive Staff) |  | AMA01003-RBTR-000269 | CN - Budget Hold | Interior Fitout | Variation | -288500 | 288500 | 2024-09-03
77 | SAB PVO 012 - Omission of Joinery LED Lights (Adjustment) |  | AMA01003-RBTR-000267 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV | Variation | -29262.77 | 29262.77 | 2024-09-03
78 | DEPA PVO 001 R1 & PVO 002 R1 - Adjustment |  | AMA01003-RBTR-000278 | Interior Fitout | CN - Budget Hold | Variation | -1300549.5 | 1300549.5 | 2024-09-10
79 | CN-Budget Hold to fund future GBCI - LEED invoices for Design and Construction Review |  | AMA99999-WTRAN-003079 | CN - Budget Hold | GBC - Sustainability Accreditation | Variation | 0 | 0 | 2023-08-17
80 | GBCI invoices (Construction Review) - Adjustment |  | AMA01003-RBTR-000285 | GBC - Sustainability Accreditation | CN - Budget Hold | Variation | -643.12 | 643.12 | 2024-10-01
81 | DEWAN PVO 013 - Addition of Accessories to Existing Artwork Proposal |  | AMA01003-RBTR-000293 | CN - Budget Hold | DAE -Prf Fees | Variation | -130350 | 130350 | 2024-10-13
82 | NSCC Final Account Settlement with NSCC (TB Piling Works) |  | AMA01003-RBTR-000292 | CN - Budget Hold | NSCC - Piling | Variation | -1491099.05 | 1491099.05 | 2024-10-13
83 | Contract Award to MAS Manpower |  | AMA01003-RBTR-000303 | CN - Budget Hold | MAS - Labour Supply - Wet Works |  | -4004000 | 4004000 | 2024-10-23
84 | SAB DVO 12 (PVO 13) - Adjustment |  | AMA01003-RBTR-000302 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -1828.5 | 1828.5 | 2024-10-23
85 | SAB PVO-021 - Additional Storm Water Drainage Works to GF and Basement |  | AMA01003-RBTR-000310 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV | Variation | -110148.64 | 110148.64 | 2024-10-29
86 | SAB PVO-015 - Omission of Back-of-House (BOH) Finishes in L01 to L04 from SAB Contract |  | AMA01003-RBTR-000311 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -349595.15 | 349595.15 | 2024-10-29
87 | SAB PVO 22 (Addl Primary Side CHW Valve Arrangement) & PVO 23 (Provision of new IBS Infra Reqt for Indoor GSM) |  | AMA01003-RBTR-000330 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV | Variation | -1240669 | 1240669 | 2024-11-12
88 | DEWAN PVO 04, 05, 06 & 07 (Adjustments) |  | AMA01003-RBTR-000329 | DAE -Prf Fees | PS - Budget Hold | Variation | -339994.38 | 339994.38 | 2024-11-12
89 | DEPA PVO 05 P2 & PVO 06 P2 (Adjustment) |  | AMA01003-RBTR-000328 | Interior Fitout | CN - Budget Hold | Variation | -251277.89 | 251277.89 | 2024-11-12
90 | Contract Award to MAS for Amphitheatre Works |  | AMA01003-RBTR-000327 | CN - Budget Hold | MAS - Amphitheatre |  | -1078892.27 | 1078892.27 | 2024-11-12
91 | DEWAN DVO 11 (PVO 012 - Grand Stair Balustrade Redesign (Design Works) - Adjustment |  | AMA01003-RBTR-000333 | DAE -Prf Fees | PS - Budget Hold | Variation | -5901 | 5901 | 2024-11-14
92 | SAB PVO 026 - Supply of Labour and Supervision by Al Fanar for MEP Works in AMAALA Yacht Club on behalf of Saudi Arabian Baytur (SAB) |  | AMA01003-RBTR-000339 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -23125000 | 23125000 | 2024-11-24
93 | GBCI Final invoices (Construction Review) - Adjustment |  | AMA01003-RBTR-000341 | GBC - Sustainability Accreditation | CN - Budget Hold | Variation | -509.48 | 509.48 | 2024-11-26
94 | DEWAN PVO 07 (P3 ) and RFC 008 (Adjustment) |  | AMA01003-RBTR-000346 | PS - Budget Hold | DAE -Prf Fees | Variation | -73361.38 | 73361.38 | 2024-12-09
95 | DEPA DVO 01 (PVO 01) & DVO 02 (PVO 02) - Adjustment |  | AMA01003-RBTR-000349 | Interior Fitout | CN - Budget Hold | Variation | -535044.11 | 535044.11 | 2024-12-11
96 | DEWAN DVO 13 / PVO 09 - Staff Canteen and Marina Operation Office (DEWAN) - Adjustment |  | AMA01003-RBTR-000356 | PS - Budget Hold | DAE -Prf Fees | Variation | -163131 | 163131 | 2024-12-24
97 | DEPA DVO 03 / PVO 003 - Changes in Back-of-House (BOH) Finishes Areas in AYC (L01 to L04) |  | AMA01003-RBTR-000357 | Interior Fitout | CN - Budget Hold | Variation | -684238.31 | 684238.31 | 2024-12-24
98 | ESCCO PVO 001 - Disassembly and Reassembly of Electronic Items from VT Fixtures |  | AMA01003-RBTR-000377 | CN - Budget Hold | ESCCO - Vertical Transport | Variation | -123400 | 123400 | 2025-01-14 |  | DVO
99 | Contract Award to Al Fanar |  | AMA01003-RBTR-000368 | CN - Budget Hold | Al Fanar - MEP Labour Supply |  | -23125000 | 23125000 | 2025-01-06
100 | DEPA PVO 008 - ID Finishes on Vertical Transport Fixture Elements |  | AMA01003-RBTR-000370 | CN - Budget Hold | Interior Fitout | Variation | -370875 | 370875 | 2025-01-06 |  | no
101 | SAB PVO 027 - Omission of Reflective Metal Cladding from Saudi Arabian Baytur (SAB) Contract |  | AMA01003-RBTR-000369 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -1457002.08 | 1457002.08 | 2025-01-06 |  | dvo
102 | Amaala Owner Controlled Insurance Program (Al Rajhi Takaful) |  | AMA01003-RBTR-000378 | CN - Budget Hold | Al Rahji Takaful - Owner Controlled Insurance Program |  | -63223 | 63223 | 2025-01-14
103 | Budget Transfer Request (BTR) of SAR 26,781,117 from overall Contingency Control Account 1.DC.98998.98.98 to AMAALA Yacht Club, split between (a) Construction (CN) Control Account 1.TB01.003.01.CN & FF&E & OSE Control Account 1.TB01 |  | AMA99999-WTRAN-004123 | IDC98998.98 (20-Jan-2025) | CN - Budget Hold | Additional Budget | 0 | 26351961 | 2025-01-20 |  | 26781117
104 | Budget Transfer Request (BTR) of SAR 26,781,117 from overall Contingency Control Account 1.DC.98998.98.98 to AMAALA Yacht Club, split between (a) Construction (CN) Control Account 1.TB01.003.01.CN & FF&E & OSE Control Account 1.TB01 |  | AMA99999-WTRAN-004123 | IDC98998.98 (20-Jan-2025) | FF&E OSE - Budget Hold | Additional Budget | 0 | 429156 | 2025-01-20
105 | Contract Award (C33) Yacht Club – Reflective Ceiling Works Package (ARMETAL) |  | AMA01003-RBTR-000382 | CN - Budget Hold | ARMETAL - Reflective ceiling |  | -7129950 | 7129950 | 2025-01-22
106 | Euro Consult For Engineering Consultancy - Accommodation and Transportation |  | AMA01003-RBTR-000393 | PS - Budget Hold | ECC-Mgt Fees (Accom & Transpo) |  | -54000 | 54000 | 2025-02-19
107 | AL Fanar PVO 001 - Al Fanar's Construction Manpower Services Extension |  | AMA01003-RBTR-000429 | CN - Budget Hold | Al Fanar - MEP Labour Supply | Variation | -31270936 | 31270936 | 2025-04-05 |  | dvo
108 | DEPA PVO 009 (Installation of MDF Ceiling) & PVO 010 (AYC Column Cladding) |  | AMA01003-RBTR-000396 | CN - Budget Hold | Interior Fitout | Variation | -320955 | 320955 | 2025-02-25 |  | dvo
109 | SAB DVO 018 / PVO-015 - Omission of Back-of-House (BOH) Finishes in L01 to L04 from SAB Contract |  | AMA01003-RBTR-000390 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -51035.34 | 51035.34 | 2025-02-16
110 | Contract Award (003C35) - Abu Dhabi Precast LLC |  | AMA01003-RBTR-000412 | CN - Budget Hold | ABU DHABI PRECAST - GRC Cladding |  | -7850127.97 | 7850127.97 | 2025-03-16
111 | MAS PVO 001 - Amphitheatre Works (MAS) |  | AMA01003-RBTR-000403 | CN - Budget Hold | MAS - Amphitheatre | Variation | -249727.67 | 249727.67 | 2025-02-24 |  | dvo
112 | DEPA DVO 04 (PVO 04) & DVO 07 (PVO 07) - Adjustment |  | AMA01003-RBTR-000410 | Interior Fitout | CN - Budget Hold | Variation | -111777.24 | 111777.24 | 2025-03-16
113 | MAS PVO 001 - Additional Manpower and Supervision Supply |  | AMA01003-RBTR-000411 | CN - Budget Hold | MAS - Labour Supply - Wet Works | Variation | -13737620 | 13737620 | 2025-03-16 |  | dvo
114 | SAB DVO 13 / PVO 17 PVO 017 - Facade Glazing and Glazing Doors Omission from SAB Scope - Adjustment |  | AMA01003-RBTR-000427 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -360 | 360 | 2025-04-05
115 | Budget Transfer to support financing SAB |  | 1TB01003.01.IAT.I-BTR-0009 | Marina Village Wide - CN Budget Hold | CN - Budget Hold | Additional Budget | 0 | 40000000 | 2025-03-19
116 | Euro Consult For Engineering Consultancy - Accommodation and Transportation |  | AMA01003-RBTR-000428 | ECC-Mgt Fees (Accom & Transpo) | ECC-Mgt Fees (Accom & Transpo) | to Provisional Sum | 0 | 0 | 2025-04-05
117 | BTR for Cancellation of SAB PVO 21, 22 & 23 |  | AMA01003-RBTR-000426 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold | Variation | -1350817.64 | 1350817.64 | 2025-04-05
| DEWAN Earlier VOs included in the ACC Baseline Budget (Not in ACC BTRs - to balance the remaing PS Budget Hold) |  |  | PS - Budget Hold | PS - Budget Hold
107 | AVV 001 -Additional Design and Technical Consultancy - Water Feature/ Smoke Extract/ Signage. |  |  | PS - Budget Hold | DAE -Prf Fees | Variation | -197496.2 | 197496.2 | 2021-08-09
108 | AVV 002 -Additional Design and Technical Services - Conversion of the Cpncept Rhino Model into Revit. |  |  | PS - Budget Hold | DAE -Prf Fees | Variation | -138200 | 138200 | 2021-08-09
109 | AVV 003 -Revised BIM Guidelines. |  |  | PS - Budget Hold | DAE -Prf Fees | Variation | -550000 | 550000 | 2022-01-24
110 | DVO 004 Revised Sustainability Guidelines and Change Cooling System |  |  | PS - Budget Hold | DAE -Prf Fees | Variation | -47243.52 | 47243.52 | 2022-04-10
111 | DVO 003 DEWAN Appointment of KSA Civil Defense Registered Consultant. |  |  | PS - Budget Hold | DAE -Prf Fees | Variation | -60500 | 60500 | 2022-04-10
112 | DVO 002 Front of House FF&E Consultant - Intercon |  |  | PS - Budget Hold | DAE -Prf Fees | Variation | -275000 | 275000 | 2022-08-22 |  | -113.78
| Balancing for CN Budget Hold |  |  | CN - Budget Hold | CN - Budget Hold | Balancing | -339416.93 | 339416.93 | 2025-04-10 |  | 339416.93 | -33147.18 | 33147.18 | 183967.01
| Balancing for CN Budget Hold |  |  | CN - Budget Hold | CN - Budget Hold |  | -182876.69 | 182876.69 |  |  | 97528.26 | 90607.63 | 31245.99
113 | New Contract Award (D24) - Hassan Allam Construction Saudi Limited - Scaffolding Services |  | AMA01003-RBTR-000565 | CN - Budget Hold | HAS - External Scaffolding Works |  | -3096124.9 | 3096124.9 | 2025-04-14
114 | BTR for New Contract - M Mohammad Alharbi Medical Company- Direct Payment on Bhalf of Saudi Arabian Baytur | Prelims - Mohammad Alharbi Medical Company | AMA01003-RBTR-000477 | CN - Budget Hold | Prelims - Mohammad Alharbi Medical Company |  | -14457.6 | 14457.6 | 2025-04-10
115 | BTR for New Contract - Al Anan Travels and Tours - Direct Payment on Bhalf of Saudi Arabian Baytur | Prelims - Al Anan Travels and Tours | AMA01003-RBTR-000485 | CN - Budget Hold | Prelims - Al Anan Travels and Tours |  | -26209.57 | 26209.57 | 2025-04-10
116 | BTR for New Contract - Al drees Petroleum- Direct Payment on Bhalf of Saudi Arabian Baytur | Prelims - Al drees Petroleum | AMA01003-RBTR-000484 | CN - Budget Hold | Prelims - Al drees Petroleum |  | -6521.74 | 6521.74 | 2025-04-10
117 | BTR for New Contract - Salim Hamed Cleaning- Direct Payment on Bhalf of Saudi Arabian Baytur | Prelims - Salim Hamed Cleaning | AMA01003-RBTR-000476 | CN - Budget Hold | Prelims - Salim Hamed Cleaning |  | -10869.57 | 10869.57 | 2025-04-10
118 | BTR for New Contract - Clean Coast for Contracting- Direct Payment on Bhalf of Saudi Arabian Baytur | Prelims - Clean Coast for Contracting | AMA01003-RBTR-000483 | CN - Budget Hold | Prelims - Clean Coast for Contracting |  | -49300 | 49300 | 2025-04-10
119 | BTR for New Contract - Sami General Contracting Est- Direct Payment on Bhalf of Saudi Arabian Baytur | Prelims - Sami General Contracting | AMA01003-RBTR-000490 | CN - Budget Hold | Prelims - Sami General Contracting |  | -19950 | 19950 | 2025-04-10
120 | BTR for New Contract - Eastern Horizons Foundation Transportation Comp- Direct Payment on Bhalf of Saudi Arabian Baytur | Prelims - Eastern Horizons Foundation Transportation Comp | AMA01003-RBTR-000482 | CN - Budget Hold | Prelims - Eastern Horizons Foundation Transportation Comp |  | -14349 | 14349 | 2025-04-10
121 | BTR for New Contract - Jak Generation Cont Co LLC- Direct Payment on Bhalf of Saudi Arabian Baytur | Prelims - Jak Generation Cont Co LLC | AMA01003-RBTR-000480 | CN - Budget Hold | Prelims - Jak Generation Cont Co LLC |  | -169356.59 | 169356.59 | 2025-04-10
122 | BTR for New Contract - Intelligent General Cont Co Equipment - Industrial Forklift & 5ton- Direct Payment on Bhalf of Saudi Arabian Baytur | Prelims - Intelligent General Cont Co Equipment | AMA01003-RBTR-000481 | CN - Budget Hold | Prelims - Intelligent General Cont Co Equipment |  | -70616.35 | 70616.35 | 2025-04-10
123 | New Contract - Al Rai Modern Water Factory - Direct Payment on Bhalf of Saudi Arabian Baytur | Prelims - Al Rai Modern Water Factory | AMA01003-RBTR-000486 | CN - Budget Hold | Prelims - Al Rai Modern Water Factory |  | -86695 | 86695 | 2025-04-10
124 | BTR for New Contract - Madar Building material Co- Direct Payment on Bhalf of Saudi Arabian Baytur | Direct Works - Madar Building material Co | AMA01003-RBTR-000478 | CN - Budget Hold | Direct Works - Madar Building material Co |  | -11320 | 11320 | 2025-04-10
125 | BTR for New Contract - Juffali Technical Equipment Company- Direct Payment on Bhalf of Saudi Arabian Baytur | Direct Works - Juffali Technical Equipment Company | AMA01003-RBTR-000479 | CN - Budget Hold | Direct Works - Juffali Technical Equipment Company |  | -6056.8 | 6056.8 | 2025-04-10
126 | BTR for New Contract - Factory of USG Middle East Ltd. Co - Direct Payment on Bhalf of Saudi Arabian Baytur | Direct Works - USG Middle East Ltd. Co | AMA01003-RBTR-000488 | CN - Budget Hold | Direct Works - USG Middle East Ltd. Co |  | -22017.6 | 22017.6 | 2025-04-10
127 | BTR for New Contract - Abu Dhabi Precast - Direct Payment on Bhalf of Saudi Arabian Baytur | Direct Works - Abu Dhabi Precast | AMA01003-RBTR-000487 | CN - Budget Hold | Direct Works - Abu Dhabi Precast |  | -984141.69 | 984141.69 | 2025-04-10
128 | BTR for New Contract - Saad Al Essa - Metal Industry- Direct Payment on Bhalf of Saudi Arabian Baytur | Direct Works - SAMIF | AMA01003-RBTR-000489 | CN - Budget Hold | Direct Works - SAMIF |  | -697765.48 | 697765.48 | 2025-04-10
129 | BTR for DVO 001 / PVO 001 - Amphitheatre Works (MAS) |  | AMA01003-RBTR-000566 | MAS - Amphitheatre | CN - Budget Hold |  | -44069.59 | 44069.59 | 2025-04-14
130 | BTR for New Contract Award (003C72) - SAUDI MANPOWER SOLUTIONS CO - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - SAUDI MANPOWER SOLUTIONS CO | AMA01003-RBTR-000549 | CN - Budget Hold | Direct Works - SAUDI MANPOWER SOLUTIONS CO |  | -315934.57 | 315934.57 | 2025-04-14
131 | BTR for New Contract Award (003C59) - Fosam Company LTD - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Fosam Company LTD | AMA01003-RBTR-000551 | CN - Budget Hold | Direct Works - Fosam Company LTD |  | -3620 | 3620 | 2025-04-14
132 | BTR for New Contract Award (003C56) - Glow Arabia Trading - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Glow Arabia Trading | AMA01003-RBTR-000552 | CN - Budget Hold | Direct Works - Glow Arabia Trading |  | -6550 | 6550 | 2025-04-14
133 | BTR for New Contract Award (003C54) - NEXTWARE INTERNATIONAL SUPPLY - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - NEXTWARE INTERNATIONAL SUPPLY | AMA01003-RBTR-000553 | CN - Budget Hold | Prelims - NEXTWARE INTERNATIONAL SUPPLY |  | -1845 | 1845 | 2025-04-14
134 | BTR for New Contract Award (003C51) - BROOQ ALAMAAN TRAD COMPANY - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - BROOQ ALAMAAN TRAD COMPANY | AMA01003-RBTR-000554 | CN - Budget Hold | Direct Works - BROOQ ALAMAAN TRAD COMPANY |  | -97154.16 | 97154.16 | 2025-04-14
135 | BTR for New Contract Award (003C50) - Abeer Munawer Al Shamari - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Abeer Munawer Al Shamari | AMA01003-RBTR-000555 | CN - Budget Hold | Direct Works - Abeer Munawer Al Shamari |  | -459000 | 459000 | 2025-04-14
136 | BTR for New Contract Award (003C49) - Yaz Development Contracting - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Yaz Development Contracting | AMA01003-RBTR-000556 | CN - Budget Hold | Direct Works - Yaz Development Contracting |  | -46635 | 46635 | 2025-04-14
137 | BTR for New Contract Award (003C48) -National Fire Fighting Manufactureing Company - Naffco - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Naffco | AMA01003-RBTR-000557 | CN - Budget Hold | Direct Works - Naffco |  | -73286.96 | 73286.96 | 2025-04-14
138 | BTR for New Contract Award (003C47) -GESR Alarab - Direct Payment on Behalf of Saudi Arabian Baytur - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - GESR Alarab | AMA01003-RBTR-000558 | CN - Budget Hold | Direct Works - GESR Alarab |  | -119631.33 | 119631.33 | 2025-04-14
139 | BTR for New Contract Award (003C46) -Jameel Mohamed Hussain Alqatafa Cont Est - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Jameel Mohamed Hussain Alqatafa Cont Est | AMA01003-RBTR-000559 | CN - Budget Hold | Direct Works - Jameel Mohamed Hussain Alqatafa Cont Est |  | -90972.44 | 90972.44 | 2025-04-14
140 | BTR for New Contract Award (003C45) - Virtual Projects DMCC - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Virtual Projects DMCC | AMA01003-RBTR-000560 | CN - Budget Hold | Prelims - Virtual Projects DMCC |  | -51948.13 | 51948.13 | 2025-04-14
141 | BTR for New Contract Award (003C44) - Medtel WN - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - MEDTEL | AMA01003-RBTR-000561 | CN - Budget Hold | Direct Works - MEDTEL |  | -516902.89 | 516902.89 | 2025-04-14
142 | BTR for New Contract Award (003C41) - Raddad Al adinah - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Raddad Al adinah | AMA01003-RBTR-000562 | CN - Budget Hold | Prelims - Raddad Al adinah |  | -142131.61 | 142131.61 | 2025-04-14
143 | BTR for New Contract Award (003C40) - Noreom - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Noreom | AMA01003-RBTR-000563 | CN - Budget Hold | Direct Works - Noreom |  | -100641.6 | 100641.6 | 2025-04-14
144 | BTR for new Contract award - 003C39 - Isam Kabani & Partners - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Isam Kabani & Partners | AMA01003-RBTR-000564 | CN - Budget Hold | Direct Works - Isam Kabani & Partners |  | -28888.07 | 28888.07 | 2025-04-14
145 | BTR for New Contract Award (003C116) - ARABIAN TESTING EVOLUTION COMPANY Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - ARABIAN TESTING EVOLUTION COMPANY | AMA01003-RBTR-000548 | CN - Budget Hold | Direct Works - ARABIAN TESTING EVOLUTION COMPANY |  | -425440 | 425440 | 2025-04-14
146 | BTR for New Contract Award (003C115) - Ahmed Bin Salem Bin Dagher Al-Balawi EST - (Water + Diesel supply ) - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Ahmed Bin Salem Bin Dagher | AMA01003-RBTR-000550 | CN - Budget Hold | Prelims - Ahmed Bin Salem Bin Dagher |  | -133940 | 133940 | 2025-04-14
147 | Termination and Settlement Agreement - Abu Dhabi Precast Contract |  |  | ABU DHABI PRECAST - GRC Cladding | CN - Budget Hold |  | -7850127.97 | 7850127.97 | 2025-04-17
148 | BTR for New Contract Award (003C83) - Yaz Development Contracting - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Yaz Development Contracting | AMA01003-RBTR-000570 | CN - Budget Hold | Direct Works - Yaz Development Contracting |  | -51063 | 51063 | 2025-04-20
149 | BTR for New Contract Award (003C87) - Bahamdoon Trading Co - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Bahamdoon Trading | AMA01003-RBTR-000608 | CN - Budget Hold | Prelims - Bahamdoon Trading |  | -1535 | 1535 | 2025-04-22
150 | BTR for New Contract Award (003C86) - Wood Expert - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Wood Expert | AMA01003-RBTR-000605 | CN - Budget Hold | Direct Works - Wood Expert |  | -17725 | 17725 | 2025-04-22
151 | BTR for New Contract Award (003C85) - Lumi Rentals Co - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Lumi Rentals | AMA01003-RBTR-000606 | CN - Budget Hold | Prelims - Lumi Rentals |  | -6142.43 | 6142.43 | 2025-04-22
152 | BTR for New Contract Award (003C84) - Energy & Building Masters - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Energy & Building Master | AMA01003-RBTR-000607 | CN - Budget Hold | Direct Works - Energy & Building Master |  | -58860 | 58860 | 2025-04-22
153 | BTR for New Contract Award (003C77) - Arab Co for Laboratories & Soil (ACES) - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - ACES | AMA01003-BTR-000584 | CN - Budget Hold | Direct Works - ACES |  | -5061.5 | 5061.5 | 2025-04-22
154 | BTR for New Contract Award (003C75) - Filter Expert Trading - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Filter Expert Trading | AMA01003-RBTR-000610 | CN - Budget Hold | Prelims - Filter Expert Trading |  | -8565 | 8565 | 2025-04-22
155 | BTR for New Contract Award (003C74) - Abu Nayyan Trading - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Abu Nayyan | AMA01003-RBTR-000611 | CN - Budget Hold | Prelims - Abu Nayyan |  | -17800 | 17800 | 2025-04-22
156 | BTR for New Contract Award (003C99) - The international company for building materials LTD Binex - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - International Company for Building Materials LTD | AMA01003-RBTR-000691 | CN - Budget Hold | Direct Works - International Company for Building Materials LTD |  | -37118.9 | 37118.9 | 2025-04-23
157 | BTR for New Contract Award (003C98) - Juffali Technical Equipment Company - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Juffali Technical Equipment Company | AMA01003-RBTR-000692 | CN - Budget Hold | Direct Works - Juffali Technical Equipment Company |  | -3785.5 | 3785.5 | 2025-04-23
158 | BTR for New Contract Award (003C97) - Glow Arabia Trading - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Glow Arabia Trading | AMA01003-RBTR-000679 | CN - Budget Hold | Direct Works - Glow Arabia Trading |  | -10345 | 10345 | 2025-04-23
159 | BTR for New Contract Award (003C96) - FACTORY OF USG MIDDLE EAST LTD. CO - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - USG Middle East Ltd. Co | AMA01003-RBTR-000693 | CN - Budget Hold | Direct Works - USG Middle East Ltd. Co |  | -17937.22 | 17937.22 | 2025-04-23
160 | BTR for New Contract Award (003C95) - Yaz Development Contracting - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Yaz Development Contracting | AMA01003-RBTR-000694 | CN - Budget Hold | Direct Works - Yaz Development Contracting |  | -94000 | 94000 | 2025-04-23
161 | BTR for New Contract Award (003C94) - National Fire Fighting Manufacturing Company - NAFFCO - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Naffco | AMA01003-RBTR-000695 | CN - Budget Hold | Direct Works - Naffco |  | -36872.54 | 36872.54 | 2025-04-23
162 | BTR for New Contract Award (003C93) - GESR ALARAB - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - GESR Alarab | AMA01003-RBTR-000696 | CN - Budget Hold | Direct Works - GESR Alarab |  | -224000 | 224000 | 2025-04-23
163 | BTR for New Contract Award (003C92) - Al Hayat Investment -Water features and pool works - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Al Hayat | AMA01003-RBTR-000697 | CN - Budget Hold | Direct Works - Al Hayat |  | -254143.39 | 254143.39 | 2025-04-23
164 | BTR for New Contract Award (003C91) - Medtel - Façade Rain screen - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - MEDTEL | AMA01003-RBTR-000698 | CN - Budget Hold | Direct Works - MEDTEL |  | -171879.82 | 171879.82 | 2025-04-23
165 | BTR for New Contract Award (003C90) - SAAD Al ESSA Metal industry - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - SAMIF | AMA01003-RBTR-000699 | CN - Budget Hold | Direct Works - SAMIF |  | -1116113.3 | 1116113.3 | 2025-04-23
166 | BTR for New Contract Award (003C89) - ISAM KABBANI AND PARTNERS FOR CONSTRUCTION - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Isam Kabani & Partners | AMA01003-RBTR-000700 | CN - Budget Hold | Direct Works - Isam Kabani & Partners |  | -161811.66 | 161811.66 | 2025-04-23
167 | BTR for New Contract Award (003C113) - Saint Gobain (Sodamco industrial) - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works -Saint Gobain | AMA01003-RBTR-000677 | CN - Budget Hold | Direct Works -Saint Gobain |  | -115601.47 | 115601.47 | 2025-04-23
168 | BTR for New Contract Award (003C112) - Ihsan Muhammed Thakir Idress Trading - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Ihsan Muhammed Thakir Idress Trading | AMA01003-RBTR-000678 | CN - Budget Hold | Prelims - Ihsan Muhammed Thakir Idress Trading |  | -27500 | 27500 | 2025-04-23
169 | BTR for New Contract Award (003C111) - Ramzi Abbas Mohd. Sayed Est. - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Ramzi Abbas Mohd. Sayed Est. | AMA01003-RBTR-000680 | CN - Budget Hold | Prelims - Ramzi Abbas Mohd. Sayed Est. |  | -48767 | 48767 | 2025-04-23
170 | BTR for New Contract Award (003C110) - AAMTAC Compant LTD - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works- AAMTAC Company LTD | AMA01003-RBTR-000681 | CN - Budget Hold | Direct Works- AAMTAC Company LTD |  | -22553 | 22553 | 2025-04-23
171 | BTR for New Contract Award (003C108) - M Mohammad Alharbi Medical company (Al Bashri) - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Mohammad Alharbi Medical Company | AMA01003-RBTR-000682 | CN - Budget Hold | Prelims - Mohammad Alharbi Medical Company |  | -15876.8 | 15876.8 | 2025-04-23
172 | BTR for New Contract Award (003C107) - SAUDI MANPOWER SOLUTIONS CO - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - SAUDI MANPOWER SOLUTIONS CO | AMA01003-RBTR-000683 | CN - Budget Hold | Direct Works - SAUDI MANPOWER SOLUTIONS CO |  | -61829.46 | 61829.46 | 2025-04-23
173 | BTR for New Contract Award (003C106) - Al Drees Petroleum - Fuel for Vehicles - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Al drees Petroleum | AMA01003-RBTR-000684 | CN - Budget Hold | Prelims - Al drees Petroleum |  | -6521.74 | 6521.74 | 2025-04-23
174 | BTR for New Contract Award (003C105) - Clean Coast for Contracting - (Water + Diesel supply ) - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Clean Coast for Contracting | AMA01003-RBTR-000685 | CN - Budget Hold | Prelims - Clean Coast for Contracting |  | -27800 | 27800 | 2025-04-23
175 | BTR for New Contract Award (003C104) - SAMI GENERAL CONTRACTING EST.- Sewage Removal - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Sami General Contracting | AMA01003-RBTR-000687 | CN - Budget Hold | Prelims - Sami General Contracting |  | -21350 | 21350 | 2025-04-23
176 | BTR for New Contract Award (003C103) - JAK GENERATION GEN CONT CO LLC - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Jak Generation Cont Co LLC | AMA01003-RBTR-000686 | CN - Budget Hold | Prelims - Jak Generation Cont Co LLC |  | -100373.12 | 100373.12 | 2025-04-23
177 | BTR for New Contract Award (003C102) - Intelligent General Cont. co. - Equipment - Industrial Forklift &5ton - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Intelligent General Cont Co Equipment | AMA01003-RBTR-000688 | CN - Budget Hold | Prelims - Intelligent General Cont Co Equipment |  | -11000 | 11000 | 2025-04-23
178 | BTR for New Contract Award (003C101) - AL RAYI WATER PLANT FACTORY - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - Al Rayi Water | AMA01003-RBTR-000689 | CN - Budget Hold | Prelims - Al Rayi Water |  | -18047 | 18047 | 2025-04-23
179 | BTR for New Contract Award (003C100) - Fosam Company LTD - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - Fosam Company LTD | AMA01003-RBTR-000690 | CN - Budget Hold | Direct Works - Fosam Company LTD |  | -36950 | 36950 | 2025-04-23
180 | BTR for New Contract Award (003C118) - (March) DOSAR Al Najd - Direct Payment on Behalf of Saudi Arabian Baytur | Direct Works - DOSAR Al Najd | AMA01003-RBTR-000707 | CN - Budget Hold | Direct Works - DOSAR Al Najd |  | -123937.39 | 123937.39 | 2025-04-28
182 | BTR for New Contract Award (003C109) - (March) GLSAN CONTRACTING COMPANY - Direct Payment on Behalf of Saudi Arabian Baytur | Prelims - GLSAN Contracting Company | AMA01003-RBTR-000708 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -1773295.38 | 1773295.38 | 2025-04-28
183 | BTR for DVO 001 / PVO 001 - ESCCO DVO 001 |  | AMA01003-RBTR-000740 | ESCCO - Vertical Transport | CN - Budget Hold |  | -45975 | 45975 | 2025-05-12
184 | BTR for PVO 001 - Aluminum Flashing |  | AMA01003-RBTR-000739 | CN - Budget Hold | Façade & Glazing Works |  | -478548 | 478548 | 2025-05-12 |  | dvo
185 | BTR for PVO 011 - Installation of Ceilings to Storage Rooms |  |  | CN - Budget Hold | DEPA Interior Fitout |  | -34684 | 34684 | 2025-05-12 |  | dvo
186 | BTR for PVO 013 - Supply and Installation of Honeycomb Limestones |  | AMA01003-RBTR-000738 | CN - Budget Hold | DEPA Interior Fitout |  | -850370.6 | 850370.6 | 2025-05-12 |  | no
187 | BTR for New Contract Award (003C82) - GSR - (Jan/Feb) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000726 | CN - Budget Hold | Direct Works - GESR Alarab |  | -115200.54 | 115200.54 | 2025-05-12 |  | 260501.21 | May Direct Payment
188 | AFA - (Jan/Feb) Direct Payment on Behalf of Saudi Arabian Baytur (1) |  | AMA01003-RBTR-000727 | CN - Budget Hold | Direct Works - Jameel Mohamed Hussain Alqatafa Cont Est |  | -36285.34 | 36285.34 | 2025-05-12
189 | GLS - (Jan/Feb) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000728 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -86956.52 | 86956.52 | 2025-05-12
190 | BTR for New Contract Award (003C67) - DGH - (Jan/Feb) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000729 | CN - Budget Hold | Prelims - Ahmed Bin Salem Bin Dagher |  | -22058.81 | 22058.81 | 2025-05-12
191 | BTR for New Contract Award - JEN - Third-Party Authority for Fire and Life Safety Review & Certification Endorsement (Call off Order No: 030) |  | AMA01003-RBTR-000741 | PS - Budget Hold | Jensen Hughes-Prf Fees |  | -38103.2 | 38103.2 | 2025-05-12
192 | BTR for New Contract Award (003C150) - Al Rajhi Takaful - AMAALA - OCIP Premium Declaration 9 for 16 October 2024 - 15 January 2025 |  | AMA01003-RBTR-000748 | CN - Budget Hold | Al Rahji Takaful - Owner Controlled Insurance Program |  | -10747.78 | 10747.78 | 2025-05-05
193 | BTR for PVO 012 - Supply and Installation of Additional Millwork to the Show Kitchens |  | AMA01003-RBTR-000757 | CN - Budget Hold | DEPA Interior Fitout |  | -312470.43 | 312470.43 | 2025-05-25 |  | no
194 | BTR for PVO 001 - Supply and Installation of Additional Kitchen Shelf Opening Hatches |  | AMA01003-RBTR-000758 | CN - Budget Hold | RAQTAN - Kitchen and Laundry |  | -15939 | 15939 | 2025-05-25 |  | dvo
195 | BTR for PVO 028 - Changes in materials of Grand Stair Handrail |  | AMA01003-RBTR-000760 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV |  | -856801.79 | 856801.79 | 2025-05-26 |  | dvo
196 | BTR for PVO 009 / DVO 009 - Installation of MEF Platform/Ceiling |  | AMA01003-RBTR-000779 | DEPA Interior Fitout | CN - Budget Hold |  | -5290 | 5290 | 2025-07-01
197 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Direct Works - Wood Expert |  | -1750 | 1750 | 2025-06-18
198 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -14278.07 | 14278.07 | 2025-06-18
199 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Direct Works - Abeer Munawer Al Shamari |  | -141365.93 | 141365.93 | 2025-06-18
200 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Direct Works - Isam Kabani & Partners |  | -83164.12 | 83164.12 | 2025-06-18
201 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Medtel - STO Façade Mock-up |  | -244899.26 | 244899.26 | 2025-06-18
202 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Direct Works - GESR Alarab |  | -224000 | 224000 | 2025-06-18
203 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Direct Works - Yaz Development Contracting |  | -94000 | 94000 | 2025-06-18
204 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Direct Works - BROOQ ALAMAAN TRAD COMPANY |  | -5930.56 | 5930.56 | 2025-06-18
205 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Prelims - Masa Equipment Est |  | -123000 | 123000 | 2025-06-18
206 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Direct Works - Glow Arabia Trading |  | -2625 | 2625 | 2025-06-18
207 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Direct Works - Madar Building material Co |  | -1500 | 1500 | 2025-06-18
208 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Direct Works - International Company for Building Materials LTD |  | -23368 | 23368 | 2025-06-18
209 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Prelims - Al Rayi Water |  | -28608 | 28608 | 2025-06-18
210 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Prelims - Jak Generation Cont Co LLC |  | -2500 | 2500 | 2025-06-18
211 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Prelims - Sami General Contracting |  | -33425 | 33425 | 2025-06-18
212 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Prelims - Clean Coast for Contracting |  | -39500 | 39500 | 2025-06-18
213 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Prelims - Mohammad Alharbi Medical Company |  | -12000 | 12000 | 2025-06-18
214 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -100000 | 100000 | 2025-06-18
215 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000768 | CN - Budget Hold | Prelims - Al Tala'a International Transportation Co |  | -6608.7 | 6608.7 | 2025-06-18
216 | BTR for VAT Adjustment for New Contract Award (003C7) |  | AMA01003-RBTR-000780 | Direct Works - ACES | CN - Budget Hold |  | -660.2 | 660.2 | 2025-07-01
217 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000767 | CN - Budget Hold | Direct Works - Alcatop |  | -545237.5 | 545237.5 | 2025-06-18
218 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000767 | CN - Budget Hold | Direct Works - Saveto Saudi Vetonit Co Ltd |  | -2730 | 2730 | 2025-06-18
219 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000767 | CN - Budget Hold | Prelims - Al Anan Travels and Tours |  | -34071.88 | 34071.88 | 2025-06-18
220 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000767 | CN - Budget Hold | Prelims - Saudi Brokers |  | -59606.12 | 59606.12 | 2025-06-18
221 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000774 | CN - Budget Hold | Direct Works -Saint Gobain |  | -4000 | 4000 | 2025-06-24
222 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000774 | CN - Budget Hold | Direct Works - Abu Dhabi Precast |  | -1096087.69 | 1096087.69 | 2025-06-24
223 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000774 | CN - Budget Hold | Prelims - Intelligent General Cont Co Equipment |  | -7800 | 7800 | 2025-06-24
224 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000774 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -606213.26 | 606213.26 | 2025-06-24
225 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000774 | CN - Budget Hold | Direct Works - Top Construction Co Ltd |  | -43846.11 | 43846.11 | 2025-06-24
226 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000774 | CN - Budget Hold | Direct Works - TBK Metal |  | -10690 | 10690 | 2025-06-24
227 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000774 | CN - Budget Hold | Prelims - Aknan Al Bena |  | -75000 | 75000 | 2025-06-24
228 | BTR for (April) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000774 | CN - Budget Hold | Prelims - Al drees Petroleum |  | -21739.13 | 21739.13 | 2025-06-24
229 | Inter Program Budget Transfer from 1.RI.12.073.01.CN to 1.TB.01.003.01.CN |  |  |  | CN - Budget Hold |  | 0 | 62089112 | 2025-06-29
230 | DEPA PVO 016 |  | AMA01003-RBTR-000799 / AMA01003-RBTR-000835 | CN - Budget Hold | DEPA Interior Fitout |  | -21275.25 | 21275.25 | 2025-07-14 |  | DVO
231 | DEPA PVO 015 |  | AMA01003-RBTR-000799 / AMA01003-RBTR-000835 | CN - Budget Hold | DEPA Interior Fitout |  | -2521135.52 | 2521135.52 | 2025-07-14 |  | no
232 | Al fanar -PVO 002 |  | AMA01003-RBTR-000799 | CN - Budget Hold | Al Fanar - MEP Labour Supply |  | -9188438.51 | 9188438.51 | 2025-07-14
233 | BTR for New Contract Award (003C152) - LFS - (Apr) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000791 | CN - Budget Hold | Direct Works - Lakeshore |  | -624120.15 | 624120.15 | 2025-07-08
234 | PVO 029 (Mesh Grating and Platform) |  | AMA01003-RBTR-000792 | CN - Budget Hold | Saudi Baytur - Main Works |  | -275000 | 275000 | 2025-07-08 |  | dvo
235 | PVO 027 / DVO 022 (Omission of Reflective Ceiling)_adjustment |  | AMA01003-RBTR-000788 | CN - Budget Hold | Saudi Baytur - Main Works |  | -54637.58 | 54637.58 | 2025-07-07
236 | PVO 030 - Direct Payments (Jan, Feb and Mar 2025 invoices) |  | AMA01003-RBTR-000788 | Saudi Baytur - Main Works | CN - Budget Hold |  | -8870230.27 | 8870230.27 | 2025-07-07 |  | dvo
237 | PVO 010 / DVO 010 (Addl Wall and Column Partitions)_adjustment |  | AMA01003-RBTR-000800 | CN - Budget Hold | DEPA Interior Fitout |  | -52279.98 | 52279.98 | 2025-07-14
238 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Direct Works - Isam Kabani & Partners |  | -184185.7 | 184185.7 | 2025-07-27
239 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Direct Works - Abu Dhabi Precast |  | -232406.39 | 232406.39 | 2025-07-27
240 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Direct Works - SAMIF |  | -1719705.93 | 1719705.93 | 2025-07-27
241 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 / AMA01003-RBTR-000833 | CN - Budget Hold | Direct Works - MEDTEL |  | -337848.8 | 337848.8 | 2025-07-27
242 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -26105.01 | 26105.01 | 2025-07-27
243 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Direct Works - GESR Alarab |  | -233500 | 233500 | 2025-07-27
244 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Direct Works - Yaz Development Contracting |  | -94000 | 94000 | 2025-07-27
245 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Direct Works - TBK Metal |  | -9900 | 9900 | 2025-07-27
246 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Prelims - Al Rai Modern Water Factory |  | -20338.5 | 20338.5 | 2025-07-27
247 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Prelims - Intelligent General Cont Co Equipment |  | -25500 | 25500 | 2025-07-27
248 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Prelims - Jak Generation Cont Co LLC |  | -64500 | 64500 | 2025-07-27
249 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Prelims - Sami General Contracting |  | -18375 | 18375 | 2025-07-27
250 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Prelims - Clean Coast for Contracting |  | -27820 | 27820 | 2025-07-27
251 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Prelims - Salim Hamed Cleaning |  | -6521.74 | 6521.74 | 2025-07-27
252 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Prelims - Al Anan Travels and Tours |  | -16253.91 | 16253.91 | 2025-07-27
253 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Prelims - Mohammad Alharbi Medical Company |  | -26838.38 | 26838.38 | 2025-07-27
254 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Direct Works - Wood Expert |  | -3000 | 3000 | 2025-07-27
255 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -597310.83 | 597310.83 | 2025-07-27
256 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -100000 | 100000 | 2025-07-27
257 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Prelims - Ihsan Muhammed Thakir Idress Trading |  | -21500 | 21500 | 2025-07-27
258 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000834 | CN - Budget Hold | Direct Works - Top Construction Co Ltd |  | -4249.96 | 4249.96 | 2025-07-27
259 | 003F08 - CML - PVO 001 - SAR 822,640.54 |  | AMA01003-RBTR-000844 | CN - Budget Hold | CML-Mgt Fees |  | -822640.54 | 822640.54 | 2025-08-06 |  | dvo
260 | 1TB01003.01.FFEOSE.003F06.02-ADL - Variation |  | AMA01003-RBTR-000855 | CN - Budget Hold | Areen - FF&E OS&E Items |  | -568680.75 | 568680.75 | 2025-08-12
261 | Savings on DVO 023 against PVO value (Iroko Handrail) |  | AMA01003-RBTR-000854 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold |  | -179488.12 | 179488.12 | 2025-08-12
262.a | BTR for K&A PVO 003 (Extension) |  | AMA01003-RBTR-000856 | MS - Budget Hold | KAA-Mgt Fees |  | -569838.42 | 569838.42 | 2025-08-12
262.b | BTR for K&A PVO 003 (Extension) |  | AMA01003-RBTR-000856 | CN - Budget Hold | KAA-Mgt Fees |  | -1085561.38 | 1085561.38 | 2025-08-12 |  | dvo
263 | BTR for PVO 003 (Al Fanar) |  | AMA01003-RBTR-000859 | CN - Budget Hold | Al Fanar - MEP Labour Supply |  | -13280714 | 13280714 | 2025-08-18 |  | dvo
264 | BTR for (May) Direct Payment on Behalf of Saudi Arabian Baytur, Tower Crane Dismantling. |  | AMA01003-RBTR-000863 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -174000 | 174000 | 2025-08-20
265 | Savings on DVO 011 against PVO value (DEPA) |  |  | DEPA Interior Fitout | CN - Budget Hold |  | -7434.1 | 7434.1 | On process
265 | Overrun on DVO 001 against PVO value (CML) |  | AMA01003-RBTR-000873 | CN - Budget Hold | CML-Mgt Fees |  | -60000 | 60000 | 2025-09-14
266 | Overrun on DVO 003 against PVO value (Al Fanar) |  | AMA01003-RBTR-000880 | CN - Budget Hold | Al Fanar - MEP Labour Supply |  | -1276670.22 | 1276670.22 | 2025-09-21
267 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Fast Steps |  | -16550 | 16550 | 2025-09-15 |  | Fast Steps | GRP Ladder - Direct Works
268 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Glow Arabia Trading |  | -29940.5 | 29940.5 | 2025-09-15 |  |  | Copper tube , flare nuts
269 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Yaz Development Contracting |  | -94000 | 94000 | 2025-09-15
270 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Masa Equipment Est |  | -123000 | 123000 | 2025-09-15 |  |  | Fall protection rails
271 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Jak Generation Cont Co LLC |  | -2500 | 2500 | 2025-09-15 |  |  | Pest Control
272 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Top Construction Co Ltd |  | -47500 | 47500 | 2025-09-15 |  |  | Land Surveyor Crew July
273 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Isam Kabani & Partners |  | -254893.19 | 254893.19 | 2025-09-15 |  |  | Waterproofing and Moisture Protection packers
274 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Salim Hamed Cleaning |  | -6521.74 | 6521.74 | 2025-09-15 |  |  | Cleaning?
275 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Mohammad Alharbi Medical Company |  | -14630.7 | 14630.7 | 2025-09-15 |  |  | Nurse
276 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -150000 | 150000 | 2025-09-15 |  |  | SAB Salaries for July 2025
277 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - TBK Metal |  | -124665.4 | 124665.4 | 2025-09-15 |  |  | Railings
278 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - GESR Alarab |  | -160000 | 160000 | 2025-09-15 |  |  | Rental surveyor with Equipment
279 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - GESR Alarab |  | -128000 | 128000 | 2025-09-15 |  |  | Rental surveyor with Equipment
280 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Top Construction Co Ltd |  | -47500 | 47500 | 2025-09-15 |  |  | Land Surveyor Crew June
281 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Intelligent General Cont Co Equipment |  | -7500 | 7500 | 2025-09-15 |  |  | Rental charges for forklift
282 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Clean Coast for Contracting |  | -53815 | 53815 | 2025-09-15 |  |  | Supply of sweet water and diesel
283 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Energy & Building Master |  | -52974 | 52974 | 2025-09-15
284 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Juffali Technical Equipment Company |  | -2271.3 | 2271.3 | 2025-09-15 |  |  | Rebar cutter
285 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Al Rai Modern Water Factory |  | -26647 | 26647 | 2025-09-15
286 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -577369.19 | 577369.19 | 2025-09-15 |  |  | Salaries for April 2025
287 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Mohammad Alharbi Medical Company |  | -17330.7 | 17330.7 | 2025-09-15 |  |  | Nurse
288 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Clean Coast for Contracting |  | -32290 | 32290 | 2025-09-15 |  |  | Supply of sweet water and diesel
289 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Ihsan Muhammed Thakir Idress Trading |  | -12500 | 12500 | 2025-09-15 |  |  | Maintenance spare parts for Generator and Heavy Equipment
290 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Madar Building material Co |  | -1500 | 1500 | 2025-09-15 |  |  | Plywood
291 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -611972.33 | 611972.33 | 2025-09-15 |  |  | Salaries for July 2025
292 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Abeer Munawer Al Shamari |  | -161215 | 161215 | 2025-09-15 |  |  | EFFISUS Waterproofing
293 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Jak Generation Cont Co LLC |  | -20521.74 | 20521.74 | 2025-09-15 |  |  | Pest Control for June 2025
294 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Fast Steps |  | -5700 | 5700 | 2025-09-15 |  | Fast Stepls | GRP ladder
295 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Naffco |  | -76840.62 | 76840.62 | 2025-09-15 |  |  | Supply, Installation and Commissioning of Fire Fighting System IPC 05?
296 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works -Saint Gobain |  | -2700 | 2700 | 2025-09-15 |  |  | Weberep
297 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Sami General Contracting |  | -23800 | 23800 | 2025-09-15 |  |  | Transportation of sewage
298 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -74404.71 | 74404.71 | 2025-09-15 |  |  | ELV Engineer for August and September 2025
299 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Energy & Building Master |  | -5886 | 5886 | 2025-09-15
300 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Ihsan Muhammed Thakir Idress Trading |  | -15000 | 15000 | 2025-09-15 |  |  | Maintenance spare parts for Generator and Heavy Equipment
301 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -150000 | 150000 | 2025-09-15 |  |  | Petty cash for June 2025
302 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - BROOQ ALAMAAN TRAD COMPANY |  | -27221 | 27221 | 2025-09-15 |  |  | FIS EM Plus
303 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Yaz Development Contracting |  | -94000 | 94000 | 2025-09-15 |  |  | Surveying team
304 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - Isam Kabani & Partners |  | -229668.44 | 229668.44 | 2025-09-15 |  |  | Waterprrofing and Moisture Protection - Injection Packers
305 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Intelligent General Cont Co Equipment |  | -12500 | 12500 | 2025-09-15 |  |  | Rental charge for forklift
306 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -568712.14 | 568712.14 | 2025-09-15 |  |  | Testing and commissioning for Fire Alarm System
307 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Direct Works - TBK Metal |  | -49793.6 | 49793.6 | 2025-09-15
308 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Sami General Contracting |  | -29750 | 29750 | 2025-09-15 |  |  | Transportation of sewage
309 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000875 | CN - Budget Hold | Prelims - Al Rai Modern Water Factory |  | -26022.5 | 26022.5 | 2025-09-15
310 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000874 | CN - Budget Hold | Direct Works - TANSEEQ |  | -9915.37 | 9915.37 | 2025-09-14 |  | Tanseeq LLC | Road Stud
311 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000874 | CN - Budget Hold | Medtel - STO Façade Mock-up |  | -925758.13 | 925758.13 | 2025-09-14
312 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000874 | CN - Budget Hold | Medtel - STO Façade Mock-up |  | -884394.44 | 884394.44 | 2025-09-14
313 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000874 | CN - Budget Hold | Direct Works - SAMIF |  | -1898500.81 | 1898500.81 | 2025-09-14
314 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000874 | CN - Budget Hold | ABU DHABI PRECAST - GRC Cladding |  | -286304.52 | 286304.52 | 2025-09-14
315 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000874 | CN - Budget Hold | Direct Works - Alcatop |  | -223673.22 | 223673.22 | 2025-09-14
316 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000874 | CN - Budget Hold | ABU DHABI PRECAST - GRC Cladding |  | -305481.27 | 305481.27 | 2025-09-14
317 | PVO 031 - Direct Payments (Apr and May 2025 invoices) |  |  | Saudi Baytur - Main Works | CN - Budget Hold |  | -7235632.79 | 7235632.79 | Under Planning/ BTR Not Process |  | Committed | 0
318 | Savings on DVO 001 against PVO value (RAQTAN) |  | AMA01003-RBTR-000900 | RAQTAN - Kitchen and Laundry | CN - Budget Hold |  | -5796 | 5796 | 2025-10-30
318 | PVO 32 for SAB - Replacement of Railings with Road Stud. |  | AMA01003-RBTR-000900 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV |  | -27800 | 27800 | 2025-10-30 |  | dvo
319 | BTR for the award to GST Sustainability Accreditation Services |  | AMA01003-RBTR-000895 | CN - Budget Hold | GST- Sustainability Accreditation Services |  | -133000 | 133000 | 2025-10-26
320 | Savings on DVO 001 against PVO value (RAQTAN) |  | AMA01003-RBTR-000901 | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold |  | -46930 | 46930 | 2025-10-30
321 | BTR for the award to Tabuk Investment (Enviro) |  | AMA01003-RBTR-000909 | CN - Budget Hold | Enviro - Deep Cleaning |  | -799625.31 | 799625.31 | 2025-11-19
322 | BTR for Direct Payment (August 2025) |  | AMA01003-RBTR-000885 | CN - Budget Hold | Direct Works - Al Hayat |  | -592674 | 592674 | 2025-10-14
323 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Direct Works - Isam Kabani & Partners |  | -158996.33 | 158996.33 | 2025-10-30
324 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Direct Works - SAMIF |  | -875601.38 | 875601.38 | 2025-10-30
325 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Direct Works - Abu Dhabi Precast |  | -30274.06 | 30274.06 | 2025-10-30
326 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Direct Works - Alcatop |  | -250480.81 | 250480.81 | 2025-10-30
327 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Direct Works - Naffco |  | -51732.06 | 51732.06 | 2025-10-30
328 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Direct Works - GESR Alarab |  | -128000 | 128000 | 2025-10-30
329 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Direct Works - MEDTEL |  | -990059.87 | 990059.87 | 2025-10-30
330 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Direct Works - Yaz Development Contracting |  | -94000 | 94000 | 2025-10-30
331 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Direct Works - TBK Metal |  | -5020 | 5020 | 2025-10-30
332 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Prelims - Al Rai Modern Water Factory |  | -34561.5 | 34561.5 | 2025-10-30
333 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Prelims - Intelligent General Cont Co Equipment |  | -13000 | 13000 | 2025-10-30
334 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Prelims - Jak Generation Cont Co LLC |  | -2500 | 2500 | 2025-10-30
335 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Prelims - Sami General Contracting |  | -28000 | 28000 | 2025-10-30
336 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Prelims - Ahmed Bin Salem Bin Dagher |  | -39510 | 39510 | 2025-10-30
337 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Prelims - Salim Hamed Cleaning |  | -4347.83 | 4347.83 | 2025-10-30
338 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Prelims - Mohammad Alharbi Medical Company |  | -13799.9 | 13799.9 | 2025-10-30
339 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -603883.09 | 603883.09 | 2025-10-30
340 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -150000 | 150000 | 2025-10-30
341 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Direct Works - Top Construction Co Ltd |  | -43961.28 | 43961.28 | 2025-10-30
342 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Direct Works - HRFA |  | -88089.68 | 88089.68 | 2025-10-30
343 | BTR for (Aug) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000899 | CN - Budget Hold | Direct Works - NESMA |  | -1079426 | 1079426 | 2025-10-30
344 | BTR for Buggy Cart |  | AMA01003-RBTR-000908 | CN - Budget Hold | Extraordinary Cart - Buggy Cart |  | -397876 | 397876 | 2025-11-19
345 | Adjustment - SAB PVO 032/DVO 029 - Buggy Ramp Stud |  |  | Saudi Baytur - Main Works | CN - Budget Hold |  | 0 | 0 | To process |  | 41010
346 | BTR for Birch Street |  | AMA01003-RBTR-000916 | CN - Budget Hold | Birch Street |  | -108142.99 | 108142.99 | 2025-11-26
347 | BTR for Saudico Electronic Systems |  | AMA01003-RBTR-000917 | CN - Budget Hold | Saudico Electronic Systems |  | -353487.06 | 353487.06 | 2025-11-26
348 | BTR for MAS Extension up to Dec 2025 |  | AMA01003-RBTR-000929 | CN - Budget Hold | MAS - Labour Supply - Wet Works |  | -3050936 | 3050936 | 2025-12-21
349 | Adjustment - Alutec PVO/DVO 001 Aluminum Flashing |  | AMA01003-RBTR-001028 | Alutec - Aluminum and Glazing Works | CN - Budget Hold |  | -222077.93 | 222077.93 | 2026-03-24
350 | Adjustment - SAB PVO/DVO 025 - Jan,Feb,Mar25 Direct Payment |  |  | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold |  | 0 | 0 |  |  | Remove
351 | BTR for 003D10 - AlFalak Electronic |  | AMA01003-RBTR-000928 | FF&E OSE - Budget Hold | AlFalak Electronic - HPE Servers |  | -11745 | 11745 | 2025-12-21
352 | BTR for DEPA PVO 018 |  | AMA01003-RBTR-000927 | DEPA Interior Fitout | CN - Budget Hold |  | -204382 | 204382 | 2025-12-21 |  | no
| BTR for 003D15 - SAU - Infor (SunSystems) - SAR 34,719.00 |  | AMA01003-RBTR-000945 | CN - Budget Hold | Saudico Electronic Systems |  | -34719 | 34719 | 2026-01-11
315 | BTR for (Jun & Jul) Direct Payment on Behalf of Saudi Arabian Baytur - Adjustment for Alcatop |  | AMA01003-RBTR-000946 | CN - Budget Hold | Direct Works - Alcatop |  | -10000 | 10000 | January 11, 2026
316 | Budget Transfer required for the additional WHT value following TAX Team confirmation for the correct taxation on each scope |  | AMA01003-RBTR-000965 | CN - Budget Hold | Birch Street |  | -7855.99 | 7855.99 | 2026-01-18
317 | PVO 004 Alfanar |  | AMA01003-RBTR-000964 | CN - Budget Hold | Al Fanar - MEP Labour Supply |  | -8136064 | 8136064 | 2026-01-18 |  | no
318 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Direct Works - Isam Kabani & Partners |  | -626356.44 | 626356.44 | 2026-01-18
319 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Medtel - STO Façade Mock-up |  | -901729.76 | 901729.76 | 2026-01-18
320 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -141000 | 141000 | 2026-01-18
321 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Direct Works - GESR Alarab |  | -152763 | 152763 | 2026-01-18
322 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Direct Works - Naffco |  | -1055.28 | 1055.28 | 2026-01-18
323 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Direct Works - Yaz Development Contracting |  | -102460 | 102460 | 2026-01-18
324 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Direct Works - Abeer Munawer Al Shamari |  | -297785 | 297785 | 2026-01-18
325 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Prelims - Al Rai Modern Water Factory |  | -27754.5 | 27754.5 | 2026-01-18
326 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Prelims - Intelligent General Cont Co Equipment |  | -12700 | 12700 | 2026-01-18
327 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Prelims - Jak Generation Cont Co LLC |  | -2500 | 2500 | 2026-01-18
328 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Prelims - Sami General Contracting |  | -33250 | 33250 | 2026-01-18
329 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Prelims - Ahmed Bin Salem Bin Dagher |  | -42066 | 42066 | 2026-01-18
330 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Prelims - Salim Hamed Cleaning |  | -3045.22 | 3045.22 | 2026-01-18
331 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Prelims - Mohammad Alharbi Medical Company |  | -15253.8 | 15253.8 | 2026-01-18
332 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -602046.33 | 602046.33 | 2026-01-18
333 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -150000 | 150000 | 2026-01-18
334 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Prelims - Ihsan Muhammed Thakir Idress Trading |  | -10000 | 10000 | 2026-01-18
335 | BTR for (Sep) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000963 | CN - Budget Hold | Direct Works - Top Construction Co Ltd |  | -60976.57 | 60976.57 | 2026-01-18
336 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Direct Works - Isam Kabani & Partners |  | -181291.09 | 181291.09 | 2026-01-18
337 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Direct Works - SAMIF |  | -33010 | 33010 | 2026-01-18
338 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Direct Works - Alcatop |  | -110007.58 | 110007.58 | 2026-01-18
339 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Medtel - STO Façade Mock-up |  | -940312.61 | 940312.61 | 2026-01-18
340 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -141000 | 141000 | 2026-01-18
341 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Direct Works - GESR Alarab |  | -128000 | 128000 | 2026-01-18
342 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Direct Works - Naffco |  | -62734.77 | 62734.77 | 2026-01-18
343 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Direct Works - Yaz Development Contracting |  | -131052 | 131052 | 2026-01-18
344 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Prelims - Masa Equipment Est |  | -41000 | 41000 | 2026-01-18
345 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Prelims - Al Rai Modern Water Factory |  | -31812.5 | 31812.5 | 2026-01-18
346 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Prelims - Intelligent General Cont Co Equipment |  | -373800 | 373800 | 2026-01-18
347 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Prelims - Jak Generation Cont Co LLC |  | -2500 | 2500 | 2026-01-18
348 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Prelims - Sami General Contracting |  | -31325 | 31325 | 2026-01-18
349 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Prelims - Ahmed Bin Salem Bin Dagher |  | -51210 | 51210 | 2026-01-18
350 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Prelims - Mohammad Alharbi Medical Company |  | -13799.9 | 13799.9 | 2026-01-18
351 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -551561.28 | 551561.28 | 2026-01-18
352 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -100000 | 100000 | 2026-01-18
353 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Direct Works - Top Construction Co Ltd |  | -66307.14 | 66307.14 | 2026-01-18
354 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Direct Works - HRFA |  | -108416 | 108416 | 2026-01-18
355 | BTR for (Oct) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000962 | CN - Budget Hold | Prelims - Emaar Suhali |  | -90000 | 90000 | 2026-01-18 |  | Emaar Suhali
356
357 | BTR for 003D10 - AlFalak Electronic |  | AMA01003-RBTR-000961 | FF&E OSE - Budget Hold | AlFalak Electronic - HPE Servers |  | -4910 | 4910 | 2026-01-18
358
359 | BTR for PVO 025 - Ceiling Finishes Changes in Area 7 Business Lounge Atrium & Area 10 Restaurant. |  | AMA01003-RBTR-000953 | CN - Budget Hold | DEPA Interior Fitout |  | -251957 | 251957 | 2026-01-18 |  | no
360
361 | PVO 004 Extension of Khatib & Alami’s Senior Architect Construction Supervision Services up to 31 January 2026 |  | AMA01003-RBTR-000977 | CN - Budget Hold | KAA-Mgt Fees |  | -75000 | 75000 | 2026-02-01 |  | no
362
363 | Budget transfer required to align the budget and commitment as per the Paid amount SAR 170,592,074.13 |  | AMA01003-RBTR-000978 | External - Pre Approved | CN - Budget Hold |  | -34672908.5 | 34672908.5 | 2026-02-01
364
365 | BTR for New Contract - Sevenroom Inc |  | AMA01003-RBTR-000976 | FF&E OSE - Budget Hold | Sevenrooms Inc |  | -3633.9 | 3633.9 | 2026-02-01
366 | BTR for New Contract - Infor Co (Saudi Electronics) |  | AMA01003-RBTR-000976 | CN - Budget Hold | Saudico Electronic Systems |  | -58307.19 | 58307.19 | 2026-02-01
367 | Extension of CML Independent Commissioning Agent Services until 28 February 2026 |  | AMA01003-RBTR-000983 | CN - Budget Hold | CML-Mgt Fees |  | -325350 | 325350 | 2026-02-08
368 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Direct Works - Isam Kabani & Partners |  | -358371.84 | 358371.84 | 2026-02-26
369 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | ABU DHABI PRECAST - GRC Cladding |  | -684985 | 684985 | 2026-02-26
370 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -141000 | 141000 | 2026-02-26
371 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Direct Works - Naffco |  | -557500 | 557500 | 2026-02-26
372 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Direct Works - Naffco |  | -76303.7 | 76303.7 | 2026-02-26
373 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Direct Works - Yaz Development Contracting |  | -141000 | 141000 | 2026-02-26
374 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Prelims - Al Rai Modern Water Factory |  | -64489 | 64489 | 2026-02-26
375 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Prelims - Intelligent General Cont Co Equipment |  | -224453.82 | 224453.82 | 2026-02-26
376 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Prelims - Jak Generation Cont Co LLC |  | -2500 | 2500 | 2026-02-26
377 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Prelims - Sami General Contracting |  | -34125 | 34125 | 2026-02-26
378 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Prelims - Ahmed Bin Salem Bin Dagher |  | -59415 | 59415 | 2026-02-26
379 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Prelims - Mohammad Alharbi Medical Company |  | -17746 | 17746 | 2026-02-26
380 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Direct Works - GESR Alarab |  | -831160.63 | 831160.63 | 2026-02-26
381 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Prelims - GLSAN Contracting Company |  | -100000 | 100000 | 2026-02-26
382 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Prelims - Ihsan Muhammed Thakir Idress Trading |  | -12500 | 12500 | 2026-02-26
383 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Direct Works - Top Construction Co Ltd |  | -12000 | 12000 | 2026-02-26
384 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Direct Works - NESMA |  | -863540.8 | 863540.8 | 2026-02-26
385 | BTR for (Nov and Dec) Direct Payment on Behalf of Saudi Arabian Baytur |  | AMA01003-RBTR-000995 | CN - Budget Hold | Prelims - Clean Coast for Contracting |  | -22058.81 | 22058.81 | 2026-02-26
386 | Reachware Integration (New Award) |  | AMA01003-RBTR-000994 | CN - Budget Hold | Reachware Integration |  | -57135 | 57135 | 2026-02-26
387 | BTR for K&A's Mansoor Extension DVO vs PVO adjustment |  | AMA01003-RBTR-001001 | CN - Budget Hold | KAA-Mgt Fees |  | -3720 | 3720 | 2026-03-16
388.1 | BTR for DEPA PVO - Urinal Sensor |  | To be processed | CN - Budget Hold | DEPA Interior Fitout |  | -74046.44 | 74046.44 |  |  | 74046.44
388.2 | BTR for DEPA PVO/DVO - Urinal Sensor |  | AMA01003-RBTR-001032 | DEPA Interior Fitout | CN - Budget Hold |  | -1953.72 | 1953.72 | 2026-04-12
389 | BTR for DEPA DVO - ID lights installation |  | AMA01003-RBTR-001023 | CN - Budget Hold | DEPA Interior Fitout |  | -51810 | 51810 | 2026-03-24 |  | 51810
390 | BTR for PVOs 001 and 002 with total amount SAR 87,500.00 (ARMETAL) |  | AMA01003-RBTR-001004 | CN - Budget Hold | ARMETAL - Reflective ceiling |  | -87500 | 87500 | 2026-03-17
391 | PVO-003 - Relocation of Passenger Elevator Control Panels (ESCCO) |  | AMA01003-RBTR-001025 | CN - Budget Hold | ESCCO - Vertical Transport |  | -10400 | 10400 | 2026-03-24
392 | PVO-002 - Replacement for the Missing Passenger Elevator Door Locks (ESCCO) |  | AMA01003-RBTR-001026 | CN - Budget Hold | ESCCO - Vertical Transport |  | -24700 | 24700 | 2026-03-24
393 | PVO-003 - Supply and Installation of Facade Pressure Plate Cover Flashing (Alutec) |  | AMA01003-RBTR-001028 | CN - Budget Hold | Alutec - Aluminum and Glazing Works |  | -261408 | 261408 | 2026-03-24
394 | PVO 004 - Provision of Vinyl Film with Frit Pattern to the Facade Glazing of the North and South Boutiques (Alutec) |  | AMA01003-RBTR-001028 | CN - Budget Hold | Alutec - Aluminum and Glazing Works |  | -48290 | 48290 | 2026-03-24
395 | PVO 004 - MAS Labour Extension through January and February 2026 |  | AMA01003-RBTR-001024 | CN - Budget Hold | MAS - Labour Supply - Wet Works |  | -1567562 | 1567562 | 2026-03-24
396 | PVO-027 - Removal and Reinstallation of ST-125 Wall Cladding to VVIP Toilet (DEPA) |  | AMA01003-RBTR-001027 | CN - Budget Hold | DEPA Interior Fitout |  | -25000 | 25000 | 2026-03-24
397 | PVO-030 - Concealment of Linear LED Lights at Riva Lounge and Toilets (DEPA) |  | AMA01003-RBTR-001023 | CN - Budget Hold | DEPA Interior Fitout |  | -38760 | 38760 | 2026-03-24
398 | Areen Extension 2 |  | AMA01003-RBTR-001041 | CN - Budget Hold | Areen - FF&E OS&E Items |  | -248084.71 | 248084.71 | 2026-04-26
399 | BTR for Contract Award – SevenRooms Inc – Reservation System |  | AMA01003-RBTR-001040 | CN - Budget Hold | Sevenrooms Inc |  | -29117.66 | 29117.66 | 2026-04-26
400 | PVO/DVO 016 - Descope FF12.04 Millwork & Procure Globe via Depa |  | AMA01003-RBTR-001053 | CN - Budget Hold | DEPA Interior Fitout |  | -38268.51 | 38268.51 | 2026-05-11 |  | 21275.25 | 59543.76 | 38268.51
401 | 1TB01003-AMA01003-RFC-000059 - Provision of Power and Data Connectivity for KOT Printers |  | AMA01003-RBTR-001054 | CN - Budget Hold | Al Fanar - MEP Labour Supply |  | -65000 | 65000 | 2026-05-13
402 | OCIP Direct Payment no 11 AMAALA Yacht Club |  | AMA01003-RBTR-001052 | CN - Budget Hold | Al Rahji Takaful - Owner Controlled Insurance Program |  | -15076.28 | 15076.28 | 2026-05-11 |  |  | 76325.65
403 | PeopleVine Implementation for Yacht Club-AMAALA |  | AMA01003-RBTR-001057 | CN - Budget Hold | PeopleVine |  | -336187.5 | 336187.5 | 2026-05-25 |  |  | 842734.4
404 | Adjustment DVO & PVO 26 (Direct Payments - April and May 26) |  | BTR to be processed. | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold |  | -842734.4 | 842734.4 |  |  |  | -393212.11
405 | Adjustment DVO & PVO 25 (Direct Payments - Jan, Feb and Mar 26) |  | BTR to be processed. | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold |  | -76325.65 | 76325.65 |  |  |  | 416263.78
406 | Adjustment DVO & PVO 12 (DEPA's Millworks to Show Kitchen) |  | BTR to be processed. | DEPA Interior Fitout | CN - Budget Hold |  | -312470.43 | 312470.43 |  |  |  | 23051.67
407 | Adjusment PVO & DVO 001 Armetal |  | BTR to be processed. | ARMETAL - Reflective ceiling | CN - Budget Hold |  | -7952.25 | 7952.25
408 | Adjusment PVO & DVO 002 Armetal |  | BTR to be processed. | ARMETAL - Reflective ceiling | CN - Budget Hold |  | -12469.2 | 12469.2
409 | Adjustment DVO & PVO 26 (Direct Payments - Jun and Jul 26) |  | BTR to be processed. | SAB - Civil and Arch Works, MEPD & ICT/ELV | CN - Budget Hold |  | -16549.99 | 16549.99
410 | Adjusment PVO & DVO 002 ESCCO |  | BTR to be processed. | ESCCO - Vertical Transport | CN - Budget Hold |  | -10708 | 10708
411 | Adjusment PVO & DVO 003 ESCCO |  | BTR to be processed. | ESCCO - Vertical Transport | CN - Budget Hold |  | -3744 | 3744
412 | BTR for DVO - CML Extension up to May 26 |  | BTR to be processed. | CN - Budget Hold | CML-Mgt Fees |  | -312400 | 312400
413 | BTR for DVO - DEPA BOH Finishes (Part 2) |  | BTR to be processed. | CN - Budget Hold | DEPA Interior Fitout |  | -581730.52 | 581730.52
414 | BTR for DVO - K&A Extension up to May 26 |  | BTR to be processed. | CN - Budget Hold | KAA-Mgt Fees |  | -314880 | 314880
415 | BTR for DVO - DEPA Member's Lobby Staircase Finishes part 2 |  | BTR to be processed. | CN - Budget Hold | DEPA Interior Fitout |  | -74300 | 74300
416 | Adjustment to PVO per approved DVO - DEPA EI 16 Access Doors |  | BTR to be processed. | DEPA Interior Fitout | CN - Budget Hold |  | -28414.67 | 28414.67
417 | Adjustment to PVO 23 & 24 per approved DVOs |  |  | DEPA Interior Fitout | CN - Budget Hold |  | -70578.21 | 70578.21
418 | BTR for DVO - Alfanar PVO 009 |  | BTR under process | CN - Budget Hold | Al Fanar - MEP Labour Supply |  | -8294779 | 8294779 |  |  | 8294779
419 | Adjustment - DEPA PVO & DVO 025 |  | AMA01003-RBTR-001109 | DEPA Interior Fitout | CN - Budget Hold |  | -45528.65 | 45528.65 | 2026-08-16
420 | Adjustment - Final Account - Jensen Huges Saudi Arabia LLC - COO#07 |  | BTR to be processed. | Jensen Hughes-Prf Fees | CN - Budget Hold |  | -56700 | 56700 |  |  |  | Item No. - 255 - Final Account - Jensen Huges Saudi Arabia LLC - COO#07
421 | Adjustment - Final Account - Jensen Huges Saudi Arabia LLC - COO#030 |  | BTR to be processed. | Jensen Hughes-Prf Fees | CN - Budget Hold |  | -23800 | 23800 |  |  | 251957 | Item No. - 256 - Final Account - Jensen Huges Saudi Arabia LLC - COO#030
422 | BTR for DVO - EVO 30: Application of STO Ventec System to Conceal the Paving Level Gap at the Grand Stairs |  | BTR to be processed. | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV |  | -115000 | 115000 |  |  | 206428.35 | Item No. - 211 - EVO 30: Application of STO Ventec System to Conceal the Paving Level Gap at the Grand Stairs
423 | BTR for DEPA PVO 033 F&B Design Changes |  | BTR under process | CN - Budget Hold | DEPA Interior Fitout |  | -632257.26 | 632257.26 |  |  | -56700 | 115000
424 | BTR for adjustment to DEPA PVO 027 per DVO 027 |  | BTR under process | DEPA Interior Fitout | CN - Budget Hold |  | -12991.5 | 12991.5
425 | Inter-Project Transfer to MH3 Fibrex Façade Installer |  | BTR under process | CN - Budget Hold | Marina Hotel 3 - CN Hold |  | -164010 | 164010
426 | BTR for adjustment to Alutec PVO 02, 03 & 04 per DVO 02, 03 & 04 |  | AMA01003-RBTR-001108 | Alutec - Aluminum and Glazing Works | CN - Budget Hold |  | -300368.72 | 300368.72 | 2026-08-16
427 | Inter-Project Transfer to MH3 IMAR Façade Installer |  | BTR under process | CN - Budget Hold | Marina Hotel 3 - CN Hold |  | -645354.74 | 645354.74
428 | BTR for appointment of Samtiah Arabia |  | AMA01003-RBTR-001156 | CN - Budget Hold | Samtiah Arabis Ltd - Operation systems |  | -59637.55 | 59637.55 | 2026-09-24
429 | Contract Award to Al-Futtaim |  |  | CN - Budget Hold | Al-futtaim |  | -691955 | 691955
430 | RJT- OCIP Insurance Premium - Declaration 11 |  |  | CN - Budget Hold | RJT OICP Insurance Premium |  | -15076.28 | 15076.28
431 | Ajustment - AREEN PVO and DVO 003 |  |  | CN - Budget Hold | Areen - FF&E OS&E Items |  | -3685.63 | 3685.63
432 | Alutec DVO 003: EI-29 Replacement of Damaged Aluminum Panels (BC to Alutec) |  |  | Alutec - Aluminum and Glazing Works | CN - Budget Hold |  | -31245.99 | 31245.99 |  |  |  | Item No. - 195 - Employer’s Instruction No. 029 – Replacement of Damaged Aluminum Panels (BC to Alutec) |  |  |  |  | -31245.99
| TOTALS | [5 empty] | -769189443.3 | 1037499873.65
[8 empty] | 268310430.35 | 206221318.35
267501065.61
-809364.74
44069.59
[7 empty] | 29136815.43 | 19677959.47
[7 empty] | 12298951.39 | 54758986.33
[7 empty] | -16837864.04 | 35081026.86
45888756.06
[7 empty] | -46073513.67 | 46073513.67
[7 empty] | 2312919.14 | 0
[7 empty] | -48386432.81 | 46073513.67
-809364.74
Note on I284: Jose Chavenia: This is the correct contract code
Note on I319: Jose Chavenia: This is the correct value

## Schedule C
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01 | [17 empty] | Request for Change |  |  | -6935613.645 |  |  |  |  | Potential Variation Order (PVO) | [6 empty] | Variation Orders (VO) | [12 empty] | Determined Variation Orders (DVO)
REPORT NO: - MONTHLY REPORT NO. 49 | [17 empty] | Cancelled |  |  |  | 37 |  |  |  | Cancelled |  |  |  | 16 |  |  | Cancelled |  |  | 13 | [9 empty] | Cancelled |  |  | 8
REPORTING PERIOD: - OCTOBER 2026 | [17 empty] | Approved |  |  |  | 163 |  |  |  | Approved |  |  |  | 144 |  |  | Approved |  |  | 139 | [9 empty] | Approved |  |  | 118
[18 empty] | Pending |  |  |  | 3 |  |  |  | Pending |  |  |  | 24 |  |  | Pending |  |  | 14 | [9 empty] | Pending |  |  | 20
[15 empty] | Formula for Direct Payment |  |  | Superseded |  |  |  | 0 | Every day update - Hide when issuing Cost Report |  |  | Superseded |  |  |  | 0 | Every day update - Hide when issuing Cost Report |  | Superseded |  |  | 0 | [9 empty] | Superseded |  |  | 0 | Every day update - Hide when issuing Cost Report
|  | Process Completed/ Cancelled | [15 empty] | Transferred |  |  |  | 3 |  |  |  | Transferred |  |  |  | 0 | [5 empty] | 166 | [9 empty] | Review Complete |  |  | 0
|  | Early Warnings | [19 empty] | 206 | [7 empty] | 168 | [18 empty] | 146
Provisional Sum Expend
Procurement Early Warning
Intra Project Process
Item No. | Description of Change | Project Stage | Change Category | Initiated By Amaala Representative | Action Pending By Amaala Representative | Status | PROJECT DETAILS | [6 empty] | EARLY WARNINGS |  |  | RFC | [7 empty] | PVO | [7 empty] | VO |  |  |  | EI |  |  | DVO | [12 empty] | FUNDING |  | Comments / Current Status |  | DON’T DELETE
[7 empty] | OWNER | Project Name | Project Code | Asset | Asset Code | PACKAGE | Contractor / Consultant | Nr. | Date | Cost Report Amount (SAR) | Nr. | Revision No | Date | Status | Aconex Workflow Approval Ref. | Time Impact (Days) | Tracker Amount (SAR) | Cost Report Amount (SAR) | Nr. | Revision No | Date | Status | Aconex Workflow Approval Ref. | Time Impact (Days) | Tracker Amount (SAR) | Amount (SAR) | Nr. | Date | Status | Aconex Workflow Approval Ref. | Nr. | Date | Aconex Reference | Nr. | Revision No | CONTRACTOR'S / CONSULTANT |  |  | ENGINEER'S REPRESENTATIVE |  |  | EMPLOYER'S REPRESENTATIVE |  | Tracker Amount (SAR) |  | Status | Contingency / Additional Budget
[42 empty] | Aconex Reference | Date | Submission Amount (SAR) | Aconex Reference | Date | Submission Amount (SAR) | Aconex Reference | Date |  | Submission Amount (SAR)
[53 empty] | Source | Status
Sequential line nr | Insert brief description and scope of change | Choose from dropped down menu | Choose drop down menu |  |  |  | Who initiated the change | [6 empty] | Insert EW no | Date of EW Reported | Initial cost assessment (inc build-up) | Insert RFC no from RFC form | Insert REV no if applicable | Date of RFC Approved | Approve Rejected Pending |  | Initial Time assessment (inc build-up) | Initial cost assessment (inc build-up) | Initial cost assessment (inc build-up) | Insert PVO no | Insert REV no if applicable | Date of PVO Approved | Approve Rejected Pending |  | Initial Time assessment (inc build-up) | Initial cost assessment (inc build-up) | Initial cost assessment (inc build-up) | Insert VO no | Date of VO issue | Approve Rejected Pending |  | Insert EI no | Date of EI issue |  | Insert DVO no | Insert REV no if applicable |  | Date recieved from Contractor | cost submission (inc build-up) |  | Date recieved from Contractor | cost submission (inc build-up) |  | Date recieved from Contractor | Initial cost assessment (inc build-up) | cost submission (inc build-up) | Approve Rejected Pending | Confirm source for additional funding | Insert wether additional budget request is pending or approved | Insert comments to identify: - current status - outstanding actions - if item is cancelled - status of additional budget request
PR # 1 | PROCUREMENT EARLY Warnings_NSCC - Triple Bay Piling | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 |  |  |  |  | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE
PR # 2 | PROCUREMENT EARLY Warnings_Civil and Architectural Package | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Civil and Arch Works | Baytur | 1 | 2022-10-18 | [7 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Amaala Commercial team - actioned approved budget informally due to appointment of Baytur |  | 0
PR # 3 | PROCUREMENT EARLY Warnings_Mechanical, Electrical & Plumbing | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MEPD | Baytur | 2 | 2022-10-18 | [7 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Amaala Commercial team - actioned approved budget informally due to appointment of Baytur |  | 0
PR # 4 | PROCUREMENT EARLY Warnings_ICT / ELV | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | ICT / ELV | Baytur | 3 | 2022-10-18 | [7 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Amaala Commercial team - actioned approved budget informally due to appointment of Baytur |  | 0
PR # 5 | PROCUREMENT EARLY Warnings_Vertical Transportation | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Vertical Transport | ESCCO | 4 | 2022-10-18 | [7 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
PR # 6.1 | PROCUREMENT EARLY Warnings_Hard & Soft Scape | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Hard and Soft Landscaping |  | 5 | 2022-10-18 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Due to the budget transfer to Interior Fitout Package to fund the Contract Award to DEPA. |  | 0
PR # 6.2 | PROCUREMENT EARLY Warnings_Hard & Soft Scape (Removal of Mass Concrete from Landscape package to Structural Works Contractor - PVO 001 - SAB) | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Hard and Soft Landscaping |  | 5.1 | 2023-03-16 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE
PR # 7 | PROCUREMENT EARLY Warnings_Interior Fitout | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Interior Fitout |  | 6 | 2022-10-18 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
PR # 8.1 | PROCUREMENT EARLY Warnings_Specialist Kitchen | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Special Kitchen |  | 7 | 2022-10-18 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
PR # 8.2 | PROCUREMENT EARLY Warnings_Specialist Kitchen (AMAALA Yacht Club (AYC) - Staff Canteen Redesign) | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Special Kitchen |  | 7 | 2023-03-16 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE
PR # 9 | PROCUREMENT EARLY Warnings_Loose FF&E (FOH) | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Loose FF&E items (FOH) |  | 9 | 2023-03-05 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE
PR # 10 | PROCUREMENT EARLY Warnings_Loose FF&E (BOH) | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Loose FF&E items (BOH) |  | 8 | 2022-10-18 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
PR # 12 | PROCUREMENT EARLY Warnings_Art Work | Pre Contract Variation | Design Dev |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Art Work |  | 10 | 2023-03-05 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
NSCC - 001 | Design Changes from Contract to IFC - AYC | Post Contract Variation | Design Development | HANEEF | OTHER | PVO - Pending for Approval on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | NSCC - Piling | NSCC |  |  |  | RFC 01 |  | 2022-07-27 | APPROVED | AMA-WTRAN-000777 | YES | ACTIVE | 0 | PVO 01 |  | 2022-08-10 | APPROVED | AMA-WTRAN-000808 | YES | ACTIVE | -3634284.17 | VO 01 | 2022-08-10 | APPROVED | AMA-WTRAN-000809 | EI 004 R2 | 2022-10-20 | 1TB04400-031D03-WSP-LTR-0028 | [8 empty] | AMA04400-WTRAN-002873 | 2023-06-20 | ACTIVE |  | APPROVED |  |  | Closed. Included in NSCC Item No 11 (EI-14) below. |  | 0
1 | Additional Service - Scope Gap - Pool & Water Feature, Specialist Smoke Extract & Signage & Way Finding | Post Contract - Consultant Variation | Scope Gap | CLOSED | CLOSED |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 2 | 0 | 2021-08-11 | APPROVED | AML-WTRAN-000106 | NO | ACTIVE | 197496.2 | RFC 02 |  | 2021-08-11 | APPROVED | AML-WTRAN-000106 | NO | ACTIVE | 197496.2 | CI 001 | 2021-09-13 | APPROVED | AML-TRANSMIT-000007 |  |  |  | AVI 001 |  | DAE-LTR-000006 | 2021-12-05 | 197496.2 |  |  |  | AMA-TRANSMIT-000065 | 2021-12-14 | ACTIVE | 197496.2 | APPROVED |  |  |  |  | 0
2 | Additional Service - Conversion of Façade / Shell from Rhino to Revit | Post Contract - Consultant Variation | Design Development | CLOSED | CLOSED |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 3 | 0 | 2021-08-11 | APPROVED | AML-WTRAN-000105 | YES | ACTIVE | 138200 | RFC 03 |  | 2021-08-11 | APPROVED | AML-WTRAN-000105 | YES | ACTIVE | 138200 | CI 002 | 2021-09-13 | APPROVED | AML-WTRAN-000030 |  |  |  | AVI 002 |  | DAE-TRANSMIT-000065 | 2021-12-15 | 138200 |  |  |  | AMA-TRANSMIT-000066 | 2021-12-14 | ACTIVE | 138200 | APPROVED |  |  | The whole change process managed by Keith's team |  | 0
3 | Revised BIM Guidelines - AMAALA to TRSDC | Post Contract - Consultant Variation | Design Development | CLOSED | CLOSED |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 4 | 0 | 2021-12-11 | APPROVED | AMA-WTRAN-000126 | NO | ACTIVE | 550000 | RFC 04 |  | 2021-12-11 | APPROVED | AMA-WTRAN-000126 | NO | ACTIVE | 550000 | CI 003 | 2021-12-18 | APPROVED | AMA-WTRAN-000187 |  |  |  | AVI 003 |  | DAE-LTR-000002 | 2021-11-04 | 550000 |  |  |  | AMA-TRANSMIT-000129 | 2022-01-25 | ACTIVE | 550000 | APPROVED |  |  | The whole change process managed by Keith's team |  | 0
4 | Additional Service - Art Consultant | Post Contract - Consultant Variation | Design Development | SHIHAM | CLOSED |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 5 | 0 | 2021-12-18 | APPROVED | AMA-WTRAN-000189 | NO | ACTIVE | 350000 | RFC 05 |  | 2021-12-18 | APPROVED | AMA-WTRAN-000189 | NO | ACTIVE | 350000 | CI 004 | 2021-12-29 | APPROVED | AMA-WTRAN-000291 |  |  |  | DVO 01 |  |  |  | 261030 |  |  |  | AMA-WTRAN-000974 | 2022-07-31 | ACTIVE | 261030 | APPROVED |  |  | The whole change process managed by Keith's team |  | 0
5 | Additional Service - FOH FF&E Consultant - Intercon | Post Contract - Consultant Variation | Design Development | SHIHAM | CLOSED |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 6 | 1 | 2022-01-24 | APPROVED | AMA-WTRAN-000338 | NO | ACTIVE | 275000 | RFC 06 |  | 2022-01-24 | APPROVED | AMA-WTRAN-000338 | NO | ACTIVE | 275000 | CI 005 |  | APPROVED |  |  |  |  | DVO 02 |  | DAE-TRANSMIT-000246 | 2022-08-22 | 275000 |  |  |  | AMA-WTRAN-001088 | 2022-09-06 | ACTIVE | 275000 | APPROVED |  |  | The whole change process managed by Keith's team |  | 0
6 | Additional Service ‐ KSA Civil Defence | Post Contract - Consultant Variation | Design Development | SHIHAM | CLOSED |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 7 | 0 | 2022-01-24 | APPROVED | AMA-WTRAN-000339 | NO | ACTIVE | 60500 | RFC 07 |  | 2022-01-24 | APPROVED | AMA-WTRAN-000339 | NO | ACTIVE | 60500 | CI 006 | 2022-01-29 | APPROVED | AMA-WTRAN-000350 |  |  |  | DVO 03 |  | DAE-WTRAN-000193 | 2022-08-11 | 60500 |  |  |  | AMA-WTRAN-001101 | 2022-09-08 | ACTIVE | 60500 | APPROVED |  |  |  |  | 0
7 | Revised Sustainability Guidelines & Change of Cooling System | Post Contract - Consultant Variation | Design Development | SHIHAM | CLOSED |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 8 | 0 | 2022-01-10 | APPROVED | AMA-WTRAN-000322 | NO | ACTIVE | 47243.52 | RFC 08 |  | 2022-01-10 | APPROVED | AMA-WTRAN-000322 | NO | ACTIVE | 47243.52 | CI 007 |  | APPROVED |  |  |  |  | DVO 04 |  |  |  | 45604.9 |  |  |  | AMA-WTRAN-001110 | 2022-09-11 | ACTIVE | 45604.9 | APPROVED |  |  |  |  | 0
TNT - 013 | Additional Scope of Work - Tender Preparation & BOQ - AYC | Consultant Variation | Amaala | SHIHAM | SHIHAM | PVO - Pending from Contractor / Consultant | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | T&T-Prf Fees | Turner Townsend |  |  |  | 2 | 0 | 2022-07-31 | CANCELLED | AMA-WTRAN-000979 | NO | NOT ACTIVE | 0 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Cancelled. As advised by BL, T&T this is closed and T&T never provided a cost submission. |  | 0
8 | AdditionL SPA Feature on Level 2 / 3 | Post Contract Variation | Design Development | SHIHAM | CLOSED | DVO - Accepted | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 10 | 1 | 2022-09-29 | APPROVED | AMA-WTRAN-001138 | NO | ACTIVE | 0 | 2 | 0 | 2022-10-25 | APPROVED | AMA01003-WTRAN-001225 | NO | ACTIVE | 16000 | VO 01 | 2022-11-21 | APPROVED | AMA01003-WTRAN-001226 |  |  |  | DVO 05 |  | DAE01003-GENCORR-000106 | 2022-12-08 | 16000 |  |  |  | AMA01003-WTRAN-001281 | 2022-12-16 | ACTIVE | 16000 | APPROVED |  |  |  |  | 0
9 | Delay in Design Submission | Post Contract - Consultant Variation | Design Dev | SHIHAM | CLOSED | RFC - Rejected | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 9 | 0 | 2022-03-08 | CANCELLED | AMA-WTRAN-000572 | YES | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | RFC returned by Ian Williamson - WF-000149 |  | 0
10 | Extension of Time Request | Pre Contract Variation | Design Dev | SHIHAM | CLOSED |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 11 | 0 |  | CANCELLED |  |  | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Cancelled. No EOT Claim from Dewan. |  | 0
11 | Flood Risk Management (Porte Cochere) | Pre Contract Variation | Amaala | SHIHAM | SHIHAM | PVO - Pending from Contractor / Consultant | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 12 | 0 | 2022-10-02 | APPROVED | AMA-WTRAN-001140 | YES | ACTIVE | 0 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | No cost implication to Dewan as it will be incorporated to IFC |  | 0
SIC - 001 | Vehicle Requirement - Internal Budget Transfer from AYC to LVD | Post Contract Variation | Amaala | VASEEF | OTHER | RFC - Rejected | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SOI TB Ground Improvement Works | SIC | [6 empty] | CANCELLED |  |  | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
SIC - 002 | Design Changes from Contract to IFC - AYC | Post Contract Variation | Amaala |  |  | PVO - Pending from Contractor / Consultant | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SOI TB Ground Improvement Works | SIC |  |  |  | 1 |  |  | CANCELLED |  |  | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | GI Works in AYC is completed. |  | 0
SIC - 005 | Extension of Time - AYC | Pre Contract Variation | Extension of Time (EOT) | JOSE | JOSE | DVO - Accepted | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SOI TB Ground Improvement Works | SIC |  |  |  | 22 |  | 2022-09-29 | APPROVED | AMA-WTRAN-002553 | YES | ACTIVE |  | 14 | 0 | 2023-02-14 | APPROVED | AMA04004-WTRAN-003633 | YES | ACTIVE | 0 | VO 14 | 2023-02-14 | APPROVED | AMA04004-WTRAN-003634 | [11 empty] | AMA04004-WTRAN-003865 | 2023-03-16 | ACTIVE | 0 | APPROVED |  |  | No cost impact, but 30 days EOT. |  | 0
12 | PART A - Proposed Redesign services associated with AYC Piling PART B - Redesign services associated with the change of Tunnel connection geometry between AYC & MLH | Consultant Variation | Design Development | HANEEF | CLOSED | DVO - Accepted | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 13 | 0 | 2022-10-17 | APPROVED | AMA-RFC-000003 | YES | ACTIVE | 400000 | 1 | 0 | 2022-11-01 | APPROVED | AMA-WTRAN-001066 | YES | ACTIVE | 351150 | VO 02 | 2022-11-15 | APPROVED | AMA01003-WTRAN-001218 |  |  |  | DVO 06 |  | DAE01003-GENCORR-000108 | 2022-12-19 | 351150 |  |  |  | AMA01003-WTRAN-001333 | 2023-01-05 | ACTIVE | 351150 | APPROVED |  |  | Note that these costs (Part 1) might be at NSCC expense. Also note there are two costs involved Part 1 and Part 2. |  | 0
13 | Regeneration Kitchen - AYC | Consultant Variation | Design Dev |  |  | RFC - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 14 | 0 |  | CANCELLED | AMA01003-RFC-000006 |  | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Cancelled as the RFC value only includes for Design Fee. The PD requested that the Construction Cost shall be included in the RFC value.
13 | AMAALA Yacht Club (AYC) - Staff Canteen Redesign (DEWAN) | Consultant Variation | Design Development |  |  | DVO - Accepted | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 14 | 0 | 2023-04-16 | APPROVED | AMA01003-RFC-000007 |  | ACTIVE | 439201 | PVO 03 |  | 2023-05-22 | APPROVED | AMA01003-WTRAN-003313 | NO | ACTIVE | 493201 | VO 03 | 2023-05-28 | APPROVED | AMA01003-WTRAN-003530 | VO 03 | 2023-05-29 | 1TB01003-003D01-AMA-LTR-0004 | DVO 07 |  | DAE01003-GENCORR-000113 | 2023-05-31 | 413183 |  |  |  | AMA01003-WTRAN-004073 | 2023-06-19 | ACTIVE | 413183 | APPROVED |  |  | AMA01003-RFC-000007 (Part A - for the Redesign fee). Included in RFC-032.
13 | AMAALA Yacht Club (AYC) - Staff Canteen Redesign (Raqtan) | Post Contract Variation | Design Dev |  |  | PVO - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Special Kitchen | RAQTAN |  |  |  | 14 | 0 | 2023-04-16 | CANCELLED | AMA01003-RFC-000007 |  | NOT ACTIVE | 400000 | PVO 03 | [5 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Superseded by RFC 032
13 | AMAALA Yacht Club (AYC) - Staff Canteen Redesign (SAB) | Post Contract Variation | Design Dev |  |  | PVO - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 14 | 0 | 2023-04-16 | CANCELLED | AMA01003-RFC-000007 |  | NOT ACTIVE | 2160799 | PVO 03 | [5 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Superseded by RFC 032
NSCC - 011 | Proposed Value Enginnering for Foundation - PART B - AYC | Post Contract Variation | Design Development | JOSE | JOSE | DVO - Accepted | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | NSCC - Piling | NSCC |  |  |  | 3 | 0 | 2022-10-17 | APPROVED | AMA-RFC-000003 | YES | ACTIVE | 3634284 | 4 | 0 | 2022-11-01 | APPROVED | AMA-WTRAN-001067 | YES | ACTIVE | 3634284.17 | VO 08 | 2022-12-14 | APPROVED | AMA04400-WTRAN-001512 | EI 014 | 2023-01-05 | 1TB04400-031D03-WSP-LTR-0071 | DVO 009 |  | 1TB04400-005C13-NSC-LTR-0285 | 2023-03-14 | -3237183.47 | 1TB04400-031D03-WSP-LTR-0097 | 2023-03-23 | -3801279.3 | AMA04400-WTRAN-002873 | 2023-06-20 | ACTIVE | -3801279.3 | APPROVED |  |  | This will be assessed/closed along with NSCC Item 1 (VO 01/EI-04) above. |  | 0
F + P - 008 | LEED Requirements - AYC | Post Contract Variation | Design Development | VEDHAKUMAR | CLOSED | DVO - Accepted | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Executive Architect Services | Foster + Partners |  |  |  | 10 | 0 | 2022-03-23 | APPROVED | AMA-SUS.-WTRAN-000002 | NO | ACTIVE | 53148.295 | 8 | 0 | 2022-04-15 | APPROVED | AMA-WTRAN-000453 | NO | ACTIVE | 53148.295 | VO 08 | 2022-04-15 | APPROVED | AMA-WTRAN-000454 | [7 empty] | 53148.295 |  |  |  | AMA-WTRAN-000818 | 2022-07-21 | ACTIVE | 53148.295 | APPROVED |  |  | Rate of conversion:- 1 GBP = 4.91 SAR Value SAR 53,148 for BT to RSMLI Asset for F+P Contract. |  | 0 | 53148.295
NSCC - 019 | Additional Scope of Work - Temporary Shoring - AYC | Consultant Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | NSCC - Piling | NSCC |  |  |  | RFC 013 | 0 | 2022-12-20 | CANCELLED | AMA04400-WTRAN-001611 | YES | NOT ACTIVE | 7000000 | 14 | 0 | 2023-01-05 | CANCELLED | WF-001912 | NO | NOT ACTIVE | 7689931.41 | [17 empty] | NOT ACTIVE |  |  |  |  | Works not to proceed due to design liability |  | 0
NSCC - 024 | Updated Consolidation of the Contractor’s Claim up to 14 April 2023 (AYC Section) | Post Contract Variation | Final Account |  |  | DVO - Pending for Approval on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | NSCC - Piling | NSCC | EW 11 | 2023-06-30 | 0 |  |  |  | APPROVED |  |  | ACTIVE |  |  |  |  | APPROVED |  |  | ACTIVE |  |  |  | APPROVED |  |  |  |  | DV 013 | [7 empty] | AMA04400-WTRAN-003774 | 2024-10-26 | ACTIVE | 1491099.05 | APPROVED |  |  | Part of DVO 013 (Final Account Settlement with NSCC). |  | 0
NSCC - 025 | NSCC EOT Claim 14a - Delay to dewatering and excavation works in AYC Section | Post Contract Variation | Design Dev |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | NSCC - Piling | NSCC | 12 | 2023-03-16 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE
14 | SAB Extended Hours and Friday Works | Post Contract Variation | Amaala |  |  | PVO - Pending for Approval on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 10 |  | 2023-06-13 | CANCELLED | AMA01003-CHNGRSPS-000011 | NO | NOT ACTIVE | -17992 | PVO 04 |  | 2023-08-03 | CANCELLED | AMA01003-WTRAN-005081 | NO | NOT ACTIVE | -17992 |  |  | CANCELLED | [14 empty] | NOT ACTIVE |  | CANCELLED |  |  | It is agreed between KAA and SAB that KAA will directly invoice SAB on overtime works. AMA01003-WTRAN-012086 - Cancellation of PVO |  | 0
15 | Changes in IFT as compared with IFC (Saudi Baytur Scope) | Post Contract Variation | Design Development |  |  | DVO - Accepted | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 1 |  | 2025-03-24 | APPROVED | AMA01003-WTRAN-002261 | NO | ACTIVE | 4745791 | 2 |  | 2023-04-02 | APPROVED | AMA01003-WTRAN-002382 | NO | ACTIVE | 4745791 | VO 02 | 2023-05-17 | APPROVED | AMA01003-WTRAN-003206 | VO 002 / EI 002 | 2023-05-17 | 1TB01003-003C03-AMA-LTR-0026 | DV0 002 |  | SAB01003-VAR-OR-000002 | 2023-08-10 | 6668888.27 |  |  |  | AMA01003-WTRAN-006557 | 2023-09-20 | ACTIVE | 2458484 | APPROVED |  |  | Closed |  | 0 | 126 | 36 | 2287307
16 | Recoupement for payment for Façade Mock-up (STO) | Post Contract Variation | Omission |  |  | DVO - Accepted | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 18 |  | 2023-07-26 | APPROVED | AMA01003-CHNGRSPS-000018 | NO | ACTIVE | -834298.55 | PVO 07 |  | 2023-08-22 | APPROVED | AMA01003-WTRAN-005655 |  | ACTIVE | -848556 | VO 05 | 2023-08-27 | APPROVED | AMA01003-WTRAN-005760 | VO 005 | 2023-08-28 | 1TB01003-003C03-AMA-LTR-0062 | DVO 005 | [7 empty] | AMA01003-WTRAN-008972 | 2023-11-22 | ACTIVE | -848556 | APPROVED |  |  | No response from SAB on the assessment hence RSG issued Determination to close this variation. |  | 0 | 86
17 | Saudi Baytur Site Establishment - Marina Precinct (Site Offices Extension) | Post Contract Variation | Prelims |  |  | DVO - Pending from Contractor / Consultant | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 3 |  | 2023-01-25 | APPROVED | AMA01003-WTRAN-001496 | NO | ACTIVE | 12500000 | PVO 04 |  | 2024-01-20 | APPROVED | AMA01003-WTRAN-011070 |  | ACTIVE | 1518989 | VO 07 | 2024-01-20 | APPROVED | AMA01003-WTRAN-011072 | VO 007 | 2024-01-28 | 1TB01003-003C03-AMA-LTR-0114 | DVO 004 | [7 empty] | AMA01003-WTRAN-016528 | 2024-05-26 | ACTIVE | 221724 | APPROVED |  |  | Determination issued to SAB since no cost proposal received from SAB. |  | 0 | 119 | 29 | 1297265
18 | Removal of Mass Concrete from Landscape package to Structural Works Contractor - AYC (SAB) - PVO 1 | Post Contract Variation | Omission |  |  | DVO - Accepted | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 5 |  | 2023-02-19 | APPROVED | AMA01003-CHNGRSPS-000006 | NO | ACTIVE | 543269 | 1 |  | 2023-03-16 | APPROVED | AMA01003-WTRAN-002125 | NO | ACTIVE | 543269 | VO 01 | 2023-03-23 | APPROVED | AMA01003-WTRAN-002259 | VO 001 / EI 001 | 2023-04-05 | 1TB01003-003C03-AMA-LTR-0013 | DVO 001 | 01 | 1TB01003-003C03-SAB-LTR-0010 | 2023-06-13 | 1119159.12 |  |  |  | AMA01003-WTRAN-004682 | 2023-07-20 | ACTIVE | 343524.99 | APPROVED |  |  |  |  | 0
20 | Omission of Dewatering from SAB Contract. | Post Contract Variation | Omission |  |  | DVO - Accepted | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 13 | 2023-05-23 | 0 | RFC 12 |  | 2023-06-21 | APPROVED | AMA01003-RFC-000012 | NO | ACTIVE | -4800000 | 5 |  | 2023-07-20 | APPROVED | AMA01003-WTRAN-004674 | NO | ACTIVE | -4907800 | VO 03 | 2023-07-26 | APPROVED | AMA01003-WTRAN-004830 | VO 003 / EI 003 | 2023-07-27 | 1TB01003-003C03-AMA-LTR-0048 | DVO 003 |  | SAB01003-GENCORR-000042 | 2023-08-08 | -2567500 |  |  |  | AMA01003-WTRAN-006340 | 2023-09-14 | ACTIVE | -4902500 | APPROVED |  |  | Closed |  | 0 | 49 |  | -5300
21 | Changes in Ext. & Int. Temporary Watertight Shoring System | Post Contract Variation | Design Development |  |  | DVO - Accepted | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 14 | 2023-05-23 | 0 | RFC 013 |  | 2023-06-21 | APPROVED | AMA01003-CHNGRSPS-000014 | NO | ACTIVE | -9961758.4 | 6 |  | 2023-08-03 | APPROVED | AMA01003-WTRAN-005082 | NO | ACTIVE | -11148179.01 | VO 04 | 2023-08-08 | APPROVED | AMA01003-WTRAN-005082 | VO 004 / EI 004 | 2023-08-09 | 1TB01003-003C03-AMA-LTR-0050 | DVO 004 | [7 empty] | AMA01003-WTRAN-007965 | 2023-10-29 | ACTIVE | -11545998.09 | APPROVED |  |  | Closed |  | 0 | 81 |  | 397819.08
22 | Omission of Surveying Equipment from SAB Contract | Post Contract Variation | Amaala |  |  | RFC - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 15 | 2023-05-23 | -7890 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
23 | Off-Hire of Service Vehicles | Post Contract Variation | Prelims |  |  | DVO - Accepted | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | 16 | 2023-05-23 | 0 | RFC 020 |  | 2023-08-30 | APPROVED | AMA01003-CHNGRSPS-000020 | NO | ACTIVE | -742815.79 | 8 |  | 2023-09-17 | APPROVED | AMA01003-WTRAN-006408 | NO | ACTIVE | -742815.79 | VO 06 | 2023-09-21 | APPROVED | AMA01003-WTRAN-006611 | VO 006 / EI 006 | 2023-09-21 | 1TB01003-003C03-AMA-LTR-0067 | DVO 006 | [7 empty] | AMA01003-WTRAN-008973 | 2023-11-22 | ACTIVE | -774075.97 | APPROVED |  |  | Closed |  | 0 | 62 |  | 31260.18
24 | Omission of food and welfare provision to AMAALA Staff from SAB Contract. | Post Contract Variation | Amaala |  |  | RFC - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 17 | 2023-05-23 | -90000 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
25 | Cost saving to Site Office Monthly Running Cost due to late installation of the Office Establishment by SAB. | Post Contract Variation | Amaala |  |  | RFC - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 17 | 2023-05-23 | -200000 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
NSSC - 006 | Excavation Works - AYC | Pre Contract Variation | Amaala | OTHER | OTHER | RFC - Pending from Contractor / Consultant | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | NSCC - Piling | NSCC | [6 empty] | CANCELLED |  |  | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Aizaz confirmed that no Excavation Works for NSCC in AYC Project |  | 0
NSSC - 007 | Increase in Concrete Piling Rates | Pre Contract Variation | Design Development | OTHER | OTHER | DVO - Accepted | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | NSCC - Piling | NSCC |  |  |  | N/A |  | 2022-12-14 | APPROVED | Not Required as per CA | NO | ACTIVE | 70028 | PVO 10 |  | 2023-01-08 | APPROVED | AMA04400-WTRAN-001766 | NO | ACTIVE | 70028 | VO 010 | 2023-01-08 | APPROVED | AMA04400-WTRAN-001767 |  |  |  | DVO 007 |  | 1TB04400-005C13-NSC-LTR-0123 | 2022-10-06 | 70027.76 |  |  | 70027.76 | AMA04400-WTRAN-002535 | 2023-04-09 | ACTIVE | 70027.76 | APPROVED |  |  | Agreed |  | 0 | 0
NSSC - 013 | Labour Lease Agreement | Pre Contract Variation | Amaala | OTHER | OTHER | PVO - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | NSCC - Piling | NSCC |  |  |  | 12 |  |  | CANCELLED | AMA04400-CHNGRSPS-000006 | NO | NOT ACTIVE | -383400 | 13 | 0 | 2023-01-13 | CANCELLED | AMA04400-WTRAN-001752 | NO | NOT ACTIVE | -383400 | VO 012 | 2023-01-04 | CANCELLED | AMA04400-WTRAN-001744 | [13 empty] | NOT ACTIVE |  |  |  |  | As advised by ED, accommodation will not be removed from Contractors |  | 0
26 | Relocation of Marina Operations to AMAALA Triple Bay Yacht Club (DEWAN) | Consultant Variation | Design Dev |  |  | PVO - Rejected | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 11 |  | 2023-07-17 | CANCELLED | AMA01003-WTRAN-004576 |  | NOT ACTIVE | 536281 | 4 |  | 2023-09-01 | CANCELLED | AMA01003-WTRAN-005872 | NO | NOT ACTIVE | 248219 | VO 05 | 2023-09-03 | CANCELLED | AMA01003-WTRAN-005934 | VO 005 | 2023-09-04 | 1TB01003-003D01-AMA-LTR-0007 |  |  | DAE01003-GENCORR-000116 | 2023-09-11 | 248219 | [5 empty] | NOT ACTIVE |  | CANCELLED |  |  | Refer to SQ 41 |  | 0
26 | Relocation of Marina Operations to AMAALA Triple Bay Yacht Club (SAB) | Post Contract Variation | Design Dev |  |  | VO - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 11 |  | 2023-07-17 | CANCELLED | AMA01003-WTRAN-004576 |  | NOT ACTIVE | 1454026.96 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Refer to SQ 41 |  | 0
27 | Site Grading & Fencing for Employer's Offices | Post Contract Variation | Prelims |  |  | PVO - Pending for Approval on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | RFC 25 | 0 | 2024-01-25 | APPROVED | AMA01003-CHNGRSPS-000027 | NO | ACTIVE | 4289868.5 | PVO 11 |  | 2024-08-06 | APPROVED | AMA01003-WTRAN-019136 |  | ACTIVE | 3013648.7 | VO 10 | 2024-08-18 | APPROVED | AMA01003-WTRAN-019564 | VO 010 | 2024-08-19 | 1TB01003-003C03-AMA-LTR-0201 | DVO 010 | [7 empty] | AMA01003-WTRAN-019900 | 2024-08-28 | ACTIVE | 3013648.7 | APPROVED |  |  |  |  | 0 | 9 |  | 0
28 | Site office Fencing & Levelling | Post Contract Variation | Amaala |  |  | RFC - Pending for Approval on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | RFC 015 | 0 | 2023-07-11 | CANCELLED | AMA01003-RFC-000015 | NO | NOT ACTIVE | 4000953.59 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
29 | Supply of Fill Material to SAB | Post Contract Variation | Amaala |  |  | RFC - Pending for Approval on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | RFC 014 | 0 | 2023-07-09 | CANCELLED | AMA01003-RFC-000014 | NO | NOT ACTIVE | 0 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
30 | Omission of site offices scope | Post Contract Variation | Amaala |  |  | RFC - Pending for Approval on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | RFC 016 | 0 | 2023-07-11 | CANCELLED | AMA01003-RFC-000016 | NO | NOT ACTIVE | -8458954.72 | [6 empty] | NOT ACTIVE |  | VO 03 | [16 empty] | NOT ACTIVE | [6 empty] | 0
30 | FLS Code Deviations - Additional FLS Documentation | Consultant Variation | Design Development |  |  | DVO - Accepted | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 17 | 0 | 2023-04-16 | APPROVED | AMA01003-CHNGRSPS-000017 | NO | ACTIVE | 224020 | 5 |  | 2023-08-03 | APPROVED | AMA01003-WTRAN-005655 | NO | ACTIVE | 194800 | VO 04 | 2023-08-26 | APPROVED | AMA01003-WTRAN-005721 | VO 004 | 2023-08-27 | 1TB01003-003D01-AMA-LTR-0006 | DVO 004 |  | DAE01003-GENCORR-000115 | 2023-09-11 | 194800 |  |  |  | AMA01003-WTRAN-007241 | 2023-10-10 | ACTIVE | 194800 | APPROVED |  |  | Closed |  | 0 | 44 |  | 0
31 | AYC Fit-Out Package Contract Duration Amendment | Post Contract Variation | Amaala |  |  | RFC - Cancelled | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | 20 | 0 | 2023-11-06 | APPROVED | AMA01003-CHNGRSPS-000021 | NO | ACTIVE | 0 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
32 | Alternative Marna Operation Office Locations on AYC Basement | Post Contract Variation | Amaala |  |  | RFC - Cancelled | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | [8 empty] | NO | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
33 | Removal of Sustainability LEED AP Resource | Post Contract Variation | Omission |  |  | DVO - Accepted | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | KAA-Mgt Fees | KAA |  |  |  | RFC 022 | 0 | 2023-11-15 | APPROVED | AMA01003-CHNGRSPS-000023 | NO | ACTIVE | -958333.33 | PVO 01 | 0 | 2023-12-06 | APPROVED | AMA01003-WTRAN-009442 | NO | ACTIVE | -881666.67 | VO 01 | 2023-12-06 | APPROVED | AMA01003-WTRAN-009443 | VO 001 | 2023-12-09 | 1TB01003-003F02-AMA-LTR-0014 | DVO 001 |  | KAA01003-RESP-000313 | 2024-01-30 | -922422.8 |  |  |  | AMA01003-WTRAN-012826 | 2024-02-20 | ACTIVE | -977022.8 | APPROVED |  |  |  |  | 0 | 73
34 | Changes in AMAALA Yacht Club Back-of-House Finishes (Basement Level)_DEPA | Post Contract Variation | Omission |  |  | DVO - Pending from Contractor / Consultant | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | RFC 023 | 0 | 2023-12-23 | APPROVED | AMA01003-WTRAN-009964 | NO | ACTIVE | -336713.1 | PVO 01 | 0 | 2024-08-29 | APPROVED | AMA01003-WTRAN-019916 | NO | ACTIVE | -1033199.1 | VO 01 | 2024-08-29 | APPROVED | AMA01003-WTRAN-019917 | VO 01 R1 | 2024-09-02 | 1TB01003-003C09-AMA-LTR-0072 | DVO 001 |  | 1TB01003-003C09-DCC-LTR-0123 | 2024-09-30 | -1090593 |  |  |  | AMA01003-WTRAN-024095 |  | ACTIVE | -1255596.13 | APPROVED |  |  |  |  | 0
34 | Changes in AMAALA Yacht Club Back-of-House Finishes (Basement Level)_SAB | Post Contract Variation | Amaala |  |  | DVO - Pending from Contractor / Consultant | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | RFC 023 | 0 | 2023-12-23 | CANCELLED | AMA01003-WTRAN-009964 | NO | NOT ACTIVE | 249378.75 | PVO 09 | 0 | 2024-01-23 | CANCELLED | AMA01003-WTRAN-011376 | NO | NOT ACTIVE | 452337.15 | VO 09 | 2024-01-23 | CANCELLED | AMA01003-WTRAN-011377 | VO 009 | 2024-02-05 | 1TB01003-003C03-AMA-LTR-0120 | [5 empty] | AMA01003-GENCORR-000403 | 2024-03-13 | 139409.127 |  |  | NOT ACTIVE |  | CANCELLED |  |  | PVO (AMA01003-WTRAN-016767) and VO (AMA01003-WTRAN-016768) Cancelled. DEPA to carry out all the BOH Finishes. |  | 0
35 | Changes in AMAALA Yacht Club Back-of-House Finishes (Ground Level)_DEPA | Post Contract Variation | Omission |  |  | DVO - Pending from Contractor / Consultant | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | RFC 024 | 0 | 2023-12-31 | APPROVED | AMA01003-WTRAN-010223 | NO | ACTIVE | -212913.4 | PVO 02 | 0 | 2024-08-27 | APPROVED | AMA01003-WTRAN-019820 | NO | ACTIVE | -267350.4 | VO 02 | 2024-08-27 | APPROVED | AMA01003-WTRAN-019821 | VO 02 R1 | 2024-09-02 | 1TB01003-003C09-AMA-LTR-0069 | DVO 002 |  | 1TB01003-003C09-DCC-LTR-0124 | 2024-09-30 | -568990.79 |  |  |  | AMA01003-WTRAN-024110 | 2024-11-25 | ACTIVE | -579997.48 | APPROVED |  |  |  |  | 0
35 | Changes in AMAALA Yacht Club Back-of-House Finishes (Ground Level)_SAB | Post Contract Variation | Amaala |  |  | DVO - Pending from Contractor / Consultant | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | RFC 024 | 0 | 2023-12-31 | CANCELLED | AMA01003-WTRAN-010223 | NO | NOT ACTIVE | 56240.63 | PVO 10 | 0 | 2024-01-31 | CANCELLED | AMA01003-WTRAN-011785 | NO | NOT ACTIVE | 56240.63 | VO 08 | 2024-01-31 | CANCELLED | AMA01003-WTRAN-011785 | VO 008 | 2024-02-12 | 1TB01003-003C03-AMA-LTR-0124 | [5 empty] | AMA01003-GENCORR-000402 | 2024-03-13 | 0 |  |  | NOT ACTIVE |  | CANCELLED |  |  | PVO (AMA01003-WTRAN-016769) and VO (AMA01003-WTRAN-016770) Cancelled. DEPA to carry out all the BOH Finishes. |  | 0
36 | HKS - Approved Final Account Statement (Stage 5b not carried out) - Adjustment to Committed Cost | Post Contract Variation | Final Account |  |  | DVO - Accepted | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | HKL (Design Architect)-Prf Fees | HKS Design Consultant |  |  |  | FAS |  |  | APPROVED |  |  | ACTIVE |  |  |  |  | APPROVED |  |  | ACTIVE |  |  |  | APPROVED | [12 empty] | AMA01003-WTRAN-005459 | 2023-08-15 | ACTIVE | -89775 | APPROVED |  |  | Final Account Statement - Approved. |  | 0
37 | Façade Glazing Installations - Buildability Issue | Post Contract Variation | Omission - Contractor Performance |  |  | RFC - Pending to Upload on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | 18 | 2023-12-18 | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 17 | 0 | 2024-08-17 | APPROVED | AMA01003-WTRAN-019542 |  | ACTIVE | -10807729.2 | VO 13 | 2024-09-04 | APPROVED | AMA01003-WTRAN-020424 | VO 013 | 2024-09-05 | 1TB01003-003C03-AMA-LTR-0216 | DV 013 | [7 empty] | AMA01003-WTRAN-028101 | 2025-02-28 | ACTIVE | -10808089.2 | APPROVED |  |  | DVO issued to SAB and in dispute. Higher Management to advise. |  | 0
38 | AYC ¦ Grand Stair Structure Backfill | Post Contract Variation | Amaala |  |  | PVO - Pending for Approval on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | RFC 26 | 0 | 2024-02-12 | APPROVED | AMA01003-WTRAN-012379 | NO | ACTIVE | 166610 | PVO 12 | [5 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | SAB has not been notified of submitting a variation cost for this. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
39 | Omission of Joinery LED Light Fittings from SAB | Post Contract Variation | Scope Overlap |  |  | VO - Pending to Upload on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 27 | 0 | 2024-02-25 | APPROVED | AMA01003-WTRAN-012949 | NO | ACTIVE | -139212.69 | PVO 14 |  | 2024-03-28 | APPROVED | AMA01003-WTRAN-014620 |  | ACTIVE | -139212.69 | VO 11 | 2024-04-28 | APPROVED | AMA01003-WTRAN-015428 | VO 011 | 2024-04-28 | 1TB01003-003C03-AMA-LTR-0153 | DVO 011 | [7 empty] | AMA01003-WTRAN-019712 | 2024-08-22 | ACTIVE | -109949.92 | APPROVED |  |  |  |  | 0 | 116 | 26 | -29262.77
40 | Various Fit-out Changes (Riva Lounge "Curved Banquette Support Wall", Porte Cochere "Wall Access Panels")_SAB | Post Contract Variation | Design Development |  |  | VO - Pending to Upload on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 28 | 0 | 2024-02-11 | APPROVED | AMA01003-WTRAN-012342 | NO | ACTIVE | -14163.45 | PVO 13 |  | 2024-03-28 | APPROVED | AMA01003-WTRAN-017989 |  | ACTIVE | -12334.95 | VO 12 | 2024-08-05 | APPROVED | AMA01003-WTRAN-019077 | VO 012 | 2024-08-06 | 1TB01003-003C03-AMA-LTR-0189 | DVO 012 |  | SAB01003-GENCORR-000334 | 2024-10-05 | -14163.45 |  |  |  | AMA01003-WTRAN-022102 | 2024-10-14 | ACTIVE | -14163.45 | APPROVED |  |  |  |  | 0 | 69 | -1828.5
40 | Various Fit-out Changes (Riva Lounge "Curved Banquette Support Wall", Porte Cochere "Wall Access Panels")_DEPA | Post Contract Variation | Design Development |  |  | PVO - Pending for Approval on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | 28 | 0 | 2024-02-11 | APPROVED | AMA01003-WTRAN-012342 | NO | ACTIVE | 203124.38 | 4 |  | 2024-08-17 | APPROVED | AMA01003-WTRAN-019544 |  | ACTIVE | 72215.12 | VO 04 | 2024-09-06 | APPROVED | AMA01003-WTRAN-020463 | VO 04 | 2024-09-07 | 1TB01003-003C09-AMA-LTR-0066 | [8 empty] | AMA01003-WTRAN-027820 | 2025-02-22 | ACTIVE | 66509.75 | APPROVED |  |  | Determination |  | 0
41 | Alternative Marina Operations Storage location selected (DEWAN) | Consultant Variation | Design Dev |  |  | RFC - Pending for Approval on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 29 | 0 |  | CANCELLED | AMA01003-RFC-000029 | NO | NOT ACTIVE | 248219 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Superseded by RFC 032 |  | 0
41 | Alternative Marina Operations Storage location selected (SAB) | Consultant Variation | Design Dev |  |  | RFC - Pending for Approval on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 29 | 0 |  | CANCELLED | AMA01003-RFC-000029 | NO | NOT ACTIVE | 761399.15 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Superseded by RFC 032 |  | 0
42 | Changes in AMAALA Yacht Club Back-of-House Finishes (Level 01 to L 04)_DEPA | Post Contract Variation | Scope Gap |  |  | VO - Pending to Upload on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | 30 |  | 2024-03-28 | APPROVED | AMA01003-WTRAN-014599 | NO | ACTIVE | 202735.84 | PVO 03 |  | 2024-08-21 | APPROVED | AMA01003-WTRAN-019655 |  | ACTIVE | -122736.16 | V0 03 | 2024-09-06 | APPROVED | AMA01003-WTRAN-020465 | VO 03 | 2024-09-07 | 1TB01003-003C09-AMA-LTR-0070 | DVO 003 | [7 empty] | AMA01003-WTRAN-025026 | 2024-12-15 | ACTIVE | -806974.47 | APPROVED |  |  |  |  | 0
42 | Changes in AMAALA Yacht Club Back-of-House Finishes (Level 01 to L04)_SAB | Post Contract Variation | Scope Gap |  |  | RFC - Pending for Approval on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 30 |  | 2024-03-28 | APPROVED | AMA01003-WTRAN-014599 | NO | ACTIVE | -349595.15 | PVO 15 |  | 2024-10-18 | APPROVED | AMA01003-WTRAN-022308 | NO | ACTIVE | -349595.15 | VO 18 | 2024-10-24 | APPROVED | AMA01003-WTRAN-022646 | VO 18 | 2024-10-24 | 1TB01003-003C03-AMA-LTR-0231 | DVO 018 | [7 empty] | AMA01003-WTRAN-026512 | 2025-01-28 | ACTIVE | -400630.49 | APPROVED |  |  | Assesment issued to SAB. |  | 0
43 | Changes to Skirting and Ceiling Finishes at Member’s Lobby | Post Contract Variation | Scope Gap |  |  | PVO - Pending to Upload on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | 34 |  | 2024-03-28 | APPROVED | AMA01003-WTRAN-014600 | NO | ACTIVE | 136931.74 | 5 |  | 2024-05-30 | APPROVED | AMA01003-WTRAN-016771 |  | ACTIVE | 131832.8 | VO 05 | 2024-06-06 | APPROVED | AMA01003-WTRAN-017014 | VO 05 | 2024-06-08 | 1TB01003-003C09-AMA-LTR-0045 | DVO 005 | [7 empty] | AMA01003-WTRAN-020255 | 2024-09-03 | ACTIVE | 79197.8 | APPROVED |  |  |  |  | 0 | 87 | -52635 | 52635
44 | Passenger Elevator’s Landing Doors Finishes and Architraves | Post Contract Variation | Amaala |  |  | RFC - Pending for Approval on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | 35 |  | 2024-04-29 | CANCELLED | AMA01003-WTRAN-015545 | NO | NOT ACTIVE | 278057 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | DEPA acknowledged these are part of their scope. |  | 0
45 | Floor Finish Type CSF-1 | Post Contract Variation | Design Development |  |  | RFC - Pending for Approval on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 36 |  | 2024-05-08 | APPROVED | AMA01003-WTRAN-016017 | NO | ACTIVE | 140560.76 | PVO 18 |  | 2024-08-17 | APPROVED | AMA01003-WTRAN-019543 | NO | ACTIVE | 140560.76 | VO 14 | 2024-08-28 | APPROVED | AMA01003-WTRAN-019894 | VO 014 | 2024-08-28 | 1TB01003-003C03-AMA-LTR-0213 | DVO 014 |  | SAB01003-GENCORR-000333 | 2024-10-03 | 140560.76 |  |  |  | AMA01003-WTRAN-022103 | 2024-10-14 | ACTIVE | 140560.76 | APPROVED |  |  |  |  | 0 |  | 0
46 | DEPA Accommodation Outside TB-Construction Village | Post Contract Variation | Prelims |  |  | RFC - Approved | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | 37 |  | 2024-07-01 | APPROVED | AMA01003-WTRAN-017464 | NO | ACTIVE | 1341633 | 7 | 0 | 2024-08-21 | APPROVED | AMA01003-WTRAN-019654 | NO | ACTIVE | 288500 | VO 07 | 2024-09-04 | APPROVED | AMA01003-WTRAN-020422 | VO 07 | 2024-09-05 | 1TB01003-003C09-AMA-LTR-0065 | DVO 007 |  | 1TB01003-003C09-DCC-LTR-0127 | 2024-10-02 | 454577.38 |  |  |  | AMA01003-WTRAN-027785 | 2025-02-20 | ACTIVE | 182428.13 | APPROVED |  |  | Determination |  | 0
47 | Reduction to SAB Account due to Termination of Contract - Final Account | Post Contract Variation | Amaala |  |  | RFC - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | 19 | 2024-05-02 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
48 | New Contractor - (Civil, Arch, MEP & ICT/ELV) - Award of New Contract (Early Warning ROM) | Post Contract Variation | Amaala |  |  | RFC - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | New Contract - Civil and Arch Works, MEPD & ICT/ELV | New Contractor | 20 | 2024-05-02 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
49 | AYC Back-of-House (BOH) Doors and Fire Curtains at the Basement Level | Post Contract Variation | Scope Gap |  |  | PVO - Pending to Upload on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | 38 |  | 2024-06-10 | APPROVED | AMA01003-WTRAN-017087 | NO | ACTIVE | 1021958 | 6 | 0 | 2024-07-18 | APPROVED | AMA01003-WTRAN-018184 | YES | ACTIVE | 1021958 | VO 06 | 2024-08-05 | APPROVED | AMA01003-WTRAN-019080 | VO 06 | 2024-08-06 | 1TB01003-003C09-AMA-LTR-0055 | DVO 006 | [7 empty] | AMA01003-WTRAN-022720 | 2024-10-26 | ACTIVE | 823315.11 | APPROVED |  |  |  |  | 0
50 | Outstanding Works Block Works All Levels | Post Contract Variation | Amaala |  |  | RFC - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | [9 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Cancelled |  | 0
51 | Outstanding Works Block Works All Levels | Post Contract Variation | Amaala |  |  | RFC - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | [9 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE |  | VO 12 | 2024-05-22 | [15 empty] | NOT ACTIVE |  |  |  |  | Cancelled |  | 0
52 | Provision of New IBS Infra. Requirements for Indoor GSM | Post Contract Variation | Amaala |  |  | RFC - Approved | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 39 |  | 2024-06-10 | CANCELLED | AMA01003-WTRAN-017086 | YES | NOT ACTIVE | 308222 | PVO 23 |  | 2024-10-23 | CANCELLED | AMA01003-WTRAN-022577 |  | NOT ACTIVE | 1017433 | VO 19 | 2024-11-03 | CANCELLED | AMA01003-WTRAN-023123 | VO 019 | 2024-11-04 | 1TB01003-003C03-AMA-LTR-0233 | [10 empty] | NOT ACTIVE |  | CANCELLED |  |  |  |  | 0
53 | Landscape Package Budget - Transfer to CN Budget (Fund used in Alutec Contract Award) | Pre Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Hard and Soft Landscaping |  | 21 | 2023-05-29 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Contract Awarded to Alutec |  | 0
54 | Contract Adjustment to Medtel (per agreed Final Account Statement) | Post Contract Variation | Final Account |  |  | DVO - Accepted | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Medtel - STO Façade Mock-up | Medtel |  |  |  | FAS |  |  | APPROVED |  |  | ACTIVE |  |  |  |  | APPROVED |  |  | ACTIVE |  |  |  | APPROVED | [12 empty] | AMA01003-WTRAN-015429 | 2024-04-28 | ACTIVE | -15000 | APPROVED |  |  | Final Account Statement - Approved. |  | 0 |  |  | 4031723.49
55 | Relocation Marina Offices and Regeneration Kitchen (DEWAN) | Post Contract Variation | Design Development |  |  | PVO - Pending to Upload on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 32 |  | 2024-05-08 | APPROVED | AMA01003-WTRAN-016018 |  | ACTIVE | 898219 | PVO 009 |  | 2024-08-06 | APPROVED | AMA01003-WTRAN-019132 | NO | ACTIVE | 319588 | VO 09 | 2024-09-16 | APPROVED | AMA01003-WTRAN-020913 | VO 09 | 2024-09-16 | AMA01003-WTRAN-020912 | DVO 09 |  | 1TB01003-003D01-DAE-LTR-0028R1 | 2024-10-04 | 234500 |  |  |  | AMA01003-WTRAN-025027 | 2024-12-15 | ACTIVE | 482719 | APPROVED |  |  |  |  | 0
55 | Relocation Marina Offices and Regeneration Kitchen (Kitchen) | Post Contract Variation | Amaala |  |  | RFC - Approved | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Special Kitchen | RAQTAN |  |  |  | 32 |  | 2024-05-08 | APPROVED | AMA01003-WTRAN-016018 |  | ACTIVE | 1109644.6 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | RAQTAN has not been notified of submitting a variation cost for this. This will be dealt with in the final account reconciliation with RAQTAN; therefore, there is no need to process a PVO/VO. |  | 0
55 | Relocation Marina Offices and Regeneration Kitchen (Construction plus abortive Works) | Post Contract Variation | Amaala |  |  | RFC - Approved | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 32 |  | 2024-05-08 | CANCELLED | AMA01003-WTRAN-016018 |  | NOT ACTIVE | 2230142.99 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Included elsewhere as per approved RFA |  | 0
56 | AYC Guest Lobby Staircase Geometry & Finish Revisions (Dewan) | Post Contract Variation | Design Development |  |  | RFC - Pending for Approval on Aconex | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 41 |  | 2024-07-01 | APPROVED | AMA01003-WTRAN-017494 |  | ACTIVE | 75000 | PVO 06 |  | 2024-08-06 | APPROVED | AMA01003-WTRAN-019133 | NO | ACTIVE | 75000 | VO 06 | 2024-08-29 | APPROVED | AMA01003-WTRAN-019956 | VO 06 | 2024-09-04 | 1TB01003-003D01-AMA-LTR-0010 | DVO 010 |  | 1TB01003-003D01-DAE-LTR-0032 | 2024-10-01 | 65793 |  |  |  | AMA01003-WTRAN-022722 | 2024-10-26 | ACTIVE | 65793 | APPROVED |  |  |  |  | 0
56 | AYC Guest Lobby Staircase Geometry & Finish Revisions (Construction) | Post Contract Variation | Amaala |  |  | RFC - Pending for Approval on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | 41 |  | 2024-07-01 | CANCELLED | AMA01003-WTRAN-017494 |  | NOT ACTIVE | 0 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Consolidated into one change event under Item 58 |  | 0
57 | Basement Extract Duct 'Blueduct' Remedial Works (Dewan) | Post Contract Variation | Amaala |  |  | RFC - Approved | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 42 |  | 2024-07-01 | CANCELLED | AMA01003-WTRAN-017463 | NO | NOT ACTIVE | 84501 |  |  |  | CANCELLED |  |  | NOT ACTIVE |  |  |  | CANCELLED | [14 empty] | NOT ACTIVE |  | CANCELLED |  |  | Cancelled for DEWAN. SAB to proceed with the Design and Construction of blue duct without cost impact. |  | 0
57 | Basement Extract Duct 'Blueduct' Remedial Works (Construction) | Post Contract Variation | Contractor's Performance |  |  | RFC - Approved | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 42 |  | 2024-07-01 | APPROVED | AMA01003-WTRAN-017463 | NO | ACTIVE | 236632.77 | PVO 19 |  | 2024-08-13 | APPROVED | AMA01003-WTRAN-019392 | NO | ACTIVE | 0 | VO 16 | 2024-09-09 | APPROVED | AMA01003-WTRAN-020576 | VO 016 | 2024-09-10 | 1TB01003-003C03-AMA-LTR-0221 | DVO 016 |  | SAB01003-GENCORR-000368 | 2024-10-26 | 0 |  |  |  | AMA01003-WTRAN-023127 | 2024-11-03 | ACTIVE | 0 | APPROVED |  |  | Cancelled for DEWAN. SAB to proceed with the Design and Construction of blue duct without cost impact. |  | 0
58 | AYC Members Lobby Staircase Balustrade & Finish Revisions (Dewan) | Post Contract Variation | Design Development |  |  | RFC - Pending for Approval on Aconex | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 43 |  | 2024-07-02 | APPROVED | AMA01003-WTRAN-017495 |  | ACTIVE | 75000 | PVO 07 |  | 2024-08-06 | APPROVED | AMA01003-WTRAN-019134 | NO | ACTIVE | 75000 | VO 07 | 2024-09-10 | APPROVED | AMA01003-WTRAN-020623 | VO 07 | 2024-09-10 | 1TB01003-003D01-AMA-LTR-0011 | DVO 009 |  | 1TB01003-003D01-DAE-LTR-0033 | 2024-10-01 | 65793 |  |  |  | AMA01003-WTRAN-022721 | 2024-10-26 | ACTIVE | 65793 | APPROVED |  |  |  |  | 0
58 | Changes to Members Lobby and Guest Lobby Staircase Ballustrades | Post Contract Variation | Amaala |  |  | RFC - Pending for Approval on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | 43 |  | 2024-07-02 | APPROVED | AMA01003-WTRAN-017495 |  | ACTIVE | 27201.54 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This is related to VO 014 and will be included in the DVO 014 reconciliation with DEPA. Therefore, there is no need to process a PVO/VO. |  | 0
59 | Grand Stair Balustrade Revision to Avoid Fall Hazard (Dewan) | Post Contract Variation | Design Development |  |  | RFC - Pending for Approval on Aconex | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 44 |  | 2024-07-03 | APPROVED | AMA01003-WTRAN-017582 |  | ACTIVE | 75000 | 12 |  | 2024-08-13 | APPROVED | AMA01003-WTRAN-019393 |  | ACTIVE | 75000 | VO 08 | 2024-09-08 | APPROVED | AMA01003-WTRAN-020507 | VO 08 | 2024-09-08 | 1TB01003-003D01-AMA-LTR-0012 | DVO 011 |  | 1TB01003-003D01-DAE-LTR-0034 | 2024-10-01 | 69099 |  |  |  | AMA01003-WTRAN-023125 | 2024-11-03 | ACTIVE | 69099 | APPROVED |  |  |  |  | 0
59 | Grand Stair Balustrade Revision to Avoid Fall Hazard (Construction) | Post Contract Variation | Amaala |  |  | RFC - Pending for Approval on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 44 |  | 2024-07-03 | APPROVED | AMA01003-WTRAN-017582 |  | ACTIVE | 180170 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
60 | Deduction of Accommodation Costs from SAB (up to May 2024) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | [5 empty] | 2024-06-18 | CANCELLED | 1TB01003-003C03-AMA-LTR-0175 |  | NOT ACTIVE | -11230418.75 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
NSCC - 025 | Recovery of Cost (AYC Piles and Design) - Final Account | Post Contract Variation | Design Dev |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | NSCC - Piling | NSCC | 22 | 2024-06-30 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
NSCC - 026 | Adjustment to DVO 09 & DVO 07, Recovery of Accommodation & Engineer's Fee - Final Account | Post Contract Variation | Design Dev |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | NSCC - Piling | NSCC | 23 | 2024-06-30 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
61 | Addition of Accessories to Existing Artwork Proposal - Change Decision Pack_Artelier | Post Contract Variation | Scope Gap |  |  | PVO - Pending to Upload on Aconex | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DAE -Prf Fees | DEWAN ARCHI |  |  |  | 45 |  | 2024-07-13 | APPROVED | AMA01003-WTRAN-017928 |  | ACTIVE | 118500 | 13 |  | 2024-10-03 | APPROVED | AMA01003-WTRAN-021710 | NO | ACTIVE | 130350 | VO 10 | 2024-10-12 | APPROVED | AMA01003-WTRAN-022051 | VO 10 | 2024-10-13 | 1TB01003-003D01-AMA-LTR-0014 | DVO12 |  | 1TB01003-003D01-DAE-LTR-0036 | 2024-10-14 | 130350 |  |  |  | AMA01003-WTRAN-023126 | 2024-11-03 | ACTIVE | 130350 | APPROVED |  |  |  |  | 0
61 | Addition of Accessories to Existing Artwork Proposal - Change Decision Pack_Artwork Package | Post Contract Variation | Design Dev |  |  | PVO - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | OS&E Items | Areen |  |  |  | 45 |  | 2024-07-13 | APPROVED | AMA01003-WTRAN-017928 |  | ACTIVE | 429156 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
62 | Adjustment to FF&E Budget per the approved RFA Cost Plan | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | OS&E Items | Areen | 24 | 2024-07-31 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Per the approved RFA Ref. Final (WF-007250) 1TB01-003F06-AMA-RFA-FE-0002- FF&E and OS&E Cost Plan Budget approval - AYC |  | 0
63 | Adjustment to OSE Budget per the approved RFA Cost Plan | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | OS&E Items | Areen | 25 | 2024-07-31 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Per the approved RFA Ref. Final (WF-007250) 1TB01-003F06-AMA-RFA-FE-0002- FF&E and OS&E Cost Plan Budget approval - AYC |  | 0
64 | Potential Contract Cost Adjustment | Post Contract Variation | Amaala |  |  | RFC - Pending to Upload on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | 26 | 2024-07-31 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
65 | Langan - Approved Final Account Statement - Adjustment to Committed Cost per the Actual Reimbursable Expenses | Post Contract Variation | Final Account |  |  | DVO - Accepted | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | LUI-Prf Fees | Langan |  |  |  | FAS |  |  | APPROVED |  |  | ACTIVE |  |  |  |  | APPROVED |  |  | ACTIVE |  |  |  | APPROVED | [12 empty] | AMA01003-WTRAN-018985 | 2024-08-03 | ACTIVE | -1898.52 | APPROVED |  |  | Final Account Statement - Approved. |  | 0
66 | Additional drainage works to GF and Basement Level | Post Contract Variation | Design Dev |  |  | DVO - Pending from Contractor / Consultant | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 47 |  | 2024-09-10 | CANCELLED | AMA01003-WTRAN-020624 |  | NOT ACTIVE | 99419.13 | PVO 21 |  | 2024-10-18 | CANCELLED | AMA01003-WTRAN-022307 |  | NOT ACTIVE | 110148.84 | VO 17 | 2024-10-24 | CANCELLED | WF-008358AMA01003-WTRAN-022677 | VO 17 | 2024-10-24 | 1TB01003-003C03-AMA-LTR-0230 | [10 empty] | NOT ACTIVE |  | CANCELLED |  |  | SAB noted that some locations of the proposed drainage are not applicable. Issued to Jaya/MEP Team to clarify. |  | 0
67 | Independent Comissioning Agent (CML International) | Pre Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | CML-Mgt Fees | CML | 27 | 2023-05-29 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
68 | Issuing of Civil Defence Drawings | Post Contract Variation | Design Development |  |  | DVO - Accepted | Contractor | [5 empty] | Baytur | [6 empty] | APPROVED | JHS-GENCORR-000008 |  | ACTIVE |  | PVO 20 | 1 | 2024-08-17 | APPROVED | AMA01003-WTRAN-019545 |  | ACTIVE | 0 | VO 15 | 2024-09-01 | APPROVED | AMA01003-WTRAN-020174 | VO 015 | 2024-09-04 | 1TB01003-003C03-AMA-LTR-0218 | DVO 015 | [7 empty] | AMA01003-WTRAN-024654 | 2024-12-08 | ACTIVE | 0 | APPROVED |  |  |  |  | 0
69 | Additional Primary side CHW Valve Arrangement, Flushing Bypass and BTU Meter | Post Contract Variation | Amaala |  |  | RFC - Pending for Approval on Aconex | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 48 | 0 | 2024-09-28 | CANCELLED | AMA01003-WTRAN-021467 | NO | NOT ACTIVE | 223236 | PVO 22 |  | 2024-10-23 | CANCELLED | AMA01003-WTRAN-022578 |  | NOT ACTIVE | 223236 | VO 20 | 2024-11-18 | CANCELLED | AMA01003-WTRAN-023813 | VO 020 | 2024-11-19 | 1TB01003-003C03-AMA-LTR-0234 | [10 empty] | NOT ACTIVE |  | CANCELLED |  |  | Reminder sent to SAB on cost proposal. |  | 0
70a | Amphitheatre Works issued to MAS - Process not followed | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MAS - Amphitheatre | MAS | EW 028 | 2023-09-16 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Contract Award to MAS Executed. |  | 0
70b | Cancellation of Amphitheatre Works issued to MAS - Process not followed | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 029 | 2023-09-16 | -1108000 | [6 empty] | NOT ACTIVE |  | PVO 24 | [5 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
71a | Remaining Block work, Plaster work and Paint Work to be carried out by MAS - Process not followed | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MAS - Labour Supply - Wet Works | MAS | EW 030 | 2024-10-13 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
71b | Recovery of Remaining Block work, Plaster work and Paint Work to be carried out by MAS - Process not followed | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 031 | 2024-10-13 | -4004000 | [6 empty] | NOT ACTIVE |  | PVO 25 | [5 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This EI was drafted and issued by delivery on the 15th September 2024, Processes were not followed. No need for PVO/VO. This will be dealt with in the Final Account. |  | 0
72 | Alteration to finishes due to Façade Layout Changes - Process not Followed | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 032 | 2023-09-16 | 69000 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Works completed. DEPA has not been notified of submitting a variation cost for this. This will be dealt with in the final account reconciliation with DEPA; therefore, there is no need to process a PVO/VO. |  | 0
73 | Additional Porte Cochere Works to be carried out by MAS | Post Contract Variation | Scope Gap |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MAS - Amphitheatre | MAS | EW 033 | 2024-10-13 | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 001 |  | 2025-02-24 | APPROVED | AMA01003-WTRAN-027856 |  | ACTIVE | 249727.67 | [15 empty] | AMA01003-WTRAN-029815 | 2025-04-08 | ACTIVE | 205658.08 | APPROVED |  |  | Previously under MAS Various Works |  | 0
74 | MEP Manpower Supply to AYC Project on behalf of SAB. |  | Omission - Contractor Performance |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | RFA Approved | [5 empty] | APPROVED |  |  | ACTIVE | -23125000 | PVO 26 |  | 2024-11-12 | APPROVED | AMA01003-WTRAN-023539 | NO | ACTIVE | -23125000 | VO 21 | 2024-11-24 | APPROVED | AMA01003-WTRAN-024066 | VO 021 | 2024-11-24 | 1TB01003-003C03-AMA-LTR-0237 | DVO 021 | [7 empty] | AMA01003-WTRAN-025698 | 2025-01-06 | ACTIVE | -23125000 | APPROVED |  |  | DVO issue to SAB, awaiting signature and stamping. |  | 0
75 | Deployment of Seven (7) Surveyors | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 034 |  | 201600 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | SAB has not been notified of submitting a variation cost for this. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
76 | Employer’s instruction for ID Finishes on Vertical Transportation Fixture Elements | Post Contract Variation | Design Development |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 035 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 008 |  | 2024-12-23 | APPROVED | AMA01003-WTRAN-025347 |  | ACTIVE | 370875 | VO 08 | 2025-01-18 | APPROVED | AMA01003-WTRAN-026099 | VO 08 | 2025-01-20 | 1TB01003-003C09-AMA-LTR-0103 | [10 empty] | NOT ACTIVE |  | PENDING |  |  |  |  | 622 |  | 2025-04-20 |  |  | 2026-10-04 15:58 | -532.6655
77 | AYC – Disassembly and Reassembly of electronic items from VT fixtures | Post Contract Variation | Scope transfer - Contractor's Performance |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | ESCCO - Vertical Transport | ESCCO | EW 036 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 001 |  | 2024-12-30 | APPROVED | AMA01003-WTRAN-025580 |  | ACTIVE | 123400 | VO 01 | 2025-01-19 | APPROVED | AMA01003-WTRAN-026104 | VO 01 | 2025-01-20 | 1TB01003-003F03-AMA-LTR-0025 | [8 empty] | AMA01003-WTRAN-030617 | 2025-04-25 | ACTIVE | 77425 | APPROVED |  |  |  |  | 0
78 | Scaffolding works for Secondary Steel and Façade (Design) | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 037 |  | 75000 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE |  | VO 23 | [16 empty] | NOT ACTIVE |  |  |  |  | SAB has not been notified of submitting a variation cost for this. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
79 | Reflective Ceiling (Award to Armetal) | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | ARMETAL - Reflective ceiling | ARMETAL | EW 038 | 2024-11-07 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Contract awarded to Armetal. |  | 0
80 | Reflective Ceiling (Omission from SAB) |  | Scope transfer - Contractor's Performance |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 039 | 2024-11-07 | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 27 |  | 2024-12-23 | APPROVED | AMA01003-WTRAN-025346 |  | ACTIVE | -1457002.08 | VO 22 | 2025-01-18 | APPROVED | AMA01003-WTRAN-026104 | VO 22 | 2025-01-20 | 1TB01003-003C03-AMA-LTR-0256 | [8 empty] | AMA01003-WTRAN-033846 | 2025-06-25 | ACTIVE | -1402364.5 | APPROVED |  |  | Determination |  | 0
81 | Al Fanar MEP Manpower Supply to AYC Project on behalf of SAB. | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 040 | 2024-11-07 | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Contract Awarded to Al Fanar |  | 0
82 | Installation of MDF Platform / Ceiling | Post Contract Variation | Design Development |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 041 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 9 |  | 2025-02-06 | APPROVED | AMA01003-WTRAN-026899 |  | ACTIVE | 296700 | VO 09 | 2025-02-19 | APPROVED | AMA01003-WTRAN-027783 | VO 09 | 2025-02-22 | 1TB01003-003C09-AMA-LTR-0111 | [8 empty] | AMA01003-WTRAN-032154 | 2025-05-20 | ACTIVE | 291410 | APPROVED |  |  |  |  | 0
83 | Column Dry Wall Cladding and Partitions | Post Contract Variation | Scope transfer - Contractor's Performance |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 042 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 10 |  | 2025-02-06 | APPROVED | AMA01003-WTRAN-026900 |  | ACTIVE | 24255 | VO 10 | 2025-02-19 | APPROVED | AMA01003-WTRAN-027782 | VO 10 | 2025-02-25 | 1TB01003-003C09-AMA-LTR-0112 | [8 empty] | AMA01003-WTRAN-033876 | 2025-06-26 | ACTIVE | 76534.98 | APPROVED |  |  |  |  | 0 | 52279.98
84 | Column Dry Wall Cladding and Partitions (Blockworks Omission) | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 043 |  | -9180 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
85 | Replace the existing FOH electrical faceplates in designated areas of the Project with upgraded units meeting specifications. | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 044 |  | 0 |  |  |  | TRANSFERRED |  |  | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
86 | Replace the existing FOH electrical faceplates in designated areas of the Project with upgraded units meeting specifications. (Omission from SAB) | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 045 |  | -68541 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
87 | LPG Works (Al Fanar) | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 046 |  | 0 |  |  |  | TRANSFERRED |  |  | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
88 | LPG Works (Omission from SAB) | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 047 |  | -582220 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
89 | Al Fanar MEP Manpower Supply to AYC Project on behalf of SAB - Adjustment |  | Scope transfer - Contractor's Performance |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 048 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 1 |  | 2025-02-06 | APPROVED | AMA01003-WTRAN-026898 |  | ACTIVE | 31270936 | VO 01 | 2025-02-16 | APPROVED | AMA01003-WTRAN-027536 | VO 01 | 2025-02-17 | 1TB01003-003C34-AMA-LTR-0015 | DV 001 | [7 empty] | AMA01003-WTRAN-029814 | 2025-04-08 | ACTIVE | 31270936 | APPROVED |  |  |  |  | 0
90 | Al Fanar Allowance for Purhcasing Materials |  | Scope transfer - Contractor's Performance |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 049 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 2 |  | 2025-06-03 | APPROVED | AMA01003-WTRAN-033125 |  | ACTIVE | 9188438.51 | VO 02 | 2025-06-04 | APPROVED | AMA01003-WTRAN-033281 | VO 02 | 2025-06-01 | 1TB01003-003C34-AMA-LTR-0023 | DV 002 | [7 empty] | AMA01003-WTRAN-033844 | 2025-06-25 | ACTIVE | 9188438.51 | APPROVED |  |  |  |  | 0
91 | Allowance for SAB (Grankraft) works on mockup (same as advance payment amount) | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 050 |  | 852173.913 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Included in the approved RFA for Cost to Complete (Grankraft). This amount is being used to make direct payments to SAB's suppliers and subcontractors. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
92 | Additional Costs related to Aluminium Soffits & Cladding - Alcatop | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 051 |  | 1026091 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Included in the approved RFA for Cost to Complete (Alcatop). This amount is being used to make direct payments to SAB's suppliers and subcontractors. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
93 | Additional Costs related to Abu Dhabi Precast - GRC Cladding | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 052 |  | 3761897 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Included in the approved RFA for Cost to Complete (Abu Dhabi Precast). This amount is being used to make direct payments to SAB's suppliers and subcontractors. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
94 | Additional Costs related to Structural Metal Work - SAMIF | [5 empty] | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 053 |  | 4647142 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Included in the approved RFA for Cost to Complete (SAMIF). This amount is being used to make direct payments to SAB's suppliers and subcontractors. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
95 | Adjustment to GBCI account (per final invoice) |  | Design Development |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | GBC - Sustainability Accreditation | GBC | [6 empty] | APPROVED |  |  | ACTIVE |  |  |  |  | APPROVED |  |  | ACTIVE |  |  |  | APPROVED | [14 empty] | ACTIVE | -509.48 | APPROVED |  |  | Adjustment to GBCI account per the final invoice paid. |  | 0
96 | Dismantling and Reinstatement of Cold Rooms (Chiller 1, Chiller 2, and Chiller 3) including coordination | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Special Kitchen | RAQTAN | EW 054 | No EI issued to RAQTAN - check with JAYA. | 22250 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Works completed. RAQTAN has not been notified of submitting a variation cost for this. This will be dealt with in the final account reconciliation with RAQTAN; therefore, there is no need to process a PVO/VO. |  | 0
97 | Dismantling and Reinstatement of Cold Rooms (Chiller 1, Chiller 2, and Chiller 3) including coordination - Backcharge | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 055 |  | -22250 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
98 | Extension of Khatib & Alami Call-Off Order (Allowance) | Post Contract Variation | EOT - Contractor's Performance |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | KAA-Mgt Fees | KAA | EW 056 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 02 |  | 2025-02-17 | APPROVED | AMA01003-WTRAN-027568 |  | ACTIVE | 0 | VO 02 | 2025-02-20 | APPROVED | AMA01003-WTRAN-027805 | VO 02 | 2025-02-22 | 1TB01003-003F02-AMA-LTR-0030 | DVO 002 | [7 empty] | AMA01003-WTRAN-029047 | 2025-03-17 | ACTIVE | 0 | APPROVED |  |  |  |  | 0
99 | Aluminum Flashing for Alutec | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC | EW 057 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 01 |  | 2025-04-29 | APPROVED | AMA01003-WTRAN-030818 |  | ACTIVE | 478548 | VO 01 | 2025-05-11 | APPROVED | AMA01003-WTRAN-031610 | VO 01 | 2025-05-12 | 1TB01003-003C27-AMA-LTR-0038 | [8 empty] | AMA01003-WTRAN-045024 | 2025-12-07 | ACTIVE | 256470.07 | APPROVED |  |  |  |  | 0 | DVO issued | 2025-08-10 | 2025-08-03 |  | 2026-10-04 15:58 | -420.6655
SIC - 006 | SIC Contract (Works not Done) | Pre Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SOI TB Ground Improvement Works | SIC | EW 058 |  | -500000 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be incorporated in the SIC Final Account. Awaiting confirmation from Prog 2 Commercial. |  | 0
SIC - 006 | SIC Contract (PS - Not done) | Pre Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SOI TB Ground Improvement Works (PS) | SIC | EW 059 |  | -282972 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be incorporated in the SIC Final Account. Awaiting confirmation from Prog 2 Commercial. |  | 0
100 | DEPA EOT 01 Prolongation Cost (Estimated) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 060 |  | 8100000 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | DEPA to submit the actual cost upon agreement of the time imact for EOT 001. |  | 0
101 | Abu Dhabi Precast - GRC Cladding Contract Award | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | ABU DHABI PRECAST - GRC Cladding | Abu Dhabi Precast | EW 061 |  | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Contract award to Abu Dhabi Precast. |  | 0
102 | Omission of Limestone from SAB | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 062 |  | -133949.24 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Included in the approved RFA for SAB Cost to Complete (Limestone). This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
102 | Cost to Complete (SAB Amount) - Including Contingencies | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 063 |  | 53011624.83 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Included in the approved RFA for SAB Cost to Complete (SAB Cost). This amount is being used to make direct payments to SAB's suppliers and subcontractors. This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
103 | Back-of-House Finishes (EI 006)_DEPA | Post Contract Variation | Contractor's Performance |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 064 | 2026-04-28 | 0 |  |  | 2025-01-23 | APPROVED | AMA01003-WTRAN-026301 |  | ACTIVE | 2010911.37 | PVO 015 |  | 2025-06-25 | APPROVED | AMA01003-WTRAN-033845 |  | ACTIVE | 2521135.52 | VO 15 | 2025-07-07 | APPROVED | AMA01003-WTRAN-034325 | VO 15 | 2025-07-08 | 1TB01003-003C09-AMA-LTR-0142 | DVO 015 | [7 empty] | AMA01003-WTRAN-051511 | 2026-06-14 | ACTIVE | 2521135.52 | APPROVED |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0 |  | 2025-10-06 | 2025-09-29 |  | 2026-10-04 15:58 | -363.6655
103a | Completion of the remaining Back of House Finishes [PART 02] | Post Contract Variation | Contractor's Performance |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | [5 empty] | 2025-01-23 | APPROVED | AMA01003-WTRAN-026301 |  | ACTIVE | 521731 | PVO 035 |  | 2026-05-15 | APPROVED | AMA01003-WTRAN-050879 |  | ACTIVE | 581730.52 | VO 035 | 2026-06-04 | APPROVED | AMA01003-WTRAN-051347 | VO 35 | 2026-05-02 | 1TB01003-003C09-AMA-LTR-0055 | DVO 015 | [7 empty] | AMA01003-WTRAN-051511 | 2026-06-14 | ACTIVE | 581730.52 | APPROVED |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0 |  | 2026-07-31 | 2026-07-24 |  | 2026-10-04 15:58 | -65.6655
104 | Back-of-House Finishes (EI 006)_SAB | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 065 |  | -701856.29 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
105 | Additional Manpower and Supervision Supply | Post Contract Variation | Scope transfer - Contractor's Performance |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MAS - Labour Supply - Wet Works | MAS | [6 empty] | APPROVED |  |  | ACTIVE |  | PVO 001 |  | 2025-02-28 | APPROVED | AMA01003-WTRAN-028102 |  | ACTIVE | 13737620 | 1 | 2025-03-10 | APPROVED | AMA01003-WTRAN-028740 | VO 001 | 2025-03-11 | 1TB01003-003C31-AMA-LTR-0012 | [8 empty] | AMA01003-WTRAN-030619 | 2025-04-25 | ACTIVE | 13737620 | APPROVED |  |  |  |  | 0
106 | HAS - External Scaffolding Works (Contract Award) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | HAS - External Scaffolding Works | HAS | EW 066 |  | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Contract Award to HAS |  | 0
111 | Metal Mesh Grating as per CML requirements in MEP shafts | Post Contract Variation | Scope Gap |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | [6 empty] | APPROVED |  |  | ACTIVE | 230000 | PVO 29 |  | 2025-06-29 | APPROVED | AMA01003-WTRAN-033936 |  | ACTIVE | 275000 | VO 24 | 2025-07-07 | APPROVED | AMA01003-WTRAN-034324 | VO 24 | 2025-07-08 | 1TB01003-003C03-AMA-LTR-0291 | DVO 024 | [7 empty] | AMA01003-WTRAN-041164 | 2025-10-16 | ACTIVE | 228070 | APPROVED |  |  | Pre EI issued and signed by HOC - dated 20 March 2025. Works to be carried out by SAMIF |  | 0 | Reminder issue on 30/7 | 2025-10-06 | 2025-09-29 |  | 2026-10-04 15:58 | -363.6655
112 | Employer’s Instruction No.01 - Supply of additional Kitchen Shelf Opening Hatch (Servery Hatches) | Post Contract Variation | Scope transfer - Contractor's Performance |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Special Kitchen | RAQTAN | EW 067 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 001 |  | 2025-05-17 | APPROVED | AMA01003-WTRAN-031936 |  | ACTIVE | 15939 | VO 01 | 2025-05-29 | APPROVED | AMA01003-WTRAN-032742 | VO 01 | 2025-05-29 | 1TB01003-003C08-AMA-LTR-0033 | [8 empty] | 1TB01003-003C08-AMA-DVO-CM-0001 | oct 2025 | ACTIVE | 10143 | APPROVED |  |  |  |  | 0 |  | 2025-08-27 | 2025-08-20 |  | 2026-10-04 15:58 | -403.6655
113 | Employers Instruction No. 07 – Supply and Installation of Millworks to Show Kitchens | Post Contract Variation | Scope Gap |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 068 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 012 |  | 2025-05-17 | APPROVED | AMA01003-WTRAN-031937 |  | ACTIVE | 312470.43 | VO 12 | 2025-05-23 | APPROVED | AMA01003-WTRAN-032317 | VO 12 | 2025-05-26 | 1TB01003-003C09-AMA-LTR-0132 | DVO 012 | [7 empty] | AMA01003-WTRAN-050932 | 2026-05-18 | ACTIVE | 0 | APPROVED |  |  | Determination issued to DEPA on the 29 April 2026 under letter reference 1TB01003-003C09-AMA-LTR-0236 |  | 0 |  | 2025-08-24 | 2025-08-17 |  | 2026-10-04 15:58 | -406.6655
114 | Employers Instruction No. 08 – Installation of Ceilings to Cold Rooms | Post Contract Variation | Design Development |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 069 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 011 |  | 2025-04-29 | APPROVED | AMA01003-WTRAN-030819 |  | ACTIVE | 34684 | VO 11 | 2025-05-11 | APPROVED | AMA01003-WTRAN-031613 | VO 11 | 2025-05-12 | 1TB01003-003C09-AMA-LTR-0127 | DVO 011 | [7 empty] | AMA01003-WTRAN-037046 | 2025-08-21 | ACTIVE | 27249.9 | APPROVED |  |  |  |  | 0 | DVO 1ssued | 2025-08-10 | 2025-08-03 | Determination drafted 7/21/2025 | 2026-10-04 15:58 | -420.6655
115 | Employers Instruction No. 09 – Honeycomb Limestone System and External Doors | Post Contract Variation | Scope transfer - Contractor's Performance |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 070 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 013 |  | 2025-05-07 | APPROVED | AMA01003-WTRAN-031302 |  | ACTIVE | 850370.6 | VO 13 | 2025-05-11 | APPROVED | AMA01003-WTRAN-031613 | VO 13 | 2025-05-12 | 1TB01003-003C09-AMA-LTR-0129 | [10 empty] | NOT ACTIVE |  | PENDING |  |  |  |  | 510 | DVO issued | 2025-08-10 | 2025-08-03 |  | 2026-10-04 15:58 | -420.6655
116 | Employer's Instruction No. 10 - Changes In the Balustrade Materials at the Member's Lobby and Guest Foyer | Post Contract Variation | Design Development |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 071 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 014 |  | 2025-05-17 | APPROVED | AMA01003-WTRAN-031938 |  | ACTIVE | 0 | VO 14 | 2025-05-25 | APPROVED | AMA01003-WTRAN-032522 | VO 014 | 2025-05-26 | 1TB01003-003C09-AMA-LTR-0133 | DVO 014 | 0 | [6 empty] | AMA01003-WTRAN-053899 | 2026-08-15 | ACTIVE | 0 | APPROVED |  |  | Commercial carried out a determination in line with letter ref 1TB01003-003C09-AMA-LTR-0257 dated 22 july 2026 |  | 0 |  | 2025-08-24 | 2025-08-17 |  | 2026-10-04 15:58 | -406.6655
117 | Employer's Instruction No. 017 - Grand Stair Handrail (Alcatop) | Post Contract Variation | Design Development |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 072 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 28 |  | 2025-05-20 | APPROVED | AMA01003-WTRAN-032153 |  | ACTIVE | 856801.79 | VO 23 | 2025-06-18 | APPROVED | AMA01003-WTRAN-033505 | VO 23 | 2025-06-18 | 1TB01003-003C03-AMA-LTR-0285 | [8 empty] | AMA01003-WTRAN-036019 | 2025-08-04 | ACTIVE | 677313.67 | APPROVED |  |  |  | -179488.12 | 0 | DVO issued 21/7/25 | 2025-09-16 | 2025-09-09 | DVO initiated | 2026-10-04 15:58 | -383.6655
118 | Employer’s Instruction for Variation – Panic Alarm System for ADA toilets | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 073 |  | 87285 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be included in the material supply DVO with Al Fanar; therefore, there is no need to process a PVO/VO. |  | 0
119 | Additional Labour for Al Fanar (July to Oct 2025) | Post Contract Variation | Scope transfer - Contractor's Performance |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 074 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 3 |  |  | APPROVED | AMA01003-WTRAN-036214 |  | ACTIVE | 13280713.77 | VO 03 | 2025-08-19 | APPROVED | AMA01003-WTRAN-036949 | VO 03 | 2025-08-19 | 1TB01003-003C34-AMA-LTR-0030 | [8 empty] | AMA01003-WTRAN-038231 | 2025-09-04 | ACTIVE | 14557384.22 | APPROVED |  |  |  |  | 0
119a | Potential savings against MAS labour supply agreement | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MAS - Labour Supply - Wet Works | MAS | EW 075 |  | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
120 | GRC Repair Works | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MASS - GRC Repair Works | MASS - GRC Repair Works | EW 076 |  | 0 |  |  |  | CANCELLED |  |  | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
121 | Omission of Interior Designer Selected Light Fittings (included in the FF&E) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 077 |  | -1173602.39 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
122 | Omission of Swimming Pool Lights (supplied by Al Fanar) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 078 |  | -581464.2 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
123 | Direct Payments to SAB's Subcontractors and Suppliers (Jan, Feb and Mar 2025). | Post Contract Variation | Scope transfer - Contractor's Performance |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 079 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 30 |  | 2025-06-29 | APPROVED | AMA01003-WTRAN-033937 |  | ACTIVE | -8870230.27 | VO 25 | 2024-07-07 | APPROVED | AMA01003-WTRAN-034305 | VO 25 | 2025-07-08 | 1TB01003-003C03-AMA-LTR-0292 | [8 empty] | AMA01003-WTRAN-045025 | 2025-12-07 | ACTIVE | -8946555.92 | APPROVED |  |  |  |  | 0 | DVO issued on 30/Jul/25 | 2025-10-06 | 2025-09-29 |  | 2026-10-04 15:58 | -363.6655 |  | 76325.65
124 | Clause 11.11 (Backcharging by Employer) - Supply of Electricians by Al Fanar for ESCCO’s Vertical Transportation Installations | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | ESCCO - Vertical Transport | ESCCO | EW 080 |  | -15675 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with RAQTAN; therefore, there is no need to process a PVO/VO. |  | 0
125 | Descope FF12.04 Millwork & Procure Globe via Depa | Post Contract Variation | Design Development |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | 50 |  | 2025-06-01 | APPROVED | AMA01003-RFC-000050 |  | ACTIVE | 21275.25 | PVO 016 |  | 2025-06-01 | APPROVED | AMA01003-WTRAN-032895 |  | ACTIVE | 21275.25 | VO 16 | 2025-06-01 | APPROVED | AMA01003-WTRAN-032895 | VO 16 | 2025-06-01 | 1TB01003-003C09-AMA-LTR-0138 | DVO 016 | [7 empty] | AMA01003-WTRAN-050007 | 2026-04-19 | ACTIVE | 59543.76 | APPROVED |  |  |  |  | 0 | DVO issued 5/Nov/25 | 2025-08-30 | 2025-08-23 |  | 2026-10-04 15:58 | -400.6655
126 | Extension of Areen Design Limited Services as FF&E and OS&E Procurement Agent for the AMAALA Yacht Club (AYC) Project. | Post Contract Variation | EOT - Contractor's Performance |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | FF&E and OSE Procurement Agent | Areen | EW 081 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 001 |  | 2025-07-15 | APPROVED | AMA01003-WTRAN-034664 |  | ACTIVE | 519230.25 | VO 01 | 2025-07-24 | APPROVED | AMA01003-WTRAN-035323 | VO 01 | 2025-07-24 | 1TB01003-003F06-AMA-LTR-0010 | [8 empty] | AMA01003-WTRAN-036019 | 2025-08-04 | ACTIVE | 568680.75 | APPROVED |  |  |  |  | 0 |  | 2025-10-22 | 2025-10-15 |  | 2026-10-04 15:58 | -347.6655
127 | Extension of Khatib & Alami Construction Supervision Services, until 31 December 2025. | Post Contract Variation | EOT - Contractor's Performance |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | KAA-Mgt Fees | KAA | EW 082 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 03 |  | 2025-07-28 | APPROVED | AMA01003-WTRAN-035537 |  | ACTIVE | 1655399.8 | VO 03 | 2025-08-04 | APPROVED | AMA01003-WTRAN-036030 | VO 03 | 2025-08-05 | 1TB01003-003F02-AMA-LTR-0037 | DVO 003 | [7 empty] | AMA01003-WTRAN-037047 | 2025-08-21 | ACTIVE | 1655399.8 | APPROVED |  |  |  |  | 0
128 | Supply and Installation of Steel Support Framing for Roller Shutter Door | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 083 |  | TBC | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [6 empty] | 2025-06-21 | Pending | [10 empty] | NOT ACTIVE |  |  |  |  | Pre ei drafted and issued to delivery team |  | 0
129 | Extension of CML Independent Commissioning Agent Services - Construction Phase | Post Contract Variation | EOT - Contractor's Performance |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | CML-Mgt Fees | CML | EW 084 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 1 |  | 2025-07-28 | APPROVED | AMA01003-WTRAN-035536 |  | ACTIVE | 822640.54 | VO 001 | 2025-08-13 | APPROVED | AMA01003-WTRAN-036496 | VO 001 | 2025-08-13 | 1TB01003-003F08-AMA-LTR-0013 | [8 empty] | AMA01003-WTRAN-037630 | 2025-08-27 | ACTIVE | 882640.54 | APPROVED |  |  |  |  | 0
130 | Direct Payments to SAB's Subcontractors and Suppliers (Apr & May 2025). | Post Contract Variation | Scope transfer - Contractor's Performance |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 085 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 31 |  | 2025-08-30 | APPROVED | AMA01003-WTRAN-037741 |  | ACTIVE | -7235632.79 | VO 26 | 2025-09-14 | APPROVED | AMA01003-WTRAN-038897 | VO 26 | 2025-09-15 | 1TB01003-003C03-AMA-LTR-0300 | [8 empty] | AMA01003-WTRAN-046218 | 2026-01-06 | ACTIVE | -8078367.19 | APPROVED | [5 empty] | DVO isued on 05Nov25 | -842734.4 |  |  |  |  | -842734.4 | 842734.4
131 | Direct Payments to SAB's Subcontractors and Suppliers (May 2025). | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 086 |  | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0 | [7 empty] | 919060.05
132 | Encashment of Performance Bond | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 087 |  | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
133 | Encashment of Advance Bond | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 088 |  | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
134 | Modification to Members Lobby & Guest Foyer Staircase Finishes | Post Contract Variation | Design Development |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | 53 |  |  | APPROVED | AMA01003-RFC-000053 |  | ACTIVE | 104000 | PVO 017 |  | 2025-08-11 | APPROVED | AMA01003-WTRAN-036403 |  | ACTIVE | 104000 | VO 17 | 2025-08-11 | APPROVED | AMA01003-WTRAN-036403 | VO 17 | 2025-08-12 | 1TB01003-003C09-AMA-LTR-0151 | DVO 017 | [7 empty] | AMA01003-WTRAN-051855 | 2026-06-25 | ACTIVE | 74300 | APPROVED |  |  | Commercial carrying out a Determination under approval Ref to WF-021497 |  | 0
135 | Powder coating of wiring accessories (to suit ID requirements) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 089 |  | 20000 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be included in the material supply DVO with Al Fanar; therefore, there is no need to process a PVO/VO. |  | 0
136 | MEP Material Supply by Al Fanar (Al Fanar DVO 002; SAR 9,188,438.51) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 090 |  | TBC | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
137 | Al Fanar manpower deployment extension up to July 2025 (DVO 001; SAR 31,270,936) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 091 |  | TBC | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
138 | Al Fanar manpower deployment extension up to Oct 2025 (DVO 003; SAR 13,280,713.77) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 092 |  | TBC | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
139 | EI 05: Clearance of blocked drainage at Basement | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 093 |  | TBC | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
140 | EI 14: Installation of Decorative Lights | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 094 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 20 |  | 2025-11-24 | APPROVED | AMA01003-WTRAN-044253 |  | ACTIVE | 150000 | VO 020 | 2025-12-01 | APPROVED | AMA01003-WTRAN-044773 | VO 020 | 2025-12-04 | 1TB01003-003C09-AMA-LTR-0185 | [10 empty] | ACTIVE | 51810 | APPROVED |  |  |  |  | 0
141 | Omission of Accommodation Budget from SAB (Payment for Tamimi) - to be deducted from SAB Contract Adjustment EW 063. | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 095 |  | -10718725 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
142 | Overrun on SAB's Accommodation Budget (Payment for Tamimi) - to be deducted from SAB Contract Adjustment EW 063. | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 096 |  | -9279215.75 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
143 | Payment to Tamimi Accommodation | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Tamimi (SAB Accommodation Payment) | Tamimi | EW 097 |  | 0 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This amount is the estimated payment to Tamimi for SAB's accommodation. This will be dealt during the final account. |  | 0
144 | Direct Payments to SAB's Subcontractors and Suppliers (June and July 2025). | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 098 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 33 |  | 2025-11-16 | APPROVED | AMA01003-WTRAN-043571 |  | ACTIVE | -9541748.66 | VO 28 | 2025-11-24 | PENDING | AMA01003-WTRAN-044295 | VO 28 | 2025-11-27 | 1TB01003-003C03-AMA-LTR-0305 | DVO 028 | 0 | [6 empty] | AMA01003-WTRAN-050982 | 2026-05-19 | ACTIVE | -9525198.67 | APPROVED |  |  | Determination issued to SAB on the 29 April 2026 under letter reference 1TB01003-003C03-AMA-LTR-0329 |  | 0 |  | 16549.99
145 | Direct Payments to SAB's Subcontractors and Suppliers (August 2025). | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 100 |  | -5277917.79 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
146 | Direct Payments to SAB's Subcontractors and Suppliers (September 2025). | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 101 |  | -3192741.9 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
147 | Direct Payments to SAB's Subcontractors and Suppliers (October 2025). | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 102 |  | -3189139.87 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Direct Payment |  | 0
148 | Direct Payments to SAB's Subcontractors and Suppliers (Nov and Dec 2025). | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 103 |  | -4203149.6 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
149 | Direct Payments to SAB's Subcontractors and Suppliers (Jan and Feb 2026). | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 104 |  | TBC | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
151 | EI 05: Powder coating of ID light fittings (to suit ID requirements) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 105 |  | 21000 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [5 empty] | EI 04 | 2025-08-19 | 1TB01003-003C34-AMA-LTR-0031 | [10 empty] | NOT ACTIVE |  |  |  |  | This will be included in the material supply DVO with Al Fanar; therefore, there is no need to process a PVO/VO. |  | 0
152 | EI 13: Supply and Install Access Doors | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 106 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 19 |  | 2025-11-07 | APPROVED | AMA01003-WTRAN-043064 |  | ACTIVE | 60000 | VO 19 | 2025-11-13 | APPROVED | AMA01003-WTRAN-043479 | VO 19 | 2025-11-15 | 1TB01003-003C09-AMA-LTR-0178 | DVO 019 | [7 empty] | AMA01003-WTRAN-051510 | 2026-06-14 | ACTIVE | 31585.33 | APPROVED |  |  | Determination issued to DEPA on the 29 April 2026 under letter reference 1TB01003-003C09-AMA-LTR-0233 |  | 0
153 | EI 07: Change in Sprinkler Cover Colour | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 107 |  | TBC | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [5 empty] | EI 07 | 2025-08-27 | 1TB01003-003C34-AMA-LTR-0035 | [10 empty] | NOT ACTIVE |  |  |  |  | This will be included in the material supply DVO with Al Fanar; therefore, there is no need to process a PVO/VO. |  | 0
154 | EI 06: Change in Powder Coating of Air Outlets | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 108 |  | TBC | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [5 empty] | EI 06 | 2025-08-26 | 1TB01003-003C34-AMA-LTR-0034 | [10 empty] | NOT ACTIVE |  |  |  |  | This will be included in the material supply DVO with Al Fanar; therefore, there is no need to process a PVO/VO. |  | 0
155 | EI 05: Change in Powder Coating of Air Outlest | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 109 | [5 empty] | CANCELLED |  |  | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | EI 05: See item No. 139 |  | 0
156 | Replacement of buggy ramp handrail with road studs. | Post Contract Variation | Design Development |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | 54 |  | 2025-09-12 | APPROVED | AMA01003-RFC-000054 |  | ACTIVE | 0 | PVO 32 |  | 2025-09-12 | APPROVED | AMA01003-WTRAN-038781 |  | ACTIVE | 27800 | VO 27 | 2025-09-12 | APPROVED | AMA01003-WTRAN-038781 | VO 27 | 2025-09-14 | 1TB01003-003C03-AMA-LTR-0301 | DVO 027 | [7 empty] | AMA01003-WTRAN-043732 | 2025-11-18 | ACTIVE | -13210 | APPROVED |  |  |  | 41010 | 0 | DVO isued on 05Nov25
157 | Notice of Backcharge to SAB - Altenative Labour Support to Abu Dhabi Precast (IMAR & Fibrex) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 110 |  | 0 | RFA 005 | 0 | 2025-10-28 | APPROVED | AMA01009-WTRAN-187015 | NO | ACTIVE | -286488 | 42 | 0 | 2026-08-06 | APPROVED | AMA01003-WTRAN-053606 | NO | ACTIVE | -606210 | VO 036 | 2026-08-13 | APPROVED | AMA01003-WTRAN-053818 | [13 empty] | NOT ACTIVE |  | PENDING |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 46299
158 | EI 16: Change in Aged Mirror finish to members' bar & Signature Restaurant | Post Contract Variation | Design Development |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 111 |  | 0 | 56 |  |  | APPROVED |  |  | ACTIVE |  | 18 |  | 2025-11-01 | APPROVED | AMA01003-WTRAN-042423 |  | ACTIVE | -204382 | VO 18 | 2025-11-01 | APPROVED | AMA01003-WTRAN-042423 | VO 18 | 2025-11-05 | 1TB01003-003C09-AMA-LTR-0177 | DVO 018 | 0 | [6 empty] | AMA01003-WTRAN-052754 | 2026-07-19 | ACTIVE | -204382 | APPROVED |  |  | Commercial carrying out a Determination under approval Ref to WF-021496 |  | 0
159 | Balance Works for ICT System (NESMA) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 112 |  | 2674938 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be part of the direct payments negative PVO. Therefore, there is no need to process a separate PVO/VO for this item. |  | 0
160 | EI-15: Removing and replace tiling around faulty Urinal Sensors | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 113 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 21 |  | 2025-11-24 | APPROVED | AMA01003-WTRAN-044254 |  | ACTIVE | 72092.72 | VO 021 | 2025-12-01 | APPROVED | AMA01003-WTRAN-044771 | VO 021 | 2025-12-04 | 1TB01003-003C09-AMA-LTR-0186 | [8 empty] | AMA01003-WTRAN-048184 | 2025-02-18 | ACTIVE | 74046.44 | APPROVED |  |  |  |  | 0
161 | Omission of Internal Windows (Kitchen Service Hatches) from SAB - Supply and install by RAQTAN | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 114 |  | -8078.16 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | This will be dealt with in the final account reconciliation with SAB; therefore, there is no need to process a PVO/VO. |  | 0
162 | EI-17: Road Markings Paint Application | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 115 |  | 8000 | [6 empty] | NOT ACTIVE |  | PVO 022 |  |  | PENDING |  |  | NOT ACTIVE |  | VO 022 |  | PENDING | [14 empty] | NOT ACTIVE | [6 empty] | 0
163 | Extension of Al Fanar Mapower Services to AMAALA Yacht Club Project through to December 2025, and DLP Contingency (January to March 2025). | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 116 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 04 |  | 2025-12-14 | APPROVED | AMA01003-WTRAN-045282 |  | ACTIVE | 8136064 |  | 2025-12-23 | APPROVED | AMA01003-WTRAN-045703 | VO 004 | 2025-12-23 | 1TB01003-003C34-AMA-LTR-0043 | [8 empty] | AMA01003-WTRAN-047632 | 2026-02-08 | ACTIVE | 8136064 | APPROVED |  |  |  |  | 0
164 | Extension of MAS Manpower Services (Nov to Dec 2025) - TB01003-003C31-AMA-RFA-CM-0002 | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MAS - Labour Supply - Wet Works | MAS | EW 117 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 002 |  | 2025-11-13 | APPROVED | AMA01003-WTRAN-043439 |  | ACTIVE | 3050936 | VO 02 | 2025-11-20 | APPROVED | AMA01003-WTRAN-043985 | VO 002 | 2025-11-20 | 1TB01003-003C31-AMA-LTR-0023 | [8 empty] | AMA01003-WTRAN-044940 | 2025-12-04 | ACTIVE | 3050936 | APPROVED |  |  |  |  | 0
165 | Provision for the additional CCTV Cameras for Yacht Lounge Bars (cut off and making good). | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 118 |  | 0 | 55 |  |  | CANCELLED |  |  | NOT ACTIVE | 0 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Works completed. No notice and claim for DEPA, therefore no no need to process a PVO/VO. |  | 0
166 | EI-18: Consolidated Fit-Out Instructions (Ceiling, LPG, Capping, Beech Ovens & Hood Cladding) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 119 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 023 |  | 2025-11-24 | APPROVED | AMA01003-WTRAN-044255 |  | ACTIVE | 234288.38 | VO 023 | 2025-12-01 | APPROVED | AMA01003-WTRAN-044774 | VO 023 | 2025-12-04 | 1TB01003-003C09-AMA-LTR-0187 | DVO 023 | [7 empty] | AMA01003-WTRAN-050983 | 2026-05-19 | ACTIVE | 201886.12 | APPROVED |  |  | Determination issued to DEPA on the 29 April 2026 under letter reference 1TB01003-003C09-AMA-LTR-0235
167 | EI-19: Replacement of Vanity Top Soap Dispensers and Rectification of Existing Vanity Units | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 120 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 024 |  | 2025-11-24 | APPROVED | AMA01003-WTRAN-044256 |  | ACTIVE | 136268.96 | VO 024 | 2025-12-01 | APPROVED | AMA01003-WTRAN-044772 | VO 024 | 2025-12-04 | 1TB01003-003C09-AMA-LTR-0188 | DVO 024 | [7 empty] | AMA01003-WTRAN-050984 | 2026-05-19 | ACTIVE | 98093.01 | APPROVED |  |  | Determination issued to DEPA on the 29 April 2026 under letter reference 1TB01003-003C09-AMA-LTR-0233 |  | 0
168 | EI-20: Rectification of the Damaged Ceilings Based on the Various Damage Reports | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 121 | BC | 100000 | [6 empty] | NOT ACTIVE |  |  |  |  | PENDING |  |  | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
169 | EI-03: Cooled Glass Display Case at Café (CPD10). | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Special Kitchen | RAQTAN | EW 122 |  | 0 | [6 empty] | NOT ACTIVE |  |  |  |  | PENDING |  |  | NOT ACTIVE |  |  |  | PENDING | [14 empty] | NOT ACTIVE |  |  |  |  | PVO to prepare, though this has no cost impact. |  | 0
170 | EI-18 : Amendment of Secondary Steel Structure vs Honeycomb Limestone Cladding | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 123 |  | 54000 | [6 empty] | NOT ACTIVE |  |  |  |  | PENDING |  |  | NOT ACTIVE |  |  |  | PENDING | [14 empty] | NOT ACTIVE |  |  |  |  | PVO to prepare |  | 0
171 | EI-03: External Glass Door Application at Chart Model Room Staircase | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC | EW 124 |  | 0 |  |  |  | CANCELLED |  |  | NOT ACTIVE |  |  |  |  | CANCELLED |  |  | NOT ACTIVE |  |  |  | CANCELLED | [14 empty] | NOT ACTIVE | [6 empty] | 0
172 | Further MEP Material Supply by Al Fanar (excluded in the previous DVO) - Al Fanar letter 1TB01003-003C34-ACY-LTR-0057 | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 125 |  | 0 | [6 empty] | NOT ACTIVE |  |  |  |  | CANCELLED |  |  | NOT ACTIVE |  |  |  | CANCELLED | [14 empty] | NOT ACTIVE |  |  |  |  | RFA to be raised. |  | 0
173 | Replacement of External Doors - requested by the Operator (Cluster Manager - Back of House) |  | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC | EW 126 |  | 0 | [6 empty] | NOT ACTIVE |  |  |  |  | CANCELLED |  |  | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | No action has been taken in 5 months, hence cancelled |  | 0
174 | Adjustment for DEPA PVO 008, PVO 015 and PVO 013 (expected DVOs to be agreed) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 127 |  | 1936178.33 | [6 empty] | NOT ACTIVE |  |  |  |  | PENDING |  |  | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
175 | Additional Microperforated Ceiling and Wall Changes in Area 7 Business Lounge Atrium & Area 10 Restaurant | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 128 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 25 |  | 2026-01-05 | APPROVED | AMA01003-WTRAN-046176 |  | ACTIVE | 251957 | VO 025 | 2026-03-30 | APPROVED | AMA01003-WTRAN-049427 | VO 025 | 2026-03-30 | 1TB01003-003C09-AMA-LTR-0209 | DV0 025 | 0 | [6 empty] | AMA01003-WTRAN-052755 |  | ACTIVE | 206428.35 | APPROVED |  |  | Commercial carrying out a Determination under approval Ref to WF-021495 |  | 0
176 | Allow for rectification of damaged ceiling and other finishes. | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 128 | BC | 900000 | [6 empty] | NOT ACTIVE |  |  |  |  | PENDING |  |  | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | PVO to prepare |  | 0
177 | Employer’s Instruction No. 01 – Stainless Steel Flashing at Entrance Area (North and South) of the AMAALA Yacht Club | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | ARMETAL - Reflective ceiling | ARMETAL | EW 129 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 01 |  | 2026-02-18 | APPROVED | AMA01003-WTRAN-048183 |  | ACTIVE | 40390 | VO 01 | 2026-02-28 | APPROVED | AMA01003-WTRAN-048616 | VO 01 | 2026-03-02 | 1TB01003-003C33-AMA-LTR-0013 | DVO 001 | 0 | [6 empty] | AMA01003-WTRAN-050976 | 2026-05-19 | ACTIVE | 32437.75 | APPROVED |  |  |  |  | 0 |  | 7952.25
178 | Prelims - GLSAN Contracting Company (Red Sea) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Prelims - GLSAN Contracting Company (Red Sea) | Baytur | EW 130 |  | 0 | [6 empty] | NOT ACTIVE |  |  |  |  | PENDING |  |  | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
179 | Employer’s Instruction No. 005 - Replacement of Damaged Double-Curved Glass Panel at Business Atrium | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC | EW 131 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 02 |  | 2026-01-05 | APPROVED | AMA01003-WTRAN-046177 |  | ACTIVE | 325683 | VO 02 | 2026-01-28 | APPROVED | AMA01003-WTRAN-047104 | VO 02 | 2026-01-29 | 1TB01003-003C27-AMA-LTR-0060 | DVO 02 | 0 | [6 empty] | AMA01003-WTRAN-053445 | 2026-08-03 | ACTIVE | 226153.62 | APPROVED |  |  | Commercial carrying out a determination for approval under WF-021841 |  | 0
180 | Backcharging: Replacement of Damaged Double-Curved Glass Panel at Business Atrium | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 132 | BC | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 026 |  | 2026-01-05 | APPROVED | AMA01003-WTRAN-046175 |  | ACTIVE | -325683 | VO 026 | 2026-02-02 | APPROVED | AMA01003-WTRAN-047315 | VO 026 | 2026-02-04 | 1TB01003-003C09-AMA-LTR-0210 | DVO 026 | 0 | [6 empty] | AMA01003-WTRAN-055033 | 2026-09-19 | ACTIVE | -226153.62 | APPROVED |  |  | Commercial issued a determination under ref letter 1TB01003-003C09-AMA-LTR-0260 dated 19 July 2026 |  | 0
181 | Employer’s Instruction No. 024 – Removal and Reinstallation of ST-125 Wall Cladding to VVIP Toilet | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 133 | BC | 0 |  |  |  | APPROVED |  |  | ACTIVE | 25000 | PVO 027 |  | 2026-02-12 | APPROVED | AMA01003-WTRAN-047851 |  | ACTIVE | 25000 | VO 027 | 2026-02-26 | APPROVED | AMA01003-WTRAN-048412 | VO 027 | 2026-02-26 | 1TB01003-003C09-AMA-LTR-0223 | DVO 027 | 0 | [6 empty] | AMA01003-WTRAN-053447 | 2026-08-03 | ACTIVE | 12008.5 | APPROVED |  |  | Commercial carrying out a Determination under approval Ref to WF-021806 |  | 0
182 | Backcharging: Removal and Reinstallation of ST-125 Wall Cladding to VVIP Toilet | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 134 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE | -25000 | PVO 05 |  | 2026-02-12 | APPROVED | AMA01003-WTRAN-047852 |  | ACTIVE | -25000 | VO 05 | 2026-02-26 | APPROVED | AMA01003-WTRAN-048415 | VO 005 | 2026-02-26 | 1TB01003-003C34-AMA-LTR-0049 | DVO 005 | 0 | [6 empty] | AMA01003-WTRAN-055035 | 2026-09-19 | ACTIVE | -12008.5 | APPROVED |  |  | Determination was approved and issued to the contractor under Letter ref 1TB01003-003C34-AMA-LTR-0065 |  | 0
183 | EI 01: Extend the Senior Architect Construction Supervision Services until 31 January 2025. | Post Contract Variation | Amaala |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | KAA-Mgt Fees | KAA | EW 135 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 04 |  | 2025-01-15 | APPROVED | AMA01003-WTRAN-046530 |  | ACTIVE | 75000 | VO 04 | 2026-01-28 | APPROVED | AMA01003-WTRAN-047102 | VO 04 | 2026-01-29 | 1TB01003-003F02-AMA-LTR-0045 | [8 empty] | AMA01003-WTRAN-048185 | 2026-02-18 | ACTIVE | 78720 | APPROVED |  |  |  |  | 0
184 | Employer’s Instruction No. 01 – Extension of CML Independent Commissioning Agent Services until 28 February 2026 | Post Contract Variation | EOT - Contractor's Performance |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | CML-Mgt Fees | CML | EW 136 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 02 |  | 2026-01-17 | APPROVED | AMA01003-WTRAN-046616 |  | ACTIVE | 325350 | VO 01 | 2026-01-26 | APPROVED | AMA01003-WTRAN-047020 | VO 01 | 2026-01-29 | 1TB01003-003F08-AMA-LTR-0021 | [8 empty] | AMA01003-WTRAN-048990 | 2026-03-10 | ACTIVE | 325350 | APPROVED |  |  |  |  | 0
185 | Employer’s Instruction No. 022 – Replacement of Fire Pump and Jockey Pump | Post Contract Variation | Contractor's Performance |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  | Direct Payment to NAFCCO - This will be covered in the direct Payment PVO. | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
186 | Employer’s Instruction No. 024 – BMS Integration for Water Meters and BTU Meters | Post Contract Variation | Contractor's Performance |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  | Direct Payment to GLSAN - This will be covered in the direct Payment PVO. | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
187 | Employer’s Instruction No. 021 – Fire Extinguishers (Partial Levels 2, 3, 4 and Roof Areas) | Post Contract Variation | Contractor's Performance |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  | Direct Payment to NAFCCO - This will be covered in the direct Payment PVO. | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
188 | Employer's Instruction No. 020 – Replacement of the Aluminium Ceiling Panels | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 137 |  | 282122.46 | [6 empty] | NOT ACTIVE |  |  |  |  | PENDING |  |  | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | PVO to prepare |  | 0
189 | Type P3 Fiber Optic Lights Installation | Post Contract Variation | Contractor's Performance |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  | Direct Payment to HRFA - This will be covered in the direct Payment PVO. | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
190 | Employer’s Instruction No. 026 – Design, Manufacturing, Supply, Installation, and Commissioning of Kee Safety Kee Point | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 138 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 39 |  | 2026-02-27 | APPROVED | AMA01003-WTRAN-048579 |  | ACTIVE | 39485 | VO 33 | 2026-03-10 | APPROVED | AMA01003-WTRAN-049011 | VO 33 | 2026-03-15 | 1TB01003-003C03-AMA-LTR-0326 | DVO 033 | 0 | [6 empty] | AMA01003-WTRAN-050975 | 2026-05-19 | ACTIVE | 39485 | APPROVED |  |  | Determination issued to SAB on the 29 April 2026 under letter reference 1TB01003-003C03-AMA-LTR-0330 |  | 0
191 | Backcharge Notification: Marvel System for Ecology Unit provided by Raqtan on behalf of SAB | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 139 |  | -233351.85 | [6 empty] | NOT ACTIVE |  | PVO 34 |  |  | PENDING |  |  | NOT ACTIVE |  | VO 29 |  | PENDING | [14 empty] | NOT ACTIVE |  |  |  |  | PVO to prepare |  | 0
192 | Marvel System for Ecology Unit provided by Raqtan on behalf of SAB | Post Contract Variation | Scope transfer - Contractor's Performance |  |  |  | Contractor | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Special Kitchen | RAQTAN | EW 140 |  | 233351.85 | [6 empty] | NOT ACTIVE |  |  |  |  | PENDING |  |  | NOT ACTIVE |  |  |  | PENDING | [14 empty] | NOT ACTIVE |  |  |  |  | PVO to prepare |  | 0
193 | Employer’s Instruction No. 025 – Aluminum Cladding Panel Replacement at Various Locations (Discrepancy between the model and actual site conditions (construction tolerances).) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 141 |  | 269447.1 | [6 empty] | NOT ACTIVE |  | 37 |  |  | PENDING |  |  | NOT ACTIVE |  | VO 31 |  | PENDING | [14 empty] | NOT ACTIVE |  |  |  |  | PVO to prepare |  | 0
194 | Employer’s Instruction No. 029 – Replacement of Damaged Aluminum Panels | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 142 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 38 |  | 2026-02-27 | APPROVED | AMA01003-WTRAN-048575 |  | ACTIVE | 95857.63 | VO 32 | 2026-03-10 | APPROVED | AMA01003-WTRAN-049010 | VO 32 | 2026-03-13 | 1TB01003-003C03-AMA-LTR-0325 | DVO 032 | 0 | [6 empty] | AMA01003-WTRAN-055032 | 2026-09-19 | ACTIVE | 95857.63 | APPROVED |  |  | Determination approved internally and issued to SAB under Aconex Ref Letter 1TB01003-003C03-AMA-LTR-0338 dated 19 Aug 2026 |  | 0
195 | Employer’s Instruction No. 029 – Replacement of Damaged Aluminum Panels (BC to Alutec) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC | EW 143 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 6 |  | 2026-02-27 | APPROVED | AMA01003-WTRAN-048577 |  | ACTIVE | -31245.99 | VO 06 | 2026-03-10 | APPROVED | AMA01003-WTRAN-049012 | VO 06 | 2026-03-13 | 1TB01003-003C27-AMA-LTR-0067 | DVO 06 | 0 | [6 empty] | AMA01003-WTRAN-055127 | 2026-09-24 | ACTIVE | -31245.99 | APPROVED |  |  | Determination was approved and issued to the contractor under Aconex Letter Ref 1TB01003-003C27-AMA-LTR-0083 dated 18 Aug 2026 |  | 0
196 | Employer’s Instruction No. 029 – Replacement of Damaged Aluminum Panels (BC to DEPA) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 144 | BC | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 29 |  | 2026-02-27 | APPROVED | AMA01003-WTRAN-048576 |  | ACTIVE | -34198.38 | VO 29 | 2026-03-10 | APPROVED | AMA01003-WTRAN-049018 | VO 29 | 2026-03-13 | 1TB01003-003C09-AMA-LTR-0228 | DVO 029 | 0 | [6 empty] | AMA01003-WTRAN-055034 | 2026-09-19 | ACTIVE | -34198.38 | APPROVED |  |  | Commercial issued a determination under ref letter 1TB01003-003C09-AMA-LTR-0261 dated 18 aug 2026 |  | 0
197 | Employer’s Instruction No. 029 – Replacement of Damaged Aluminum Panels (BC to MAS) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MAS - Labour Supply - Wet Works | MAS | EW 145 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 3 |  | 2026-02-27 | APPROVED | AMA01003-WTRAN-048578 |  | ACTIVE | -14023.79 | VO 03 | 2026-03-10 | APPROVED | AMA01003-WTRAN-049014 | VO 03 | 2026-03-13 | 1TB01003-003C31-AMA-LTR-0027 | [10 empty] | NOT ACTIVE |  | PENDING |  |  | Commercial issued a determination under approval WF WF-022784 ref letter1TB01003-003C31-AMA-LTR-0033 dated 29 Sep 2026 |  | 205
198 | Employer’s Instruction No. 029 – Replacement of Damaged Aluminum Panels (BC to SALCO) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 |  |  |  | MVW Team to issue BC to SALCO. | -16389.47 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
199 | Employer’s Instruction No. 25 – Concealment of Linear LED Lights at Riva Lounge and Toilets | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 146 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 30 |  | 2026-03-02 | APPROVED | AMA01003-WTRAN-048724 |  | ACTIVE | 38760 | VO 30 | 2026-03-10 | APPROVED | AMA01003-WTRAN-049016 | VO 30 | 2026-03-13 | 1TB01003-003C09-AMA-LTR-0227 | DVO 030 | 0 | [6 empty] | Determination under approval | 2026-07-06 | NOT ACTIVE | 27417.61 | PENDING |  |  | Commercial carrying out a Determination under approval Ref to WF-021839 |  | 205
200 | Employer’s Instruction No. 030 – Changes in the Aluminum Panels Design (Accommodation of Actual Site Conditions: Adjustments are required to align with on-site realities resulting from changes within adjacent or interfacing work packages. • Aesthetic Enhancements: Revisions have been introduced to improve the visual outcome of the façade elements.) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 144 |  | 131987.45 | [6 empty] | NOT ACTIVE |  |  |  |  | PENDING |  |  | NOT ACTIVE |  |  |  | PENDING | [14 empty] | NOT ACTIVE |  |  |  |  | PVO to prepare. This is SAB |  | 0
201 | Employer’s Instruction No. 027 – Replacement of Amplifiers | Post Contract Variation | Contractor's Performance |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  | Direct Payment to Glsan - This will be covered in the direct Payment PVO. | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
202 | Employer’s Instruction No. 03 – Replacement for the Missing Passenger Elevator Door Locks | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | ESCCO - Vertical Transport | ESCCO | EW 145 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 2 |  | 2026-02-18 | APPROVED | AMA01003-WTRAN-048182 |  | ACTIVE | 24700 | VO 02 | 2026-02-28 | APPROVED | AMA01003-WTRAN-048618 | VO 02 | 2026-03-02 | 1TB01003-003F03-AMA-LTR-0043 | DVO 002 | 0 | [6 empty] | AMA01003-WTRAN-050977 | 2026-05-19 | ACTIVE | 13992 | APPROVED |  |  |  |  | 0
203 | Employer’s Instruction No. 03 – Replacement for the Missing Passenger Elevator Door Locks (BC to DEPA) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 146 | BC | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 28 |  | 2026-02-18 | APPROVED | AMA01003-WTRAN-048181 |  | ACTIVE | -24700 | VO 28 | 2026-02-28 | APPROVED | AMA01003-WTRAN-048617 | VO 28 | 2026-03-02 | 1TB01003-003C09-AMA-LTR-0225 | DVO 028 | [7 empty] | AMA01003-WTRAN-051856 | 2026-06-25 | ACTIVE | -13992 | APPROVED |  |  | Commercial carrying out a Determination under approval Ref to WF-021494 |  | 0
204 | Stainless Steel Mesh at Louver Area | Pre Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | ARMETAL - Reflective ceiling | ARMETAL | [6 empty] | APPROVED |  |  | ACTIVE |  | 2 |  | 2026-03-02 | APPROVED | AMA01003-WTRAN-048722 |  | ACTIVE | 47110 | VO 02 | 2026-02-17 | APPROVED | AMA01003-WTRAN-048137 | VO 02 | 3.3.26 | 1TB01003-003C33-AMA-LTR-0014 | DVO 002 | 0 | [6 empty] | AMA01003-WTRAN-050978 | 2026-05-19 | ACTIVE | 34640.8 | APPROVED |  |  |  |  | 0 |  | 12469.2
205 | Cost adjustment based on the Cash recovered The impact of this adjustment to SA Baytur 003C03 for the recovered Performance Bond and Advance Payment Bond, and the alignment to the aligned Paid amount is that NO further budget, commitment or payment transactions are to be made to this contract. | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | [6 empty] | APPROVED |  |  | ACTIVE |  |  |  |  | APPROVED |  |  | ACTIVE |  |  |  | APPROVED | [13 empty] | 2026-01-15 | ACTIVE | -17854517.05 | APPROVED |  |  | Manual Adjustment in ACC by the Payment Team |  | 0
206 | EVO No. 003 - Supply and Installation of Façade Pressure Plate Cover Flashing | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC | EW 147 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 3 |  | 2026-03-01 | APPROVED | AMA01003-WTRAN-048720 |  | ACTIVE | 261408 | VO 03 | 2026-02-17 | APPROVED | AMA01003-WTRAN-048129 | VO 03 | 2026-02-18 | 1TB01003-003C27-AMA-LTR-0063 | DVO 03 | 0 | [6 empty] | AMA01003-WTRAN-053449 | 2026-08-03 | ACTIVE | 90936.91 | APPROVED |  |  | Commercial carrying out a determination for approval under WF-021842 |  | 0
207 | EVO No. 004 -Provision of Vinyl Film with Frit Pattern to the Façade Glazing of the North and South Boutiques | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC | EW 148 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 4 |  | 2026-03-02 | APPROVED | AMA01003-WTRAN-048721 |  | ACTIVE | 48290 | VO 04 | 2026-02-17 | APPROVED | AMA01003-WTRAN-048131 | VO 04 | 2026-02-18 | 1TB01003-003C27-AMA-LTR-0064 | DVO 04 | 0 | [6 empty] | AMA01003-WTRAN-053450 | 2026-08-03 | ACTIVE | 17921.75 | APPROVED |  |  | Commercial carrying out a determination for approval under WF-021843 |  | 0
208 | EVO No. 005 - Extension of Consultant’s Senior Architect (Khatib & Alami) to 31 May 2026 | Post Contract Variation | Amaala |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | KAA-Mgt Fees | KAA | EW 149 |  | 0 | EVO 005 | 0 | 2026-03-16 | APPROVED | AMA01003-WTRAN-049140 | NO | ACTIVE | 314880 | PVO 005 | 0 | 2026-05-18 | APPROVED | AMA01003-WTRAN-050928 | NO | ACTIVE | 314880 | VO 05 | 2026-05-18 | APPROVED | AMA01003-WTRAN-050928 | VO 05 | 2026-03-16 | 1TB01003-003F02-AMA-LTR-0047 | DVO 005 | [7 empty] | AMA01003-WTRAN-051512 | 2026-06-14 | ACTIVE | 314880 | APPROVED |  |  |  |  | 0
209 | EVO No. 005 - Supply of Alutec Manpower to Install the External Glass Balustrade on Behalf of Alcatop | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC | EW 150 |  | 332640 |  |  |  | APPROVED |  |  | ACTIVE |  |  |  |  | PENDING |  |  | NOT ACTIVE | [5 empty] | VO 05 | 2026-02-18 | 1TB01003-003C27-AMA-LTR-0065 | [10 empty] | NOT ACTIVE |  |  |  |  | Emergency Variation order was issued on the 18th Feb 2026. PVO, DVO to be processed |  | 0
210 | EVO No. 005 - Supply of Alutec Manpower to Install the External Glass Balustrade on Behalf of Alcatop (BC to Alcatop) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 151 |  | -332640 |  |  |  | APPROVED |  |  | ACTIVE |  |  |  |  | PENDING |  |  | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
211 | EVO 30: Application of STO Ventec System to Conceal the Paving Level Gap at the Grand Stairs | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 152 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | PVO 36 |  | 2026-03-02 | APPROVED | AMA01003-WTRAN-048719 |  | ACTIVE | 115000 | VO 30 | 2026-02-18 | APPROVED | AMA01003-WTRAN-048178 | VO 030 | 2026-02-19 | 1TB01003-003C03-AMA-LTR-0324 | DVO 030 | 0 | [6 empty] | AMA01003-WTRAN-052760 | 2026-07-19 | ACTIVE | 115000 | APPROVED |  |  | Determination issued to SAB on the 29 April 2026 under letter reference 1TB01003-003C03-AMA-LTR-0330 |  | 0
212 | EVO No. 005 - Extension of Consultant’s Senior Architect (Khatib & Alami) to 31 May 2026 - Backcharge | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 153 |  | 0 | EVO 005 | 0 | 2026-03-16 | APPROVED | AMA01003-WTRAN-049140 | NO | ACTIVE | -196800 | 34 | 0 | 2026-05-18 | APPROVED | AMA01003-WTRAN-050929 | NO | ACTIVE | -196800 | VO 034 | 2026-07-16 | APPROVED | AMA01003-WTRAN-052728 | VO 034 | 2026-07-16 | 1TB01003-003C09-AMA-LTR-0254 | DVO 034 | 0 | [6 empty] | WF-022727 | 2026-09-23 | NOT ACTIVE | -196800 | PENDING |  |  | Commercial carrying out a determination in line with approved aconex letter ref 1TB01003-003C09-AMA-LTR-0265 |  | 80
213 | RFA 003: MAS labour extension up through January and February 2026 | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MAS - Labour Supply - Wet Works | MAS | EW 154 |  | 0 |  |  |  | APPROVED |  |  | ACTIVE |  | 4 |  | 2026-03-01 | APPROVED | AMA01003-WTRAN-048657 |  | ACTIVE | 1567562 | VO 04 | 2026-03-10 | APPROVED | AMA01003-WTRAN-049015 | VO 004 | 2026-03-13 | 1TB01003-003C31-AMA-LTR-0028 | [8 empty] | AMA01003-WTRAN-049492 | 2026-03-31 | ACTIVE | 1567562 | APPROVED |  |  |  |  | 0
214 | Employer's Instruction No. 02 - Relocation of Passenger Elevator Control Panels for PL-1, PL-2, PL-3, PL-4 & PL-5 | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | ESCCO - Vertical Transport | ESCCO | EW 155 | [5 empty] | APPROVED |  |  | ACTIVE |  | PVO 03 |  | 2026-03-02 | APPROVED | AMA01003-WTRAN-048723 |  | ACTIVE | 10400 | VO 03 | 2026-03-10 | APPROVED | AMA01003-WTRAN-049017 | VO 03 | 2026-03-13 | 1TB01003-003F03-AMA-LTR-0044 | DVO 03 | 0 | [6 empty] | AMA01003-WTRAN-050764 | 2026-05-11 | ACTIVE | 6656 | APPROVED |  |  |  |  | 0
215 | EVO 29 Rectification of damaged waterproofing at Water Features | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | EW 156 |  | 60000 |  |  |  | APPROVED |  |  | ACTIVE |  |  |  |  | PENDING |  |  | NOT ACTIVE | [5 empty] | VO 029 | 2026-02-18 | 1TB01003-003C03-AMA-LTR-0323 | [10 empty] | NOT ACTIVE |  |  |  |  | PVO to prepare |  | 0
216 | EVO 29 Rectification of damaged waterproofing at Water Features (BC) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 157 | BC | -60000 | [6 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | PVO to prepare |  | 0
217 | EVO 31: Omission of the Doors' Edge Guards | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 158 |  |  | EVO 031 | 0 | 2026-03-05 | APPROVED | AMA01003-WTRAN-048808 | NO | ACTIVE | -25000 | PVO 031 | 0 | 2026-05-12 | APPROVED | AMA01003-WTRAN-050799 | NO | ACTIVE | -25000 | VO 031 | 2026-03-05 | APPROVED | AMA01003-WTRAN-048808 | VO 031 | 2026-02-24 | 1TB01003-003C09-AMA-LTR-0229 | DVO-31 | 0 | [6 empty] | AMA01003-WTRAN-053448 | 2026-08-03 | ACTIVE | -25000 | APPROVED |  |  | Commercial carrying out a Determination under approval Ref to WF-021840 |  | 0
218 | EVO 04: Replacement of passenger elevator doors and accessories (Backcharge to DEPA) | Post Contract Variation | Back Charge |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | ESCCO - Vertical Transport | ESCCO | EW 159 |  | 0 | EVO 04 | 0 | 2026-03-24 | APPROVED | AMA01003-WTRAN-049245 | YES | ACTIVE | 765046.05 | PVO 04 |  | 2026-05-12 | APPROVED | AMA01003-WTRAN-050797 | YES | ACTIVE | 765046.05 | EVO 04 | 2026-03-24 | APPROVED | AMA01003-WTRAN-049245 | EVO 04 | 2026-03-25 | 1TB01003-003F03-AMA-LTR-0045 | [10 empty] | NOT ACTIVE |  | PENDING |  |  |  |  | 193
219 | EVO 04: Replacement of passenger elevator doors and accessories (Backcharge to DEPA) | Post Contract Variation | Back Charge |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | EW 160 |  | 0 | EVO 04 | 0 | 2026-03-24 | APPROVED | AMA01003-WTRAN-049245 | NO | ACTIVE | -765046.05 | PVO 032 | 0 | 2026-05-12 | APPROVED | AMA01003-WTRAN-050798 | YES | ACTIVE | -765046.05 | [17 empty] | NOT ACTIVE |  | PENDING |  |  |  |  | 46299
220 | Areen Extension 002 | Post Contract Variation |  |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | FF&E and OSE Procurement Agent | Areen | [6 empty] | APPROVED |  |  | ACTIVE |  | PVO 002 |  | 2026-03-13 | APPROVED | AMA01003-WTRAN-049116 |  | ACTIVE | 242502.8 | VO 02 | 2026-03-13 | APPROVED | AMA01003-WTRAN-049116 | VO 02 | 2026-03-14 | 1TB01003-003F06-AMA-LTR-0015 | [8 empty] | AMA01003-WTRAN-049493 | 2026-03-31 | ACTIVE | 248084.71 | APPROVED |  |  |  |  | 0
221 | Provision of Power and Data Connectivity for KOT Printers | Post Contract Variation | Operator's Change |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | EW 161 |  | 0 | RFC-000059 | 0 | 2026-04-26 | APPROVED | AMA01003-WTRAN-050202 | YES | ACTIVE | 65000 | PVO 006 | 0 | 2026-04-26 | APPROVED | AMA01003-WTRAN-050202 |  | ACTIVE | 65000 | VO 06 | 2026-04-26 | APPROVED | AMA01003-WTRAN-050202 | [13 empty] | NOT ACTIVE |  | PENDING |  |  |  |  | 46299
222 | Proposed F&B changes to enhance operational functionality and the overall guest experience, as requested by the Operator Kitchen | Post Contract Variation | Operator's Change |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | RFA-0002 | 0 | 2026-04-07 | APPROVED | AMA01003-WTRAN-049656 |  | ACTIVE | 645426 | 33 |  | 2026-08-09 | APPROVED | AMA01003-WTRAN-053656 | YES | ACTIVE | 632257.26 | VO 033 | 2026-05-12 | APPROVED | AMA01003-WTRAN-050802 | [13 empty] | NOT ACTIVE |  | PENDING |  |  |  |  | 46299
223 | Proposed F&B changes to enhance operational functionality and the overall guest experience, as requested by the Operator Fitout | Post Contract Variation | Operator's Change |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Special Kitchen | RAQTAN |  |  |  | RFA-0002 | 0 | 2026-04-07 | CANCELLED | AMA01003-WTRAN-049656 |  | NOT ACTIVE | 720575 | PVO 02 | 0 | 2026-05-16 | CANCELLED | AMA01003-WTRAN-050802 | NO | NOT ACTIVE | 720574.79 | VO 02 | 2026-05-16 | CANCELLED | AMA01003-WTRAN-050802 | [13 empty] | NOT ACTIVE |  |  |  |  | Cancelled, works give to MSFT under VBH trhough Teijun refer to line item 325 |  | 0
224 | Proposed F&B changes to enhance operational functionality and the overall guest experience, as requested by the Operator MEP | Post Contract Variation | Operator's Change |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar |  |  |  | RFA-0002 | 0 | 2026-04-07 | CANCELLED | AMA01003-WTRAN-049656 |  | NOT ACTIVE | 138883 |  |  |  | CANCELLED |  |  | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
225 | Extension of CML Independent Commissioning Agent Services until 31 May 2026 | Post Contract Variation |  |  |  |  | Consultant | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | CML-Mgt Fees | CML |  |  |  | EVO 03 | 0 | 2026-04-28 | APPROVED | AMA01003-WTRAN-050329 |  | ACTIVE | 312400 | PVO 03 |  | 2026-05-05 | APPROVED | AMA01003-WTRAN-050878 |  | ACTIVE | 312400 | VO 03 | 2026-04-28 | APPROVED | AMA01003-WTRAN-050329 | VO 03 | 2026-04-29 | 1TB01003-003F08-AMA-LTR-0025 | DVO-03 | [7 empty] | AMA01003-WTRAN-051284 | 2026-06-06 | ACTIVE | 312400 | APPROVED |  |  |  |  | 0
226 | Supply and Installation of Additional Flashing Pressure Plate above Doors | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC | EW 151 |  | 0 | EVO 07 |  | 2026-05-06 | APPROVED | AMA01003-WTRAN-050595 | NO | ACTIVE | 42000 | PVO-07 | 0 | 2026-07-16 | APPROVED | AMA01003-WTRAN-052734 | NO | ACTIVE | 42000 | VO 07 | 2026-05-06 | APPROVED | AMA01003-WTRAN-050595 | VO 07 | 2026-05-06 | 1TB01003-003C27-AMA-LTR-0072 | DVO 07 | 0 | [6 empty] | AMA01003-WTRAN-055036 | 2026-09-19 | ACTIVE | 14594.67 | APPROVED |  |  | Commercial carried out a determination approved and issued to the contractor under Ref Letter 1TB01003-003C27-AMA-LTR-0084 |  | 0
227 | Rectification of damages to the interior fit‑out works (Backcharge to Alfanar) | Post Contract Variation |  |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | [9 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
228 | Rectification of damages to the interior fit‑out works (Backcharge to Alfanar) | Post Contract Variation |  |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | [9 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
229 | Rectification of Wooden steps | Post Contract Variation |  |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | [9 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
230 | Provision of Vinyl Film with Frit Pattern to the full Façade Glazing of the North & South Boutiques (Full Coverage) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC | [9 empty] | NOT ACTIVE |  | 8 | [5 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
231 | EVO No. 005 - Extension of Consultant’s Senior Architect (Khatib & Alami) to 31 May 2026 - Backcharge | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC |  |  |  | EVO 005 | 0 | 2026-03-16 | APPROVED | AMA01003-WTRAN-049140 | NO | ACTIVE | -118080 | 9 | 0 | 2026-05-18 | APPROVED | AMA01003-WTRAN-050930 | NO | ACTIVE | -118080 | VO 09 | 2026-07-16 | APPROVED | AMA01003-WTRAN-052727 | VO 09 | 2026-07-16 | 1TB01003-003C27-AMA-LTR-0077 | DVO 09 | 0 | [6 empty] | WF-022728 | 2026-09-23 | NOT ACTIVE | -118080 | PENDING |  |  | Commercial carrying out a determination in line with the approved aconex ref 1TB01003-003C27-AMA-LTR-0086 dated 15 Sep 2026 |  | 80
232 | EVO No. 005 - Extension of Consultant’s Senior Architect (Khatib & Alami) to 31 May 2026 - Backcharge | Post Contract Variation | Back Charge |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | EVO 005 | 0 | 2026-03-16 | APPROVED | AMA01003-WTRAN-049140 | NO | ACTIVE | -78720 | 40 | 0 | 2026-05-18 | APPROVED | AMA01003-WTRAN-050928 | NO | ACTIVE | -78720 | VO 034 | 2026-07-16 | APPROVED | AMA01003-WTRAN-052726 | VO 034 | 2026-07-16 | 1TB01003-003C03-AMA-LTR-0334 | DVO 034 | 0 | [6 empty] | WF-022726 | 2026-09-23 | NOT ACTIVE | -78720 | PENDING |  |  | Commercial carrying out a determination in line with the approved aconex ref 1TB01003-003C03-AMA-LTR-0341 dated 15 Sep 2026 |  | 80
233 | MEP Cladding Works and Supply and Install Sanitary ware on Amaala Yacht Club | Post Contract Variation | Amaala |  |  |  | Employer | MARINA HOTEL 3 | 1.TB.01.009 | MARINA HOTEL 3 | 1.TB.01.009.01 | KTH - MEP Works Package - 2240072 - KORTEK | KORTEC |  |  |  | EVO 015 | 0 | 2026-03-27 | APPROVED | AMA01009-WTRAN-239408 | NO | ACTIVE | 578140.17 | PVO 015 | 0 | 2026-05-05 | APPROVED | AMA01009-WTRAN-253582 | NO | ACTIVE | 583143.7 | VO 015 | 2026-03-11 | APPROVED | AMA01009-WTRAN-239408 | VO 015 | 2026-03-11 | 1TB01009-009C05-AMA-LTR-0106 | [10 empty] | NOT ACTIVE |  | PENDING |  |  |  |  | 207
234 | MAS Additional Labour Requirement - Extension (13 May to 31 July 2026) | Post Contract Variation | Back Charge |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MAS - Labour Supply - Wet Works | MAS |  |  |  | EVO 005 R1 | 0 | 2026-07-12 | APPROVED | AMA01003-WTRAN-052517 |  | ACTIVE | 174900 | PVO 05 | 0 | 2026-09-26 | APPROVED | AMA01003-WTRAN-055133 |  | ACTIVE | 174900 | VO 05 | 2026-05-31 | APPROVED | AMA01003-WTRAN-051195 | [13 empty] | NOT ACTIVE |  | PENDING |  |  | S Fairfield: No corresponding back charge attached- Response Issued to M Hansen 19 Aug 2026 |  | 46299
235 | Supply of Plant/Equipment and Labour for ALCATOP Works at Amaala Yacht Club (AYC) Project | Pre Contract Variation | Back Charge |  |  |  | Employer | FOURSEASONS | 1.TB.01.012 | FOURSEASONS | 1.TB.01.012.01 | ALC - Alcatop Package - Fourseasons | ALCATOP |  |  |  | EVO 042 | 0 | 2026-05-07 | APPROVED | AMA02012-WTRAN-386212 | NO | ACTIVE | 150000 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
236 | Rectification of Glass Balustrade Damaged by Al Fanar | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur | [9 empty] | NOT ACTIVE |  | 41 | [5 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
237 | Rectification of Glass Balustrade Damaged by Al Fanar (Backcharge) | Post Contract Variation | Operator's Change |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | [6 empty] | CANCELLED |  |  | NOT ACTIVE |  | 7 | [5 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
238 | Supply and Installation of Vinyl Film, Gaskets, Touchless Door Sensors, Master Key Cylinders, and Conversion of Manual Sliding Doors to Automatic | Pre Contract Variation | Design Development |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC |  |  |  | EVO 010 | 0 | 2026-05-15 | APPROVED | AMA01003-WTRAN-050994 | NO | ACTIVE | 158694 |  |  |  | PENDING |  |  | NOT ACTIVE |  | VO 010 | 2026-05-19 | APPROVED | AMA01003-WTRAN-050994 | [13 empty] | NOT ACTIVE | [6 empty] | 0
239 | Extension of Areen services - 31 May 2026 | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | FF&E and OSE Procurement Agent | Areen |  |  |  | RFA 003 | 0 | 2026-06-14 | APPROVED | AMA01003-WTRAN-051506 | NO | ACTIVE | 31327.91 | PVO 003 |  | 2026-06-25 | APPROVED | AMA01003-WTRAN-051857 |  | ACTIVE | 31327.91 | VO 03 | 2026-07-19 | APPROVED | AMA01003-WTRAN-052725 | VO 03 | 2026-07-19 | 1TB01003-003F06-AMA-LTR-0018 | DVO 003 | 0 | [6 empty] | AMA01003-WTRAN-054834 | 2026-09-12 | ACTIVE | 35013.54 | APPROVED |  |  |  |  | 0
240 | FFE and Material Improvements | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | EVO 036 | 0 | 2026-06-23 | APPROVED | AMA01003-WTRAN-051812 | NO | ACTIVE | 208289.15 | 36 | 0 | 2026-09-30 | PENDING | WF-022771 | YES | NOT ACTIVE | 150375.12 | VO 36 | 2026-06-10 | APPROVED | AMA01003-WTRAN-051812 | [13 empty] | NOT ACTIVE | [6 empty] | 0
241 | Request for Approval (RFA) to Appoint Al Futtaim Contracting (AFC) to Take Over the Remaining Elevator Works at the AMAALA Yacht Club Project | Pre Contract Variation | Back Charge |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Futtaim Pioneer Elevators - Al Futtaim Pioneer | AL FUTTAIM |  |  |  | RFA 06 | 0 | 2026-05-15 | TRANSFERRED | AMA01003-WTRAN-050877 | NO | NOT ACTIVE | 850000 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | Contract Awarded |  | 0
242 | Back Charge to Essco related to snagging and elevator compliance Note SAR 370,875 will be ommitted from DEPA scope based on approved PVO to fund from Al Futtaim appointment | Pre Contract Variation | Back Charge |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | ESCCO - Vertical Transport | ESCCO |  |  |  | RFA 06 | 0 | 2026-05-15 | APPROVED | AMA01003-WTRAN-050877 | NO | ACTIVE | -200000 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
243 | Food & Beverage (F&B) Design Changes (MEP) – AMAALA Yacht Club | Pre Contract Variation | Design Development |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar |  |  |  | EVO 008 | 0 | 2026-05-31 | CANCELLED | AMA01003-WTRAN-051194 | NO | NOT ACTIVE | 138883 |  |  |  | CANCELLED |  |  | NOT ACTIVE |  | VO 08 | 2026-05-31 | CANCELLED | AMA01003-WTRAN-051194 | [13 empty] | NOT ACTIVE |  |  |  |  | Cancelled - works to be awarded to KORTEK - uinder MH3 |  | 0
244 | MEP Additional works during snagging | Post Contract Variation | Operator's Change |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | [9 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
245 | Extension of Consultant’s Senior Architect (Khatib & Alami) to 31 August 2026 | Post Contract Variation | Design Development |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | KAA-Mgt Fees | KAA |  |  |  | EVO 006 | 0 | 2026-06-08 | REVISED & RE-SUBMIT | AMA01003-WTRAN-051402 | NO | NOT ACTIVE | 236160 | [6 empty] | NOT ACTIVE |  | VO 06 | 2026-06-02 | REJECTED | AMA01003-WTRAN-051402 | [13 empty] | NOT ACTIVE |  |  |  |  | F Albalawi - Rejected. To be done in-house - Design team |  | 0
246 | Extension of CML Independent Commissioning Agent Services until 30 June 2026 | Post Contract Variation | Design Development |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | CML-Mgt Fees | CML |  |  |  | EVO 004 | 0 | 2026-06-08 | APPROVED | AMA01003-WTRAN-051403 | NO | ACTIVE | 0 | PVO 04 |  | 2026-07-06 | APPROVED | AMA01003-WTRAN-052163 |  |  | 0 | VO 04 | 2026-06-08 | APPROVED | AMA01003-VAR-OR-000001 | VO 04 | 2026-06-08 | 1TB01003-003F08-AMA-LTR-0027 | DVO-04 | [7 empty] | AMA01003-WTRAN-053446 | 2026-08-03 | ACTIVE | 0 | APPROVED |  |  |  |  | 0
247 | Supply and installation of internal vinyl film at four (4) locations across Levels 1, 2, and 3 | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | EVO 037 | 0 | 2026-06-15 | APPROVED | AMA01003-WTRAN-051589 | NO | ACTIVE | 68217.5 | 37 |  |  | PENDING |  |  | NOT ACTIVE |  | VO 37 | 2026-06-15 | APPROVED | AMA01003-WTRAN-051589 | [13 empty] | NOT ACTIVE | [6 empty] | 0
248 | Rectification of ceiling holes, including the application of spray acoustic paint | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | EVO 038 | 0 | 2026-06-17 | APPROVED | AMA01003-WTRAN-051652 | NO | ACTIVE | 20000 | 38 | 0 | 2026-09-12 | APPROVED | AMA01003-WTRAN-054833 | YES | ACTIVE | 119791.67 | VO 38 | 2026-06-17 | APPROVED | AMA01003-WTRAN-051652 | [13 empty] | NOT ACTIVE | [6 empty] | 0
249 | Al Fanar Extension #4 (remaining materials, tranasfer material, manpower and equipment) | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar | [9 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE |  | VO 09 | [16 empty] | NOT ACTIVE | [6 empty] | 0
250 | Replacement of Glass fin, (L0-N1) BC to Al fanar | Post Contract Variation | Back Charge |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Façade & Glazing Works | ALUTEC |  |  |  | EVO 11 | 0 | 2026-07-12 | APPROVED | AMA01003-WTRAN-052518 | NO | ACTIVE | 5259 | PVO 011 | 0 | 2026-09-12 | APPROVED | AMA01003-WTRAN-054830 | NO | ACTIVE | 5259 | VO 11 | [16 empty] | NOT ACTIVE | [6 empty] | 0
251 | Replacement of Glass fin, (L0-N1) BC to Al fanar | Post Contract Variation | Back Charge |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar |  |  |  | EVO 011 | 0 | 2026-07-12 | APPROVED | AMA01003-WTRAN-052518 | NO | ACTIVE | -5259 | PVO 011 | 0 | 2026-09-12 | APPROVED | AMA01003-WTRAN-054831 | NO | ACTIVE | -5259 | VO 011 | 2026-09-22 | APPROVED | AMA01003-WTRAN-055100 | VO 011 | 2026-09-19 | 1TB01003-003C34-AMA-LTR-0069 | [10 empty] | NOT ACTIVE | [6 empty] | 0
252 | Al Fanar - Interim Forecast Final Account Alignment | Post Contract Variation | Back Charge |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar |  |  |  | RFA | 0 | 2026-06-14 | APPROVED | AMA01003-WTRAN-051509 | NO | ACTIVE | 8294779.8 | PVO 09 | 0 | 2026-07-06 | APPROVED | AMA01003-WTRAN-052162 | NO | ACTIVE | 8294779.8 | VO 09 | 2026-07-16 | APPROVED | AMA01003-WTRAN-052724 | VO 09 | 2026-07-16 | 1TB01003-003C34-AMA-LTR-0062 | DVO 009 | 0 | [6 empty] | AMA01003-WTRAN-052756 | 2026-07-19 | ACTIVE | 8294779 | APPROVED |  |  |  |  | 0
253 | Final Account - Euro Consult | Post Contract Variation | Final Account |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | ECC-Mgt Fees | EURO CONSULT |  |  |  | FA Statement | 0 | 2026-06-23 | APPROVED | AMA01003-WTRAN-051811 | NO | ACTIVE | -53506.74 | N/A | 0 | 2026-06-23 | APPROVED | AMA01003-WTRAN-051811 |  | ACTIVE | -53507 | N/A | 2026-06-23 | APPROVED | AMA01003-WTRAN-051811 | [13 empty] | NOT ACTIVE |  | PENDING |  |  |  |  | 46299
254 | Add Aluminum Profile to Relocate Water Feature LED Lighting | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | 60 | 0 | 2026-08-15 | APPROVED | AMA01003-WTRAN-053852 | NO | ACTIVE | 36173.25 | 39 | 0 | 2026-08-15 | APPROVED | AMA01003-WTRAN-053852 | NO | ACTIVE | 36173.25 | VO 39 | 2026-08-15 | APPROVED | AMA01003-WTRAN-053852 | [13 empty] | NOT ACTIVE |  | PENDING |  |  |  |  | 46299
255 | Final Account - Jensen Huges Saudi Arabia LLC - COO#07 | Post Contract Variation | Final Account |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Jensen Hughes-Prf Fees | JensenHuges |  |  |  | FA Statement | 0 | 2026-07-09 | APPROVED | AMA01003-WTRAN-052428 | NO | ACTIVE | -56700 | N/A | 0 | 2026-07-09 | APPROVED | AMA01003-WTRAN-052428 | NO | ACTIVE | -56700 | N/A |  |  | N/A | N/A |  | N/A | FA | 0 | [6 empty] | AMA01003-WTRAN-052428 | 2026-07-09 | ACTIVE | -56700 | APPROVED |  |  |  |  | 0
256 | Final Account - Jensen Huges Saudi Arabia LLC - COO#030 | Post Contract Variation | Final Account |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Jensen Hughes-Prf Fees COO 30 | JensenHuges |  |  |  | FA Statement | 0 | 2026-07-06 | APPROVED | AMA01003-WTRAN-052427 | NO | ACTIVE | -23800 | N/A | 0 | 2026-07-09 | APPROVED | AMA01003-WTRAN-052427 | NO | ACTIVE | -23800 | N/A |  |  | N/A | N/A |  | N/A | FA | 0 | [6 empty] | AMA01003-WTRAN-052427 | 2026-07-09 | ACTIVE | -23800 | APPROVED |  |  |  |  | 0
257 | Food & Beverage (F&B) Design Changes (MEP) – Duplicate of Al Fanar, if this is approved Cancel Al Fanar | Post Contract Variation | Amaala |  |  |  | Employer | MARINA HOTEL 3 | 1.TB.01.009 | MARINA HOTEL 3 | 1.TB.01.009.01 | KTH - MEP Works Package - 2240072 - KORTEK | KORTEC |  |  |  | EVO 016 | 0 | 2026-07-14 | APPROVED | AMA01009-WTRAN-268175 | NO | ACTIVE | 367770 | PVO 016 | 0 | 2026-08-17 | PENDING | WF-098900 | NO | NOT ACTIVE | 550238.84 |  |  | PENDING | [14 empty] | NOT ACTIVE | [6 empty] | 0
258 | Extension of CML Independent Commissioning Agent Services until 31 August 2026 | Post Contract Variation | Design Development |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | CML-Mgt Fees | CML |  |  |  | EVO 05 | 0 | 2026-07-15 | APPROVED | AMA01003-WTRAN-052688 | NO | ACTIVE | 104475.08 | PVO 05 | 0 | 2026-08-25 | APPROVED | AMA01003-WTRAN-054059 | NO | ACTIVE | 101675.08 | [17 empty] | NOT ACTIVE | [6 empty] | 0
259 | Supply & Installation of Additional Kitchen Equipment at AYC | Post Contract Variation | Amaala |  |  |  | Employer | VILLAGE BOUTIQUE HOTEL | 1.TB.01.006 | VILLAGE BOUTIQUE HOTEL | 1.TB.01.006.03 | TEIJUN VBH | TEIJUN |  |  |  | EVO 059 | 0 | 2026-07-12 | APPROVED | AMA01006-WTRAN-144963 | NO | ACTIVE | 1079464.7 | PVO 059 | 0 | 2026-07-15 | PENDING | WF-045814 | NO | NOT ACTIVE | 1025491.48 | VO 059 | 2026-07-15 | PENDING | WF-045814 | VO 059 | 2026-07-09 | 1TB01006-006C22-AMA-LTR-0211 | [10 empty] | NOT ACTIVE | [6 empty] | 0
260 | Supply of Renderers for the Amaala Yacht Club (AYC) Project | Post Contract Variation | Amaala |  |  |  | Employer | MARINA HOTEL 3 | 1.TB.01.009 | MARINA HOTEL 3 | 1.TB.01.009.01 | IMAR MH3 | IMAR MH3 |  |  |  | RFA 005 | 0 | 2025-10-28 | APPROVED | AMA01009-WTRAN-187015 | NO | ACTIVE | 155181 | PVO 014 | 0 | 2026-07-13 | APPROVED | AMA01009-WTRAN-267915 | NO | ACTIVE | 442200 | VO 014 | 2026-07-16 | APPROVED | AMA01009-WTRAN-268928 | EI 03 | 2026-09-14 | 1TB01009-009C09-AMA-LTR-0052 | DVO 010 | 0 | [6 empty] | AMA01009-WTRAN-281418 | 2026-08-18 | ACTIVE | 442200 | APPROVED |  |  |  |  | 0
261 | Supply of Façade Installers for the Amaala Yacht Club (AYC) Project | Post Contract Variation | Amaala |  |  |  | Employer | MARINA HOTEL 3 | 1.TB.01.009 | MARINA HOTEL 3 | 1.TB.01.009.01 | FIBREX MH3 | FIBREX MH3 |  |  |  | RFA 005 | 0 | 2025-10-28 | APPROVED | AMA01009-WTRAN-187015 | NO | ACTIVE | 69235 | PVO 002 | 0 | 2026-07-13 | APPROVED | AMA01009-WTRAN-267912 | NO | ACTIVE | 164010 | VO 02 | 2026-07-16 | APPROVED | AMA01009-WTRAN-268926 | EI 03 | 2026-07-14 | 1TB01009-009C35-AMA-LTR-0043 | DVO 002 | 0 | [6 empty] | WF-099497 | 2026-07-14 | NOT ACTIVE | 163800 | PENDING |  |  | Commercial actioning a determination under Aconex WF-097994 dated 19 aug 2026 |  | 82
262 | All Push Bar fire Exit doors repaint | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA | [9 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
263 | Enhancement Works from Site Walkthrough (30-Jun-26): Chart & Model Globe, Operator Library Books, AMAALA Lounge Lighting, VVIP Loose Furniture, Board Room Table, Level 02 Private Dining, and FF&E Wind-Damage Making-Good. | Post Contract Variation | Amaala |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | EVO 040 | 0 | 2026-08-17 | REJECTED | AMA01003-WTRAN-054006 | NO | NOT ACTIVE | 1151653.13 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | F Albalawi: Rejected |  | 0
264 | Recovery of Costs for Extended CML Testing & Commissioning Services Resulting from Alfanar Delays in ELV Commissioning Works. | Post Contract Variation | Contractor's Performance |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar |  |  |  | EVO 05 | 0 | 2026-07-15 | APPROVED | AMA01003-WTRAN-052688 | NO | ACTIVE | -52237.54 | PVO 010 | 0 | 2026-08-25 | APPROVED | AMA01003-WTRAN-054059 | NO | ACTIVE | -50837.54 | VO 010 | 2026-09-02 | APPROVED | AMA01003-WTRAN-054573 | [13 empty] | NOT ACTIVE | [6 empty] | 0
265 | Recovery of Costs for Extended CML Testing & Commissioning Services Resulting from GLSAN (SAB’s ELV Specialist) Delays in ELV Works. | Post Contract Variation | Contractor's Performance |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | EVO 05 | 0 | 2026-07-15 | APPROVED | AMA01003-WTRAN-052688 | NO | ACTIVE | -52237.54 | PVO 043 | 0 | 2026-08-25 | APPROVED | AMA01003-WTRAN-054059 | NO | ACTIVE | -50837.54 | VO 035 | 2026-09-02 | APPROVED | AMA01003-WTRAN-054575 | [13 empty] | NOT ACTIVE | [6 empty] | 0
266 | Provision of Temporary and Permanent Ceiling Access Panels | Post Contract Variation | Design Development |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | EVO 041 | 0 | 2026-08-17 | APPROVED | AMA01003-WTRAN-054009 | NO | ACTIVE | 69037.2 | 41 |  |  | PENDING |  |  | NOT ACTIVE |  | VO 041 | [16 empty] | NOT ACTIVE | [6 empty] | 0
267 | Amphitheatre Construction Works - Final Account | Post Contract Variation | Final Account |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | MAS - Amphitheatre | MAS | EW 01 - MAS | 2026-08-12 | -9520 | FA Statement | 0 | 2026-08-19 | REVISED & RE-SUBMIT | AMA01003-WTRAN-053794 | NO | NOT ACTIVE | -9520 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE |  |  |  |  | P Donaghy: Please confirm if they owe us accommodation charges P Donaghy: So is there outstanding accommodation on the other contract? Yes or No? |  | 0
268 | RFA for Extension of Al Fanar’s manpower deployment from 1 August 2026 to 22 September 2026 | Post Contract Variation | Design Development |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | Al Fanar - MEP Labour Supply | Al Fanar |  |  |  | RFA 005 | 0 | 2026-09-12 | APPROVED | AMA01003-WTRAN-054832 | NO | ACTIVE | 842550 | PVO 012 | 0 | 2026-09-26 | APPROVED | AMA01003-WTRAN-055131 | NO | ACTIVE | 842550 | VO 012 | 2026-10-01 | APPROVED | AMA01003-WTRAN-055242 | VO 012 | 2026-10-02 | 1TB01003-003C34-AMA-LTR-0071 | [10 empty] | NOT ACTIVE |  | PENDING |  |  |  |  | 2
269 | Direct Payments Made by AMAALA on Behalf of Saudi Arabian Baytur to Subcontractors and Suppliers (August 2025 to May 2026) | Post Contract Variation | Back Charge |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | RFA's | 0 | N/A | APPROVED | Number of RFA's | NO | ACTIVE | -18772378.16 | PVO 044 | 0 | 2026-08-27 | APPROVED | AMA01003-WTRAN-054369 | NO | ACTIVE | -18772378.16 | VO 038 | 2026-08-31 | PENDING | WF-022563 | VO 038 | 2026-08-31 | 1TB01003-003C03-AMA-LTR-0340 | [10 empty] | NOT ACTIVE |  | PENDING |  |  |  |  | 34
270 | Rectification of the GRC panel sealant coating - Supply of painters | Post Contract Variation | Back Charge |  |  |  | Employer | MARINA HOTEL 3 | 1.TB.01.009 | MARINA HOTEL 3 | 1.TB.01.009.01 | IMAR MH3 | IMAR MH3 |  |  |  | Pre EI 006 | 0 | 2026-09-22 | APPROVED | AMA01009-WTRAN-295472 | NO | ACTIVE | 36400 |  |  |  | PENDING |  |  | NOT ACTIVE |  |  |  | PENDING | [14 empty] | NOT ACTIVE | [6 empty] | 0
271 | MAS Additional Labour Requirement - Extension (13 May to 31 July 2026) - Back charge SAB | Post Contract Variation | Back Charge |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | EVO 005 R1 | 0 | 2026-07-12 | APPROVED | AMA01003-WTRAN-052517 | NO | ACTIVE | -174900 | PVO 045 | 0 | 2026-09-26 | APPROVED | AMA01003-WTRAN-055132 | NO | ACTIVE | -174900 | VO 039 | 2026-10-01 | APPROVED | AMA01003-WTRAN-055241 | VO 039 | 2026-10-02 | 1TB01003-003C03-AMA-LTR-0342 | [10 empty] | NOT ACTIVE |  | PENDING |  |  |  |  | 2
272 | Saudi Consolidated Engineering Company - Khatib & Alami Final account | Post Contract Variation | Final Account |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | KAA-Mgt Fees | KAA |  |  |  | Final Account | 0 | 2026-09-23 | PENDING | WF-022724 | NO | ACTIVE | -49207 | [6 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
273 | Payment of SAB's Sub-Contractors through DEPA – GLSAN, Blue Wellness and BMC | Post Contract Variation | Back Charge |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | DEPA Interior Fitout | DEPA |  |  |  | RFC ### | 0 | 2026-10-03 | PENDING | RFC DRAFT-005640 | NO | ACTIVE | 1196461.25 | PVO 042 | 0 | 2026-10-03 | PENDING | RFC DRAFT-005640 | NO | NOT ACTIVE | 1196461.25 | VO 042 | 2026-10-03 | PENDING | RFC DRAFT-005640 | [13 empty] | NOT ACTIVE | [6 empty] | 0
274 | Back-charge to SAB – Payment of SAB's Sub-Contractors through DEPA and Nesma | Post Contract Variation | Back Charge |  |  |  | Employer | AMAALA YATCH CLUB | 1.TB.01.003 | AMAALA YATCH CLUB | 1.TB.01.003.01 | SAB - Civil and Arch Works, MEPD & ICT/ELV | Baytur |  |  |  | RFC ### | 0 | 2026-10-03 | PENDING | RFC DRAFT-005640 | NO | ACTIVE | -1412346.44 | PVO 046 | 0 | 2026-10-03 | PENDING | RFC DRAFT-005640 | NO | NOT ACTIVE | -1412346.44 | VO 040 | 2026-10-03 | PENDING | RFC DRAFT-005640 | [13 empty] | NOT ACTIVE | [6 empty] | 0
275 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
276 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
277 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
278 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
279 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
280 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
281 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
282 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
283 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
284 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
285 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
286 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
287 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
288 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
289 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
290 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
291 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
292 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
293 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
294 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
295 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
296 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
297 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
298 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
299 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
300 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
301 | [22 empty] | NOT ACTIVE | [7 empty] | NOT ACTIVE | [18 empty] | NOT ACTIVE | [6 empty] | 0
[16 empty] | 32875259.423 | [6 empty] | 0 | -6935613.645 | [6 empty] | 0 | 29368511.955 | [11 empty] | 3422226.175 |  |  | -3591842.413 |  |  | 0 | 6670901.385
[14 empty] | Early Warnings: |  | 0 |  |  |  |  | RFC: |  |  | 158694 | [5 empty] | PVO: |  | -112821 | [16 empty] | DVO: |  | 574831.03
[11 empty] | Time Impact: |  |  |  |  | -75000 | 1722523.76 | [6 empty] | 29145943.015 | [28 empty] | Funding Source:
[11 empty] | None | [12 empty] | 36081556.66 | [26 empty] | -15269121.07 |  | Contingency | Seek approval from Portfolio Lead for expenditure against contingency allowance
[32 empty] | 1576884.6 | [18 empty] | -1095922.41 |  | Add. Budget | Budget Request form to be completed and signed off by authorised parties
[11 empty] | Medium |  |  |  |  | 3520000 | 63223.11 | [35 empty] | TBC | Funding to be discussed and agreed with Portfolio Lead
[11 empty] | High | [5 empty] | 1722523.76 | [6 empty] | #REF! | [7 empty] | 691830 | [18 empty] | 1894981.1 |  | 0
[16 empty] | 9188438.51 | [34 empty] | 2833999.1
[16 empty] | 9188438.51 | [15 empty] | 34684 | [18 empty] | 902512.91
[16 empty] | 5181058.51 | [15 empty] | 850370.6
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | [9 empty] | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56
[36 empty] | 35100 | [14 empty] | -1740055.17
13654504.22
[16 empty] | 13280713.77 | [34 empty] | -15269121.07
-373790.45
[48 empty] | 535044.11 | 75809169.37 |  | 75274125.26
-695101.74
75969227
56493648.14
[16 empty] | 53011624.83 | [34 empty] | -1958329.77
[16 empty] | -3482023.31 | [34 empty] | 75969227
74010897.23
74575941.34
[32 empty] | -0.050737 | [18 empty] | 565044.11
-5.0737
-26095541.44
[16 empty] | -11561418.85 | [15 empty] | -5.0737
2584216.29
75969227
[32 empty] | 1021958 | 1.345%
76991185
-14273321.1
-50131848.28
Formulas:
DON’T DELETE = IF([Status]="PENDING",TODAY()-[Date],0)
Internal and External Procedures
AMAALA Internal Procedure
Engineer
Contractor
AMAALA INTERNAL
Commercial Team
Note on Q171: 13,737,620 transferred to MAS labour and supervision 760,869.57 moved to Scaffolding Budget 1,471,000 Transferred to K&A Extension
Note on Q186: Jose Chavenia: -900K as of 12 Aug 2025 actual manpower
Note on Q188: Jose Chavenia: BOQ value
Note on Q189: Jose Chavenia: BOQ Value

## Schedule D (hidden)
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
R&O No | Description | Total Risk | Total Opportunity
1 | Risks:
1.01 | EOT Variation exposure due to splitting packages on a very complex asset.
1.02 | Potential scope gaps are inevitable despite team's best efforts due to the tender package split.
1.03 | Complex engineering design coordination [ Façade/SS/PS] – Engineering Consultant may be required to progress works when they stop (RBG etc).
1.04 | SAB accommodation outside AMAALA Construction Village (higher rates).
1.05 | Revert back of the omitted dewatering from SAB (in case the Marina Basin dewatering discontinue).
1.06 | Delay in the procurement of structural steelworks by SAB.
1.07 | The current tower crane erected is not adequate for the installation of structural steelworks (SAB to ensure that this will be covered by the structural steelworks subcontractor).
1.08 | Increase in rate by Tamimi from the tender pre-agreed rate in Bus Transport Service by SAB Workers.
1.09 | Scope gap between SAB and DEPA's Contract/Scope.
1.1 | DEPA accommodation outside AMAALA Construction Village.
1.11 | Flat/curved Glass facades and glazing doors - buildability issue.
1.12 | Potential descoping of glazed balustrades, anodised aluminium architectural systems, limestone cladding, GFRC cladding, roof enclosure, aluminium soffits, glazed façade system and associated works, rainscreen system and MEP long lead items from SAB scope.
1.13 | Potential cost adjustment to SAB Contract.
1.14 | Appointment of Al Fanar for the supply of labour and supervision for remaining MEP Works (to be omitted from SAB scope).
1.15 | Appointment of MAS to carry out the amphitheatre works and balance works for wet works on behalf of SAB (to be omitted from SAB).
1.16 | Reflective stainless steel omitted from SAB awarded to ARMETAL.
1.17 | GRC Cladding omitted from SAB awarded to Abu Dhabi Precast.
1.18 | External Scaffolding awarded to Hassan Allam
1.19 | Supply of MEP Materials by Al Fanar
1.2 | Direct Payments to SAB Suppliers and Subcontractors
1.21 | Al Fanar Manpower Extension up to October 2025
1.22 | Areen procurement services extension
1.23 | CML ICA services extension
1.24 | K&A Construction Supervision extension
2 | Opportunity
2.01
2.02
2.03
|  | 0 | 0
| Variance | 0

## Schedule E (SS) (hidden)
PROJECT NAME: | BLUEWATERS - RESIDENTIAL |  | BLUEWATERS - WHARF RETAIL | [9 empty] | Time Impact: | [42 empty] | CHANGE TRACKER
PROJECT NR: | DPDP-6003 |  | REDP-6004 | [9 empty] | None | [44 empty] | EW |  | RFC |  | VO
DATE: | #REF! |  | 2015-05-25 | [9 empty] | Low | Less than 14 days | [41 empty] | Cancelled |  | 52 |  | 14 |  | 0
[13 empty] | Medium | 14 to 30 days | [41 empty] | Transferred to RFC |  | 26 |  | 0 |  | 0
#REF! | [12 empty] | High | Critical Path: Greater than 30 days | [41 empty] | Approved |  | 0 |  | 26 |  | 0
[56 empty] | Pending |  | 18 |  | 17 |  | 0
[56 empty] | Total Raised |  | 96 |  | 57 |  | 0
Item No. | Description of Change | Change Category | Change Category | NPC |  |  |  |  | EW | [5 empty] | DASH BOARD EW | [5 empty] | RFC |  |  |  | DASH BOARD RFC | [8 empty] | EI |  | DASH BOARD ERI's | [5 empty] | VOAF | [6 empty] | DASH BOARD VOAF | [6 empty] | VO | [6 empty] | FUNDING |  | Comments / Current Status
|  |  |  | Initiated by | Nr. | Date | Cost Impact (AED) | Time Impact (L,M,H) | Initiated by | Nr. | Date | Cost Impact (AED) | Time Impact (L,M,H) | EW Status | [6 empty] | Nr. | Date | Amount (AED) | RFC Status | [9 empty] | Nr. | Date | [6 empty] | Nr. | Date |  |  |  |  | Amount (AED) | [7 empty] | Nr. | Date |  |  |  |  | Amount (AED) | Contingency / Additional Budget
[15 empty] | Total EW | Cancelled EW | Transfer to RFC | Mirage Pending < 30 days | Mirage Pending 30 to 60 days | Mirage Pending > 60 days |  |  |  |  | Total EW | Cancelled EW | Approved (inc. in Lump Sum) | Approved (Authority) | Approved (proceed to ERI) | Meraas Pending < 30 days | Meraas Pending 30 to 60 days | Meraas Pending > 60 days | Pending RFC |  |  | Total ERI's Issued | ERI's inc. in Lump Sum | Contractor submitted Costs | Contractor Pending < 30 days | Contractor Pending 30 to 60 days | Contractor Pending > 60 days |  | QS | PMC | Meraas |  |  |  | Cancelled | Disputed | Approved (VO Issued) | Mirage Pending < 30 days | Mirage Pending > 30 days | Meraas Pending < 30 days | Meraas Pending > 30 days |  | QS | PMC | Meraas
[45 empty] | Contracts | Projects | Tendering | [11 empty] | Contracts | Projects | Tendering |  | Source | Status
Sequential line nr | Insert brief description and scope of change |  |  | Who initiated the change | Insert NPC no | Date of NPC issue | Initial Cost assessment (inc build-up) | Initial Time assessment (inc build-up) | Who initiated the change | Insert EW no | Date of EW issue | Initial Cost assessment (inc build-up) |  |  | 97 | 53 | 26 | 15 | 1 | 2 | Insert RFC no from RFC form | Date of RFC issue | Initial cost assessment (inc build-up) |  | 57 | 14 | 22 | 3 | 1 | 1 | 15 | 1 | 17 | Insert EI no | Date of EI issue | 5 | 4 | 0 | 0 | 0 | 1 | Insert VOAF no | Date of issue from QS | Date of issue from PMC | Date of issue from Contracts Dept | Date of issue from Projects Dept | Date of issue from Tendering Dept | Updated cost (inc full particulars) | 46 | 0 | 0 | 0 | 0 | 1 | 0 | Insert VO no | Date of issue from QS | Date of issue from PMC | Date of issue from Contracts Dept | Date of issue from Projects Dept | Date of issue from Tendering Dept | Final agreed cost with Contractor | Confirm source for additional funding | Insert whether additional budget request is pending or approved | Insert comments to identify: - current status - outstanding actions - if item is cancelled - status of additional budget request
0 | Removal of Contract Provisional Sum and transfer to PL Contingency | [7 empty] | Tendering | A.0 | 2015-08-13 | 0 |  | Cancelled | 1 | 1
1 | Cost Plan evolution from Broad Order of Cost to measured concept | Design Dev | [6 empty] | Design Dev | A.1 | 2014-12-18 | incl |  | Cancelled | 1 | 1 | [48 empty] | Included in Schematic cost plan
2 | Change basement and podium hollow core slabs to cast in-situ concrete | Design Dev | [6 empty] | Design Dev | A.2 | 2014-12-18 | incl |  | Cancelled | 1 | 1 | [48 empty] | Included in Schematic cost plan
3 | Revised contingency due to increase in value (no adjustment for budget saving) | Design Dev | [6 empty] | Design Dev | A.3 | 2014-12-18 | incl |  | Cancelled | 1 | 1 | [48 empty] | Contingency fixed per IDC budget
4 | Contractor's FF&E not included within Approved Budget | Design Dev | [6 empty] | Design Dev | A.4 | 2014-12-18 | incl |  | Cancelled | 1 | 1
5 | Project Contingency - Precontract | Meraas | [6 empty] | Meraas | A.5 |  |  |  | Cancelled | 1 | 1 | [48 empty] | Contingency fixed per IDC budget
6 | Difference in Mirage fee budget to awarded (balances on overall portfolio) - Currently funded from Contingency. | Meraas | [6 empty] | Meraas | A.6 | 2015-01-22 | 0 |  | Cancelled | 1 | 1 | [48 empty] | Allocated from contingency
7 | Contractor's price received under budget - Determined price was low so remaining budget was retained to align anticipated package award values | Tendering | [6 empty] | Tendering | A.7 | 2015-01-04 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | EW re-introduced in line with cost reporting protocol agreed with Meraas.
8 | Provisional Sum of AED 200M added to contractor's price for funding of A7 above and partial contingency spend. Included in Post Contract EW | Tendering | [6 empty] | Tendering | A.8 | 2015-01-04 |  |  | Cancelled | 1 | 1 | [48 empty] | Included in Schedule C Provisional Sums
9 | Schematic Design Cost Estimate over IDC budget (adjusted for Early Warning A.39 and A.40) | Design Dev | [6 empty] | Design Dev | A.9 | 2015-03-19 | 0 |  | Cancelled | 1 | 1 | [48 empty] | Included in Schematic cost plan | 8880000
10 | MLC Peer Review of Omnium Schematic Design Cost Estimate (included in item A.9) | Design Dev | [6 empty] | Design Dev | A.10 | 2015-03-25 | 0 |  | Cancelled | 1 | 1 | [48 empty] | Included in Schematic cost plan
11 | Potential savings to façade estimate after market testing of rates and MLC measure of Block A and H | Design Dev | [6 empty] | Design Dev | A.11 | 2015-03-25 | 0 |  | Cancelled | 1 | 1 | [48 empty] | Included in Schematic cost plan
12 | Potential reduction of costs to roofs and roof screening estimate based on MLC remeasure | Design Dev | [6 empty] | Design Dev | A.12 | 2015-03-25 | 0 |  | Cancelled | 1 | 1 | [48 empty] | Included in Schematic cost plan
13 | Omission of CAR insurance from contractors Preliminaries - CAR insurance effected by Employer | Meraas | [6 empty] | Meraas | A.13 | 2015-03-25 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 08 | 2015-05-24 | -440000 | Approved | 1 |  | 1 | [6 empty] | 5 | 2015-06-20 | 1 | 1 |  |  |  |  | To be included in lump sum | [6 empty] | 1
14 | Introduction of channel drains and screeds to fall to basement | Meraas | [6 empty] | Meraas | A.14 | 2015-03-18 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 01 | 2015-03-18 | 0 | Cancelled | 1 | 1 | [38 empty] | Change not required
15 | Additional 4 boreholes requested to Geotechnical survey | Authority |  | Meraas | 2 | 2015-05-13 | 41070 |  | Authority | A.15 | 2015-04-20 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 02 | 2015-04-28 | 41070 | Approved | 1 |  |  | 1 | [13 empty] | 001 | 2015-11-05 | 2015-11-05 |  |  |  | 39810 | 1 |  |  |  |  | 1 | [10 empty] | VOAF, VO and SOFA forms issued
16 | Target 10% reduction of costs to roofs and roof screening through VE | Design Dev | [6 empty] | Design Dev | A.16a | 2015-04-21 | 0 |  | Cancelled | 1 | 1 | [48 empty] | Cancelled review VE schedule
17 | Omission of Aconex from contractors Preliminaries - effected by Employer (0.12% of final agreed contract lump sum) | Meraas | [6 empty] | Meraas | A.16b | 2015-04-21 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 04 | 2015-05-24 | -1483759 | Approved | 1 |  |  |  | 1 |  |  |  |  | 4 | 2015-06-20 | 1 |  |  |  |  | 1 | To be included in lump sum | [6 empty] | 1
18 | Cost of mock-up built off site | Meraas |  | Meraas | 3 | 2015-05-13 | 1500000 |  | Meraas | A.17 | 2015-04-21 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 09 | 2015-06-07 | 0 | Approved | 1 |  | 1 | [6 empty] | 7 | 2015-06-25 | 1 | 1 | [27 empty] | Contractors has agreed to pay for mock-up. Previous estimate AED 1,556,000
19 | Shoring adjacent to retail site boundary | Design Dev | [6 empty] | Design Dev | A.18 | 2015-04-21 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 03 | 2015-05-05 | 3815024 | Approved | 1 |  | 1 | [6 empty] | 2 | 2015-05-20 | 1 | 1 |  |  |  |  | To be included in lump sum | [6 empty] | 1 | [13 empty] | `
20 | Authority deviations | Authority | [6 empty] | Authority | A.19 | 2015-04-21 |  |  | Transferred to RFC | 1 |  | 1 |  |  |  | 20 | 2015-07-05 | 3513000 | Approved | 1 |  |  | 1 | [36 empty] | RFC cancelled. To be kept as EW pending resolution between DM and Meraas
21 | UKEF financing fee | Meraas |  | Meraas | 4 | 2015-05-24 | 10800000 |  | Meraas | A.20 | 2015-04-21 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 05 | 2015-05-24 | 10773492 | Approved | 1 |  | 1 | [6 empty] | 6 | 2015-06-23 | 1 | 1
22 | Screening of lower basement level B2 from tunnel | Design Dev | [6 empty] | Design Dev | A.21 | 2015-04-21 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 32 | 2015-10-21 | 504000 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1
23 | Podium feature pool revised design | Design Dev | [6 empty] | Design Dev | A.22 | 2015-04-21 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 38 | 2015-10-21 | 1458312 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1
24 | Podium / Mosque urban edge design including vertical transport | Design Dev | [6 empty] | Design Dev | A.23 | 2015-04-21 | 0 |  | Cancelled | 1 | 1
25 | Security booths to parking entrances (5 No.) | Meraas |  | Meraas | 9 | 2015-05-31 | 200000 |  | Meraas | A.24 | 2015-04-21 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 15 | 2015-06-11 | 223000 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1
26 | Additional cost of full height entrance doors to apartments | Meraas |  | Meraas | 5 | 2015-05-24 | 1100000 |  | Meraas | A.25 | 2015-04-21 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 06 | 2015-10-19 | 305000 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | RFC Revised. Previous estimate AED 200,000 issued 1 June 2015
27 | Additional cost of full height internal doors to apartments | Meraas | [6 empty] | Meraas | A.26 | 2015-04-21 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 07 | 2015-10-20 | 404000 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | RFC Revised. Previous estimate AED 505,000 issued 1 June 2015
28 | Glazed façade proposal to lobbies, revised toilet block and wall finishes to roof top pools to Blocks F, G, H & J | Meraas | [6 empty] | Meraas | A.27 | 2015-04-21 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 33 | 2015-10-21 | 1094000 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1
29 | Change shower walls and doors to full height | Meraas |  | Meraas | 10 | 2015-05-31 | 505000 |  | Meraas | A.28 | 2015-04-21 | 0 |  | Cancelled | 1 | 1 | [48 empty] | Current specification issued now within budget
30 | Change shower drain cover to concealed option | Meraas | [6 empty] | Meraas | A.29 | 2015-04-21 | 0 |  | Cancelled | 1 | 1 | [48 empty] | Current specification issued now within budget
31 | Introduction of Facilities Management areas to basement | Meraas |  | Meraas | 6 | 2015-05-24 | TBA |  | Meraas | A.30 | 2015-04-21 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 13 | 2015-06-28 | 2319000 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | RFC Revision 2 approved
32 | Potential VE - Paint finish in lieu of stone clad feature walls to apartments | Design Dev | [6 empty] | Design Dev | A.31 | 2015-04-13 | 0 |  | Cancelled | 1 | 1 | [6 empty] | 0 | [41 empty] | Included with item EW A.72
33 | Potential VE - Replace false ceilings with paint finish to 80% of MEP areas to the basement and ground floor | Design Dev | [6 empty] | Design Dev | A.32 | 2015-04-13 | 0 |  | Cancelled | 1 | 1 | [6 empty] | 0 | [41 empty] | Included with item EW A.72
34 | Potential VE - Reduce supply price of cooker extract hood to apartments | Design Dev | [6 empty] | Design Dev | A.33 | 2015-04-13 | 0 |  | Cancelled | 1 | 1 | [6 empty] | 0 | [41 empty] | Included with item EW A.72
35 | Potential Value Engineering - Reduce number of palm trees by 10% (44 No) | Design Dev | [6 empty] | Design Dev | A.34 | 2015-04-13 | 0 |  | Cancelled | 1 | 1
36 | Reduce thickness of plaster to apartment walls from 15mm to 12mm thick | Design Dev | [6 empty] | Design Dev | A.35 | 2015-04-21 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 19 | 2015-08-16 | 0 | Cancelled | 1 | 1 | [15 empty] | To be included in lump sum | [6 empty] | 1
37 | Potential VE - Reduce size of water features to apartment block podium entrances | Design Dev | [6 empty] | Design Dev | A.36 | 2015-04-21 | 0 |  | Cancelled | 1 | 1 | [6 empty] | 0 | [41 empty] | Included with item EW A.75
38 | Use of composite post tensioned slab contract rates in lieu of conventional PT slab rates | Design Dev | [6 empty] | Design Dev | A.37 | 2015-04-21 | 0 |  | Cancelled | 1 | 1 | [48 empty] | Included in Schematic cost plan
39 | Potential Value Engineering - Current budget overrun to be recovered in detail design | Design Dev | [6 empty] | Design Dev | A.38 | 2015-04-21 | 0 |  | Cancelled | 1 | 1
40 | Changes to roof design from concept to schematic (increased roof coverage and screening louvers) excluding potential VE | Meraas |  | Meraas | 11 | 2015-05-24 | 29000000 |  | Meraas | A.39 | 2015-04-25 | 0 |  | Cancelled | 1 | 1 |  |  |  |  | 11 | 2015-08-17 | 33204000 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | Currently included in LS offer from Alico
41 | Introduction of façade fins from concept to schematic design | Meraas |  | Meraas | 12 | 2015-05-31 | 8110000 |  | Meraas | A.40 | 2015-05-05 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 12 | 2015-06-03 | 8880000 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | Currently included in LS offer from Alico
42 | Value Engineering to roofs and roof screening | Meraas | [6 empty] | Meraas | A.41 | 2015-05-25 |  |  | Cancelled | 1 | 1 | [48 empty] | VE proposal included in EW A.39
43 | Additional piles | Design Dev | [6 empty] | Design Dev | A.42 | 2015-05-25 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 10 | 2015-07-23 | 5151042 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1
44 | Inclusion of transformers in construction works budget | Authority |  | Authority | 13 | 2015-05-31 | 8000000 |  | Authority | A.43 | 2015-05-25 |  |  | Transferred to RFC | 1 |  | 1 |  |  |  | 34 | 2015-10-21 | 8095000 | Approved | 1 |  | 1 | [37 empty] | RFC approved but retained as EW on Meraas instruction
45 | Value Engineering Proposals - Refer Schedule I | Design Dev | [6 empty] | Design Dev | A.44 | 2015-05-25 | 0 |  | Cancelled | 1 | 1 | [48 empty] | VE proposals included in separate items
46 | Residential plot contribution towards TIS Consultants costs | Authority | [6 empty] | Authority | A.45 | 2015-05-25 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 35 | 2015-10-21 | 150000 | Approved | 1 |  |  | 1 | [36 empty] | RFC to be issued to Meraas with updated RFC format
47 | Potential Value Engineering - Omit 1 No recessed down lighters over bedhead in all bedrooms | Design Dev | [6 empty] | Design Dev | A.46 |  | 0 |  | Cancelled | 1 | 1 | [48 empty] | Included in EW A.58 for façade MEP tender budget overrun
48 | Potential Value Engineering - Omit sprinklers to bathrooms smaller than 5.1m2 | Design Dev | [6 empty] | Design Dev | A.47 |  | 0 |  | Cancelled | 1 | 1 | [48 empty] | EW cancelled as DM requirement to keep sprinklers in bathrooms
49 | Dewatering tender saving | Tendering | [6 empty] | Tendering | A.48 | 2015-06-16 | 0 |  | Cancelled | 1 | 1 | [48 empty] | Included in CPR award
50 | Introduction of plunge pools to Townhouses | Meraas |  | Meraas | 7 | 2015-05-24 | 1110000 |  | Meraas | A.49 | 2015-06-08 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 14 | 2015-10-20 | 1128000 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | RFC Revised. Previous estimate AED 918,000 issued 17 June 2015
51 | Introduction of water features to Townhouse entrances | Meraas |  | Meraas | 8 | 2015-05-24 | TBA |  | Meraas | A.50 | 2015-06-10 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 16 | 2015-10-20 | 1766000 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | RFC Revised. Previous estimate AED 819,000 issued 17 June 2015
52 | Anticipated shoring tender saving | Tendering | [6 empty] | Tendering | A.51 | 2015-06-16 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1
53 | Anticipated waterproofing tender extra | Tendering | [6 empty] | Tendering | A.52 | 2015-06-16 | 0 |  | Cancelled | 1 | 1 | [48 empty] | Included in CPR award
54 | Anticipated vertical transport tender saving | Tendering | [6 empty] | Tendering | A.53 | 2015-06-16 | 0 |  | Cancelled | 1 | 1 | [48 empty] | Included in CPR award
55 | Additional cost of Option 1 finishes to entrance lobbies | Meraas | [6 empty] | Meraas | A.54 | 2015-06-22 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 17 | 2015-06-28 | 0 | Cancelled | 1 | 1 | [38 empty] | Previous estimate AED 8,194,000. Design revised to within budget
56 | Additional costs due to increase amount of void formers contained in the external works package | Design Dev | [6 empty] | Design Dev | A.55 | 2015-07-13 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum as provisional amount | [6 empty] | 1 | [15 empty] | Refer to Schedule I for VE to this item
57 | Current Façade Tender Over run based on lowest BAFO Bid | Tendering | [6 empty] | Tendering | A.56 | 2015-07-13 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | Budget overrun based on Alico offer and includes Value Engineering
58 | Potential VE items to Facade as per Schedule I - included in EW A.56 | Tendering | [6 empty] | Tendering | A.57 | 2015-07-15 | 0 |  | Cancelled | 1 | 1
59 | Current MEPD Tender over run based on lowest BAFO Bid | Tendering | [6 empty] | Tendering | A.58 | 2015-07-13 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | Budget overrun based on ASU offer and includes Category A and not Cat B Value Engineering
60 | Potential VE items to MEPD as per Schedule I - included in EW A.58 | Tendering | [6 empty] | Tendering | A.59 | 2015-07-15 | 0 |  | Cancelled | 1 | 1
61 | Potential reduction in quantity and profile size of vertical and horizontal roof louvers | Design Dev | [6 empty] | Design Dev | A.60 |  | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 18 | 2015-07-23 | 0 | Cancelled | 1 | 1 | [15 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | RFC amount (AED 12,860,000). Refer item EW A.56 for façade tender budget overrun
62 | Balance of waterproofing budget not included in CPR award for podium waterproofing | Tendering | [6 empty] | Tendering | A.61 | 2015-08-13 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | CPR award for substructure waterproofing only
63 | Balance of MEP Early Works budget not included in CPR award | Tendering | [6 empty] | Tendering | A.62 | 2015-08-13 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1
64 | Primary structural steel for façade cladding | Design Dev | [6 empty] | Design Dev | A.63 | 2015-08-13 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | To be included in lump sum
65 | Contractor's 1st Interim Application for Extension of Time to Completion | Delay | [6 empty] | Design Dev | A.64 | 2015-07-29 | 14000000 |  | Pending | 1 |  |  |  |  | 1 | [44 empty] | Under review.
66 | Cost overrun of direct works | Design Dev | [6 empty] | Design Dev | A.65 | 2015-09-07 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1
67 | Additional cost of PODs over budget provisions | Design Dev | [6 empty] | Design Dev | A.66 | 2015-09-07 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | Based on Unipod offer for full scope of work
68 | Cost saving on finishes and fit out | Design Dev | [6 empty] | Design Dev | A.67 | 2015-09-07 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1
69 | Tilt & Turn windows to façades | Design Dev | [6 empty] | Design Dev | A.68 | 2015-09-15 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 36 | 2015-10-19 | 0 | Cancelled | 1 | 1 | [15 empty] | To be included in lump sum | [6 empty] | 1
70 | Additional façade VE proposals -Refer Schedule I | Design Dev | [6 empty] | Design Dev | A.69 | 2015-09-15 | #REF! |  | Cancelled | 1 | 1
71 | Direct Works VE Proposals - Refer Schedule I | Design Dev | [6 empty] | Design Dev | A.70 | 2015-09-15 | #REF! |  | Cancelled | 1 | 1 | [48 empty] | Refer Schedule I
72 | Additional MEPD VE category B proposals | Design Dev | [6 empty] | Design Dev | A.71 | 2015-09-15 | #REF! |  | Pending | 1 |  |  |  |  | 1 | [44 empty] | Category B VE to be confirmed
73 | Finishes & Fit out VE Proposals - Refer Schedule I | Design Dev | [6 empty] | Design Dev | A.72 | 2015-10-11 | #REF! |  | Cancelled | 1 | 1
74 | Fixed Fittings & Furnishings VE Proposals - Refer Schedule I | Design Dev | [6 empty] | Design Dev | A.73 | 2015-10-11 | 0 |  | Cancelled | 1 | 1
75 | Cost overrun of external works | Design Dev | [6 empty] | Design Dev | A.74 | 2015-10-11 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1
76 | External Works VE Proposals - Refer Schedule I | Design Dev | [6 empty] | Design Dev | A.75 | 2015-10-11 | #REF! |  | Cancelled | 1 | 1
77 | Cost overrun of light fittings | Design Dev | [6 empty] | Design Dev | A.76 | 2015-10-11 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1
78 | Additional Time Lapse Cameras | Design Dev | [6 empty] | Meraas | [11 empty] | 37 | 2015-09-30 | 58501 | Pending | 1 | [6 empty] | 1 | 1
79 | Additional proffessional fees (Supervision costs) as a result of KASGC claim for extension of time. (End December 2016 - End March 2017) | Delay | [6 empty] | Design Dev | A.77 | 2015-10-15 | 12500000 |  | Pending | 1 |  |  |  | 1
80 | Addition of fire rated glazed elements to façade | Design Dev | [6 empty] | Design Dev | A.78 | 2015-10-15 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1
81 | Additional C profile aluminium trims | Design Dev | [6 empty] | Design Dev | A.79 | 2015-10-15 | 0 |  | Cancelled | 1 | 1 | [25 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | Included in EW A.56 |  | 8462700.8
82 | Simplify trims to façade | Design Dev | [18 empty] | 39 | 2015-10-26 | -1236785 | Pending | 1 | [5 empty] | 1 |  | 1 | [31 empty] | Not included in Alico LS
83 | Omit Louvres to end of apartments | Design Dev | [18 empty] | 40 | 2015-10-26 | -2622891 | Pending | 1 | [5 empty] | 1 |  | 1 | [31 empty] | Not included in Alico LS
84 | Omit Brise Soleil to Balconies | Design Dev | [18 empty] | 41 | 2015-10-26 | -5781473 | Pending | 1 | [5 empty] | 1 |  | 1 | [31 empty] | Not included in Alico LS
85 | Change Timber Effect Aluminium Panels | Design Dev | [18 empty] | 42 | 2015-10-26 | 0 | Cancelled | 1 | 1 | [38 empty] | Estimated saving AED (1,457,871) rejected by Meraas
86 | Change finish to Secondary Facade Frames | Design Dev | [18 empty] | 43 | 2015-10-26 | 0 | Cancelled | 1 | 1 | [38 empty] | Estimated saving AED (1,742,958) rejected by Meraas
87 | Change internal cladding of primary frame | Design Dev | [18 empty] | 44 | 2015-10-26 | -644395 | Pending | 1 | [5 empty] | 1 |  | 1 | [31 empty] | Not included in Alico LS
88 | Change cladding to external face of primary fin from grooved to plain (non grooved) finish | Design Dev | [18 empty] | 46 | 2015-10-26 | 0 | Cancelled | 1 | 1 | [38 empty] | Estimated saving AED (1,523,814) rejected by Meraas
89 | Omit fibre C column and beam cladding to roofs | Design Dev | [18 empty] | 48 | 2015-10-26 | -4757348 | Pending | 1 | [5 empty] | 1 |  | 1 | [31 empty] | Not included in Alico LS
90 | Reduce thickness of acoustic layer below screeds | Design Dev | [18 empty] | 50 | 2015-10-26 | -783139 | Pending | 1 | [5 empty] | 1 |  | 1 | [8 empty] | To be included in lump sum | [6 empty] | 1
91 | Change from Epoxy parking floor coating to polyurethane coating | Design Dev | [18 empty] | 52 | 2015-10-26 | 0 | Cancelled | 1 | 1 | [38 empty] | Estimated saving AED (2,219,271) to omit coating rejected by Meraas. New RFC to be submitted with Polyurethane alternative.
92 | Omit anti carbonation paint to soffit of parking slabs | Design Dev | [18 empty] | 53 | 2015-10-26 | -1607087 | Pending | 1 | [5 empty] | 1 |  | 1
93 | Omit waterproofing to faces of water supply and drainage shafts | Design Dev | [18 empty] | 54 | 2015-10-26 | -769888 | Pending | 1 | [5 empty] | 1 |  | 1
94 | Paint to bathroom PODS | Design Dev | [18 empty] | 56 | 2015-10-25 | 0 | Cancelled | 1 | 1 | [38 empty] | Estimated saving AED (1,368,000) rejected by Meraas
95 | Change Quartz counter tops country of origin | Design Dev | [18 empty] | 57 | 2015-10-25 | -722019 | Pending | 1 | [5 empty] | 1 |  | 1 | [8 empty] | To be included in lump sum | [6 empty] | 1
96 | Zanussi alternative white goods specification | Design Dev | [18 empty] | 58 | 2015-10-25 | -5275731 | Pending | 1 | [5 empty] | 1 |  | 1 | [8 empty] | To be included in lump sum | [6 empty] | 1
97 | Change hinges to apartment doors | Design Dev | [18 empty] | 59 | 2015-10-25 | -757900 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1
98 | Change cladding to apartments entrances | Design Dev | [18 empty] | 60 | 2015-10-25 | 0 | Cancelled | 1 | 1 | [15 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | Estimated saving AED (955,455) rejected by Meraas
99 | Change skirting to apartment corridor to tiled skirting | Design Dev | [18 empty] | 61 | 2015-10-25 | 0 | Cancelled | 1 | 1 | [15 empty] | To be included in lump sum | [6 empty] | 1 | [15 empty] | Estimated saving AED (1,368,000) rejected by Meraas. RFC to be resubmitted with MDF skirting
100 | Roof louvers to mesh | Design Dev | [18 empty] | 63 | 2015-10-22 | -3757233 | Approved | 1 |  | 1 | [14 empty] | To be included in lump sum | [6 empty] | 1
101 | F&B Toilet extraction - Option 2 | Design Dev | [18 empty] | 64 | 2015-10-27 | 123000 | Pending | 1 | [5 empty] | 1 |  | 1 | [8 empty] | To be included in lump sum | [6 empty] | 1
102 | Local kitchens | Design Dev | [18 empty] | 66 | 2015-11-04 | 0 | Cancelled | 1 | 1 | [15 empty] | To be included in lump sum | [6 empty] | 1
103 | Replace U channel skirting detail with MDF face mounted skirtings | Design Dev | [18 empty] | 67 | 2015-11-04 | -2387000 | Pending | 1 | [5 empty] | 1 |  | 1 | [8 empty] | To be included in lump sum | [6 empty] | 1
104 | Omit BOH ceilings | Design Dev | [18 empty] | 68 | 2015-11-04 | -19000 | Approved | 1 |  | 1
105 | Replace U channel to door surrounds with 40mm timber architrave | Design Dev | [18 empty] | 69 | 2015-11-04 | -1365000 | Pending | 1 | [5 empty] | 1 |  | 1 | [8 empty] | To be included in lump sum | [6 empty] | 1
106 | Black granite to door thresholds and entrances | Design Dev | [18 empty] | 71 | 2015-11-09 | 679000 | Pending | 1 | [5 empty] | 1 |  | 1
107 | Change from Stainless steel to alumnium hinges and handles to façade windows | Design Dev | [7 empty] | A.80 | 2015-11-15 | 0 |  | Transferred to RFC | 1 |  | 1 |  |  |  | 74 | 2015-12-15 | -4708520 | Approved | 1 |  | 1 | [14 empty] | To be included in the lump sum | [6 empty] | 1
108 | Remove waterproofing to underside of pods | Design Dev | [18 empty] | 55 | 2015-11-19 | 967119 | Pending | 1 | [5 empty] | 1 |  | 1 | [8 empty] | To be included in the lump sum | [6 empty] | 1
109 | Omit cold cathode to balconies | Design Dev | [18 empty] | 23 | 2015-10-21 | 0 | Cancelled | 1 | 1
110 | Change polyurethane back to epoxy in car park area | Design Dev | [7 empty] | A.81 | 2015-12-15 | 0 |  | Pending | 1 |  |  | 1
111 | Raise ceiling height to avoid void protection - Apartments | Design Dev | [18 empty] | 73 | 2015-12-15 | 405588 | Pending | 1 |  |  |  |  | 1 |  |  | 1
112 | Raise ceiling height to avoid void protection - Corridors | Design Dev | [7 empty] | A.82 | 2015-12-15 | 29745 |  | Pending | 1 |  |  | 1
113 | Additional retail conopy podium lights introduced as per drawing No: 6003-0000-NEO-2650-DG-1701-PDF-0A | Design Dev | [7 empty] | A.83 | 2015-12-15 | 375000 |  | Pending | 1 |  |  | 1
114 | Layout changes to DEWA substations No 1 and 5 | Design Dev | [7 empty] | A.84 | 2015-12-15 | 6296 |  | Pending | 1 |  |  | 1
115 | Revised design to Man Safe System | Design Dev | [7 empty] | A.85 | 2015-12-15 | 100674 |  | Pending | 1 |  |  | 1
116 | Additional ceiling details provided highlighting additional fiber cement ceiling finishes to basement and ground floor not included with in the Fiber Cement Package | Design Dev | [7 empty] | A.86 | 2015-12-15 | 689900 |  | Pending | 1 |  |  | 1
117 | Reduction of Entrance Canopies size from 4.5m to 3m as per drwgs 1605/1102/setting out plans/GA plans and Aconex ref: 6003-MLD-TRANSMIT-000877; to blocks B, C, D, E, F, G, H and J | Design Dev | [7 empty] | A.87 | 2015-12-15 | -663402 |  | Pending | 1 |  |  | 1
118 | Risk associated with Contractor's below the line items - AED20m claimed; 25% risk factor | Design Dev | [7 empty] | A.88 | 2015-12-15 | 5000000 |  | Pending | 1 |  |  | 1
119 | Change Door bell finish from White to Silver to match ironmongery | Design Dev | [7 empty] | A.89 | 2015-12-15 | 110982 |  | Pending | 1 |  |  | 1
120 | Reduce No of hinges on doors with less than 2.3m high to 3 hinges instead of 4 | Design Dev | [7 empty] | A.90 | 2015-12-15 | -17060 |  | Pending | 1 |  |  | 1
121 | Omission of all laundry cupboard to apartments | Design Dev | [7 empty] | A.91 | 2015-12-15 | -1546752 |  | Pending | 1 |  |  | 1
122 | Offset of RFC’s included in lump sum | Design Dev | [7 empty] | A.92 | 2015-12-15 | -39661196 |  | Pending | 1 |  |  | 1
123 | Risk for the use of Elenco due to DCD certification | Design Dev | [7 empty] | A.93 | 2015-12-15 | 4400000 |  | Pending | 1 |  |  | 1
124 | EW for VE items unlikely to succeed. Shown in orange | Design Dev | [7 empty] | A.94 | 2015-12-15 | 15042892 |  | Pending | 1 |  |  | 1
125 | Variance between ECP and lump sum for non awarded packages | Design Dev | [7 empty] | A.95 | 2015-12-15 | #REF! |  | Pending | 1 |  |  | 1
126 | Variance between ECP and lump sum for awarded packages | Design Dev | [18 empty] | CPR | 2015-12-15 | #REF! | Approved | 1 |  | 1
[7 empty] | 60366070 |  |  |  |  | #REF! | [10 empty] | #REF! | [24 empty] | 39810 | [13 empty] | 0 |  |  |  |  | 8462700.8 | 0
Notes
1. Items in yellow are included within the lump sum and have therefore been balanced off withiin the above tracker
2. Items in orange are VE options subject to an RFC. However following informal discussions the items are expected to be rejectedand have therefore been balanced off within the above tracker
[9 empty] | Initiation of Changes |  |  |  |  | Initiation of Changes | [44 empty] | Initiation of Changes
[9 empty] | Design Dev |  |  | #REF! |  | Design Dev | [8 empty] | 10928378 | [35 empty] | Design Dev |  |  | 0
[9 empty] | Meraas |  |  | 0 |  | Meraas | [8 empty] | 58231234 | [35 empty] | Meraas |  |  | 0
[9 empty] | Authority |  |  | 0 |  | Authority | [8 empty] | 11799070 | [20 empty] | 34 | [14 empty] | Authority |  |  | 0
[9 empty] | Tendering |  |  | 0 |  | Tendering | [8 empty] | 0 | [35 empty] | Tendering |  |  | 0
[9 empty] | Kier ASGC |  |  | 0 |  | Kier ASGC | [8 empty] | 0 | [35 empty] | Kier ASGC |  |  | 0
[9 empty] | Total Raised |  |  | #REF! |  | Total Raised | [8 empty] | 80958682 | [35 empty] | Total Raised |  |  | 0
[11 empty] | EW + RFC's per Change Management Tracker | #REF! |  | #REF! | [6 empty] | VE
[11 empty] | CPR awards Level 3 not in CMT per Meraas Instruction | #REF! |  | #REF! | [6 empty] | EW and RFC's less retained budget
[11 empty] | Balance | #REF! |  | #REF!
[11 empty] | Check against level 1 | #REF! |  | #REF! | [6 empty] | Approved VE
[12 empty] | #REF! |  | #REF!
#REF!
[11 empty] | EW excl prov sum | #REF! |  | #REF! | [6 empty] | EW
[11 empty] | Less: Retained budget | 0 |  | 0 | [6 empty] | Less: Prov Sum
[11 empty] | Nett EW | #REF! |  | 0 | [6 empty] | Less: Retained budget
[11 empty] | less: CPR's awarded | #REF! |  | #REF! | [6 empty] | Nett EW
[12 empty] | #REF! |  | #REF! | [6 empty] | RFC's
[11 empty] | Add: RFC's | #REF! |  | #REF! | [6 empty] | TOTAL RFC's & EW (EXCL CPR'S)
#REF!
[11 empty] | Add back VE pending | #REF!
[11 empty] | Add back VE conditional | #REF!
#REF!
#REF!
ADD CALCULATION
[11 empty] | Nett EW & Award CRPS | #REF!
Adjust for
[11 empty] | Tilt & Turn windows to façades | -1478000 | Omit because not considered in ADD cost estimate
[11 empty] | Additional façade VE proposals -Refer Schedule I | #REF! | Added because potential VE considered separately
[11 empty] | Other VE Proposals - Refer Schedule I | #REF! | Part Added because potential VE considered separately
[11 empty] | Additional MEPD VE category B proposals | #REF! | Added because potential VE considered separately
#REF!
External Change Management Procedure
Meraas Internal Procedure
Early Warnings
Note on BP20: Keith Glazier: If VO is not approved type "Cancelled"
Note on M78: Paul Brand: ddt: RFC 36 ddt: RFC 11 ddt:RFC 12
Note on M80: Paul Brand: Light fittings and sanitary ware excluded

## Schedule F (SS) (hidden)
BLUEWATERS - RESIDENTIAL
DPDP-6003
| DATE: | 2016-01-15
CHANGE MANAGEMENT DASHBOARD
EARLY WARNINGS (EW) | [8 empty] | REQUEST FOR CHANGE (RFC) | [8 empty] | EMPLOYERS REPRESENTATIVE INSTRUCTION (ERI)
|  | Value | Total | Previous | Period | [5 empty] | Value | Total | Previous | Period | [5 empty] | Action | Total | Previous | Period
Total EW's Raised |  |  | 97 | 97 | 0 |  |  |  | Total RFC's Raised |  | 35801243 | 57 | 57 | 0 |  |  |  | Total ERI's Issued |  |  | 5 | 5 | 0
Closed |  |  | 53 | 53 | 0 |  |  |  | Closed |  |  | 14 | 14 | 0 |  |  |  | ERI's inc. in Lump Sum |  | No further action | 4 | 4 | 0
Transferred to RFC |  |  | 26 | 26 | 0 |  |  |  | Approved (inc. in Lump Sum) |  | 59300480 | 22 | 22 | 0 |  |  |  | Contractor submitted Costs |  | Proceed to VOAF | 0 | 0 | 0
Mirage Pending < 30 days |  | -45887214 | 15 | 15 | 0 |  |  |  | Approved (Authority) |  | 3704070 | 3 | 3 | 0 |  |  |  | Contractor Pending < 30 days |  | Contractors Variation Claims with full particulars | 0 | 0 | 0
Mirage Pending 30 to 60 days |  | 12500000 | 1 | 1 | 0 |  |  |  | Approved (proceed to ERI) |  | -1483759 | 1 | 1 | 0 |  |  |  | Contractor Pending 30 to 60 days |  |  | 0 | 0 | 0
Mirage Pending > 60 days |  | 12000000 | 2 | 2 | 0 |  |  |  | Meraas Pending < 30 days |  | 405588 | 1 | 1 | 0 |  |  |  | Contractor Pending > 60 days |  |  | 1 | 1 | 0
Total Pending EW's |  | -21387214 | 18 | 18 | 0 |  |  |  | Meraas Pending 30 to 60 days |  | -26183637 | 15 | 15 | 0 |  |  |  | Total Pending Contractor Variation Claims |  |  | 1 | 1 | 0
[9 empty] | Meraas Pending > 60 days |  | 58501 | 1 | 1 | 0
[9 empty] | Total Pending RFC's |  | -25719548 | 17 | 17 | 0
Comments: | [8 empty] | Comments: | [8 empty] | Comments:
TOP 5 PENDING EARLY WARNINGS | [8 empty] | TOP 5 PENDING RFC's | [8 empty] | TOP 5 ERI'S ISSUED IN PERIOD
Item No. | Description |  |  | Initiated by |  | EW No. | Date | Cost Impact | Item No. | Description |  |  | Initiated by |  | RFC No. | Date | Cost Impact | ERI No. | Description |  |  | ERI Issue Date |  | ERI Return Date | RFC Ref. | Est. Cost Impact
65 | Contractor's 1st Interim Application for Extension of Time to Completion |  |  | Design Deviation |  | 64 | 2015-07-29 | 14000000 | 84 | Omit Brise Soleil to Balconies |  |  | Mirage |  | 41 | 2015-10-26 | -5781473 | 5 | Omission of CAR insurance from contractors Preliminaries - CAR insurance effected by Employer |  |  | 2015-06-20 |  | TBC | 8 | -440000
79 | Additional proffessional fees (Supervision costs) as a result of KASGC claim for extension of time. (End December 2016 - End March 2017) |  |  | A.80 |  | 77 | 2015-10-15 | 12500000 | 96 | Zanussi alternative white goods specification |  |  | Mirage |  | 58 | 2015-10-25 | -5275731 | 4 | Omission of Aconex from contractors Preliminaries - effected by Employer (0.12% of final agreed contract lump sum) |  |  | 2015-06-20 |  | TBC | 4 | -1483759
118 | Risk associated with Contractor's below the line items - AED20m claimed; 25% risk factor |  |  | Mirage |  | 88 | 2015-12-15 | 5000000 | 103 | Replace U channel skirting detail with MDF face mounted skirtings |  |  | Mirage |  | 67 | 2015-11-04 | -2387000 | 7 | Cost of mock-up built off site |  |  | 2015-06-25 |  | TBC | 7 | 0
123 | Risk for the use of Elenco due to DCD certification |  |  | Design Deviation |  | 93 | 2015-12-15 | 4400000 | 105 | Replace U channel to door surrounds with 40mm timber architrave |  |  | Mirage |  | 69 | 2015-11-04 | -1365000 | 2 | Shoring adjacent to retail site boundary |  |  | 2015-05-20 |  | TBC | 3 | 3815024
124 | EW for VE items unlikely to succeed. Shown in orange |  |  | Meraas |  | 94 | 2015-12-15 | 15042892 | 89 | Omit fibre C column and beam cladding to roofs |  |  | Mirage |  | 48 | 2015-10-26 | -4757348 | 6 | UKEF financing fee |  |  | 2015-06-23 |  | TBC | 5 | 10773492
MERAAS VARIATION APPROVAL FORM (VOAF) | [8 empty] | CONTRACTOR'S VARIATIONS (CLAUSE 13.1) | [8 empty] | CONTRACTOR'S CLAIMS (CLAUSE 20.1)
|  | Value | Total | Previous | Period | [5 empty] | Value | Total | Previous | Period | [5 empty] | Value | Total | Previous | Period
Total VOAF's |  | 78990 | 48 | 48 | 0 |  |  |  | Total Variations Received |  | 0 | 42 | 42 | 0 |  |  |  | Total Claims Received |  | 66592588 | 64 | 0 | 64
Cancelled |  |  | 46 | 46 | 0 |  |  |  | Closed or inc. in Lump Sum |  |  | 0 | 0 | 0 |  |  |  | Closed / Rejected |  |  | 1 | 0 | 1
Disputed |  | 0 | 0 | 0 | 0 |  |  |  | Awaiting Costs (No ERI) |  |  | 21 | 21 | 0 |  |  |  | Awaiting Details |  |  | 62 | 0 | 62
Approved (VO Issued) |  | 39810 | 1 | 1 | 0 |  |  |  | Awaiting Costs (ERI issued) |  |  | 0 | 0 | 0 |  |  |  | Disputed |  | 0 | 0 | 0 | 0
Mirage Pending < 30 days |  | 0 | 0 | 0 | 0 |  |  |  | Approved (proceed to RFC) |  | 0 | 0 | 0 | 0 |  |  |  | Approved (Proceed to VOAF) |  | 0 | 0 | 0 | 0
Mirage Pending > 30 days |  | 0 | 0 | 0 | 0 |  |  |  | Mirage Pending < 30 days |  | 0 | 1 | 1 | 0 |  |  |  | Mirage Pending < 30 days |  | 66592588 | 1 | 0 | 1
Meraas Pending < 30 days |  | 39180 | 1 | 1 | 0 |  |  |  | Mirage Pending 30 to 60 days |  | 0 | 0 | 0 | 0 |  |  |  | Mirage Pending 30 to 60 days |  | 0 | 0 | 0 | 0
Meraas Pending > 30 days |  | 0 | 0 | 0 | 0 |  |  |  | Mirage Pending > 60 days |  | 0 | 20 | 20 | 0 |  |  |  | Mirage Pending > 60 days |  | 0 | 0 | 0 | 0
Total Pending VOAF's |  | 39180 | 1 | 1 | 0 |  |  |  | Total Pending RFC's |  | 0 | 21 | 21 | 0 |  |  |  | Total Pending Claims |  | 66592588 | 1 | 0 | 1
Comments: | [8 empty] | Comments: | [8 empty] | Comments: Mirage has presented their assessment of ASGC JV's claim to Meraas
TOP 5 PENDING VOAF'S | [8 empty] | TOP 5 CONTRACTOR'S VARIATIONS | [8 empty] | TOP 5 CONTRACTOR'S CLAIMS
Item No. | Description |  |  | Action with |  | VOAF No. | Date | Cost Impact | Vo. Ref. | Description |  |  | Aconex / Letter Ref |  |  | Date | Cost Impact | Item No. | Description |  |  | Aconex / Letter Ref |  | Date | Time (days) | Cost Impact
1 | Additional 4 boreholes requested to Geotechnical survey |  |  | Meraas |  | 1 | 2015-11-05 | 39810 | [9 empty] | 53 | Contractor's 1st Interim Application for Extension of Time to Completion - supplementary information and editable files |  |  | 6003-KAS-LETTER-000268 |  | 2015-07-29 | 159 | 31318000
[18 empty] | 81 | Revised Time for Completion submission |  |  | 6003-KAS-LETTER-000379 |  | 2015-11-23 | 232 | 66592588
Note on R13: Keith Glazier: includes ALEC site office move
Note on AM23: Keith Glazier: Use RFC estimate

## Schedule E (hidden)
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
[12 empty] | (A) For Commercial leads use (please provide all the details, where there is no submission type 'Not submitted' or 'Not Applicable') | [8 empty] | Refer to Note (A)
Claims Summary |  | Contract |  |  |  |  | Type of Claim |  |  |  |  | Notice Requirements | [6 empty] | Detailed Claim with Supporting Particulars | [7 empty] | EOT: (i) Contractor's Claim (ii) Engineer's Recommendation (iii) Employer's Assessment for Consultation / Agreement (iv) Employer's Determination | [13 empty] | Cost: (i) Contractor's Claim (ii) Engineer's Recommendation (iii) Employer's Assessment for Consultation / Agreement (iv) Employer's Determination | [9 empty] | Comments | (i) (ii) Claim Status (iii) Action (iv) Internal Remarks |  |  |  | (i) Rejection (ii) Notices |  |  | (i) KPI |  | (i) Project Summary
Claim No. | Description of Claim | Contract No. | Asset Code | Project Name | Scope | Contractor / Consultant Name | EoT | Prolongation | Disruption | Acceleration | Other Claims | Date on which Contractor became aware of event | Contractor's Notification of Claim [Note, this may just be a notification without a detailed claim and supporting particulars. But Contractor may use this as an opportunity to also provide a detailed claim and supporting particulars with his notice.] |  | Period between Contractor becoming aware of event and providing a notice | Does period comply with the Contract? [i.e. within 20 Business Days] | Engineer / Employer's response to Contractor's Notice [If detailed claim and supporting particulars have not been provided along with the notice then no time limit for response. However good practice would be to respond with an acknowledgment within 10 Days and remind the Contractor of its obligation to submit a detailed claim. If detailed claim and supporting particulars have been provided along with the notice then Engineer / Employer shall respond within 30 Days (note, not Business Days)] |  | Detailed claim with supporting particulars provided by Contractor [Note: Whilst there is no requirement to do so, the Contractor may have provided this along with the Notice] |  | Period between Contractor becoming aware of event and providing a detailed claim with supporting particulars | Does period comply with the Contract? [i.e. within 30 Business Days of Contractor becoming aware of event] | Engineer / Employer's Detailed Comments to Contractor [This should be within 21 Days (note, not Business Days) of Contractor's Claim] |  | Resubmission / Further Particulars Provided by Contractor [There may be more than one resubmission] [Fill in the original submission if there is no resubmission made or TBA if expecting a Resubmission] |  | Contractor's Claim (Days) |  | Engineer's Recommendation (Days) |  |  |  | Employer's Assessment for Consultation / Agreement |  |  |  | Determination (or by Agreement) (Days) |  |  |  | Contractor's Claim (SAR) | Engineer's Recommendation (SAR) |  |  | Employer's Assessment for Consultation / Agreement (SAR) |  |  | Employer's Determination (or by Agreement) (SAR) |  |  | Last Action Date / Type of Discussion between Employer, Engineer & Contractor [e.g. letters, workshops, emails, meetings, etc.] | Status 1 | Status 2 | Action | Remark | Rejected on Merit or Revise & Resubmit | Notice of Dissatisfaction Yes or No | Notice of Dispute Yes or No | Assessment Report Closure Month (MM-YY) | DVO/VO Closure Month (MM-YY) | Project Start Date | Project Completion Date | Revised Completion Date
[12 empty] | (A) Date | Letter Reference | (B) Date of Receipt by RSG | (B-A) In Business Days | Yes/No | Letter Reference | Date Issued | Letter Reference | (C) Date of Receipt by RSG | (C-A) in Business Days | Yes/No | Letter Reference | Date Issued | Letter Reference | Date of Receipt by RSG | EOT Days | Compensable Days (Costs) | EOT Days | Compensable Days (Costs) | Letter Reference | Date Issued | EOT Days | Compensable Days (Costs) | Letter Reference | Date Issued | EOT Days | Compensable Days (Costs) | Letter / VO Reference | Date Issued | SAR | SAR | Letter Reference | Date Issued | SAR | Letter Reference | Date Issued | SAR | Letter / VO Reference | Date Issued | [13 empty] | DO NOT DELETE THIS COLUMN
1 | Change In Ground Condition | 1TB01003C13 | 1.TB.01.003.01 | AMAALA Yacht Club | Triple Bay Wide Ground Improvement | Soil Improvement Contracting | x |  |  |  |  | 2021-11-24 | YAM.-LTR-000004 | 2023-01-17 | 300 | NO | 1TB00004-007C02-SAP-LTR-0043 | 2022-01-18 | YAM.-LTR-000009 | 2022-03-09 | 76 | NO | 1TB04004-004D01-SAP-LTR-0008 | 2022-03-29 |  |  | 93 | 93 | 30 | 30 | [6 empty] | 30 | 0 | SAP04004-GENCORR-000776 | 2023-03-18 | 0 | 0 | [10 empty] | Determination Issued | Closed |  | Merit |  |  |  |  | 2021-10-05 | 2021-12-27 | 2022-01-26
2 | Consolidated Claim - Prolongation Costs (Delay in IFC's, SANSRS Coordinates) | 1TB01003C14 | 1.TB.01.003.01 | AMAALA Yacht Club | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting | x | x |  |  |  | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 122 | 122 | 96 | 96 | TB04400-031D03-WSP-LTR-0138 | 2023-11-12 | 112 | 97 |  |  | 112 | 326542.895 |  |  | 653085.79 | 1491099.05 | 1TB04400-400000-AMA-LTR-0056 | 2024-10-13 | 326542.895 |  |  | 326542.895 |  |  | Closed - Determination issued to NSCC (agreed). | Assessment Report Issued | Determination Issued | Closed | DVO issued to NSCC | [5 empty] | 2022-03-31 | 2023-12-31 | 2024-04-21
2.1 | Consolidated Claim - Investigation Reports (Unforeseen Physical Conditions) | 1TB01003C14 | 1.TB.01.003.01 | AMAALA Yacht Club | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting |  |  |  |  | x | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 122 | 122 |  |  |  |  | 112 | 97 |  |  | 112 | 194579.22 |  |  | 389158.44 |  |  |  | 194579.22 |  |  | 194579.22 |  |  |  | Assessment Report Issued | Determination Issued | Closed | DVO issued to NSCC | [5 empty] | 2022-03-31 | 2023-12-31 | 2024-04-21
2.3 | Consolidated Claim - Idle Costs | 1TB01003C14 | 1.TB.01.003.01 | AMAALA Yacht Club | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting | x |  |  |  | x | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 122 | 122 |  |  |  |  | 112 | 97 |  |  | 112 | 2772915.4851 |  |  | 5545830.9701 |  |  |  | 2772915.4851 |  |  | 2772915.4851 |  |  |  | Assessment Report Issued | Determination Issued | Closed | DVO issued to NSCC | [5 empty] | 2022-03-31 | 2023-12-31 | 2024-04-21
2.4 | Consolidated Claim - 3rd Party Investigation Boreholes ACES | 1TB01003C14 | 1.TB.01.003.01 | AMAALA Yacht Club | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting |  |  |  |  | x | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 122 | 122 |  |  |  |  | 112 | 97 |  |  | 112 | 79505.0633 |  |  | 159010.1267 |  |  |  | 79505.0633 |  |  | 79505.0633 |  |  |  | Assessment Report Issued | Determination Issued | Closed | DVO issued to NSCC | [5 empty] | 2022-03-31 | 2023-12-31 | 2024-04-21
3 | Consolidated Claim - Prolongation Costs (Delay in IFC's, SANSRS Coordinates) | 1TB01005C23 | 1.TB.01.005.01 | Red Sea Marine Life Institute | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting | x | x |  |  |  | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 143 | 143 |  |  |  |  | 83 | 69 |  |  | 83 | 558459.06 |  |  | 2091538.02 | 558459.06 | Currently Under Review |  | 558459.06 |  |  | 558459.06 |  |  | Under Process | Assessment Report Issued | Open | Planning Team | Review related to Prolongation Costs to RSMLI | [5 empty] | 44651 | 45066 | 45149
3.1 | Consolidated Claim - Investigation Reports (Unforeseen Physical Conditions) | 1TB01005C23 | 1.TB.01.005.01 | Red Sea Marine Life Institute | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting |  |  |  |  | x | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 143 | 143 |  |  |  |  | 83 | 69 |  |  | 83 | 161161.608 |  |  | 201452.01 | 161161.608 | Currently Under Review |  | 161161.608 |  |  | 161161.608 |  |  | Under Process | Assessment Report Issued | Open | Claims Team | Review related to Investigation and Reports to RSMLI | [5 empty] | 44651 | 45066 | 45149
3.2 | Consolidated Claim - Idle Costs | 1TB01005C23 | 1.TB.01.005.01 | Red Sea Marine Life Institute | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting | x |  |  |  | x | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 143 | 143 |  |  |  |  | 83 | 69 |  |  | 83 | 1648361.58 |  |  | 12477085.3476 | 1648361.58 | Currently Under Review |  | 1648361.58 |  |  | 1648361.58 |  |  | Under Process | Assessment Report Issued | Open | Planning Team | Review related to Idle Costs related to RSMLI | [5 empty] | 44651 | 45066 | 45149
3.3 | Consolidated Claim - 3rd Party Investigation Boreholes ACES | 1TB01005C23 | 1.TB.01.005.01 | Red Sea Marine Life Institute | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting |  |  |  |  | x | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 143 | 143 |  |  |  |  | 83 | 69 |  |  | 83 | 37158.5733 |  |  | 159010.1267 | 37158.5733 | Currently Under Review |  | 37158.5733 |  |  | 37158.5733 |  |  | Under Process | Assessment Report Issued | Open | Planning Team | Review related to 3rd Part Investigation Boreholes - ACES to RSMLI | [5 empty] | 44651 | 45066 | 45149
3.4 | Consolidated Claim - Additional Costs Associated with Unforseeable Conditions | 1TB01005C23 | 1.TB.01.005.01 | Red Sea Marine Life Institute | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting |  |  |  |  | x | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 143 | 143 |  |  |  |  | 83 | 69 |  |  | 83 | 2596990.7429 |  |  | 3133416.212 | 2596990.7429 | Currently Under Review |  | 2596990.7429 |  |  | 2596990.7429 |  |  | Under Process | Assessment Report Issued | Open | Planning Team | Review related to 3rd Part Investigation Boreholes - ACES to RSMLI | [5 empty] | 44651 | 45066 | 45149
4 | Consolidated Claim - Prolongation Costs (Delay in IFC's, SANSRS Coordinates) | 1TB01002C21 | 1.TB.01.002.03 | Marina Lifestyle Hotel & Village | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting | x | x |  |  |  | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 156 | 156 |  |  |  |  | 122 | 122 |  |  | 122 | 705328.26 |  |  | 1528963.82 | 705328.26 | Currently Under Review |  | 705328.26 |  |  | 705328.26 |  |  | Under Process | Assessment Report Issued | Open | Planning Team | Review related to Prolongation Costs to MLH | [5 empty] | 44651 | 45066 | 45188
4.1 | Consolidated Claim - Investigation Reports (Unforeseen Physical Conditions) | 1TB01002C21 | 1.TB.01.002.03 | Marina Lifestyle Hotel & Village | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | 33 |  |  |  |  | x | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 156 | 156 |  |  |  |  | 122 | 122 |  |  | 122 | 65438.784 |  |  | 81798.48 | 65438.784 | Currently Under Review |  | 65438.784 |  |  | 65438.784 |  |  | Under Process | Assessment Report Issued | Open | Claims Team | Review related to Investigation and Reports to MLH | [5 empty] | 44651 | 45066 | 45188
4.2 | Consolidated Claim - Idle Costs | 1TB01002C21 | 1.TB.01.002.03 | Marina Lifestyle Hotel & Village | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | 35 | x |  |  |  | x | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 156 | 156 |  |  |  |  | 122 | 122 |  |  | 122 | 2174109.5 |  |  | 13670953.9749 | 2174109.5 | Currently Under Review |  | 2174109.5 |  |  | 2174109.5 |  |  | Under Process | Assessment Report Issued | Open | Planning Team | Review related to Idle Costs related to MLH | [5 empty] | 44651 | 45066 | 45188
4.3 | Consolidated Claim - 3rd Party Investigation Boreholes ACES | 1TB01002C21 | 1.TB.01.002.03 | Marina Lifestyle Hotel & Village | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting |  |  |  |  | x | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 156 | 156 |  |  |  |  | 122 | 122 |  |  | 122 | 37158.5733 |  |  | 159010.1267 | 37158.5733 | Currently Under Review |  | 37158.5733 |  |  | 37158.5733 |  |  | Under Process | Assessment Report Issued | Open | Planning Team | Review related to 3rd Part Investigation Boreholes - ACES to MLH | [5 empty] | 44651 | 45066 | 45188
5 | Consolidated Claim - Prolongation Costs (Delay in IFC's, SANSRS Coordinates) | 1TB02011C27 | 1.TB.02.011.01 | Rosewood Resort | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting | x | x |  |  |  | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 179 | 179 |  |  |  |  | 175 | 158 |  |  | 175 | 672073.46 |  |  | 1566556.57 | 672073.46 | Currently Under Review |  | 672073.46 |  |  | 672073.46 |  |  | Under Process | Assessment Report Issued | Open | Planning Team | Review related to Prolongation Costs to ROSEWOOD | [5 empty] | 44651 | 44973 | 45148
5.1 | Consolidated Claim - Idle Costs | 1TB02011C27 | 1.TB.02.011.01 | Rosewood Resort | Triple Bay Piling - Beach, RSMLI, Yacht Club and Marina Village Precinct (Hotel 1 and 2) | NSCC International Saudi Contracting | x |  |  |  | x | 2023-04-29 | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  | TB04400-005C13-NSC-LTR-0326 | 2023-04-29 | 0 | YES |  |  |  |  | 179 | 179 |  |  |  |  | 122 | 105 |  |  | 175 | 23736.6 |  |  | 280739.0328 | 23736.6 | Currently Under Review |  | 23736.6 |  |  | 23736.6 |  |  | Under Process | Assessment Report Issued | Open | Planning Team | Review related to Idle Costs related to ROSEWOOD | [5 empty] | 44651 | 44973 | 45148
6 | Engineer's Instruction No. 5, 7, 9 & 10 | 1TB01031C02 | 1.TB.01.031.01 | The Marina | Triple Bay Marina Basin - Design and Build Main Contract | Alsaad General Contracting Company | x |  |  |  |  | 2021-09-09 | SGC-GENCORR-000008 | 2021-10-05 | 19 | YES |  |  | WSP-LTR-000021 | 2021-12-01 | 60 | YES | SGC-LTR-000015 | 2021-11-25 |  |  | 465 | 465 |  |  |  |  | 324 | 177 |  |  | 324 | 14631530.8 |  |  | 46455401.69 | 14631530.8 | Awaiting ContractorCommercial Submission |  | 14631530.8 |  |  | 14631530.8 |  |  | EOT determined - Awaiting Contractors Commercial Submission | Assessment Report Issued | Determination Issued | Commercial Team | Awaiting Contractors Commercial Submission | [5 empty] | 44161 | 45078 | 45402
7 | Request for Interim Extension of Time # 1 a) Change in location of Jettie b) Change in Location due to HAT c) Construction of Retaining Wall d) Force Majeure Protest at France e) Force Majuere At KSA Border f) Construction of Jettie Platform g) Installation of Fence | 1TB01005C17 | 1.TB.01.005.01 | Red Sea Marine Life Institute | Marine Life Operation Facility for Marina Village | Hassan Hamdi Al Harbi Contracting Est. (HASCO) | x |  |  |  |  | 2023-01-19 | 1TB01005-005C17-HAH-LTR-0014 | 2023-05-31 | 95 | NO | 1TB01005-005C17-AMA-LTR-0021 | 2023-06-05 | [8 empty] | 72 | 72 |  |  |  |  | 0 | 0 | 1TB01005-005C17-AMA-LTR-0021 | 2023-06-05 |  |  |  |  | TBC |  |  |  | 0 | Claim rejected | 2023-09-21 |  |  |  |  | Rejected | Rejected | Closed | Claim Rejected - However concerns related to the new platform and relocation of the jettie. | [5 empty] | 44945 | 45035 | 45035
8 | Extension of Time Claim Accordance to Approved Variation Order # 002 (Changes from IFT to IFC) | 1TB01003C03 | 1.TB.01.003.01 | AMAALA Yacht Club | Construction Contract - Site Enabling, Civil Works, Structural Concrete, Structural Steel, BOH Finishes, Building Envelope, MEP Including Tertiary Infrastructure & ICT/ELV | Saudi Arabian Baytur Construction Company | x |  |  |  |  | 2023-05-17 | 1TB01003-003C03-SAB-LTR-0006 | 2023-05-18 | 2 | YES | AMA01003-GENCORR-000328 | 2023-07-06 | 1TB01003-003C03-AMA-LTR-0068 | 2023-09-21 | 92 | NO | 1TB01003-003C03-AMA-LTR-0068 | 2023-09-21 |  |  | 42 | 42 |  |  |  |  | 0 | 0 | 1TB01003-003C03-AMA-LTR-0068 | 2023-09-21 | 0 |  |  |  | 0 |  |  |  | 0 | Claim rejected | 2023-09-21 |  |  |  |  | Rejected | Rejected | Closed | Claim Rejected Based on time - Contractor very delayed | [5 empty] | 2023-01-12 | 2025-02-28 | 2025-02-28
9 | Consolidated Claim - EOT & Prolongation Costs (Delay in IFC's) | 1TB01002C01 | 1.TB.01.002.01 | Marina Lifestyle Hotel & Village | Triple Bay Wide Ground Improvement | Soil Improvement Contracting | x | x |  |  |  | 2021-11-23 | 1TB04004-004C03-SIC-LTR-0006 | 2022-03-08 | 76 | NO | 1TB04004-004C03-SAP-LTR-0010 | 2022-03-26 | 1TB04004-004C03-SIC-LTR-0018 | 2022-05-21 | 129 | NO | 1TB04004-004C03-SAP-LTR-0027 | 2022-05-29 | 1TB04004-004C03-SIC-LTR-0043 1TB04004-004C03-SIC-LTR-0103 | 03-Sep-2022 4-Jul-23 | 433 | 433 | 433 | 433 | 1TB04004-004D01-SAP-LTR-0052 | 2023-06-13 | 433 | 433 |  |  | 433 | 1421551.67 |  |  | 2201256.02 | 2194683.7 | 1TB04004-004D01-SAP-LTR-0052 | 2023-06-13 | 1421551.67 |  |  | 1421551.67 |  |  | Under Process | Assessment Report Issued | Open | Claims Team | Report and Commercial Assessment is being reviewed by Claims Team. | [5 empty] | 44523 | 44634 | 45067
29 | Extension of Time Claim AYC - non-readiness of site (Interim Claim) | 1TB01003C08 | 1.TB.01.003.01 | AMAALA Yacht Club | Kitchen & Laundry Works | Abdulaziz Al Raqtan and Partners Company for Trading and Industry Company | x |  |  |  |  | 2024-06-07 | 1TB01003-003C08-RQN-LTR-0001 | 2024-06-07 | 1 | YES | 1TB01003-003C08-AMA-LTR-0017 | 2024-07-25 | RQN01003-CLM-000004 | 2024-08-22 | 55 | YES | 1TB01003-003C08-AMA-LTR-0020 | 2024-08-17 | RQN01003-CLM-000005 | 2024-08-29 | 73 | 0 | 70 | [21 empty] | Agreed. No Cost Impact. |  | Determination Issued | Closed | Agreed DVO to be issued.
30 | Interim Extension of Time For Completion No. 01 | 1TB01003C09 | 1.TB.01.003.01 | AMAALA Yacht Club | Fitout Works | DEPA | x |  |  |  |  | 2024-10-08 | 1TB01003-003C09-DCC-LTR-0129 | 2024-10-08 | 1 | YES | [10 empty] | 164 | 0 | 86 | [21 empty] | Revised Assessment Report issued to DEPA |  | Determination Issued | Contractor | Awaiting DEPA agreement. | [8 empty] | 726
31 |  |  | 0 | 0 | 0 | 0 | [9 empty] | YES
32 |  |  | 0 | 0 | 0 | 0 | [9 empty] | YES
33 |  |  | 0 | 0 | 0 | 0 | [9 empty] | YES
34 |  |  | 0 | 0 | 0 | 0 | [9 empty] | YES
35 |  |  | 0 | 0 | 0 | 0 | [9 empty] | YES
36 |  |  | 0 | 0 | 0 | 0 | [9 empty] | YES
37 |  |  | 0 | 0 | 0 | 0 | [9 empty] | YES
38 |  |  | 0 | 0 | 0 | 0
57 | Extention of time 001 under Clause 6.3 Conditions of Contract | 1TB01003F03 |  |  |  | Elevator Systems Contracting Company (ESCCO) | [5 empty] | 2025-01-26 | ESCO1003-TRANSMIT-000121 1TB01003-003F03-ESC-LTR-0011 | 2025-01-26 | 0 | YES | AMA01003-GENCORR-000985 | 2025-02-02 | ESC01003-GENCORR-000019 dated 03 Feb 25 ESC01003-GENCORR-000020 | 2025-02-05 | 217 | [5 empty] | 216 | 0 | 96 | [21 empty] | Assessment Report issued to ESCCO. |  | Determination Issued | Closed | Determination issued
56 | Extention of time 001 under Clause 8.4.1 Conditions of Contract | 1TB01003C27 |  |  |  | Aluminium Technology Auxiliary Industries (Alutec) WLL | [6 empty] | 1TB01003-003C27-ATA-LTR-0029 | 2025-08-26 | [36 empty] | Assessment Report issued to the Claim Team. |  | Open | Claims Team | [9 empty] | 404
96 | DEPA - Interim Extension of Time For Completion No. 02 | 1TB01003C09 |  |  |  | DEPA Saudi Arabia for Contracting and Interior Decoration Co. Ltd | [6 empty] | 1TB01003-003C09-DCC-LTR-0299 | 2025-10-09 | [36 empty] | Under review by Commercial and Planning Team. |  | Open | Commercial Team | [9 empty] | 360
223215.9
1267883.15
-223215.9
0
0

## Schedule F (hidden)
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
ITEM | DESCRIPTION | STATUS | CONTRACTOR NAME | BUDGET | CONTRACT VALUE | (SAVING) / EXTRA | COMMENTS
1 | SOI TB Ground Improvement Works 2210224 - Provisional Sum | PENDING | SIC | 282971.7 | 0 | 282971.7
2 | LIU - GC Consultancy Agreement Yacht Club 2230042 - Provisional Sum | PENDING | LIU | 3947.37 | 0 | 3947.37
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
| TOTALS |  |  | 286919.07 | 0 | 286919.07

## Schedule G
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
REF. | CONTRACTOR / CONSULTANT | PACKAGE | ORIGINAL CONTRACT SUM | REVISED CONTRACT VALUE | TYPE OF BOND / INSURANCE | POLICY NO | CONTRACT REQUIRMENT | AMOUNT PROVIDED | VARIANCE TO CONTRACT | EXPIRY DATE | NR DAYS TO EXPIRE | APPROVED | BANK VERIFICATION (YES / NO) | COMMENTS
|  |  | SAR | SAR |  | Date | SAR | SAR | SAR | Date | Nr. | Yes/No
1 | NSCC - Piling Contractor | Piling Works | 18698534 | 16458381.51 | Professional Indemnity | CER-Q0322-PPI-TEIB-006976 | 20000000 | 75000000 | 0 | 2023-09-30 |  | Yes |  | FULLY PAID/ CLOSED
2 | NSCC - Piling Contractor | Piling Works | 18698534 | 16458381.51 | Third Party Liability | Q0322-CAR-TEIB-006981/V1 | 3000000 | 11250000 | 0 | 2023-09-30 |  | Yes |  | FULLY PAID/ CLOSED
3 | NSCC - Piling Contractor | Piling Works | 18698534 | 16458381.51 | Workmens Compensation | P0422-CEL-TEIB-15479455/R1 | 5000000 | 3750000 | 1250000 | 2024-03-30 |  | Yes |  | FULLY PAID/ CLOSED
4 | NSCC - Piling Contractor | Piling Works | 18698534 | 16458381.51 | Contractors all Risk | Q0322-CAR-TRIB-006981/V1 | 132445250.8 | 132445250.8 | 0 | 2023-09-30 |  | Yes |  | FULLY PAID/ CLOSED
5 | NSCC - Piling Contractor | Piling Works | 18698534 | 16458381.51 | Plant and Equipment | Q0622-CPM-TEIB-007021/V1 | 42399455 | 158997956.25 | 0 | 2023-09-15 |  | Yes |  | FULLY PAID/ CLOSED
6 | NSCC - Piling Contractor | Piling Works | 18698534 | 16458381.51 | Advance Payment Bond | KCLG2200439 | 21990478.4 | 21990478.4 | 0 | 2023-11-30 |  | Yes |  | FULLY PAID/ CLOSED
7 | NSCC - Piling Contractor | Piling Works | 18698534 | 16458381.51 | Performance Bond | KCLG2200438 | 10995239.2 | 10995239.2 | 0 | 2024-09-15 |  | Yes |  | FULLY PAID/ CLOSED
8 | Dewan Architects & Engineers | Designers | 5973808 | 7501639.1 | Professional Indemnity | P/05/PIT/2025/00010 | AED 30,000,000 | AED 30,000,000 | 0 | 2026-07-31 | -65.6655 | Yes |  | RENEWED.
9 | Dewan Architects & Engineers | Designers | 5973808 | 7501639.1 | Third Party Liability | P/05/PIT/2025/00007 | AED 12,000,000 | AED 12,000,000 | 0 | 2026-07-31 | -65.6655 | Yes |  | RENEWED.
10 | Dewan Architects & Engineers | Designers | 5973808 | 7501639.1 | Workmens Compensation |  | 1000000 | 1000000 | 0 | 2025-08-17 | -413.6655 | Yes |  | TO BE RENEWED.
11 | HKS Architects Ltd | Designers | 10891204 | 10891204 | Professional Indemnity |  | £10,000,001 | £10,000,001 | £0 | 2023-02-28 |  | Yes |  | FULLY PAID/ CLOSED
12 | HKS Architects Ltd | Designers | 10891204 | 10891204 | Third Party Liability |  | £10,000,000 | £10,000,000 | £0 | 2023-06-10 |  | Yes |  | FULLY PAID/ CLOSED
13 | Soil Improvement Contracting Company | Contractor | 3082688.7 | 3082688.7 | Professional Indemnity |  | 75000000 | 75000000 | 0 | 2035-04-30 | 3129.3345 | Yes |  | 30/04/2023 plus 12 years ( 2 years Maintenance Period and Extended Reporting Period 10 Years ) | 4380 | 2047-04-27
14 | Soil Improvement Contracting Company | Contractor | 3082688.7 | 3082688.7 | Third Party Liability |  | 11250000 | 11250000 | 0 | 2023-06-14 |  | Yes |  | Under discussion between SIC and RSG. SIC noted that SIC is required to maintain the Insurance up to acquisition of TOC (30/April/2023) under YAM04004-TRANSMIT-000469.
15 | Soil Improvement Contracting Company | Contractor | 3082688.7 | 3082688.7 | Workmens Compensation |  | 11250000 | 11250000 | 0 | 2023-06-14 |  | Yes |  | Under discussion between SIC and RSG. SIC noted that SIC is required to maintain the Insurance up to acquisition of TOC (30/April/2023) under YAM04004-TRANSMIT-000469.
16 | Soil Improvement Contracting Company | Contractor | 3082688.7 | 3082688.7 | Vehicle |  | 67718856 | 67718856 | 0 | 2024-02-16 |  | Yes |  | Notice under AMA04004-NTFN-000302 is issued to SIC for the renewal of the policy.
17 | Soil Improvement Contracting Company | Contractor | 3082688.7 | 3082688.7 | Advance Payment Bond |  | 13068405.8 | 13068405.8 | 0 |  |  | Yes |  | Fully recovered
18 | Soil Improvement Contracting Company | Contractor | 3082688.7 | 3082688.7 | Performance Bond |  | 6534202.9 | 6534202.9 | 0 | unlimited |  | Yes
19 | Soil Improvement Contracting Company | Contractor | 3082688.7 | 3082688.7 | Contractors all Risk |  | 67718856 | 67718856 | 0 | 2023-04-30 |  | Yes |  | Under discussion between SIC and RSG. SIC noted that SIC is required to maintain the Insurance up to acquisition of TOC (30/April/2023) under YAM04004-TRANSMIT-000469. | Parson via SAP04004-ACK-000029 requested SIC to obtain confirmation in writing from the Insurance provider for 00 months maintenance period is covered in the renewed policy. SIC is yet te response.
20 | Saudi Arabian Baytur | Contractor | 260955414.4 | 260955414.4 | Professional Indemnity | P-03-2023-6-612-019584 | 7500000 | 7500000 | 0 | 2025-03-11 | -572.6655 | Yes |  | 26 months from a date to be agreed Plus 10 Years Extended Reporting Period. (Reminder of renewal issued)
21 | Saudi Arabian Baytur | Contractor | 260955414.4 | 260955414.4 | Third Party Liability | P-03-2023-6-603-019583 | 3750000 | 3750000 | 0 | 2025-03-11 | -572.6655 | Yes |  | Reminder of renewal issued.
22 | Saudi Arabian Baytur | Contractor | 260955414.4 | 260955414.4 | Workmens Compensation | P-03-2023-6-611-019587 | 3750000 | 3750000 | 0 | 2025-03-11 | -572.6655 | Yes |  | Reminder of renewal issued.
23 | Saudi Arabian Baytur | Contractor | 260955414.4 | 260955414.4 | Plant and Equipment | P-03-2023-5-506-019580 | 3888500 | 3888500 | 0 | 2025-01-11 | -631.6655 | Yes |  | Reminder of renewal issued.
24 | Saudi Arabian Baytur | Contractor | 260955414.4 | 260955414.4 | Advance Payment Bond | MD2314900035 | 26095541.44 | 26095541.44 | 0 | 2025-09-30 | -369.6655 | Yes
25 | Saudi Arabian Baytur | Contractor | 260955414.4 | 260955414.4 | Performance Bond | MD2314900017 | 26095541.44 | 26095541.44 | 0 | 2027-02-27 | 145.3345 | Yes
26 | Saudi Arabian Baytur | Contractor | 260955414.4 | 260955414.4 | Vehicle | P/100/2911/23/000075 & P/100/2905/23/000076 | Not specified | 10000000 | 10000000 | 2025-02-07 | -604.6655 | Yes |  | Reminder of renewal issued.
27 | Langan International UK LTD | Consultant | 172368.42 | 172368.42 | Third Party Liability | WS11003838 | 1000000 | 1000000 | 0 | 2024-08-01 |  | Yes |  | FULLY PAID/ CLOSED
28 | Langan International UK LTD | Consultant | 172368.42 | 172368.42 | Workmens Compensation | WS11003838 | 1000000 | 1000000 | 0 | 2024-08-01 |  | Yes |  | FULLY PAID/ CLOSED
29 | Langan International UK LTD | Consultant | 172368.42 | 172368.42 | Professional Indemnity | MKLV/PL0005771 | 3750000 | 3750000 | 0 | 2023-08-01 |  | Yes |  | FULLY PAID/ CLOSED
Yes
30 | Medtel WN WLL | Contractor | 834298.55 | 834298.55 | Advance Payment Bond | [6 empty] | Yes |  | FULLY PAID/ CLOSED
31 | Medtel WN WLL | Contractor | 834298.55 |  | Third Party Liability |  | 3750000 | 3750000 | 0 | 2023-07-30 |  | Yes |  | FULLY PAID/ CLOSED
32 | Medtel WN WLL | Contractor | 834298.55 |  | Workmens Compensation |  | 3750000 | 3750000 | 0 | 2023-07-30 |  | Yes |  | FULLY PAID/ CLOSED
33 | Khatib & Alami | Consultant | 13059930 | 13059930 | Professional Indemnity | P-02-2021-6-612-038628/R1 | 37500000 | 37500000 | 0 | 2025-11-22 | -316.6655 | Yes |  | Reminder of renewal issued to K&A.
34 | Khatib & Alami | Consultant | 13059930 | 13059930 | Third Party Liability | P-02-2021-6-603-013533/R2 | 3750000 | 3750000 | 0 | 2026-03-15 | -203.6655 | Yes
35 | Khatib & Alami | Consultant | 13059930 | 13059930 | Workmens Compensation | P/10212/5/14203/2023/00005 | 1000000 | 1000000 | 0 | 2026-01-31 | -246.6655 | Yes
36 | Khatib & Alami | Consultant | 13059930 | 13059930 | Vehicle | 9959-2023/8/3/2 2597-2023/8/3/2 9508-2023/8/3/2 | Not Indicated | 10000000 | 10000000 | 2025-11-29 | -309.6655 | Yes |  | Reminder of renewal issued to K&A.
37 | Elevator Systems Contracting Company (ESCCO) | Contractor | SAR 2,675,473.00 | SAR 2,675,473.00 | Professional Indemnity | 44CHB2 0393/23-01 | 1000000 | 10000000 | 9000000 | 2025-11-27 | -311.6655 | Yes |  | Reminder of renewal issued to K&A.
38 | Elevator Systems Contracting Company (ESCCO) | Contractor | SAR 2,675,473.00 | SAR 2,675,473.00 | Third Party Liability | 41CHB2 0392/23-01 | 7500000 | 7500000 | 0 | 2025-11-27 | -311.6655 | Yes |  | Reminder of renewal issued to K&A.
39 | Elevator Systems Contracting Company (ESCCO) | Contractor | SAR 2,675,473.00 | SAR 2,675,473.00 | Workmens Compensation | A-SALM-1-C-08-017 | 3750000 | 3750000 | 0 | 2028-11-26 | 783.3345 | Yes
40 | Elevator Systems Contracting Company (ESCCO) | Contractor | SAR 2,675,473.00 | SAR 2,675,473.00 | Contractor's All Risk | Not Applicable | N/A | N/A | - | - |  | N/A |  | By Amaala
41 | Elevator Systems Contracting Company (ESCCO) | Contractor | SAR 2,675,473.00 | SAR 2,675,473.00 | Contractor's Plant and Machinery | P-W01-24-40120-194852 | Not specified | 0 | - | 2026-09-25 | -9.6655 | Yes |  | Renewed, under WF for approval.
42 | Elevator Systems Contracting Company (ESCCO) | Contractor | SAR 2,675,473.00 | SAR 2,675,473.00 | Motor Vehicle (if applicable) | 36125770 | Not specified | 0 | - | 2025-02-05 |  | Yes |  | Remider of renewal issued to ESCCO.
43 | Elevator Systems Contracting Company (ESCCO) | Contractor | SAR 2,675,473.00 | SAR 2,675,473.00 | Marine Cargo Insurance | P-W01-24-101-149908 | Not specified | 1000000 | - | 2025-09-25 |  | Yes
44 | Elevator Systems Contracting Company (ESCCO) | Contractor | SAR 2,675,473.00 | SAR 2,675,473.00 | Performance Guarantee | 23OGTE49102417 | 228647 | 228647 | 0 | 2026-12-21 | 77.3345 | Yes
45 | Elevator Systems Contracting Company (ESCCO) | Contractor | SAR 2,675,473.00 | SAR 2,675,473.00 | Adv. Payment Guarantee | 23OGTE49102391 | 685942 | 685942 | 0 | 2026-03-31 | -187.6655 | Yes
46 | Abdulaziz Al Raqtan & Partners Company for Trading & Industry | Contractor | 4695209 | 4695209 | Advance Payment Bond | DLG6701693 | 1643323.15 | 1643323.15 | 0 | 2025-12-21 | -287.6655 | Yes
47 | Abdulaziz Al Raqtan & Partners Company for Trading & Industry | Contractor | 4695209 | 4695209 | Performance Bond | DLG6701971 | 469520.9 | 469520.9 | 0 | 2027-01-02 | 89.3345 | Yes
48 | Abdulaziz Al Raqtan & Partners Company for Trading & Industry | Contractor | 4695209 | 4695209 | Plant and Equipment | 8/1/013/1380000080 | 0 | 191750 | 191750 | 2025-12-31 | -277.6655 | Yes |  | Reminder of renewal to be issued.
49 | Abdulaziz Al Raqtan & Partners Company for Trading & Industry | Contractor | 4695209 | 4695209 | Vehicle | MFP/2692440 | 0 | 10000000 | 10000000 | 2025-12-31 | -277.6655 | Yes |  | Reminder of renewal to be issued.
50 | Abdulaziz Al Raqtan & Partners Company for Trading & Industry | Contractor | 4695209 | 4695209 | Workmens Compensation | 7/1/013/1370000095 | 3750000 | 3750000 | 0 | 2025-12-31 | -277.6655 | Yes |  | Reminder of renewal to be issued.
51 | DEPA Saudi Arabia for Contracting and Interior Decoration Co. Ltd | AYC Construction | SAR 75,969,227.00 | SAR 75,969,227.00 | Professional Indemnity | P0124-API-TEIB-00063186 | SAR 3,750,000 | SAR 37,480,000 | 33730000 | 2026-03-31 | -187.6655 | Yes |  | Renewed.
52 | DEPA Saudi Arabia for Contracting and Interior Decoration Co. Ltd | AYC Construction | SAR 75,969,227.00 | SAR 75,969,227.00 | Third Party Liability | P0124-CGL-TEIB-00052416 | SAR 3,750,000 | SAR 20,407,400 | 16657400 | 2026-03-31 | -187.6655 | Yes |  | Renewed.
53 | DEPA Saudi Arabia for Contracting and Interior Decoration Co. Ltd | AYC Construction | SAR 75,969,227.00 | SAR 75,969,227.00 | Workmens Compensation | P0124-CEL-TCRO-00063722 Q0124-CEL-TCRO-019751/V1 | SAR 3,750,000 | SAR 3,750,000 | 0 | 2026-03-31 | -187.6655 | Yes |  | Renewed.
54 | DEPA Saudi Arabia for Contracting and Interior Decoration Co. Ltd | AYC Construction | SAR 75,969,227.00 | SAR 75,969,227.00 | Contractor's All Risk | N/a | N/a | N/a | N/a | N/a |  | N/a
55 | DEPA Saudi Arabia for Contracting and Interior Decoration Co. Ltd | AYC Construction | SAR 75,969,227.00 | SAR 75,969,227.00 | Contractor's Plant and Machinery | P0124-CPM-TCRO-00063230 P0124-CPM-TCRO-00063230/E1 | Not stated | SAR 89,494 | N/A | 2026-03-31 | -187.6655 | Yes |  | Renewed.
56 | DEPA Saudi Arabia for Contracting and Interior Decoration Co. Ltd | AYC Construction | SAR 75,969,227.00 | SAR 75,969,227.00 | Motor Vehicle (if applicable) | A-GIGR-1-C-13-002 | Not stated | SAR 10,000,000 | N/A | 2025-10-20 | -349.6655 | Yes |  | DEPA to renew. Reminder sent.
57 | DEPA Saudi Arabia for Contracting and Interior Decoration Co. Ltd | AYC Construction | SAR 75,969,227.00 | SAR 75,969,227.00 | Marine Cargo Insurance (if applicable) | P0124-MCD-TEIB-00007022 P0124-MCD-TEIB-00007022/E1 | Not stated | SAR 305,594,100 | N/A | 2026-03-31 | -187.6655 | Yes |  | Renewed.
58 | Aluminium Technology Auxiliary Industries (ALUTEC) | Contractor | 29899670.55 | 29899670.55 | Advance Payment Bond | QNBKSA/2024/00037 | 7474917.64 | 7474917.64 | 0 | 2025-10-31 |  | Yes |  | Reminder of renewal issued.
59 | Aluminium Technology Auxiliary Industries (ALUTEC) | Contractor | 29899670.55 | 29899670.55 | Performance Bond | QNBKSA/2024/00040 | 2989967.06 | 2989967.06 | 0 | 2027-01-27 | 114.3345 | Yes
60 | Aluminium Technology Auxiliary Industries (ALUTEC) | Contractor | 29899670.55 | 29899670.55 | Professional Indemnity | P124100703003258 | 3750000 | 3750000 | 0 | 2025-10-31 | -338.6655 | Yes |  | Reminder of renewal issued.
61 | Aluminium Technology Auxiliary Industries (ALUTEC) | Contractor | 29899670.55 | 29899670.55 | Workmens Compensation | P120100202000731/02 | 3750000 | 18500000 | 14750000 | 2025-12-31 | -277.6655 | Yes |  | Reminder of renewal to be issued.
62 | Aluminium Technology Auxiliary Industries (ALUTEC) | Contractor | 29899670.55 | 29899670.55 | Third Party Liability | P124100704003255 | 3750000 | 3750000 | 0 | 2027-01-10 | 97.3345 | Yes
63 | Aluminium Technology Auxiliary Industries (ALUTEC) | Contractor | 29899670.55 | 29899670.55 | Plant and Equipment | P120100503000499/02 | 100000 | 100000 | 0 | 2025-12-31 | -277.6655 | Yes |  | Reminder of renewal to be issued.
64 | Aluminium Technology Auxiliary Industries (ALUTEC) | Contractor | 29899670.55 | 29899670.55 | Marine and Hull | P124100301010016-6 | 0 | 12106026.72 | 12106026.72 | 2025-10-31 |  | Yes |  | Reminder of renewal issued.
65 | AREEN Design LTD | Consultant | 1107465.88 | 1107465.88 | Professional Indemnity | PL-PSC04009133494/14 | 10000000 | 14790000 | 4790000 | 2025-08-18 |  | Yes |  | Reminder of renewal issued.
Yes
66 | MAS ENGINEERING & CONSTRUCTION COMPANY LTD | Contractor | 4004000 | 4004000 | Comprehensive Plant and Equipment Insurance | 1/1/1/36/8/23/264 | 3750000 | 6468400 | 2718400 | 2026-03-31 | -187.6655 | Yes |  | Renewed, under WF for approval.
67 | MAS ENGINEERING & CONSTRUCTION COMPANY LTD | Contractor | 4004000 | 4004000 | Workmen’s Compensation & Employer’s Liability Insurance and/or GOSI | 1/1/1/35/1/23/686 | 3750000 | 3750000 | 0 | 2026-08-05 | -60.6655 | Yes
68 | MAS ENGINEERING & CONSTRUCTION COMPANY LTD | Contractor | 4004000 | 4004000 | Motor Vehicle Liability Insurance | 34978824 | Not specified | 0 |  | 2025-12-23 | -285.6655 | Yes |  | Reminder of renewal to be issued.
Yes
69 | MAS ENGINEERING & CONSTRUCTION COMPANY LTD | Contractor | 1078892.27 | 1078892.27 | Comprehensive Plant and Equipment Insurance | 1/1/1/36/8/23/264 | 3750000 | 6468400 | 2718400 | 2026-03-31 | -187.6655 | Yes |  | Renewed, under WF for approval.
70 | MAS ENGINEERING & CONSTRUCTION COMPANY LTD | Contractor | 1078892.27 | 1078892.27 | Workmen’s Compensation & Employer’s Liability Insurance and/or GOSI | 1/1/1/35/1/23/686 | 3750000 | 3750000 | 0 | 2026-08-05 | -60.6655 | Yes
71 | MAS ENGINEERING & CONSTRUCTION COMPANY LTD | Contractor | 1078892.27 | 1078892.27 | Motor Vehicle Liability Insurance | 34978824 | Not specified | 0 |  | 2025-12-23 | -285.6655 | Yes |  | Reminder of renewal to be issued.
72 | ALFANAR COMPANY | Contractor | 23125000 | 23125000 | Comprehensive Plant and Equipment Insurance | 1/EP/30174/0/6 | 3750000 | 3750000 | 0 | 2025-12-31 | -277.6655 | Yes |  | Reminder of renewal to be issued.
73 | ALFANAR COMPANY | Contractor | 23125000 | 23125000 | Workmen’s Compensation & Employer’s Liability Insurance | 1/WC/30611/0/0 | 3750000 | 3750000 | 0 | 2025-10-30 | -339.6655 | Yes |  | Reminder of renewal issued.
74 | ALFANAR COMPANY | Contractor | 23125000 | 23125000 | Motor Vehicle Liability Insurance | 1/VF/40268/0/0 | Not specified | 0 |  | 2025-12-31 | -277.6655 | Yes |  | Reminder of renewal to be issued.
76 | CML International Saudi LLC | Consultant | 2406500 | 2406500 | Third Party Public Liability Insurance | P-C01-24-50010-011312 |  | 7500000 | 7500000 | 2026-02-19 | -227.6655 | Yes |  | Approval of the renewed policy under process.
78 | CML International Saudi LLC | Consultant | 2406500 | 2406500 | Workmen's Compensation / Employers Liability Insurance | P-C01-24-60710-011127 |  | 3750000 | 3750000 | 2026-02-19 | -227.6655 | Yes |  | Approval of the renewed policy under process.
79 | CML International Saudi LLC | Consultant | 2406500 | 2406500 | Professional Indemnity Insurance | CDPII2015000643/0009 CDPII2024000085/0001 | 37500000 | 37500000 | 0 | 2026-08-08 | -57.6655 | Yes |  | Renewed.
80 | CML International Saudi LLC | Consultant | 2406500 | 2406500 | Professional Indemnity Insurance | P-C01-24-500-000014 P/11101/D/GA/PIAE/25/31 |  | 37500000 | 37500000 | 2026-08-08 | -57.6655 | Yes |  | Renewed.
81 | Euro Consult for Engineering Consultancy | Consultant | 182184.38 | 182184.38 | Professional Indemnity | P/CRO1/2024/PIAE/0000016 | 10000000 | 10000000 | 0 | 2027-04-13 | 190.3345 | Yes
82 | Euro Consult for Engineering Consultancy | Consultant | 182184.38 | 182184.38 | Third Party Liability | P/CR01/2024/PL/0000087 | 3750000 | 3750000 | 0 | 2027-06-08 | 246.3345 | Yes
83 | Euro Consult for Engineering Consultancy | Consultant | 182184.38 | 182184.38 | Workmens Compensation | P/CR01/2024/WE/0000047/R01 | 3750000 | 3750000 | 0 | 2026-04-13 | -174.6655 | Yes |  | Approval of the renewed policy under process.
84 | Euro Consult for Engineering Consultancy | Consultant | 182184.38 | 182184.38 | Motor Vehicle Insurance | P/1110/l/MT/MCC/25/20/R01 | Not specified | 0 |  | 2025-12-31 | -277.6655 | Yes |  | Reminder of renewal to be issued.

## IntFinalAccnt-DEWAN (hidden)
INTERIM FINAL ACCOUNT - DEWAN
[15 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23 |  |  | Jun23 | Jul23 | Aug23
Item | DESCRIPTION |  | Stage | Stage Fees | Claimed |  | Certified |  | Paid |  | Inv. No. | Remarks |  |  | 227251.2 | -103296 | 55068.4
|  |  | % | SAR | SAR | % | SAR | % | SAR | %
A | Design Fees - Contract
Stage-3 | SD - Schematic Design and Stage Gateway Approval |  |  | 1792142 | 1792142 |  | 1792142 |  | 1792142 |  |  |  | 0 | 0
| 3 | Interim Submission of deliverables at 50% Stage | 40% | 716856.8 | 716856.8 |  | 716856.8 |  | 716856.8 |  |  |  | 0 | 0
|  | Detailed Submission of deliverables at 100% Stage | 40% | 716856.8 | 716856.8 |  | 716856.8 |  | 716856.8 |  |  |  | 0 | 0
|  | Employer written approval of deliverables | 20% | 358428.4 | 358428.4 |  | 358428.4 |  | 358428.4 |  |  |  | 0 | 0
[13 empty] | 0 | 0
Stage-4 | DD - Detailed Design and Stage Gateway Approval |  |  | 2389523 | 2389523 |  | 2389523 |  | 2389523 |  |  |  | 0 | 0
| 4 | Interim Submission of deliverables at 50% Stage | 40% | 955809.2 | 955809.2 |  | 955809.2 |  | 955809.2 |  |  |  | 0 | 0
|  | Detailed Submission of deliverables at 100% Stage | 40% | 955809.2 | 955809.2 |  | 955809.2 |  | 955809.2 |  |  |  | 0 | 0
|  | Employer written approval of deliverables | 20% | 477904.6 | 477904.6 |  | 477904.6 |  | 477904.6 |  |  |  | 0 | 0
[13 empty] | 0 | 0
Stage-5a | IFT - Final Design and Proposal Documentation |  |  | 1194762 | 1194762 |  | 1194762 |  | 1194762 |  |  |  | 0 | 0
| 5a | Submission of Deliverables | 80% | 955809.6 | 955809.6 |  | 955809.6 |  | 955809.6 |  |  |  | 0 | 0
|  | Employer written approval of deliverables | 20% | 238952.4 | 238952.4 |  | 238952.4 |  | 238952.4 |  |  |  | 0 | 0
[13 empty] | 0 | 0
Stage-5b | IFC - Tender Contract and Construction Documentation |  |  | 597381 | 567511.95 |  | 567511.95 |  | 567511.95 |  |  |  | 0 | -29869.05
| 5b | Submission of Deliverables | 80% | 477904.8 | 477904.8 |  | 477904.8 |  | 477904.8 |  | D-25 | ACC approval O/S | 0 | 0
|  | Employer written approval of deliverables | 20% | 119476.2 | 89607.15 |  | 89607.15 |  | 89607.15 |  | D-37,D-38,D-39 |  | 0 | -29869.05 |  |  |  |  | -29869.05 | 29869.05 | 0 | 0
[13 empty] | 0 | 0
|  | SUB-TOTAL OF "A" |  | 5973808 | 5943938.95 | 99.5% | 5943938.95 | 99.5% | 5943938.95 | 99.5% |  |  | 0 | -29869.05 |  |  |  |  | -29869.05
[13 empty] | 0 | 0 |  |  |  |  | 0
B | VO - Additional Scope of Services | [11 empty] | 0 | 0 |  |  |  |  | 0
[13 empty] | 0 | 0 |  |  |  |  | 0
Signage & Wayfinding - AVI 001 |  |  |  | 49500 | 49500 |  | 49500 |  | 49500 |  |  | 003D01-AVV-0001 | 0 | 0 |  |  |  |  | 0
| 1 | 100% Schematic Design Submission (FOH) |  | 49500 | 49500 |  | 49500 |  | 49500 |  |  |  | 0 | 0 |  |  |  |  | 0
[13 empty] | 0 | 0 |  |  |  |  | 0
Fire & Safety - AVI 001 |  |  |  | 33000 | 33000 |  | 33000 |  | 33000 |  |  | 003D01-AVV-0001 | 0 | 0 |  |  |  |  | 0
| 1 | Upon Submission of Fire Engineering Brief |  | 8800 | 8800 |  | 8800 |  | 8800 |  |  |  | 0 | 0 |  |  |  |  | 0
| 2 | Upon Submission of Initial Fire Engineering Analysis & Modeling |  | 15400 | 15400 |  | 15400 |  | 15400 |  |  |  | 0 | 0 |  |  |  |  | 0
| 3 | Upon Submission of Final Fire Engineering Analysis Report |  | 8800 | 8800 |  | 8800 |  | 8800 |  |  |  | 0 | 0 |  |  |  |  | 0
[13 empty] | 0 | 0 |  |  |  |  | 0
Pool & Water Features MEP Engineering - AVI 001 |  |  |  | 114996.2 | 114996.2 |  | 114996.2 |  | 114996.2 |  |  | 003D01-AVV-0001 | 0 | 0 |  |  |  |  | 0
| 1 | Initial Payment upon award of Services |  | 28748.5 | 28748.5 |  | 28748.5 |  | 28748.5 |  |  |  | 0 | 0 |  |  |  |  | 0
| 2 | Upon Submission of Schematic Design - SD |  | 34499.3 | 34499.3 |  | 34499.3 |  | 34499.3 |  |  |  | 0 | 0 |  |  |  |  | 0
| 3 | Upon Submission of Detail Design - DD |  | 34499.3 | 34499.3 |  | 34499.3 |  | 34499.3 |  |  |  | 0 | 0 |  |  |  |  | 0
| 4 | Upon Submission of Tender Documents (a) Final Design - IFT |  | 11499.4 | 11499.4 |  | 11499.4 |  | 11499.4 |  |  |  | 0 | 0 |  |  |  |  | 0
| 5 | Upon Submission of Tender Documents (b) Tender, Contract & Construction Documentation |  | 5749.7 | 5749.7 |  | 5749.7 |  | 5749.7 |  |  |  | 0 | 0 |  |  |  |  | 0
[13 empty] | 0 | 0 |  |  |  |  | 0
VO 02 - Conversion of Façade/Shell Model from Rhino to Revit - AVI 002 |  |  |  | 138200 | 138200 |  | 138200 |  | 138200 |  |  | 003D01-AVV-0002 | 0 | 0 |  |  |  |  | 0
| 1 | Upon Completion of the Converted Model from Rhino to Revit |  | 138200 | 138200 |  | 138200 |  | 138200 |  |  |  | 0 | 0 |  |  |  |  | 0
[13 empty] | 0 | 0 |  |  |  |  | 0
VO 03 - Additional Service ‐ KSA Civil Defence - DVO 003 |  |  |  | 60500 | 0 |  | 0 |  | 0 |  |  |  | 0 | -60500 |  |  |  |  | -60500
| 1 | Downpayment |  | 30250 | 0 |  | 0 |  | 0 |  |  |  | 0 | -30250 |  |  |  |  | -30250 |  | 30250
| 2 | After finishing the review cycle and submittal to Civil Defense |  | 18150 | [8 empty] | 0 | -18150 |  |  |  |  | -18150 |  |  | 18150
| 3 | Upon Civil Defense Approval |  | 12100 | [8 empty] | 0 | -12100 |  |  |  |  | -12100
[13 empty] | 0 | 0 |  |  |  |  | 0
VO 04 - Revised Sustainability Guidelines - DVO 004 |  |  |  | 45604.9 | 45604.9 |  | 45604.9 |  | 45604.9 |  |  | 003D01-DVO-0004 | 0 | 0 |  |  |  |  | 0
| 1 | Lead Certification - 50% DD Submission |  | 32772.3 | 32772.3 |  | 32772.3 |  | 32772.3 |  |  |  | 0 | 0 |  |  |  |  | 0
| 2 | Energy Model - 50% DD Submission |  | 12832.6 | 12832.6 |  | 12832.6 |  | 12832.6 |  |  |  | 0 | 0 |  |  |  |  | 0
[13 empty] | 0 | 0 |  |  |  |  | 0
VO 05 - Revised BIM Guidelines - AVI 003 |  |  |  | 550000 | 550000 |  | 550000 |  | 550000 |  |  | 003D01-AVV-0002 | 0 | 0 |  |  |  |  | 0
| 1 | 50% DD Submission |  | 275000 | 275000 |  | 275000 |  | 275000 |  |  |  | 0 | 0 |  |  |  |  | 0
| 2 | 100% DD Submission |  | 275000 | 275000 |  | 275000 |  | 275000 |  |  |  | 0 | 0 |  |  |  |  | 0
[13 empty] | 0 | 0 |  |  |  |  | 0
VO 06 Front of House FF&E - DVO 002 |  |  |  | 275000 | 261250 |  | 261250 |  | 261250 |  |  | 003D01-DVO-0002 | 0 | -13750 |  |  |  |  | -13750
| 1 | SD Validation |  | 27500 | 27500 |  | 27500 |  | 27500 |  | D-21 | ACC approval O/S | 0 | 0 |  |  |  |  | 0
| 2 | 50% DD Submission |  | 82500 | 82500 |  | 82500 |  | 82500 |  | D-21 | ACC approval O/S | 0 | 0 |  |  |  |  | 0
| 3 | 100% DD Submission |  | 96250 | 96250 |  | 96250 |  | 96250 |  | D-22R | ACC approval O/S | 0 | 0 |  |  |  |  | 0 |  | 19250
| 4 | Final Design Submission - IFT |  | 55000 | 55000 |  | 55000 |  | 55000 |  | D-40, D-41 |  | 0 | 0 |  |  | 0 |  | 0 |  | 44000
| 5 | Tender Docs & IFCs |  | 13750 | [8 empty] | 0 | -13750 |  |  | 13750 |  | -13750
[13 empty] | 0 | 0 |  |  |  |  | 0
VO 07 Art Consultancy Services - DVO 001 |  |  |  | 261030 | 132000 |  | 132000 |  | 132000 |  |  | 003D01-DVO-0001 | 0 | -129030 |  |  |  |  | -129030
| 1 | Stage 1 - Preparation of Brief |  | 16500 | 16500 |  | 16500 |  | 16500 |  |  |  | 0 | 0 |  |  |  |  | 0
| 2 | Stage 2 - Art Concept Design |  | 49500 | 49500 |  | 49500 |  | 49500 |  |  |  | 0 | 0 |  |  |  |  | 0
| 3 | Stage 3 - Art Development Stage |  | 49500 | 49500 |  | 49500 |  | 49500 |  | D-23R | ACC approval O/S | 0 | 0 |  |  |  |  | 0 |  | 9900
| 4 | Stage 4 - Final Documentation/ Tender |  | 16500 | 16500 |  | 16500 |  | 16500 |  | D-31, D-34 |  | 0 | 0 |  |  |  |  | 0 |  |  | 3300
| 5 | Stage 5 - Art Work Commission/ Fabrication |  | 70950 | [8 empty] | 0 | -70950 |  |  |  |  | -70950
| 6 | Stage 6 - Logistic & Delivery |  | 16500 | [8 empty] | 0 | -16500 |  |  |  |  | -16500
| 7 | Stage 7 - Installation |  | 41580 | [8 empty] | 0 | -41580 |  |  |  |  | -41580
[13 empty] | 0 | 0 |  |  |  |  | 0
VO 08 SPA Additional Features - DVO 005 |  |  |  | 16000 | 16000 |  | 16000 |  | 16000 |  |  | 003D01-DVO-0005 | 0 | 0 |  |  |  |  | 0
|  | LCD - Dewan | [10 empty] | 0 | 0 |  |  |  |  | 0
| 1 | Stage 2 - Art Concept Design |  | 2500 | 2500 |  | 2500 |  | 2500 |  | D-35 |  | 0 | 0 |  |  |  |  | 0 | 2000
| 2 | Stage 3 - Art Development Stage |  | 2500 | 2500 |  | 2500 |  | 2500 |  | D-35 |  | 0 | 0 |  |  |  |  | 0 | 2000
|  | MEP - SPA | [10 empty] | 0 | 0 |  |  |  |  | 0
| 3 | Stage 5 - Art Work Commission/ Fabrication |  | 5500 | 5500 |  | 5500 |  | 5500 |  | D-35 |  | 0 | 0 |  |  |  |  | 0 | 4400
| 4 | Stage 7 - Installation |  | 5500 | 5500 |  | 5500 |  | 5500 |  | D-35 |  | 0 | 0 |  |  |  |  | 0 | 4400
[13 empty] | 0 | 0 |  |  |  |  | 0
VO 09 Revised Piling Design - DVO 006 |  |  |  | 351150 | 351150 |  | 351150 |  | 351150 |  |  | 003D01-DVO-0006 | 0 | 0 |  |  |  |  | 0
|  | LCD - Dewan (Structure) | [10 empty] | 0 | 0 |  |  |  |  | 0
| 1 | 50% DD Submission |  | 77472 | 77472 |  | 77472 |  | 77472 |  | D-24R, D-36 | 003D01-PC-23/ PC-26 | 0 | 0 |  |  |  |  | 0
| 2 | 100% DD Submission |  | 77472 | 77472 |  | 77472 |  | 77472 |  | D-28R, D-36 |  | 0 | 0 |  |  |  |  | 0
| 3 | Revised IFCs |  | 38736 | 38736 |  | 38736 |  | 38736 |  | D-32R, D-36 |  | 0 | 0 |  |  |  |  | 0
|  | LCD - Dewan (AOR) | [10 empty] | 0 | 0 |  |  |  |  | 0
| 4 | Submission of Revised Design |  | 25000 | 25000 |  | 25000 |  | 25000 |  | D-27 |  | 0 | 0 |  |  |  |  | 0
| 5 | Approval of Revised Design |  | 25000 | 25000 |  | 25000 |  | 25000 |  | D-33 |  | 0 | 0 |  |  |  |  | 0
|  | MEP - SPA | [10 empty] | 0 | 0 |  |  |  |  | 0
| 6 | 50% DD Submission |  | 42988 | 42988 |  | 42988 |  | 42988 |  | D-24R, D-36 | 003D01-PC-23/ PC-26 | 0 | 0 |  |  |  |  | 0
| 7 | 100% DD Submission |  | 42988 | 42988 |  | 42988 |  | 42988 |  | D-28R, D-36 |  | 0 | 0 |  |  |  |  | 0
| 8 | Revised IFCs |  | 21494 | 21494 |  | 21494 |  | 21494 |  | D-32R, D-36 |  | 0 | 0 |  |  |  |  | 0
[13 empty] | 0 | 0
AMAALA Yacht Club (AYC) - Staff Canteen Re-design - DVO 007 |  |  |  | 413184 | 371865.6 |  | 330547.2 |  | 330547.2 |  |  |  | -41318.4 | -82636.8 | 206592 | -123955.2 |  | 165273.6
| 1 | LDC - Dewan (Arch + Structure) | [10 empty] | 0 | 0
|  | 50% revised IFC Submission |  | 16500 | 16500 |  | 13200 |  | 13200 |  |  |  | -3300 | -3300 | 1650 | 1650
|  | 100% revised IFC Submission |  | 16500 | 13200 |  | 13200 |  | 13200 |  |  |  | 0 | -3300 |  |  | 3300
| 2 | LDC - Dewan (AOR) | [10 empty] | 0 | 0
|  | 50% revised IFC Submission |  | 25000 | 25000 |  | 20000 |  | 20000 |  |  |  | -5000 | -5000 | 2500 | 2500 | 5000
|  | 100% revised IFC Submission |  | 25000 | 20000 |  | 20000 |  | 20000 |  |  |  | 0 | -5000
| 3 | MEP - S+A | [10 empty] | 0 | 0
|  | 50% revised IFC Submission |  | 47500 | 47500 |  | 38000 |  | 38000 |  |  |  | -9500 | -9500 | 4750 | 4750 | 9500
|  | 100% revised IFC Submission |  | 47500 | 38000 |  | 38000 |  | 38000 |  |  |  | 0 | -9500
| 4 | FLS - DCC+MCA | [10 empty] | 0 | 0
|  | 50% revised IFC Submission |  | 36500 | 36500 |  | 29200 |  | 29200 |  |  |  | -7300 | -7300 | 3650 | 3650 | 7300
|  | 100% revised IFC Submission |  | 36500 | 29200 |  | 29200 |  | 29200 |  |  |  | 0 | -7300
| 5 | Signage - Brimaxx | [10 empty] | 0 | 0
|  | 50% revised IFC Submission |  | 10000 | 10000 |  | 8000 |  | 8000 |  |  |  | -2000 | -2000 | 1000 | 1000 | 2000
|  | 100% revised IFC Submission |  | 10000 | 8000 |  | 8000 |  | 8000 |  |  |  | 0 | -2000
| 6 | Kitchen & Waste Management - MCTS | [10 empty] | 0 | 0
|  | 50% revised IFC Submission |  | 43000 | 43000 |  | 34400 |  | 34400 |  |  |  | -8600 | -8600 | 4300 | 4300 | 8600
|  | 100% revised IFC Submission |  | 43000 | 34400 |  | 34400 |  | 34400 |  |  |  | 0 | -8600
| 7 | Sustainability - Climatize | [10 empty] | 0 | 0
|  | 50% revised IFC Submission |  | 18512 | 18512 |  | 14809.6 |  | 14809.6 |  |  |  | -3702.4 | -3702.4 | 1851.2 | 1851.2 | 3702.4
|  | 100% revised IFC Submission |  | 18512 | 14809.6 |  | 14809.6 |  | 14809.6 |  |  |  | 0 | -3702.4
| 8 | IT - Mediatech | [10 empty] | 0 | 0
|  | 50% revised IFC Submission |  | 9580 | 9580 |  | 7664 |  | 7664 |  |  |  | -1916 | -1916 | 958 | 958 | 1916
|  | 100% revised IFC Submission |  | 9580 | 7664 |  | 7664 |  | 7664 |  |  |  | 0 | -1916
AMAALA Yacht Club (AYC) - FLS Additional Documentation - DVO 008 |  |  |  | 194800 | 175320 |  | 175320 |  | 175320
| 1 | 50% Revised IFC Submission |  | 97400 | 97400 |  | 97400 |  | 97400
| 2 | 100% Revised IFC Submission |  | 97400 | 77920 |  | 77920 |  | 77920
[13 empty] | 0 | 0 |  |  |  |  | 0
|  | SUB-TOTAL OF "B" |  | 2502965.1 | 2238886.7 | 89.45% | 2197568.3 | 87.8% | 2197568.3 | 87.8% |  |  | -41318.4 | -305396.8 |  |  |  |  | -305396.8
[13 empty] | 0 | 0 |  |  |  |  | 0
[13 empty] | 0 | 0 |  |  |  |  | 0
|  | GRAND TOTAL (A + B) |  | 8476773.1 | 8182825.65 | 96.53% | 8141507.25 | 96.04% | 8141507.25 | 96.04% |  |  | -41318.4 | -335265.85 |  |  |  |  | -335265.85 | 42669.05 | 103400 | 21450
[9 empty] | -885238.85 |  | -335265.85 |  | -885238.85 | -885238.85 |  |  |  |  | -885238.85
|  |  |  | -335265.85 |  |  |  |  | -132785.8275 |  | -83816.4625 |  | -132785.8275 | 202480.0225 |  |  |  |  | 202480.0225
[9 empty] | -1018024.6775 |  |  |  | -1018024.6775 | -1018024.6775 |  |  |  |  | -1018024.6775
|  |  |  | 1461601.1 | [8 empty] | 0 | -1461601.1 |  |  |  |  | -1461601.1
[9 empty] | -335265.85 |  |  |  | -335265.85 | -335265.85 |  |  |  |  | -335265.85
|  |  |  | 1894981.1 |  |  |  |  | -846738.85 |  |  |  | -846738.85 | -2741719.95 |  |  |  |  | -2741719.95
[13 empty] | 0 | 0 |  |  |  |  | 0
|  |  |  | 493201 |  |  |  |  | -335265.85 |  |  |  | -335265.85 | -828466.85 |  |  |  |  | -828466.85
|  |  |  | 2996166.1 | 50.16% | [7 empty] | -0.50155 | -2996166.1 |  |  |  |  | -2996166.1
|  |  |  | 8969974.1 | 50.16% | [7 empty] | -0.50155 | -8969974.1 |  |  |  |  | -8969974.1
[13 empty] | 0 | 0 |  |  |  |  | 0
[13 empty] | 0 | 0 |  |  |  |  | 0
|  |  |  | 2308164.1 | [8 empty] | 0 | -2308164.1 |  |  |  |  | -2308164.1
|  |  |  | -194801 | [8 empty] | 0 | 194801 |  |  |  |  | 194801
[13 empty] | 0 | 0 |  |  |  |  | 0
[13 empty] | 0 | 0 |  |  |  |  | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
0
0

## Schedule H (hidden)
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB | [10 empty] | Closed - Works Complete
ASSET CODE: - 1TB01003.01 | [10 empty] | Packages to Procure
REPORT NO: - MONTHLY REPORT NO. 49 | [10 empty] | Open
REPORTING PERIOD: - OCTOBER 2026
CONTRACTS | [9 empty] | CONTRACTS VALUE |  |  |  |  | PAYMENTS
SR Nr. | REEF PURCHASE REQUISITION NO. (PR) | REEF PURCHASE ORDER NO. (PO) | ACONEX CONNECTED COST (ACC) CONTRACT NO. | NAME | SCOPE OF WORK | CURRENT STATUS | ORIGINAL COMPLETION DATE | EOT RECEIVED | REVISED COMPLETION DATE | ORIGINAL CONTRACT | APPROVED VARIATIONS ORDER | APPROVED CLAIMS | FINAL ACCOUNT ADJUSTMENT | REVISED CONTRACT VALUE | NET CUMULATIVE PAYMENT APPLICATION TO DATE | NET CUMULATIVE PAYMENT CERTIFICATION TO DATE | CUMULATIVE PAYMENT RELEASED TO DATE (Excl. VAT) | % CERTIFIED TO DATE | % BALANCED TO CERTIFIED
[7 empty] | DATE | DAYS | DATE | SAR | SAR | SAR | SAR | SAR | SAR | SAR | SAR | % | %
[10 empty] | a | b | c | d | e = a + b + c + d
PROFESSIONAL SERVICES
1 | 1200523 | 2200445 | 031D01 | DEWAN ARCHITECTS & ENGINEERS | Design Consultant | OPEN | 2021-01-12 |  | TBC | 5973808 | 3316718.1 | 0 | 0 | 9290526.1 | 9068064.5 | 9026746.1 | 8988246.1 | 97.16% | 2.839% | -38500
2 | 1190082 & 1200364 | 2200010 & 2200375 | 031D02&3 | HKS ARCHITECTS LTD | Design Consultant | CLOSED | Completed |  | Completed | 11447164.36 | -89775 | 0 | 0 | 11357389.36 | 11357388.46 | 11357388.46 | 11357388.46 | 100% | 7.924e-06% | 0
3 | 1210219 | 2210167 | 031D04 | APPLIED TECHN & MANAGEMENT | Technical Review | CLOSED | Completed |  | Completed | 93750 | 0 | 0 | 0 | 93750 | 93750 | 93750 | 93750 | 100% | 0%
4 | 1220489 | 2230042 | 031D05 | LANGAN | 3rd Party GEO Techincal Review | CLOSED | Completed |  | Completed | 172368.42 | -1898.52 | 0 | 0 | 170469.9 | 168421.05 | 168421.05 | 168421.05 | 98.8% | 1.202%
5 | 1230119 | 2230041 | 003F01 | ZUHAIR FAYEZ & PARTNERS | Building Permit Assistance | CLOSED | Completed |  | Completed | 106231.5 | 0 | 0 | 0 | 106231.5 | 106231.5 | 106231.5 | 106231.5 | 100% | 0%
6 | 1230270 | 2230180 | 003F04 | JENSEN HUGHES | Fire Life Saftey Design Review | OPEN | Unknown |  | Unknown | 127291.9 | -56700 | 0 | 0 | 70591.9 | 0 | 0 | 0 | 0% | 100%
7 | Direct Payment by Finance | Direct Payment by Finance | 003D06 | MINISTRY OF MUNICIPALITY AND RURAL AFFAIRS (MUNICIPALITY OF TABUK) | Building Permit Fee | CLOSED | Completed |  | Completed | 45677.6 | -56700 | 0 | 0 | -11022.4 | 45677.6 | 45677.6 | 45677.6 | -414.4% | 514.4%
MANAGEMENT SUPERVISION SERVICES
8 | 1230078 | 2230031 | 003F02 | KHATIB & ALAMI | Technical Supervision | OPEN | 2025-02-28 |  | 2025-02-28 | 13059930 | 1071977 | 0 | 0 | 14131907 | 14078459 | 14082700 | 13487622 | 99.65% | 0.3482%
CONSTRUCTION SERVICES
9 | 1220032 | 2220038 | 003C20 | Green Business Certification | Sustainability 3rd Party Tech Review | OPEN |  |  |  | 23094.49 | -509.48 | 0 | 0 | 22585.01 | 18000.1125 | 18000.1125 | 18000.1125 | 79.7% | 20.3%
10 | 1210230 | 2210224 | 003C13 | SIC | Soil Improvements & Ground Works | OPEN | 2021-10-05 | 30 | 2022-01-26 | 3082689 | 0 | 0 | 0 | 3082689 | 1748735.938 | 1748735.938 | 1748735.938 | 56.73% | 43.27% |  | 0
11 | 1210829 | 2220032 | 003C14 | NSCC | Piling | CLOSED | Completed | 96 | Completed | 18698534 | -2240152.49 | Included in VO | 0 | 16458381.51 | 23335059.096 | 16458381.54 | 16458381.54 | 100% | -1.823e-07% |  | 0
12 | 1230066 | 2230023 | 003C03 | SAB | Site Enablement, Civil Works, Structural Concrete, Structural Steel, Back of House Finishes, Building Envelope, Mechanical Electrical & Plumbing, ICT / ELV | OPEN | 2025-02-28 |  | 2025-02-28 | 260955414.4 | -91015507.7 | 0 | 0 | 169939906.7 | 274254987.5851 | 170592084.657 | 170592084.657 | 100.4% | -0.3838% | 274254987.5851 | 170592084.657 | 170592084.657
|  |  |  | Direct Payment to the SAB's Subcontractors and Suppliers | Direct Payment to the SAB's Subcontractors and Suppliers | OPEN |  |  |  | 42594259.73 | 0 | 0 | 0 | 42594259.73 | 42594259.73 | 42594259.73 | 42594259.73 | 100% | 0%
15 | 1230173 | 2230075 | 003C21 | MEDTEL | Façade Mock up | CLOSED | Completed |  | Completed | 834298.55 | -15000 | 0 | 0 | 819298.55 | 819298.55 | 819298.55 | 819298.55 | 100% | 0% |  | -652177.957
16 | 1230328 | 2230178 | 003F03 | ESCCO | Vertical Transport | OPEN | 2024-12-22 |  | 2024-12-22 | 2675473 | 98073 | 0 | 0 | 2773546 | 1990337.824 | 1982337.664 | 1881942.44 | 71.47% | 28.53%
17 | 1230366 | 2230205 | 003C08 | AL RAQTAN | Kitchen & Laundry Works | OPEN | 2024-12-20 |  | 2024-12-20 | 4695209 | 0 | 0 | 0 | 4695209 | 6151689.085 | 3837547.3 | 3756805.06 | 81.73% | 18.27%
18 | 1230819 | 2230416 | 003C09 | DEPA | Interior Fitout | OPEN | 2024-12-13 |  | 2024-12-13 | 75969227 | 2312919.14 | 0 | 0 | 78282146.14 | 91261011.175 | 65072967.4665 | 61755849.6745 | 83.13% | 16.87%
19 | 1240229 | 2240110 | 003C27 | ALUTEC | Façade & Glazing Works | OPEN | 2024-12-30 |  | 2024-12-30 | 29899670.55 | 574831.03 | 0 | 0 | 30474501.58 | 48279532.9045 | 29131817.318 | 25792563.69 | 95.59% | 4.406%
20 | 1240515 | 2240202 | 003F06 | AREEN DESIGN | FF&E and OSE Procurement Agent | OPEN | 2024-12-30 |  | TBC | 1107465.88 | 37584647.56 | 0 | 0 | 38692113.44 | 25319298.82 | 25367673.69 | 25084575.44 | 65.56% | 34.44%
21 | 1241021 | 2240427 | 003C31 | MAS | Wet Works | OPEN | 2025-02-28 |  | 2025-02-28 | 4004000 | 18356118 | 0 | 0 | 22360118 | 23384183.21 | 22345856.21 | 19750220 | 99.94% | 0.06378%
22 | 1241083 | 2240461 | 003C32 | MAS | Amphitheatre Works | OPEN | 2025-02-28 |  | 2025-02-28 | 1078892.27 | 205658.08 | 0 | 0 | 1284550.35 | 1395241.184 | 1211278.835 | 1211278.835 | 94.3% | 5.704%
23 | 1241229 | 2250012 | 003C34 | Al Fanar Company | Provision of Manpower Services | OPEN | 2025-02-23 |  | 2025-07-31 | 23125000 | 71435593.23 | 0 | 0 | 94560593.23 | 131213586.2341 | 92352575.09 | 82146350.2 | 97.66% | 2.335%
24 | 1240893 | 2240377 | 003F08 | CML | Independent Commissioning Agent | OPEN |  |  |  | 2406500 | 0 | 0 | 0 | 2406500 | 3873841.76 | 3873847.87 | 3178291.08 | 161% | -60.97%
25 | 1240857 | 2240357 | 003F07 | EURO CONSULT | Statutory Compliance | OPEN |  |  |  | 182184.38 | 0 | 0 | 0 | 182184.38 | 128677.64 | 128677.64 | 84414 | 70.63% | 29.37%
26 | 1250131 | 2250063 | 003F09 | EURO CONSULT (Accommodation & Transporation) | Statutory Compliance | OPEN |  |  |  | 54000 | 0 | 0 | 0 | 54000 | 54000 | 54000 | 45000 | 100% | 0%
27 | 1250408 | 2250145 | 003C37 | Hassan Allam | Scaffolding Services | OPEN |  |  |  | 3096124.9 | 0 | 0 | 0 | 3096124.9 | 3096124.9 | 3096124.9 | 1774248.92 | 100% | -1.504e-14%
28 | 1250075 | 2250084 | 003C33 | Armetal | Stainless Steel Reflective Ceiling | OPEN |  |  |  | 7129950 | 0 | 0 | 0 | 7129950 | 6633442.8205 | 6633442.8205 | 6367045.35 | 93.04% | 6.964%
TOTAL (SAR) | [9 empty] | 512638208.93 | 41480291.95 | 0 | 0 | 554118500.88 | 720469300.6787 | 522199822.0415 | 499306681.927 | 94.24% | 5.76%
[15 empty] | Check: | -213967.975 | -22893140.1145
[16 empty] | 522199822.0415 | Executive Summary
[15 empty] | Check: | 0
522413790.0165
[15 empty] | Check: | -213967.975
Formulas:
REVISED COMPLETION DATE = +[EOT RECEIVED]+[ORIGINAL COMPLETION DATE]

## Schedule H DAE
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
PS.003D01 - Dewan Architects & Engineers 2200445
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | DAE Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (14days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | AMAALA ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (45days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 14.6.1 | + / - | SAR | SAR | 0% | 0% | SAR |  | Date | Date | Cl.14.7(b)(i) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 14 | d = c- d | e | f | g = f * 0% | h = f * 0% | i = f + g + h |  |  | j | k = a + 45 | l = k - j | m = i | n = ( f + h ) * 15% | O = M + N
1 | IPA - 01 |  |  |  | 470038.26 | 470038.26 | 0 | 0 | 470038.26 | 1 |  |  |  |  | 470038.26 | 470038.26 | 0 | 0 | 470038.26 |  |  | 2021-02-18 |  |  | 470038.26 | 70505.739 | 540543.999 | 540543.999
2 | IPA - 02 |  |  |  | 716856.8 | 246818.54 | 0 | 0 | 246818.54 | 2 | AML-WTRAN-000055 | 2021-04-20 |  |  | 716856.8 | 246818.54 | 0 | 0 | 246818.54 |  |  | 2021-05-23 |  |  | 246818.54 | 37022.781 | 283841.321 | 824385.32
3 | IPA - 03 |  |  |  | 1433713.6 | 716856.8 | 0 | 0 | 716856.8 | 3 | AML-WTRAN-000080 | 2021-06-08 |  |  | 1433713.6 | 716856.8 | 0 | 0 | 716856.8 |  |  | 2021-06-16 |  |  | 716856.8 | 107528.52 | 824385.32 | 1648770.64
4 | IPA - 04 |  |  |  | 1792142 | 358428.4 | 0 | 0 | 358428.4 | 4 | AML-WTRAN-000022 | 2021-09-07 |  |  | 1792142 | 358428.4 | 0 | 0 | 358428.4 |  |  | 2021-11-11 |  |  | 358428.4 | 53764.26 | 412192.66 | 2060963.3
5 | IPA - 05 |  |  |  | 1820890.5 | 28748.5 | 0 | 0 | 28748.5 | 5 | AMA-WTRAN-000297 | 2022-01-02 |  |  | 1820890.5 | 28748.5 | 0 | 0 | 28748.5 |  |  | 2022-01-16 |  |  | 28748.5 | 4312.275 | 33060.775 | 2094024.075
6 | IPA - 06 |  |  |  | 1870390.5 | 49500 | 0 | 0 | 49500 | 6 | AMA-WTRAN-000316 | 2022-01-09 |  |  | 1870390.5 | 49500 | 0 | 0 | 49500 |  |  | 2022-01-16 |  |  | 49500 | 7425 | 56925 | 2150949.075
7 | IPA - 07 |  |  |  | 1894590.5 | 24200 | 0 | 0 | 24200 | 7 | AMA-WTRAN-000317 | 2022-01-09 |  |  | 1894590.5 | 24200 | 0 | 0 | 24200 |  |  | 2022-01-16 |  |  | 24200 | 3630 | 27830 | 2178779.075
8 | IPA - 08 |  |  |  | 2032790.5 | 138200 | 0 | 0 | 138200 | 8 | AMA-WTRAN-000318 | 2022-01-09 |  |  | 2032790.5 | 138200 | 0 | 0 | 138200 |  |  | 2022-01-16 |  |  | 138200 | 20730 | 158930 | 2337709.075
9 | IPA - 09 |  | DAE-TRANSMIT-000060 | 2021-12-10 | 2988599.7 | 955809.2 | 0 | 0 | 955809.2 | 9 | AMA-WTRAN-000405 | 2022-02-10 | 2021-12-24 | -48 | 2988599.7 | 955809.2 | 0 | 0 | 955809.2 |  |  | 2022-02-16 | 2022-01-24 |  | 955809.2 | 143371.38 | 1099180.58 | 3436889.655
10 | IPA - 10 |  | DAE-LTR-000002 | 2021-11-04 | 3263599.7 | 275000 | 0 | 0 | 275000 | 10 | AMA-WTRAN-000435 | 2022-02-18 | 2021-11-18 | -92 | 3263599.7 | 275000 | 0 | 0 | 275000 |  |  | 2022-03-01 | 2021-12-19 |  | 275000 | 41250 | 316250 | 3753139.655
11 | IPA - 11 |  | DAE-LTR-000002 | 2021-11-04 | 3538599.7 | 275000 | 0 | 0 | 275000 | 11 | AMA-WTRAN-000658 | 2022-04-14 | 2021-11-18 | -147 | 3538599.7 | 275000 | 0 | 0 | 275000 |  |  | 2022-05-11 | 2021-12-19 |  | 275000 | 41250 | 316250 | 4069389.655
12 | IPA - 12 |  | DAE-LTR-000002 | 2021-11-04 | 3590348.1 | 51748.4 | 0 | 0 | 51748.4 | 12 | AMA-WTRAN-000661 | 2022-04-14 | 2021-11-18 | -147 | 3590348.1 | 51748.4 | 0 | 0 | 51748.4 |  |  | 2022-05-11 | 2021-12-19 |  | 51748.4 | 7762.26 | 59510.66 | 4128900.315
13 | IPA - 13 |  |  |  | 4546157.3 | 955809.2 | 0 | 0 | 955809.2 | 13 | AMA-WTRAN-000724 | 2022-05-24 |  |  | 4546157.3 | 955809.2 | 0 | 0 | 955809.2 |  |  | 2022-06-05 |  |  | 955809.2 | 143371.38 | 1099180.58 | 5228080.895
14 | IPA - 14 |  |  |  | 5024061.9 | 477904.6 | 0 | 0 | 477904.6 | 14 | AMA-WTRAN-000673 | 2022-04-19 |  |  | 5024061.9 | 477904.6 | 0 | 0 | 477904.6 |  |  | 2022-06-05 |  |  | 477904.6 | 71685.69 | 549590.29 | 5777671.185
15 | IPA - 15 |  |  |  | 5058561.2 | 34499.3 | 0 | 0 | 34499.3 | 15 | AMA-WTRAN-001111 | 2022-09-11 |  |  | 5058561.2 | 34499.3 | 0 | 0 | 34499.3 |  |  | 2022-10-05 |  |  | 34499.3 | 5174.895 | 39674.195 | 5817345.38
16 | IPA - 16 |  | DAE-TRANSMIT-000160 | 2022-05-25 | 6014370.8 | 955809.6 | 0 | 0 | 955809.6 | 16 | AMA-WTRAN-001120 | 2022-09-17 | 2022-06-08 | -101 | 6014370.8 | 955809.6 | 0 | 0 | 955809.6 |  |  | 2022-10-09 | 2022-07-09 |  | 955809.6 | 143371.44 | 1099181.04 | 6916526.42
17 | IPA - 17 |  | DAE-TRANSMIT-000160 | 2022-05-25 | 6023170.8 | 8800 | 0 | 0 | 8800 | 17 | AMA-WTRAN-001111 | 2022-09-11 | 2022-06-08 | -95 | 6023170.8 | 8800 | 0 | 0 | 8800 |  |  | 2022-10-05 | 2022-07-09 |  | 8800 | 1320 | 10120 | 6926646.42
18 | IPA - 18 |  | DAE-TRANSMIT-000160 | 2022-05-25 | 6068775.7 | 45604.9 | 0 | 0 | 45604.9 | 18 | AMA-WTRAN-001165 | 2022-10-12 | 2022-06-08 | -126 | 6068775.7 | 45604.9 | 0 | 0 | 45604.9 |  |  | 2022-10-18 | 2022-07-09 |  | 45604.9 | 6840.735 | 52445.635 | 6979092.055
19 | IPA - 19 |  | DAE-WTRAN-000206 | 2022-10-11 | 6085275.7 | 16500 | 0 | 0 | 16500 | 19 | AMA01003-WTRAN-001210 | 2022-11-10 | 2022-10-25 | -16 | 6085275.7 | 16500 | 0 | 0 | 16500 |  |  | 2022-12-12 | 2022-11-25 | -17 | 16500 | 2475 | 18975 | 6998067.055
20 | IPA - 20 |  | DAE-WTRAN-000199 | 2022-09-13 | 6324228.1 | 238952.4 | 0 | 0 | 238952.4 | 20 | AMA01003-WTRAN-001284 | 2022-12-18 | 2022-09-27 | -82 | 6324228.1 | 238952.4 | 0 | 0 | 238952.4 |  |  | 2022-12-26 | 2022-10-28 | -59 | 238952.4 | 35842.86 | 274795.26 | 7272862.315
21 | IPA - 21 |  | DAE-WTRAN-000211 | 2022-10-28 | 6373728.1 | 49500 | 0 | 0 | 49500 | 21 | AMA01003-WTRAN-001285 | 2022-12-18 | 2022-11-11 | -37 | 6373728.1 | 49500 | 0 | 0 | 49500 |  |  | 2022-12-26 | 2022-12-12 | -14 | 49500 | 7425 | 56925 | 7329787.315
22 | IPA - 22 (INV-21) |  | DAE01003-WTRAN-000215 | 2022-11-29 | 6483728.1 | 110000 | 0 | 0 | 110000 | 22 | AMA01003-PC-000003 | 2023-02-19 | 2022-12-13 | -68 | 6483728.1 | 110000 | 0 | 0 | 110000 |  |  | 2023-03-02 | 2023-01-13 | -48 | 110000 | 16500 | 126500 | 7456287.315
23 | IPA - 23 (INV-25) |  | AMA01003-PAYAP-000021 | 2022-12-29 | 6961632.9 | 477904.8 | 0 | 0 | 477904.8 | 23 | AMA01003-PC-000006 | 2023-02-19 | 2023-01-12 | -38 | 6961632.9 | 477904.8 | 0 | 0 | 477904.8 |  |  | 2023-03-02 | 2023-02-12 | -18 | 477904.8 | 71685.72 | 549590.52 | 8005877.835
24 | IPA - 24 (INV-22 R) |  | AMA01003-PAYAP-000022 | 2022-12-31 | 6560728.1 | 77000 | 0 | 0 | 77000 | 24 | AMA01003-PC-000004 | 2023-02-19 | 2023-01-14 | -36 | 6560728.1 | 77000 | 0 | 0 | 77000 |  |  | 2023-03-02 | 2023-02-14 | -16 | 77000 | 11550 | 88550 | 8094427.835
25 | IPA - 25 (INV-23 R) |  | AMA01003-PAYAP-000023 | 2023-01-04 | 6600328.1 | 39600 | 0 | 0 | 39600 | 25 | AMA01003-PC-000005 | 2023-02-19 | 2023-01-18 | -32 | 6600328.1 | 39600 | 0 | 0 | 39600 |  |  | 2023-03-02 | 2023-02-18 | -12 | 39600 | 5940 | 45540 | 8139967.835
26 | IPA - 26 (INV-31) |  | AMA01003-PAYAP-000024 | 2023-01-14 | 6613528.1 | 13200 | 0 | 0 | 13200 | 26 | AMA01003-PC-000002 | 2023-02-19 | 2023-01-28 | -22 | 6613528.1 | 13200 | 0 | 0 | 13200 |  |  | 2023-03-02 | 2023-02-28 | -2 | 13200 | 1980 | 15180 | 8155147.835
27 | IPA - 27 (INV-D-24R) |  | AMA01003-PAYAP-000043 | 2023-03-28 | 6709896.1 | 96368 | 0 | 0 | 96368 | 27 | AMA01003-PC-000007 | 2023-04-06 | 2023-04-11 | 5 | 6709896.1 | 96368 | 0 | 0 | 96368 |  |  | 2023-04-19 | 2023-05-12 | 23 | 96368 | 14455.2 | 110823.2 | 8265971.035
28 | IPA - 28 (INV-D-27) |  | AMA01003-PAYAP-000046 | 2023-03-29 | 6734896.1 | 25000 | 0 | 0 | 25000 | 28 | AMA01003-PC-000009 | 2023-04-06 | 2023-04-12 | 6 | 6734896.1 | 25000 | 0 | 0 | 25000 |  |  | 2023-05-19 | 2023-05-13 | -6 | 25000 | 3750 | 28750 | 8294721.035
29 | IPA - 29 (INV-D-33) |  | AMA01003-PAYAP-000047 | 2023-03-29 | 6734896.1 | 25000 | 0 | 0 | 25000 | 29 | AMA01003-PC-000011 | 2023-04-06 | 2023-04-12 | 6 | 6734896.1 | 25000 | 0 | 0 | 25000 |  |  | 2023-04-19 | 2023-05-13 | 24 | 25000 | 3750 | 28750 | 8323471.035
30 | IPA - 30 (INV-D-32R) |  | AMA01003-PAYAP-000051 | 2023-03-29 | 6783080.1 | 48184 | 0 | 0 | 48184 | 30 | AMA01003-PC-000010 | 2023-04-06 | 2023-04-12 | 6 | 6783080.1 | 48184 | 0 | 0 | 48184 |  |  | 2023-04-19 | 2023-05-13 | 24 | 48184 | 7227.6 | 55411.6 | 8378882.635
31 | IPA - 31 (INV-D-26R/41) |  | AMA01003-PAYAP-000050 | 2023-03-29 | 6795880.1 | 12800 | 0 | 0 | 12800 | 31 | AMA01003-PC-000008 | 2023-04-06 | 2023-04-12 | 6 | 6795880.1 | 12800 | 0 | 0 | 12800 |  |  | 2023-08-21 | 2023-05-13 | -100 | 12800 | 1920 | 14720 | 8393602.635
32 | IPA - 32 (INV-D-28R) |  | AMA01003-PAYAP-000068 | 2023-05-11 | 6892248.1 | 96368 | 0 | 0 | 96368 | 32 | AMA01003-PC-000013 | 2023-05-23 | 2023-05-25 | 2 | 6892248.1 | 96368 | 0 | 0 | 96368 |  |  | 2023-06-08 | 2023-06-25 | 17 | 96368 | 14455.2 | 110823.2 | 8504425.835
33 | IPA - 33 (INV-D-35) |  | AMA01003-PAYAP-000073 | 2023-05-24 | 6895448.1 | 3200 | 0 | 0 | 3200 | 33 | AMA01003-PC-000015 | 2023-06-08 | 2023-06-07 | -1 | 6895448.1 | 3200 | 0 | 0 | 3200 |  |  | 2023-06-13 | 2023-07-08 | 25 | 3200 | 480 | 3680 | 8508105.835
34 | IPA - 34 (INV-D-36) |  | AMA01003-PAYAP-000074 | 2023-05-24 | 6955678.1 | 60230 | 0 | 0 | 60230 | 34 | AMA01003-PC-000016 | 2023-06-08 | 2023-06-07 | -1 | 6955678.1 | 60230 | 0 | 0 | 60230 |  |  | 2023-06-13 | 2023-07-08 | 25 | 60230 | 9034.5 | 69264.5 | 8577370.335
35 | IPA - 35 (INV-D-37) |  | AMA01003-PAYAP-000075 | 2023-05-24 | 6985547.15 | 29869.05 | 0 | 0 | 29869.05 | 35 | AMA01003-PC-000017 | 2023-06-08 | 2023-06-07 | -1 | 6985547.15 | 29869.05 | 0 | 0 | 29869.05 |  |  | 2023-06-13 | 2023-07-08 | 25 | 29869.05 | 4480.3575 | 34349.4075 | 8611719.7425
36 | IPA - 36 (INV-D-38) |  | AMA01003-PAYAP-000082 | 2023-05-31 | 7015416.2 | 29869.05 | 0 | 0 | 29869.05 | 36 | AMA01003-PC-000018 | 2023-06-08 | 2023-06-14 | 6 | 7015416.2 | 29869.05 | 0 | 0 | 29869.05 |  |  | 2023-06-13 | 2023-07-15 | 32 | 29869.05 | 4480.3575 | 34349.4075 | 8646069.15
37 | IPA - 37 (INV-D-39) |  | AMA01003-PAYAP-000083 | 2023-05-31 | 7045285.25 | 29869.05 | 0 | 0 | 29869.05 | 37 | AMA01003-PC-000019 | 2023-06-08 | 2023-06-14 | 6 | 7045285.25 | 29869.05 | 0 | 0 | 29869.05 |  |  | 2023-06-13 | 2023-07-15 | 32 | 29869.05 | 4480.3575 | 34349.4075 | 8680418.5575
38 | IPA - 38 (INV-D-29) |  | AMA01003-PAYAP-000123 | 2023-07-31 | 7064535.25 | 19250 | 0 | 0 | 19250 | 38 | AMA01003-PC-000023 | 2023-08-19 | 2023-08-14 | -5 | 7064535.25 | 19250 | 0 | 0 | 19250 |  |  | 2023-08-21 | 2023-09-14 | 24 | 19250 | 2887.5 | 22137.5 | 8702556.0575
39 | IPA - 39 (INV-D-30) |  | AMA01003-PAYAP-000124 | 2023-07-31 | 7074435.25 | 9900 | 0 | 0 | 9900 | 39 | AMA01003-PC-000024 | 2023-08-19 | 2023-08-14 | -5 | 7074435.25 | 9900 | 0 | 0 | 9900 |  |  | 2023-08-21 | 2023-09-14 | 24 | 9900 | 1485 | 11385 | 8713941.0575
40 | IPA - 40 (INV-D-34) |  | AMA01003-PAYAP-000125 | 2023-07-31 | 7077735.25 | 3300 | 0 | 0 | 3300 | 40 | AMA01003-PC-000025 | 2023-08-19 | 2023-08-14 | -5 | 7077735.25 | 3300 | 0 | 0 | 3300 |  |  | 2023-08-30 | 2023-09-14 | 15 | 3300 | 495 | 3795 | 8717736.0575
41 | IPA - 41 (INV-D-40) |  | AMA01003-PAYAP-000126 | 2023-07-31 | 7121735.25 | 44000 | 0 | 0 | 44000 | 41 | AMA01003-PC-000027 | 2023-09-05 | 2023-08-14 | -22 | 7121735.25 | 44000 | 0 | 0 | 44000 |  |  | 2023-09-18 | 2023-09-14 | -4 | 44000 | 6600 | 50600 | 8768336.0575
42 | IPA - 42 (INV-D-41) |  | AMA01003-PAYAP-000127 | 2023-07-31 | 7132735.25 | 11000 | 0 | 0 | 11000 | 42 | AMA01003-PC-000028 | 2023-09-05 | 2023-08-14 | -22 | 7132735.25 | 11000 | 0 | 0 | 11000 |  |  | 2023-09-18 | 2023-09-14 | -4 | 11000 | 1650 | 12650 | 8780986.0575
43 | IPA - 43 (INV-D-42) |  | AMA01003-PAYAP-000172 | 2023-10-03 | 7298008.85 | 165273.6 | 0 | 0 | 165273.6 | 43 | AMA01003-PC-000031 | 2023-10-11 | 2023-10-17 | 6 | 7298008.85 | 165273.6 | 0 | 0 | 165273.6 |  |  | 2023-11-06 | 2023-11-17 | 11 | 165273.6 | 24791.04 | 190064.64 | 8971050.6975
44 | IPA - 44 (INV-D-43) |  | AMA01003-PAYAP-000195 | 2023-11-02 | 7339327.25 | 41318.4 | 0 | 0 | 41318.4 | 44 | Revised and Resubmit - Payment Application.
45 | IPA - 45 (INV-D-44) |  | AMA01003-PAYAP-000226 | 2023-12-22 | 7417247.25 | 77920 | 0 | 0 | 77920 | 45 | AMA01003-PC-000042 | 2024-01-09 | 2024-01-05 | -4 | 7463282.45 | 77920 | 0 | 0 | 77920 |  |  | 2024-01-23 | 2024-02-05 | 13 | 77920 | 11688 | 89608 | 9060658.6975
46 | IPA - 46 (INV-D-45) |  | AMA01003-PAYAP-000238 | 2024-01-10 | 7582520.05 | 165272.8 | 0 | 0 | 165272.8 | 46 | AMA01003-PC-000048 | 2024-06-26 | 2024-01-24 | -154 | 7628555.25 | 165272.8 | 0 | 0 | 165272.8 |  |  | 2024-07-18 | 2024-02-24 | -145 | 165272.8 | 24790.92 | 190063.72 | 9250722.4175
47 | IPA - 47 (INV-D-46) |  | AMA01003-PAYAP-000240 | 2024-01-12 | 7602000.05 | 19480 | 0 | 0 | 19480 | 47 | AMA01003-PC-000049 | 2024-06-26 | 2024-01-26 | -152 | 7648035.25 | 19480 | 0 | 0 | 19480 |  |  | 2024-07-18 | 2024-02-26 | -143 | 19480 | 2922 | 22402 | 9273124.4175
48 | IPA - 48 (INV-D-47) |  | AMA01003-PAYAP-000344 | 2024-08-09 | 7679920.05 | 77920 | 0 | 0 | 77920 | 48 | AMA01003-PC-000057 | 2024-06-26 | 2024-08-23 | 58 | 7725955.25 | 77920 | 0 | 0 | 77920 |  |  | 2024-08-29 | 2024-09-23 | 25 | 77920 | 11688 | 89608 | 9362732.4175
49 | IPA - 48 (INV-D-53) |  | AMA01003-PAYAP-000399 | 2024-10-13 | 7709789.1 | 29869.05 | 0 | 0 | 29869.05 | 49 | AMA01003-PC-000077 | 2024-11-19 | 2024-10-27 | -23 | 7755824.3 | 29869.05 | 0 | 0 | 29869.05 |  |  | 2024-12-11 | 2024-11-27 | -14 | 29869.05 | 4480.3575 | 34349.4075 | 9397081.825
50 | IPA - 48 (INV-D-54) |  | AMA01003-PAYAP-000512 | 2025-01-14 | 7811905.7 | 102116.6 | 0 | 0 | 102116.6 | 50 | AMA01003-PC-000101 | 2025-02-07 | 2025-01-28 | -10 | 7857940.9 | 102116.6 | 0 | 0 | 102116.6 |  |  | 2025-04-21 | 2025-02-28 | -52 | 102116.6 | 15317.49 | 117434.09 | 9514515.915
51 | IPA - 48 (INV-D-55) |  | AMA01003-PAYAP-000568 | 2025-02-13 | 8278440.7 | 466535 | 0 | 0 | 466535 | 51 | AMA01003-PC-000110 | 2025-03-10 | 2025-02-27 | -11 | 8324475.9 | 466535 | 0 | 0 | 466535 |  |  | 2025-04-21 | 2025-03-30 | -22 | 466535 | 69980.25 | 536515.25 | 10051031.165
52 | IPA - 48 (INV-D-47R) |  | AMA01003-PAYAP-000492 | 2024-12-30 | 8526659.7 | 248219 | 0 | 0 | 248219 | 52 | AMA01003-PC-000092 | 2025-01-09 | 2025-01-13 | 4 | 8572694.9 | 248219 | 0 | 0 | 248219 |  |  | 2025-04-21 | 2025-02-13 | -67 | 248219 | 37232.85 | 285451.85 | 10336483.015
53 | IPA - 49 (INV-D-56R) |  | AMA01003-PAYAP-001617 | 2025-10-02 | 8565159.7 | 38500 | 0 | 0 | 38500 | 53 | AMA01003-PC-000391 | 2025-11-27 | 2025-10-16 | -42 | 8611194.9 | 38500 | 0 | 0 | 38500
TOTAL (SAR) | [5 empty] | 9068064.5 | 0 | 0 | 9068064.5 | TOTAL (SAR) | [5 empty] | 9026746.1 | 0 | 0 | 9026746.1 | TOTAL (SAR) |  |  |  |  | 8988246.1 | 1348236.915 | 10336483.015 | 10336483.015
[9 empty] | 7395152.9 | [15 empty] | 8975446.1 |  |  | 0
[9 empty] | -1672911.6 | [15 empty] | 8822972.5 |  |  | 8988246.1
0.036364
|  |  |  | 2021-01-01 | [18 empty] | 2020-09-20 |  | -79818.4
|  |  |  | 2020-11-17 |  |  |  |  | 145792.8 | [13 empty] | 2020-08-06
2020-06-04
Formulas:
Issue date of IPC per Contract (14days) = [Date Aconex Letter]+14
Payment Date as per Contract (45days) = [Date Aconex Letter]+45
Payment Date as per Contract (45days) = [Payment Date as per Contract (45days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H HKS 1
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
PS.003D02 - HKS Architects Ltd - Design Competition Fees 2200010
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (14days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | AMAALA ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (45days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 14.6.1 | + / - | SAR | SAR | 0% | 0% | SAR |  | Date | Date | Cl.14.7(b)(i) | + / - |  | -5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 14 | d = c- d | e | f | g = f * 0% | h = f * 0% | i = f + g + h |  |  | j | k = a + 30 | l = k - j | m = i | n = ( f + h ) * -5% | O = M + N
1 | IPA - 1 |  |  |  | 555960 | 555960 | 0 | 0 | 555960 | 1 |  |  | 1900-01-13 | 14 | 555960 | 555960 | 0 | 0 | 555960 | [5 empty] | 555960 | -27798 | 528162 | 528162
TOTAL (SAR) | [5 empty] | 555960 | 0 | 0 | 555960 | TOTAL (SAR) | [5 empty] | 555960 | 0 | 0 | 555960 | TOTAL (SAR) |  |  |  |  | 555960 | -27798 | 528162 | 528162
11357388.46
0.036364
|  |  |  | 2021-01-01 | [18 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [18 empty] | 2020-08-06
2020-06-04
Formulas:
Issue date of IPC per Contract (14days) = [Date Aconex Letter]+14
Date Aconex Letter = [Date Aconex Letter, row above]-45
Payment Date as per Contract (45days) = [Payment Date as per Contract (45days), row above]-45

## Schedule H HKS 2
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
PS.003D03 - HKS Architects Ltd - Design Architect Fees 2200375
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (14days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | AMAALA ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 14.6.1 | + / - | SAR | SAR | 0% | 0% | SAR |  | Date | Date | Cl.14.7(b)(i) | + / - |  | -5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 14 | d = c- d | e | f | g = f * 0% | h = f * 0% | i = f + g + h |  |  | j | k = a + 30 | l = k - j | m = i | n = ( f + h ) * -5% | O = M + N
1 | IPA - 1 |  |  |  | 1089120.38 | 1089120.38 | 0 | 0 | 1089120.38 | 1 |  |  | 1900-01-13 | 14 | 1089120.38 | 1089120.38 | 0 | 0 | 1089120.38 | [5 empty] | 1089120.38 | -54456.019 | 1034664.361 | 1034664.361
2 | IPA - 2 |  |  |  | 2326915.38 | 1237795 | 0 | 0 | 1237795 | 2 |  |  | 1900-01-13 | 14 | 2326915.38 | 1237795 | 0 | 0 | 1237795 | [5 empty] | 1237795 | -61889.75 | 1175905.25 | 2210569.611
3 | IPA - 3 |  |  |  | 3564710.38 | 1237795 | 0 | 0 | 1237795 | 3 |  |  | 1900-01-13 | 14 | 3564710.38 | 1237795 | 0 | 0 | 1237795 | [5 empty] | 1237795 | -61889.75 | 1175905.25 | 3386474.861
4 | IPA - 4 |  |  |  | 4183608.02 | 618897.64 | 0 | 0 | 618897.64 | 4 |  |  | 1900-01-13 | 14 | 4183608.02 | 618897.64 | 0 | 0 | 618897.64 | [5 empty] | 618897.64 | -30944.882 | 587952.758 | 3974427.619
5 | IPA - 5 |  |  |  | 6321173.99 | 2137565.97 | 0 | 0 | 2137565.97 | 5 |  |  | 1900-01-13 | 14 | 6321173.99 | 2137565.97 | 0 | 0 | 2137565.97 | [5 empty] | 2137565.97 | -106878.2985 | 2030687.6715 | 6005115.2905
6 | IPA - 6 |  |  |  | 8458739.96 | 2137565.97 | 0 | 0 | 2137565.97 | 6 |  |  | 1900-01-13 | 14 | 8458739.96 | 2137565.97 | 0 | 0 | 2137565.97 | [5 empty] | 2137565.97 | -106878.2985 | 2030687.6715 | 8035802.962
7 | IPA - 7 |  |  |  | 9527522.94 | 1068782.98 | 0 | 0 | 1068782.98 | 7 |  |  | 1900-01-13 | 14 | 9527522.94 | 1068782.98 | 0 | 0 | 1068782.98 | [5 empty] | 1068782.98 | -53439.149 | 1015343.831 | 9051146.793
8 | IPA - 8 |  |  |  | 9861611.31 | 334088.37 | 0 | 0 | 334088.37 | 8 |  |  | 1900-01-13 | 14 | 9861611.31 | 334088.37 | 0 | 0 | 334088.37 | [5 empty] | 334088.37 | -16704.4185 | 317383.9515 | 9368530.7445
9 | IPA - 9 |  |  |  | 10195699.68 | 334088.37 | 0 | 0 | 334088.37 | 9 |  |  | 1900-01-13 | 14 | 10195699.68 | 334088.37 | 0 | 0 | 334088.37 | [5 empty] | 334088.37 | -16704.4185 | 317383.9515 | 9685914.696
10 | IPA - 10 |  |  |  | 10362744.2 | 167044.52 | 0 | 0 | 167044.52 | 10 |  |  | 1900-01-13 | 14 | 10362744.2 | 167044.52 | 0 | 0 | 167044.52 | [5 empty] | 167044.52 | -8352.226 | 158692.294 | 9844606.99
11 | IPA - 11 |  |  |  | 10713692.07 | 350947.87 | 0 | 0 | 350947.87 | 11 |  |  | 1900-01-13 | 14 | 10713692.07 | 350947.87 | 0 | 0 | 350947.87 | [5 empty] | 350947.87 | -17547.3935 | 333400.4765 | 10178007.4665 | 350947.87 | 333400.48
12 | IPA - 12 |  | AMA01003-PAYAP-000184 | 2023-10-15 | 10801428.46 | 87736.39 | 0 | 0 | 87736.39 | 12 | AMA01003-PC-000033 | 2023-10-18 | 2023-10-29 | 11 | 10801428.46 | 87736.39 | 0 | 0 | 87736.39 | HKS01003-RIA-000001 | 2023-10-18 | 2023-11-14 | 2023-11-17 | 3 | 87736.39 | -4386.8195 | 83349.5705 | 10261357.037 |  | 0.95
TOTAL (SAR) | [5 empty] | 10801428.46 | 0 | 0 | 10801428.46 | TOTAL (SAR) | [5 empty] | 10801428.46 | 0 | 0 | 10801428.46 | TOTAL (SAR) |  |  |  |  | 10801428.46 | -540071.423 | 10261357.037 | 10261357.037
10891204
[5 empty] | 10891204 | [19 empty] | 89775.54
[5 empty] | 177511.93 | [5 empty] | 0.036364
|  |  |  | 2021-01-01 | [18 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [18 empty] | 2020-08-06
2020-06-04
Formulas:
Issue date of IPC per Contract (14days) = [Date Aconex Letter]+14
Payment Date as per Contract (30days) = +[DATE AMAALA ACONEX REF FOR INV APPROVAL]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H ATM
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
APPLIED TECHNOLOGY & MANAGEMENT (PO 2210167)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (14days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | AMAALA ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (45days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 14.6.1 | + / - | SAR | SAR | 0% | 0% | SAR |  | Date | Date | Cl.14.7(b)(i) | + / - |  | -5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 14 | d = c- d | e | f | g = f * 0% | h = f * 0% | i = f + g + h |  |  | j | k = a + 30 | l = k - j | m = i | n = ( f + h ) * -5% | O = M + N
1 | IPA - 1 |  |  | 2021-05-31 | 93750 | 93750 | 0 | 0 | 93750 | 1 | AMA-WTRAN-000951 | 2022-07-08 | 2021-06-14 | -389 | 93750 | 93750 | 0 | 0 | 93750 | [5 empty] | 93750 | -4687.5 | 89062.5 | 89062.5
TOTAL (SAR) | [5 empty] | 93750 | 0 | 0 | 93750 | TOTAL (SAR) | [5 empty] | 93750 | 0 | 0 | 93750 | TOTAL (SAR) |  |  |  |  | 93750 | -4687.5 | 89062.5 | 89062.5
0.036364
|  |  |  | 2021-01-01 | [18 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [18 empty] | 2020-08-06
2020-06-04
Formulas:
Issue date of IPC per Contract (14days) = [Date Aconex Letter]+14
Date Aconex Letter = [Date Aconex Letter, row above]-45
Payment Date as per Contract (45days) = [Payment Date as per Contract (45days), row above]-45

## Schedule H SIC
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
SIC - AYC
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (28days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | AMAALA ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (45days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 33% | 10% | SAR |  |  | Date | Cl. 14.6.1 | + / - | SAR | SAR | 33% | 10% | SAR |  | Date | Date | Cl.14.7(b)(i) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 28 | d = c- d | e | f | g = f * 33% | h = f * 10% | i = f + g + h |  |  | j | k = a + 30 | l = k - j | m = i | n = ( f + h ) * 15% | O = M + N
1 | APA No. 01 (Adv Paym) | Advance Payment |  |  | 616537.78 | 616537.78 | 0 | 0 | 616537.78 | 1 |  |  |  |  | 616537.78 | 616537.78 | 0 | 0 | 616537.78 | [5 empty] | 616537.78 | 92480.667 | 709018.447 | 709018.447
2 | IPA No. 1 | 2021-12-30 |  |  | 712537.78 | 96000 | -31680 | -9600 | 54720 | 2 |  |  |  |  | 712537.78 | 96000 | -31680 | -9600 | 54720 | [5 empty] | 54720 | 8208 | 62928 | 771946.447
3 | IPA No. 2 | 2022-01-31 |  |  | 2035973.2 | 1323435.42 | -436733.6886 | -132343.542 | 754358.1894 | 3 |  |  |  |  | 2035973.2 | 1323435.42 | -436733.6886 | -132343.542 | 754358.1894 | [5 empty] | 754358.1894 | 113153.7284 | 867511.9178 | 1639458.3648
4 | IPA No. 3 | 2022-02-28 |  |  | 2300028.36 | 264055.16 | -87138.2028 | -26405.516 | 150511.4412 | 4 |  |  |  |  | 2300028.36 | 264055.16 | -87138.2028 | -26405.516 | 150511.4412 | [5 empty] | 150511.4412 | 22576.7162 | 173088.1574 | 1812546.5222
5 | IPA No. 4 | 2022-03-31 |  |  | 2302140.18 | 2111.82 | -696.9006 | -211.182 | 1203.7374 | 5 |  |  |  |  | 2302140.18 | 2111.82 | -696.9006 | -211.182 | 1203.7374 | [5 empty] | 1203.7374 | 180.5606 | 1384.298 | 1813930.8202
6 | IPA No. 5 | 2022-04-30 |  |  | 2302140.18 | 0 | 0 | 0 | 0 | 6 |  |  |  |  | 2302140.18 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 1813930.8202
7 | IPA No. 6 | 2022-05-31 |  |  | 2302140.18 | 0 | 0 | 0 | 0 | 7 |  |  |  |  | 2302140.18 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 1813930.8202
8 | IPA No. 7 | 2022-06-30 |  |  | 2302140.18 | 0 | 0 | 0 | 0 | 8 |  |  |  |  | 2302140.18 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 1813930.8202
9 | IPA No. 8 | 2022-07-30 |  |  | 2302140.18 | 0 | 0 | 0 | 0 | 9 |  |  |  |  | 2302140.18 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 1813930.8202 | ok
10 | IPA No. 9 | Aug & Sep 22 |  |  | 2332140.18 | 30000 | -9900 | -3000 | 17100 | 10 |  |  |  |  | 2332140.18 | 30000 | -9900 | -3000 | 17100 |  |  | 2022-12-12 |  |  | 17100 | 2565 | 19665 | 1833595.8202 | ok
11 | IPA No. 10 | 2022-10-30 |  |  | 2437140.18 | 105000 | -34650 | -10500 | 59850 | 11 |  |  |  |  | 2437140.18 | 105000 | -34650 | -10500 | 59850 | [5 empty] | 59850 | 8977.5 | 68827.5 | 1902423.3202 | ok | paid | 2023-01-29
12 | IPA No. 11 | 2022-11-30 |  |  | 2437140.18 | 0 | 0 | 0 | 0 | 12 |  |  |  |  | 2437140.18 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 1902423.3202 | ok
13 | IPA No. 12 | Dec-21/Jan-23 |  |  | 2437140.18 | 0 | 0 | 0 | 0 | 13 |  |  |  |  | 2437140.18 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 1902423.3202 | ok
14 | IPA No. 13 | 2023-02-01 |  |  | 2437140.18 | 0 | 0 | 0 | 0 | 14 |  |  |  |  | 2437140.18 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 1902423.3202 | ok
15 | IPA No. 14 | 2023-03-01 |  |  | 2478660.18 | 41520 | -13701.6 | -4152 | 23666.4 | 15 |  |  |  |  | 2478660.18 | 41520 | -13701.6 | -4152 | 23666.4 |  |  | 2023-05-18 |  |  | 23666.4 | 3549.96 | 27216.36 | 1929639.6802 | ok | paid | 2023-05-16
16 | IPA No. 15 | 2023-04-01 |  |  | 2484660.18 | 6000 | -1922.61 | -600 | 3477.39 | 16 |  |  |  |  | 2484660.18 | 6000 | -1922.61 | -600 | 3477.39 |  |  | 2023-07-03 |  |  | 3477.39 | 521.6085 | 3998.9985 | 1933638.6787 | ok
17 | IPA No. 16 | 2023-05-01 |  |  | 2490840.18 | 6180 |  | -618 | 5562 | 17 |  |  |  |  | 2490840.18 | 6180 |  | -618 | 5562 |  |  | 2023-09-28 |  |  | 5562 | 834.3 | 6396.3 | 1940034.9787
18 | IPA No. 17 | Jun & Jul-23 |  |  | 2503020.18 | 12180 |  | -1218 | 10962 | 18 |  |  |  |  | 2503020.18 | 12180 |  | -1218 | 10962 |  |  | 2023-10-17 |  |  | 10962 | 1644.3 | 12606.3 | 1952641.2787
19 | IPA No. 18 | Aug & Sep 23 |  |  | 2513730.18 | 10710 |  | -1071 | 9639 | 19 |  |  |  |  | 2513730.18 | 10710 |  | -1071 | 9639 |  |  | 2023-12-14 |  |  | 9639 | 1445.85 | 11084.85 | 1963726.1287
20 | IPA No. 19 | Oct & Nov 23 |  |  | 2522865.18 | 9135 |  | -913.5 | 8221.5 | 20 |  |  |  |  | 2522865.18 | 9135 |  | -913.5 | 8221.5 |  |  | 2024-02-14 |  |  | 8221.5 | 1233.225 | 9454.725 | 1973180.8537
21 | IPA No. 20 | 2023-12-23 |  |  | 2527500.18 | 4635 |  | -463.5 | 4171.5 | 21 |  |  |  |  | 2527500.18 | 4635 |  | -463.5 | 4171.5 |  |  | 2024-03-27 |  |  | 4171.5 | 625.725 | 4797.225 | 1977978.0787
22 | IPA No. 21 | 2024-01-23 |  |  | 2532180.18 | 4680 |  | -468 | 4212 | 22 |  |  |  |  | 2532180.18 | 4680 |  | -468 | 4212 |  |  | 2024-05-26 |  |  | 4212 | 631.8 | 4843.8 | 1982821.8787
23 | IPA No. 22 | Feb-Apr. 24 |  |  | 2545680.18 | 13500 |  | -1350 | 12150 | 23 |  |  |  |  | 2545680.18 | 13500 |  | -1350 | 12150 |  |  | 2024-08-11 |  |  | 12150 | 1822.5 | 13972.5 | 1996794.3787
24 | IPA No. 23 | 2024-05-24 |  |  | 2550315.18 | 4635 |  | -463.5 | 4171.5 | 24 |  |  |  |  | 2550315.18 | 4635 |  | -463.5 | 4171.5 |  |  | 2024-10-21 |  |  | 4171.5 | 625.725 | 4797.225 | 2001591.6037
25 | IPA No. 24 | Jun & Jul-24 |  |  | 2559450.18 | 9135 |  | -913.5 | 8221.5 | 25 |  |  |  |  | 2559450.18 | 9135 |  | -913.5 | 8221.5 |  |  | 2024-11-28 |  |  | 8221.5 | 1233.225 | 9454.725 | 2011046.3287
TOTAL (SAR) | [5 empty] | 2559450.18 | -616423.002 | -194291.24 | 1748735.938 | TOTAL (SAR) | [5 empty] | 2559450.18 | -616423.002 | -194291.24 | 1748735.938 | TOTAL (SAR) |  |  |  |  | 1748735.938 | 262310.3907 | 2011046.3287 | 2011046.3287
[5 empty] | 1897192.4 | 616537.78 | -600798.792 |  | 1943027.178 | [9 empty] | 1943027.178 | [5 empty] | 1923609.5318
[6 empty] | 1942912.4 | 15738.988 |  | 1943027.178 | [6 empty] | 1942912.4 | [8 empty] | 1748735.938 |  |  | 1886482.4
|  | 9135 |  |  |  |  | 114.778 |  |  |  | 0.036364 |  |  |  |  | 1862122.4
|  |  |  | 2021-01-01 |  | 1942912.4 | [9 empty] | -80790 | [6 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [18 empty] | 2020-08-06
2020-06-04
Formulas:
Date Aconex Letter = [Date Aconex Letter, row above]-45
Payment Date as per Contract (45days) = [Payment Date as per Contract (45days), row above]-45

## Schedule H ZFP
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
ZFP (ZUHAIR FAYEZ PARTNERSHIP CONSULTANTS - PO 2230041)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (28days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | AMAALA ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (45days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | N/A | N/A | SAR |  |  | Date |  | + / - | SAR | SAR | N/A | N/A | SAR |  | Date | Date | Schedule 2.1 | + / - |  | 15% | Date | Date
[13 empty] | c = a + 28 | d = c- d | [6 empty] | a | b | c = a + 45 | d = c - b | e | f = (e ) * 15% | g = e + f
1 | FAS | 2023-04-01 | AMA01003-FINSTAT-000001 | 2023-03-26 | 106231.5 | 106231.5 | 0 | 0 | 106231.5 | FAS | AMA01003-PC-000012 | 2023-04-08 | 2023-04-23 | 15 | 106231.5 | 106231.5 | 0 | 0 | 106231.5 | AMA01003-PC-000012 | 2023-04-08 | 2023-05-29 | 2023-05-23 | -6 | 106231.5 | 15934.725 | 122166.225 | 122166.225
TOTAL (SAR) | [5 empty] | 106231.5 | 0 | 0 | 106231.5 | TOTAL (SAR) | [5 empty] | 106231.5 | 0 | 0 | 106231.5 | TOTAL (SAR) |  |  |  |  | 106231.5 | 15934.725 | 122166.225
0.036364
|  |  |  | 2021-01-01 | [18 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [18 empty] | 2020-08-06
2020-06-04
Formulas:
Issue date of IPC per Contract (28days) = +[Date Aconex Letter]+28
Payment Date as per Contract (45days) = +[DATE AMAALA ACONEX REF FOR INV APPROVAL]+45
Payment Date as per Contract (45days) = [Payment Date as per Contract (45days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H LIU
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
LIU (LANGAN INTERNATIONAL UK - PO 2230042)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (28days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONSULTANT ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (45days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | N/A | N/A | SAR |  |  | Date |  | + / - | SAR | SAR | N/A | N/A | SAR |  | Date | Date | Schedule 2.1 | + / - |  | N/A | Date | Date
[13 empty] | c = a + 28 | d = c- d | [6 empty] | a | b | c = a + 45 | d = c - b | e | 5%WHT Included. | g = e
1 | 1 | 2023-07-01 | AMA01003-PAYAP-000114 | 2023-07-24 | 168421.05 | 168421.05 | 0 | 0 | 168421.05 | 1 | AMA01003-PC-000022 | 2023-07-27 | 2023-08-21 | 25 | 168421.05 | 168421.05 | 0 | 0 | 168421.05 | LIU01003-RIA-000001 | 2023-07-27 | 2023-08-09 | 2023-09-10 | 32 | 168421.05 | 0 | 0 | 168421.05
TOTAL (SAR) | [5 empty] | 168421.05 | 0 | 0 | 168421.05 | TOTAL (SAR) | [5 empty] | 168421.05 | 0 | 0 | 168421.05 | TOTAL (SAR) |  |  |  |  | 168421.05 | 0 | 0 | 168421.05
0.036364
|  |  |  | 2021-01-01 | [18 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [18 empty] | 2020-08-06
2020-06-04
Formulas:
Issue date of IPC per Contract (28days) = +[Date Aconex Letter]+28
Payment Date as per Contract (45days) = +[DATE AMAALA ACONEX REF FOR INV APPROVAL]+45
Payment Date as per Contract (45days) = [Payment Date as per Contract (45days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H KAA
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
KAA (SAUDI CONSOLIDATED ENGINEERING COMPANY - KHATIB & ALAMI - PO 2230031)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONSULTANT INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | N/A | N/A | SAR |  |  | Date | Cl. 24.2 | + / - | SAR | SAR | N/A | N/A | SAR |  |  | Date | Date | Schedule 3 | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 0% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = ( f + h ) * 15% | P = N + O
1 | IPA - 1 | Feb 23 to Oct 23 | KAA01003-GENCORR-000052 | 2023-11-28 | 3716548 | 3716548 | 0 | 0 | 3716548 | 1 | 1TB01003-003F02-AMA-LTR-0013 | 2023-12-06 | 2023-12-19 | 13 | 3716548 | 3716548 | 0 | 0 | 3716548 | KAA01003-RIA-000001 | 2023-12-19 |  | 2024-01-15 | 2024-01-18 | 3 | 3716548 | 557482.2 | 4274030.2 | 4274030.2 | 4274030.2
2 | IPA - 2 | 2023-11-23 | KAA01003-GENCORR-000056 | 2023-12-19 | 4171855 | 455307 | 0 | 0 | 455307 | 2 | 1TB01003-003F02-AMA-LTR-0015 | 2023-12-23 | 2024-01-09 | 17 | 4171855 | 455307 | 0 | 0 | 455307 | KAA01003-RIA-000002 | 2023-12-31 |  | 2024-01-18 | 2024-01-30 | 12 | 455307 | 68296.05 | 523603.05 | 4797633.25
3 | IPA - 3 | Dec23 - Jun24 | KAA01003-GENCORR-000185 | 2024-07-10 | 6785336 | 2613481 | 0 | 0 | 2613481 | 3 | 1TB01003-003F02-AMA-LTR-0020 | 2024-08-08 | 2024-07-31 | -8 | 6785336 | 2613481 | 0 | 0 | 2613481 | KAA01003-RIA-000003 | 2024-09-02 |  | 2024-09-18 | 2024-10-02 | 14 | 2613481 | 392022.15 | 3005503.15 | 7803136.4
4 | IPA - 4 | 2024-07-24 | KAA01003-RESP-000335 | 2024-09-15 | 7225208 | 439872 | 0 | 0 | 439872 | 4 | 1TB01003-003F02-AMA-LTR-0022 | 2024-09-25 | 2024-10-06 | 11 | 7225208 | 439872 | 0 | 0 | 439872 | KAA01003-RIA-000006 | 2024-11-25 |  | 2024-12-09 | 2024-12-25 | 16 | 439872 | 65980.8 | 505852.8 | 8308989.2
5 | IPA - 5 | 2024-08-24 | KAA01003-GENCORR-000315 | 2024-10-01 | 7661576 | 436368 | 0 | 0 | 436368 | 5 | 1TB01003-003F02-AMA-LTR-0024 | 2024-10-06 | 2024-10-22 | 16 | 7661576 | 436368 | 0 | 0 | 436368 | KAA01003-RIA-000007 | 2024-11-25 |  | 2024-12-09 | 2024-12-25 | 16 | 436368 | 65455.2 | 501823.2 | 8810812.4
6 | IPA - 6 | 2024-09-24 | KAA01003-GENCORR-000338 | 2024-10-16 | 8065428 | 403852 | 0 | 0 | 403852 | 6 | 1TB01003-003F02-AMA-LTR-0026 | 2024-11-07 | 2024-11-06 | -1 | 8051162 | 389586 | 0 | 0 | 389586 |  | 2024-12-18 |  | 2024-12-18 | 2025-01-17 | 30 | 389586 | 58437.9 | 448023.9 | 9258836.3
7 | IPA - 7 | 2024-10-24 | KAA01003-GENCORR-000415 | 2024-12-09 | 8540377 | 474949 | 0 | 0 | 474949 | 7 | 1TB01003-003F02-AMA-LTR-0031 | 2025-03-03 | 2024-12-30 | -63 | 8526111 | 474949 | 0 | 0 | 474949 | KAA01003-RIA-000008 | 2025-03-12 |  | 2025-04-21 | 2025-04-11 | -10 | 474949 | 71242.35 | 546191.35 | 9805027.65
8 | IPA - 8 | No 24 to Mar 25 | KAA01003-GENCORR-000461 | 2025-04-16 | 10429066 | 1888689 | 0 | 0 | 1888689 | 8 | 1TB01003-003F02-AMA-LTR-0032 | 2025-04-28 | 2025-05-07 | 9 | 10414800 | 1888689 | 0 | 0 | 1888689 | KAA01003-RIA-000009 | 2025-05-06 |  | 2025-06-10 | 2025-06-05 | -5 | 1888689 | 283303.35 | 2171992.35 | 11977020
9 | IPA - 9 | 2025-04-01 | KAA01003-GENCORR-000470 | 2025-05-07 | 10855492 | 426426 | 0 | 0 | 426426 | 9 | 1TB01003-003F02-AMA-LTR-0033 | 2025-05-13 | 2025-05-28 | 15 | 10841226 | 426426 | 0 | 0 | 426426 | KAA01003-RIA-000010 | 2025-05-20 |  | 2025-06-30 | 2025-06-19 | -11 | 426426 | 63963.9 | 490389.9 | 12467409.9
10 | IPA - 10 | 2025-05-01 | KAA01003-GENCORR-000484 | 2025-06-21 | 11282073 | 426581 | 0 | 0 | 426581 | 10 | 1TB01003-003F02-AMA-LTR-0034 | 2025-07-02 | 2025-07-12 | 10 | 11267807 | 426581 | 0 | 0 | 426581 | KAA01003-RIA-000011 | 2025-07-13 |  | 2025-07-31 | 2025-08-12 | 12 | 426581 | 63987.15 | 490568.15 | 12957978.05
11 | IPA - 11 | 2025-06-01 | KAA01003-GENCORR-000498 | 2025-07-16 | 11561029 | 278956 | 0 | 0 | 278956 | 11 | 1TB01003-003F02-AMA-LTR-0036 | 2025-08-05 | 2025-08-06 | 1 | 11546763 | 278956 | 0 | 0 | 278956 | KAA01003-RIA-000012 | 2025-08-17 |  | 2025-07-31 | 2025-09-16 | 47 | 278956 | 41843.4 | 320799.4 | 13278777.45
12 | IPA - 12 | 2025-07-25 | KAA01003-GENCORR-000517 | 2025-08-21 | 11962844 | 401815 | 0 | 0 | 401815 | 12 | 1TB01003-003F02-AMA-LTR-0038 | 2025-08-31 | 2025-09-11 | 11 | 11967085 | 420322 | 0 | 0 | 420322 | KAA01003-RIA-000013 | 2025-09-15 |  | 2025-10-02 | 2025-10-15 | 13 | 420322 | 63048.3 | 483370.3 | 13762147.75
13 | IPA - 13 | 2025-07-26 | KAA01003-GENCORR-000522 | 2025-09-08 | 12377119 | 414275 | 0 | 0 | 414275 | 13 | 1TB01003-003F02-AMA-LTR-0039 | 2025-09-14 | 2025-09-29 | 15 | 12381360 | 414275 | 0 | 0 | 414275 | KAA01003-RIA-000013 | 2025-09-28 |  |  | 2025-10-28 |  | 414275 | 62141.25 | 476416.25 | 14238564
14 | IPA - 14 | 2025-09-01 | KAA01003-GENCORR-000529 | 2025-09-21 | 12738341 | 361222 | 0 | 0 | 361222 | 14 | 1TB01003-003F02-AMA-LTR-0040 | 2025-09-25 | 2025-10-12 | 17 | 12742582 | 361222 | 0 | 0 | 361222 | KAA01003-RIA-000015 | 2025-10-05 |  |  | 2025-11-04 |  | 361222 | 54183.3 | 415405.3 | 14653969.3
15 | IPA - 15 | 2025-10-01 | KAA01003-GENCORR-000541 | 2025-11-09 | 13137229 | 398888 | 0 | 0 | 398888 | 15 | 1TB01003-003F02-AMA-LTR-0041 | 2025-11-18 | 2025-11-30 | 12 | 13141470 | 398888 | 0 | 0 | 398888 | KAA01003-RIA-000016 | 2025-12-07 |  |  | 2026-01-06 |  | 398888 | 59833.2 | 458721.2 | 15112690.5
16 | IPA - 16 | 2025-11-01 | KAA01003-GENCORR-000550 | 2025-12-09 | 13483381 | 346152 | 0 | 0 | 346152 | 16 | 1TB01003-003F02-AMA-LTR-0042 | 2025-12-15 | 2025-12-30 | 15 | 13487622 | 346152 | 0 | 0 | 346152 | KAA01003-RIA-000017 | 2025-12-28 |  |  | 2026-01-27 |  | 346152 | 51922.8 | 398074.8 | 15510765.3
17 | IPA - 17 | 2025-12-01 | KAA01003-GENCORR-000552 | 2026-01-07 | 13709566 | 226185 | 0 | 0 | 226185 | 17 | 1TB01003-003F02-AMA-LTR-0044 | 2026-02-04 | 2026-01-28 | -7 | 13713807 | 226185 | 0 | 0 | 226185 | KAA01003-RIA-000018 | 2026-02-26 |  |  | 2026-03-28
18 | IPA - 18 | 2026-01-01 | KAA01003-GENCORR-000556 | 2026-02-01 | 13788286 | 78720 | 0 | 0 | 78720 | 18 | 1TB01003-003F02-AMA-LTR-0046 | 2026-03-04 | 2026-02-22 | -10 | 13792527 | 78720 | 0 | 0 | 78720 | KAA01003-RIA-000019 | 2026-04-14 |  |  | 2026-05-14
19 | IPA - 19 | 2026-05-01 | KAA01003-GENCORR-000574 | 2026-06-14 | 14078459 | 290173 | 0 | 0 | 290173 | 19 | 1TB01003-003F02-AMA-LTR-0048 | 2026-06-17 | 2026-07-05 | 18 | 14082700 | 290173 | 0 | 0 | 290173 | KAA01003-RIA-000020 | 2026-07-22 |  |  | 2026-08-21
TOTAL (SAR) | [5 empty] | 14078459 | 0 | 0 | 14078459 | TOTAL (SAR) | [5 empty] | 14082700 | 0 | 0 | 14082700 | TOTAL (SAR) | [5 empty] | 13487622 | 2023143.3 | 15510765.3 | 13762147.75
448023.9
[11 empty] | 0.036364 | [7 empty] | 876240
|  |  |  | 2021-01-01 | [14 empty] | 1007676 |  |  |  |  | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Formulas:
Issue date of IPC per Contract (21days) = [Date Aconex Letter]+21
Payment Date as per Contract (30days) = +[INVOICE DATE]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H GBC
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
GBC (GREEN BUSINESS CERTIFICATION PO 2220038)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (28days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | AMAALA ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 20% | 10% | SAR |  |  | Date | Cl. 14.6.1 | + / - | SAR | SAR | 20% | 10% | SAR |  | Date | Date | Cl.14.7(b)(i) | + / - |  | 0% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 28 | d = c- d | e | f | g = f * 10% | h = f * 10% | i = f + g + h |  |  | j | k = a + 30 | l = k - j | m = i | n = ( f + h ) * 0% | O = M + N
1 | PAI # 01 | 2021-08-01 |  | 2021-08-29 | 4500 | 4500 | 0 | 0 | 4500 | PAI # 01 |  |  |  | 0 | 4500 | 4500 | 0 | 0 | 4500 |  |  | 2021-09-28 | 2021-09-28 | 0 | 4500 | 0 | 4500 | 4500
2 | PAI # 02 | 2023-07-01 |  | 2023-07-11 | 18000.1125 | 13500.1125 | 0 | 0 | 13500.1125 | PAI # 02 |  |  |  | 0 | 18000.1125 | 13500.1125 | 0 | 0 | 13500.1125 |  |  | 2023-09-11 | 2023-08-10 | -32 | 13500.1125 | 0 | 13500.1125 | 18000.1125
TOTAL (SAR) | [5 empty] | 18000.1125 | 0 | 0 | 18000.1125 | TOTAL (SAR) | [5 empty] | 18000.1125 | 0 | 0 | 18000.1125 | TOTAL (SAR) |  |  |  |  | 18000.1125 | 0 | 18000.1125 | 18000.1125
0.036364
|  |  |  | 2021-01-01 | [18 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [18 empty] | 2020-08-06
2020-06-04
Formulas:
Payment Date as per Contract (30days) = [Date Aconex Letter]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H NSCC
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
NSCC ( BEACH + RSMLI + AYC + B&M)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | NSCC Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | WSP Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (28days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | AMAALA ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (56days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 20% | 10% | SAR |  |  | Date | Cl. 14.6.1 | + / - | SAR | SAR | 20% | 10% | SAR |  | Date | Date | Cl.14.7(b)(i) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 28 | d = c- d | e | f | g = f * 10% | h = f * 10% | i = f + g + h |  |  | j | k = a + 56 | l = k - j | m = i | n = ( f + h ) * 15% | O = M + N
1 | IPA No. 01 Adv Pay | Advance Payment | NSC-LTR-000010 | 2022-04-26 | 21990478.4 | 21990478.4 | 0 | 0 | 21990478.4 | 1 | WSP-TRAN-000502 | 2022-05-17 | 2022-05-10 | -7 | 21990478.4 | 21990478.4 | 0 | 0 | 21990478.4 | AMA-WTRAN-000703 | 2021-06-12 | 2022-06-02 | 2022-05-10 | -23 | 21990478.4 | 3298571.76 | 25289050.16 | 25289050.16
2 | IPA No. 02 | 2022-06-01 | NSC-GENCORR-000027 | 2022-07-26 | 26268812.961 | 4278334.561 | -855666.9122 | -427833.4561 | 2994834.1927 | 2 | WSP-LTR-000024 | 2022-08-17 | 2022-08-23 | 6 | 25785042.03 | 3794563.63 | -758912.726 | -379456.363 | 2656194.541 | 0 |  | 2022-09-28 | 2022-09-20 | -8 | 2656194.541 | 512266.09 | 3168460.631 | 28457510.7911
3 | IPA No. 03 | 2022-07-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 26141408.724 | -127404.237 | 25480.8474 | 12740.4237 | -89182.9659 | 3 | WSP-LTR-0033 | 2022-10-29 | 2022-11-15 | 17 | 26141408.72 | 356366.69 | -71273.338 | -35636.669 | 249456.683 | 0 |  | 2022-12-13 | 2022-12-13 | 0 | 249456.683 | 48109.5032 | 297566.1862 | 28755076.9772
4 | IPA No. 04 | 2022-08-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 26141408.724 | 0 | 0 | 0 | 0 | 4 | WSP-LTR-0034 | 2022-10-29 | 2022-11-15 | 17 | 27021751.78 | 880343.06 | -176068.612 | -88034.306 | 616240.142 | 0 |  | 2022-12-13 | 2022-12-13 | 0 | 616240.142 | 118846.3131 | 735086.4551 | 29490163.4323
5 | IPA No. 05 | 2022-09-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 26141408.724 | 0 | 0 | 0 | 0 | 5 | WSP-LTR-0035 | 2022-10-29 | 2022-11-15 | 17 | 27685514.27 | 663762.49 | -132752.498 | -66376.249 | 464633.743 |  |  | 2022-12-13 | 2022-12-13 | 0 | 464633.743 | 89607.9362 | 554241.6792 | 30044405.1115
6 | IPA No. 06 | 2022-10-01 | ITB04400-005C13-NSC-LTR-0155 | 2022-11-05 | 49952622.093 | 23811213.369 | -4762242.6738 | -2381121.3369 | 16667849.3583 | 5 | WSP-LTR-0047 | 2022-12-07 | 2022-12-03 | -4 | 35999599.74 | 8314085.47 | -1662817.094 | -831408.547 | 5819859.829 |  |  | 2023-01-09 | 2022-12-31 | -9 | 5819859.829 | 1122401.5384 | 6942261.3674 | 36986666.4789
7 | IPA No. 07 | 2022-11-01 | 1TB04400-005C13-NSC-LTR-0175 | 2022-12-05 | 64836836.26 | 14884214.167 | -2976842.8334 | -1488421.4167 | 10418949.9169 | 7 | WSP-LTR-0065 | 2023-01-04 | 2023-01-02 | -2 | 47916286.57 | 11916686.83 | -2263220.966 | -1191668.683 | 8461797.181 | AMA-WTRAN-001848 | 2023-01-22 | 2023-01-22 | 2023-01-30 | 8 | 8461797.181 | 1608752.7221 | 10070549.9031 | 47057216.3819
8 | IPA No. 08 | 2022-12-01 | 1TB04400-005C13-NSC-LTR-0214 | 2023-01-05 | 90327542.07 | 25490705.81 | -5098141.162 | -2549070.581 | 17843494.067 | 8 | 1TB04400-031D03-WSP-LTR-0076 | 2023-01-25 | 2023-02-02 | 8 | 64522189.92 | 16605903.35 | -3441297.07 | -1660590.335 | 11504015.945 |  |  | 2023-02-21 | 2023-03-02 | 9 | 11504015.945 | 2241796.9522 | 13745812.8972 | 60803029.2792
9 | IPA No. 09 | 2023-01-01 | 1TB04400-005C13-NSC-LTR-0249 | 2023-02-08 | 96668575.42 | 6341033.35 | -1268206.67 | -634103.335 | 4438723.345 | 9 | WSP-LTR-0081 | 2023-02-20 | 2023-03-08 | 16 | 71520564.09 | 6998374.17 | -1399674.834 | -699837.417 | 4898861.919 |  |  | 2023-03-22 | 2023-04-05 | 14 | 4898861.919 | 944780.5129 | 5843642.432 | 66646671.7111
10 | IPA No. 010 | 2023-02-01 | 1TB04400-005C13-NSC-LTR-0276 | 2023-03-05 | 108287794.66 | 11619219.24 | -2323843.848 | -1161921.924 | 8133453.468 | 10 | 1TB04400-031D03-WSP-LTR-0095 | 2023-03-20 | 2023-04-02 | 13 | 80312222.39 | 8791658.3 | -1758331.66 | -879165.83 | 6154160.81 |  |  | 2023-04-30 | 2023-04-30 | 0 | 6154160.81 | 1186873.8705 | 7341034.6805 | 73987706.3916
11 | IPA No. 011 | 2023-03-23 | 1TB04400-005C13-NSC-LTR-0306 | 2023-04-06 | 110782748.19 | 2494953.53 | -498990.706 | -249495.353 | 1746467.471 | 11 | WSP-LTR-0106 | 2023-05-06 | 2023-05-04 | -2 | 82330258.61 | 2018036.22 | -403607.244 | -201803.622 | 1412625.354 |  |  | 2023-05-29 | 2023-06-01 | 3 | 1412625.354 | 272434.8897 | 1685060.2437 | 75672766.6353
12 | IPA No. 012 | 2023-04-23 | NSC-LTR-000328 | 2023-05-06 | 128956135.94 | 18173387.75 | -3634677.55 | -1817338.775 | 12721371.425 | 12 | WSP-LTR-0113 | 2023-05-29 | 2023-06-03 | 5 | 83494856.14 | 1164597.53 | -232919.506 | -116459.753 | 815218.271 |  |  | 2023-07-09 | 2023-07-01 | -8 | 815218.271 | 157220.6665 | 972438.9376 | 76645205.5729
13 | IPA No. 013 | 2023-05-23 | NSC-LTR-000345 | 2023-06-07 | 142611789.44 | 13655653.5 | -2731130.7 | -1365565.35 | 9558957.45 | 13 | WSP-LTR-0123 | 2023-07-13 | 2023-07-05 | -8 | 96431928.06 | 12937071.92 | -2587414.394 | -1293707.192 | 9055950.334 |  |  | 2023-08-09 | 2023-08-02 | -7 | 9055950.334 | 1746504.7092 | 10802455.0432 | 87447660.6161 | 10349657.526 | 11902106.1549
14 | IPA No. 014 | 2023-06-23 | NSC-LTR-000355 | 2023-07-08 | 152534311.54 | 9922522.1 | -1984504.42 | -992252.21 | 6945765.47 | 14 | WSP04400-GENCORR-000389 | 2023-07-20 | 2023-08-05 | 16 | 104469956.08 | 8038028.02 | -2914009.27 | -803802.802 | 4320215.948 |  |  | 2023-09-18 | 2023-09-02 | -16 | 4320215.948 | 1085133.7827 | 5405349.7307 | 92853010.3468
15 | IPA No. 015 | 2023-07-23 | NSC-LTR-000372 | 2023-08-09 | 155268179.51 | 2733867.97 | -546773.594 | -273386.797 | 1913707.579 | 15 | 1TB04400-031D03-WSP-LTR-0131 | 2023-09-07 | 2023-09-06 | -1 | 110082094.19 | 5612138.11 | -2871704.46 | -561213.821 | 2179219.829 |  |  | 2023-11-14 | 2023-10-04 | -41 | 2179219.829 | 757638.6434 | 2936858.4724 | 95789868.8192
16 | IPA No. 016 | 2023-08-23 | NSC-LTR-0382 | 2023-09-10 | 156723846.89 | 1455667.38 | 5323299.192 | 6591101.682 | 13370068.254 | 16 | 1TB04400-031D03-WSP-LTR-0133 | 2023-09-19 | 2023-10-08 | 19 | 111559586.84 | 1477492.65 | -1070045.3 | -147749.27 | 259698.08 |  |  | 2023-11-14 | 2023-11-05 | -9 | 259698.08 | 199461.507 | 459159.587 | 96249028.4061
17 | IPA No. 017 | Sep & Oct-23 | NSC-LTR-0394 | 2023-10-30 | 157447051.52 | 723204.63 | -658237.37 | -36160.227 | 28807.033 | 17 | 1TB04400-031D03-WSP-LTR-0141 | 2023-12-05 | 2023-11-27 | -8 | 112359492.42 | 799905.58 | -246429.43 | 4438460.17 | 4991936.32 |  |  | 2023-12-25 | 2023-12-25 | 0 | 4991936.32 | 785754.8625 | 5777691.1825 | 102026719.5886
18 | IPA No. 018 | 2024-06-24 | 1TB04400-005C13-NSC-LTR-0402-0 | 2024-06-26 | 98506998.99 | 2989950 | 0 | -149497.5 | 2840452.5 | 18 | 1TB04400-400000-AMA-LTR-0053 | 2024-07-09 | 2024-07-24 | 15 | 115349442.42 | 2989950 | 0 | -149497.5 | 2840452.5 |  |  | 2024-09-18 | 2024-08-21 | -28 | 2840452.5 | 426067.875 | 3266520.375 | 105293239.9636
19 | IPA No. 019 | 2024-08-24 | 1TB04400-005C13-NSC-LTR-0405 | 2024-09-03 | 98506998.99 | 5148035 | 0 | -257401.75 | 4890633.25 | 19 | 1TB04400-400000-AMA-LTR-0054 | 2024-09-16 | 2024-10-01 | 15 | 120497477.42 | 5148035 | 0 | -257401.75 | 4890633.25 |  |  | 2024-10-31 | 2024-10-29 | -2 | 4890633.25 | 733594.9875 | 5624228.2375 | 110917468.2011
19 | IPA No. 020 | 2024-10-24 | 1TB04400-005C13-NSC-LTR-0408 | 2024-10-14 | 108561602.79 | 10054603.8 | 0 | 4925349.97 | 14979953.77 | 19 | 1TB04400-400000-AMA-LTR-0057 | 2024-12-09 | 2024-11-11 | -28 | 130552081.22 | 10054603.8 | 0 | 4925349.97 | 14979953.77 |  |  | 2024-12-09 | 2024-12-09 | 0 | 14979953.77 | 2246993.0655 | 17226946.8355 | 128144415.0366
TOTAL (SAR) | [5 empty] | 175639640.32 | -21990478.4 | -2254377.936 | 151394783.984 | TOTAL (SAR) | [5 empty] | 130552081.22 | -21990478.402 | 0.031 | 108561602.849 | TOTAL (SAR) |  |  |  |  | 108561602.849 | 19582812.1876 | 128144415.0367 | 128144415.0366
PLOT TB - 09 BEACH
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | NSCC Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | WSP Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (28days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | AMAALA ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (56days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 20% | 10% | SAR |  |  | Date | Cl. 14.6.1 | + / - | SAR | SAR | 20% | 10% | SAR |  | Date | Date | Cl.14.7(b)(i) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 28 | d = c- d | e | f | g = f * 10% | h = f * 10% | i = f + g + h |  |  | j | k = a + 56 | l = k - j | m = i | n = ( f + h ) * 15% | O = M + N
1 | IPA No. 01 Adv Pay | Advance Payment | NSC-LTR-000010 | 2022-04-26 | 4762363.6 | 4762363.6 | 0 | 0 | 4762363.6 | 1 | WSP-TRAN-000502 | 2022-05-17 | 2022-05-10 | -7 | 4762363.6 | 4762363.6 | 0 | 0 | 4762363.6 | AMA-WTRAN-000703 | 2021-06-12 | 2022-06-02 | 2022-05-10 | -23 | 4762363.6 | 714354.54 | 5476718.14 | 5476718.14
2 | IPA No. 02 | 2022-06-01 | NSC-GENCORR-000027 | 2022-07-26 | 5369247.85 | 606884.25 | -121376.85 | -60688.425 | 424818.975 | 2 | WSP-LTR-000024 | 2022-08-17 | 2022-08-23 | 6 | 5361086.14 | 598722.54 | -119744.508 | -59872.254 | 419105.778 |  |  | 2022-09-28 | 2022-09-20 | -8 | 419105.778 | 80827.5429 | 499933.3209 | 5976651.4609
3 | IPA No. 03 | 2022-07-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 5352513.6 | -16734.25 | 3346.85 | 1673.425 | -11713.975 | 3 | WSP-LTR-0033 | 2022-10-29 | 2022-11-15 | 17 | 5352513.6 | -8572.54 | 1714.508 | 857.254 | -6000.778 |  |  | 2022-12-13 | 2022-12-13 | 0 | -6000.778 | -1157.2929 | -7158.0709 | 5969493.39
4 | IPA No. 04 | 2022-08-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 5352513.6 | 0 | 0 | 0 | 0 | 4 | WSP-LTR-0034 | 2022-10-29 | 2022-11-15 | 17 | 5352513.6 | 0 | 0 | 0 | 0 |  |  | 2022-12-13 | 2022-12-13 | 0 | 0 | 0 | 0 | 5969493.39
5 | IPA No. 05 | 2022-09-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 5352513.6 | 0 | 0 | 0 | 0 | 5 | WSP-LTR-0035 | 2022-10-29 | 2022-11-15 | 17 | 5352513.6 | 0 | 0 | 0 | 0 |  |  | 2022-12-13 | 2022-12-13 | 0 | 0 | 0 | 0 | 5969493.39
6 | IPA No. 06 | 2022-10-01 | ITB04400-005C13-NSC-LTR-0155 | 2022-11-05 | 6174473.1 | 821959.5 | -164391.9 | -82195.95 | 575371.65 | 6 | WSP-LTR-0047 | 2022-12-07 | 2022-12-03 | -4 | 5352513.6 | 0 | 0 | 0 | 0 |  |  | 2023-01-09 | 2022-12-31 | -9 | 0 | 0 | 0 | 5969493.39 |  |  | 2022-10-31
7 | IPA No. 07 | 2022-11-01 | 1TB04400-005C13-NSC-LTR-0175 | 2022-12-05 | 6174473.1 | 0 | 0 | 0 | 0 | 7 | WSP-LTR-0065 | 2023-01-04 | 2023-01-02 | -2 | 5352513.6 | 0 | 0 | 0 | 0 | AMA-WTRAN-001848 | 2023-01-22 | 2023-01-22 | 2023-01-30 | 8 | 0 | 0 | 0 | 5969493.39 |  |  | 2022-10-31
8 | IPA No. 08 | 2022-12-01 | 1TB04400-005C13-NSC-LTR-0214 | 2023-01-05 | 6419993.48 | 245520.38 | -49104.076 | -24552.038 | 171864.266 | 8 | 1TB04400-031D03-WSP-LTR-0076 | 2023-01-25 | 2023-02-02 | 8 | 5352513.6 | 0 | 0 | 0 | 0 |  |  | 2023-02-21 | 2023-03-02 | 9 | 0 | 0 | 0 | 5969493.39 |  |  | 2022-10-31
9 | IPA No. 09 | 2023-01-01 | 1TB04400-005C13-NSC-LTR-0249 | 2023-02-08 | 6707669.48 | 287676 | -57535.2 | -28767.6 | 201373.2 | 9 | WSP-LTR-0081 | 44977 | 2023-03-08 | 16 | 5352513.6 | 0 | 0 | 0 | 0 |  |  | 2023-03-22 | 2023-04-05 | 14 | 0 | 0 | 0 | 5969493.39
10 | IPA No. 010 | 2023-02-01 | 1TB04400-005C13-NSC-LTR-0276 | 2023-03-05 | 7193372.82 | 485703.34 | -97140.668 | -48570.334 | 339992.338 | 10 | 1TB04400-031D03-WSP-LTR-0095 | 2023-03-20 | 2023-04-02 | 13 | 5352513.6 | 0 | 0 | 0 | 0 |  |  | 2023-04-30 | 2023-04-30 | 0 | 0 | 0 | 0 | 5969493.39
11 | IPA No. 011 | 2023-03-23 | 1TB04400-005C13-NSC-LTR-0306 | 2023-04-06 | 8023216.64 | 829843.82 | -165968.764 | -82984.382 | 580890.674 | 11 | WSP-LTR-0106 | 2023-05-06 | 2023-05-04 | -2 | 5921039.66 | 568526.06 | -113705.212 | -56852.606 | 397968.242 |  |  | 2023-05-29 | 2023-06-01 | 3 | 397968.242 | 76751.0181 | 474719.2601 | 6444212.6501
12 | IPA No. 012 | 2023-04-23 | NSC-LTR-000328 | 2023-05-06 | 8655381.26 | 632164.62 | -126432.924 | -63216.462 | 442515.234 | 12 | WSP-LTR-0113 | 2023-05-29 | 2023-06-03 | 5 | 6077126.66 | 156087 | -31217.4 | -15608.7 | 109260.9 |  |  | 2023-07-09 | 2023-07-01 | -8 | 109260.9 | 21071.745 | 130332.645 | 6574545.2951
13 | IPA No. 013 | 2023-05-23 | NSC-LTR-000345 | 2023-06-07 | 9363137.74 | 707756.48 | -141551.296 | -70775.648 | 495429.536 | 13 | WSP-LTR-0123 | 2023-07-13 | 2023-07-05 | -8 | 6078979.94 | 1853.28 | -370.656 | -185.328 | 1297.296 |  |  | 2023-08-09 | 2023-08-02 | -7 | 1297.296 | 250.1928 | 1547.4888 | 6576092.7839
14 | IPA No. 014 | 2023-06-23 | NSC-LTR-000355 | 2023-07-08 | 9406093.74 | 42956 | -8591.2 | -4295.6 | 30069.2 | 14 | WSP04400-GENCORR-000389 | 2023-07-20 | 2023-08-05 | 16 | 6133400.94 | 54421 | -4300459.84 | -5442.1 | -4251480.94 |  |  | 2023-09-18 | 2023-09-02 | -16 | -4251480.94 | 7346.835 | -4244134.105 | 2331958.6789
15 | IPA No. 015 | 2023-07-23 | NSC-LTR-000372 | 2023-08-09 | 11207997.84 | 1801904.1 | -360380.82 | -180190.41 | 1261332.87 | 15 | 1TB04400-031D03-WSP-LTR-0131 | 2023-09-07 | 2023-09-06 | -1 | 8780690.04 | 2647289.1 | -198580.49 | -264728.91 | 2183979.7 |  |  | 2023-11-14 | 2023-10-04 | -41 | 2183979.7 | 357384.0285 | 2541363.7285 | 4873322.4074
16 | IPA No. 016 | 2023-08-23 | NSC-LTR-0382 | 2023-09-10 | 11639978.72 | 431980.88 | -3473236.752 | 300682.672 | -2740573.2 | 16 | 1TB04400-031D03-WSP-LTR-0133 | 2023-09-19 | 2023-10-08 | 19 | 9286971.68 | 506281.64 | 0 | -50628.17 | 455653.47 |  |  | 2023-11-14 | 2023-11-05 | -9 | 455653.47 | 68348.0205 | 524001.4905 | 5397323.8979
17 | IPA No. 017 | Sep & Oct-23 | NSC-LTR-0394 | 2023-10-30 | 11639978.72 | 0 | 0 | 0 | 0 | 17 | 1TB04400-031D03-WSP-LTR-0141 | 2023-12-05 | 2023-11-27 | -8 | 9286971.68 | 0 | 0 | 226230.41 | 226230.41 |  |  | 2023-12-25 | 2023-12-25 | 0 | 226230.41 | 33934.5615 | 260164.9715 | 5657488.8694
18 | IPA No. 018 | 2024-06-24 | 1TB04400-005C13-NSC-LTR-0402-0 | 2024-06-26 | 4922408.08 | 397800 | 0 | -19890 | 377910 | 18 | 1TB04400-400000-AMA-LTR-0053 | 2024-07-09 | 2024-07-24 | 15 | 9684771.68 | 397800 | 0 | -19890 | 377910 |  |  | 2024-09-18 | 2024-08-21 | -28 | 377910 | 56686.5 | 434596.5 | 6092085.3694
19 | IPA No. 019 | 2024-08-24 | 1TB04400-005C13-NSC-LTR-0405 | 2024-09-03 | 4922408.08 | 0 | 0 | 0 | 0 | 19 | 1TB04400-400000-AMA-LTR-0054 | 2024-09-16 | 2024-10-01 | 15 | 9684771.68 | 0 | 0 | 0 | 0 |  |  | 2024-10-31 | 2024-10-29 | -2 | 0 | 0 | 0 | 6092085.3694
20 | IPA No. 020 | 2024-10-24 | 1TB04400-005C13-NSC-LTR-0408 | 2024-10-14 | 5179132.19 | 256724.11 | 0 | 246120.41 | 502844.52 | 20 | 1TB04400-400000-AMA-LTR-0057 | 2024-12-09 | 2024-11-11 | -28 | 9941495.79 | 256724.11 | 0 | 246120.41 | 502844.52 |  |  | 2024-12-09 | 2024-12-09 | 0 | 502844.52 | 75426.678 | 578271.198 | 6670356.5674 |  |  | 56
TOTAL (SAR) | [5 empty] | 12294502.83 | -4762363.6 | -117650.342 | 7414488.888 | TOTAL (SAR) | [5 empty] | 9941495.79 | -4762363.598 | 0.006 | 5179132.198 | TOTAL (SAR) |  |  |  |  | 5179132.198 | 1491224.3694 | 6670356.5674 | 6670356.5674 |  |  | 2022-12-26
PLOT TB - 04.1 MARINA RSMLI
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | NSCC Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | WSP Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (28days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | AMAALA ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (56days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 20% | 10% | SAR |  |  | Date | Cl. 14.6.1 | + / - | SAR | SAR | 20% | 10% | SAR |  | Date | Date | Cl.14.7(b)(i) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 28 | d = c- d | e | f | g = f * 10% | h = f * 10% | i = f + g + h |  |  | j | k = a + 56 | l = k - j | m = i | n = ( f + h ) * 15% | O = M + N
1 | IPA No. 01 Adv Pay | Advance Payment | NSC-LTR-000010 | 2022-04-26 | 7575490 | 7575490 | 0 | 0 | 7575490 | 1 | WSP-TRAN-000502 | 2022-05-17 | 2022-05-10 | -7 | 7575490 | 7575490 | 0 | 0 | 7575490 | AMA-WTRAN-000703 | 2021-06-12 | 2022-06-02 | 2022-05-10 | -23 | 7575490 | 1136323.5 | 8711813.5 | 8711813.5
2 | IPA No. 02 | 2022-06-01 | NSC-GENCORR-000027 | 2022-07-26 | 9529565.117 | 1954075.117 | -390815.0234 | -195407.5117 | 1367852.5819 | 2 | WSP-LTR-000024 | 2022-08-17 | 2022-08-23 | 6 | 9198174.94 | 1622684.94 | -324536.988 | -162268.494 | 1135879.458 |  | 0 | 2022-09-28 | 2022-09-20 | -8 | 1135879.458 | 219062.4669 | 1354941.9249 | 10066755.4249
3 | IPA No. 03 | 2022-07-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 9268894.015 | -260671.102 | 52134.2204 | 26067.1102 | -182469.7714 | 3 | WSP-LTR-0033 | 2022-10-29 | 2022-11-15 | 17 | 9268894.01 | 70719.07 | -14143.814 | -7071.907 | 49503.349 |  |  | 2022-12-13 | 2022-12-13 | 0 | 49503.349 | 9547.0745 | 59050.4235 | 10125805.8483
4 | IPA No. 04 | 2022-08-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 9268894.015 | 0 | 0 | 0 | 0 | 4 | WSP-LTR-0034 | 2022-10-29 | 2022-11-15 | 17 | 9548631.86 | 279737.85 | -55947.57 | -27973.785 | 195816.495 |  |  | 2022-12-13 | 2022-12-13 | 0 | 195816.495 | 37764.6097 | 233581.1047 | 10359386.9531
5 | IPA No. 05 | 2022-09-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 9268894.015 | 0 | 0 | 0 | 0 | 5 | WSP-LTR-0035 | 2022-10-29 | 2022-11-15 | 17 | 9853125.27 | 304493.41 | -60898.682 | -30449.341 | 213145.387 |  |  | 2022-12-13 | 2022-12-13 | 0 | 213145.387 | 41106.6104 | 254251.9974 | 10613638.9504
6 | IPA No. 06 | 2022-10-01 | ITB04400-005C13-NSC-LTR-0155 | 2022-11-05 | 26848060.545 | 17579166.53 | -3515833.306 | -1757916.653 | 12305416.571 | 6 | WSP-LTR-0047 | 2022-12-07 | 2022-12-03 | -4 | 18085079.84 | 8231954.57 | -1646390.914 | -823195.457 | 5762368.199 | 0 | 0 | 2023-01-09 | 2022-12-31 | -9 | 5762368.199 | 1111313.8669 | 6873682.0659 | 17487321.0164
7 | IPA No. 07 | 2022-11-01 | 1TB04400-005C13-NSC-LTR-0175 | 2022-12-05 | 40631148.51 | 13783087.965 | -2756617.593 | -1378308.7965 | 9648161.5755 | 7 | WSP-LTR-0065 | 2023-01-04 | 2023-01-02 | -2 | 29991660.74 | 11906580.9 | -2261199.78 | -1190658.09 | 8454723.03 | AMA-WTRAN-001848 | 2023-01-22 | 2023-01-22 | 2023-01-30 | 8 | 8454723.03 | 1607388.4215 | 10062111.4515 | 27549432.4679
8 | IPA No. 08 | 2022-12-01 | 1TB04400-005C13-NSC-LTR-0214 | 2023-01-05 | 57009785.44 | 16378636.93 | -3275727.386 | -1637863.693 | 11465045.851 | 8 | 1TB04400-031D03-WSP-LTR-0076 | 2023-01-25 | 2023-02-02 | 8 | 46543956.19 | 16552295.45 | -3430575.49 | -1655229.545 | 11466490.415 |  |  | 2023-02-21 | 2023-03-02 | 9 | 11466490.415 | 2234559.8857 | 13701050.3007 | 41250482.7686
9 | IPA No. 09 | 2023-01-01 | 1TB04400-005C13-NSC-LTR-0249 | 2023-02-08 | 58873947.67 | 1864162.23 | -372832.446 | -186416.223 | 1304913.561 | 9 | WSP-LTR-0081 | 2023-02-20 | 2023-03-08 | 16 | 49452644.05 | 2908687.86 | -581737.572 | -290868.786 | 2036081.502 |  |  | 2023-03-22 | 2023-04-05 | 14 | 2036081.502 | 392672.8611 | 2428754.3631 | 43679237.1317
10 | IPA No. 010 | 2023-02-01 | 1TB04400-005C13-NSC-LTR-0276 | 2023-03-05 | 63540526.26 | 4666578.59 | -933315.718 | -466657.859 | 3266605.013 | 10 | 1TB04400-031D03-WSP-LTR-0095 | 2023-03-20 | 2023-04-02 | 13 | 50435282.39 | 982638.34 | -196527.668 | -98263.834 | 687846.838 |  |  | 2023-04-30 | 2023-04-30 | 0 | 687846.838 | 132656.1759 | 820503.0139 | 44499740.1456
11 | IPA No. 011 | 2023-03-23 | 1TB04400-005C13-NSC-LTR-0306 | 2023-04-06 | 64674977.66 | 1134451.4 | -226890.28 | -113445.14 | 794115.98 | 11 | WSP-LTR-0106 | 2023-05-06 | 2023-05-04 | -2 | 51463758.78 | 1028476.39 | -205695.278 | -102847.639 | 719933.473 |  |  | 2023-05-29 | 2023-06-01 | 3 | 719933.473 | 138844.3127 | 858777.7856 | 45358517.9313
12 | IPA No. 012 | 2023-04-23 | NSC-LTR-000328 | 2023-05-06 | 70880333.04 | 6205355.38 | -1241071.076 | -620535.538 | 4343748.766 | 12 | WSP-LTR-0113 | 2023-05-29 | 2023-06-03 | 5 | 51682823.49 | 219064.71 | -43812.942 | -21906.471 | 153345.297 |  |  | 2023-07-09 | 2023-07-01 | -8 | 153345.297 | 29573.7358 | 182919.0328 | 45541436.9641
13 | IPA No. 013 | 2023-05-23 | NSC-LTR-000345 | 2023-06-07 | 71531025.34 | 650692.3 | -130138.46 | -65069.23 | 455484.61 | 13 | WSP-LTR-0123 | 2023-07-13 | 2023-07-05 | -8 | 52385192.85 | 702369.36 | -140473.872 | -70236.936 | 491658.552 |  |  | 2023-08-09 | 2023-08-02 | -7 | 491658.552 | 94819.8636 | 586478.4156 | 46127915.3797
14 | IPA No. 014 | 2023-06-23 | NSC-LTR-000355 | 2023-07-08 | 72229636.65 | 698611.31 | -139722.262 | -69861.131 | 489027.917 | 14 | WSP04400-GENCORR-000389 | 2023-07-20 | 2023-08-05 | 16 | 53096886 | 711693.15 | 1386450.57 | -71169.315 | 2026974.405 |  |  | 2023-09-18 | 2023-09-02 | -16 | 2026974.405 | 96078.5752 | 2123052.9803 | 48250968.36
15 | IPA No. 015 | 2023-07-23 | NSC-LTR-000372 | 2023-08-09 | 72320513.05 | 90876.4 | -18175.28 | -9087.64 | 63613.48 | 15 | 1TB04400-031D03-WSP-LTR-0131 | 2023-09-07 | 2023-09-06 | -1 | 53187762.41 | 90876.41 | 949220.2 | -9087.641 | 1031008.969 |  |  | 2023-11-14 | 2023-10-04 | -41 | 1031008.969 | 12268.3153 | 1043277.2844 | 49294245.6443 | 280597.629
16 | IPA No. 016 | 2023-08-23 | NSC-LTR-0382 | 2023-09-10 | 72425611.89 | 105098.84 | 5848124.71 | 3231996.206 | 9185219.756 | 16 | 1TB04400-031D03-WSP-LTR-0133 | 2023-09-19 | 2023-10-08 | 19 | 53240316.92 | 52554.51 | -797710.4 | -5255.45 | -750411.34 |  |  | 2023-11-14 | 2023-11-05 | -9 | -750411.34 | 7094.859 | -743316.481 | 48550929.1633
17 | IPA No. 017 | Sep & Oct-23 | NSC-LTR-0394 | 2023-10-30 | 72373067.56 | -52544.33 | -474610.1 | 2627.219 | -524527.211 | 17 | 1TB04400-031D03-WSP-LTR-0141 | 2023-12-05 | 2023-11-27 | -8 | 53240316.92 | 0 | -151509.8 | 2283241.35 | 2131731.55 |  |  | 2023-12-25 | 2023-12-25 | 0 | 2131731.55 | 342486.2025 | 2474217.7525 | 51025146.9158
18 | IPA No. 018 | 2024-06-24 | 1TB04400-005C13-NSC-LTR-0402-0 | 2024-06-26 | 46942826.92 | 1278000 | 0 | -63900 | 1214100 | 18 | 1TB04400-400000-AMA-LTR-0053 | 2024-07-09 | 2024-07-24 | 15 | 54518316.92 | 1278000 | 0 | -63900 | 1214100 |  |  | 2024-09-18 | 2024-08-21 | -28 | 1214100 | 182115 | 1396215 | 52421361.9158
19 | IPA No. 019 | 2024-08-24 | 1TB04400-005C13-NSC-LTR-0405 | 2024-09-03 | 46942826.92 | 0 | 0 | 0 | 0 | 19 | 1TB04400-400000-AMA-LTR-0054 | 2024-09-16 | 2024-10-01 | 15 | 54518316.92 | 0 | 0 | 0 | 0 |  |  | 2024-10-31 | 2024-10-29 | -2 | 0 | 0 | 0 | 52421361.9158
20 | IPA No. 020 | 45589 | 1TB04400-005C13-NSC-LTR-0408 | 45579 | 52909590.98 | 5966764.06 | 0 | 2347141.35 | 8313905.41 | 20 | 1TB04400-400000-AMA-LTR-0057 | 45635 | 45607 | -28 | 60485080.98 | 5966764.06 | 0 | 2347141.35 | 8313905.41 |  |  | 45635 | 45635 | 0 | 8313905.41 | 1247085.8115 | 9560991.2215 | 61982353.1373
TOTAL (SAR) | [5 empty] | 79617831.62 | -7575490 | -956637.53 | 71085704.09 | TOTAL (SAR) | [5 empty] | 60485080.98 | -7575490 | 0.009 | 52909590.989 | TOTAL (SAR) |  |  |  |  | 52909590.989 | 9072762.1484 | 61982353.1373 | 61982353.1373
[29 empty] | 41098344.23 | 151509.799
PLOT TB - 04.2 MARINA AYC
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | NSCC Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | WSP Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (28days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | AMAALA ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (56days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 20% | 10% | SAR |  |  | Date | Cl. 14.6.1 | + / - | SAR | SAR | 20% | 10% | SAR |  | Date | Date | Cl.14.7(b)(i) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 28 | d = c- d | e | f | g = f * 10% | h = f * 10% | i = f + g + h |  |  | j | k = a + 56 | l = k - j | m = i | n = ( f + h ) * 15% | O = M + N
1 | IPA No. 01 Adv Pay | Advance Payment | NSC-LTR-000010 | 2022-04-26 | 3739706.8 | 3739706.8 | 0 | 0 | 3739706.8 | 1 | WSP-TRAN-000502 | 2022-05-17 | 2022-05-10 | -7 | 3739706.8 | 3739706.8 | 0 | 0 | 3739706.8 | AMA-WTRAN-000703 | 2021-06-12 | 2022-06-02 | 2022-05-10 | -23 | 3739706.8 | 560956.02 | 4300662.82 | 4300662.82 | 0.15
2 | IPA No. 02 | 2022-06-01 | NSC-GENCORR-000027 | 2022-07-26 | 4603684.82 | 863978.02 | -172795.604 | -86397.802 | 604784.614 | 2 | WSP-LTR-000024 | 2022-08-17 | 2022-08-23 | 6 | 4535307.39 | 795600.59 | -159120.118 | -79560.059 | 556920.413 | 0 |  | 2022-09-28 | 2022-09-20 | -8 | 556920.413 | 107406.0796 | 664326.4926 | 4964989.3126
3 | IPA No. 03 | 2022-07-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 4433747.711 | -169937.109 | 33987.4218 | 16993.7109 | -118955.9763 | 3 | WSP-LTR-0033 | 2022-10-29 | 2022-11-15 | 17 | 4433747.71 | -101559.68 | 20311.936 | 10155.968 | -71091.776 | 0 |  | 2022-12-13 | 2022-12-13 | 0 | -71091.776 | -13710.5568 | -84802.3328 | 4880186.9798
4 | IPA No. 04 | 2022-08-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 4433747.711 | 0 | 0 | 0 | 0 | 4 | WSP-LTR-0034 | 2022-10-29 | 2022-11-15 | 17 | 4820023.11 | 386275.4 | -77255.08 | -38627.54 | 270392.78 | 0 |  | 2022-12-13 | 2022-12-13 | 0 | 270392.78 | 52147.179 | 322539.959 | 5202726.9388
5 | IPA No. 05 | 2022-09-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 4433747.711 | 0 | 0 | 0 | 0 | 5 | WSP-LTR-0035 | 2022-10-29 | 2022-11-15 | 17 | 4945995.14 | 125972.03 | -25194.406 | -12597.203 | 88180.421 |  |  | 2022-12-13 | 2022-12-13 | 0 | 88180.421 | 17006.2241 | 105186.6451 | 5307913.5839
6 | IPA No. 06 | 2022-10-01 | ITB04400-005C13-NSC-LTR-0155 | 2022-11-05 | 7874061.529 | 3440313.818 | -688062.7636 | -344031.3818 | 2408219.6726 | 6 | WSP-LTR-0047 | 2022-12-07 | 2022-12-03 | -4 | 4992316.8 | 46321.66 | -9264.332 | -4632.166 | 32425.162 | 0 | 0 | 2023-01-09 | 2022-12-31 | -9 | 32425.162 | 6253.4241 | 38678.5861 | 5346592.17
7 | IPA No. 07 | 2022-11-01 | 1TB04400-005C13-NSC-LTR-0175 | 2022-12-05 | 8738729.48 | 864667.951 | -172933.5902 | -86466.7951 | 605267.5657 | 7 | WSP-LTR-0065 | 2023-01-04 | 2023-01-02 | -2 | 5010873.5 | 18556.7 | -3711.34 | -1855.67 | 12989.69 | AMA-WTRAN-001848 | 2023-01-22 | 2023-01-22 | 2023-01-30 | 8 | 12989.69 | 2505.1545 | 15494.8445 | 5362087.0145
8 | IPA No. 08 | 2022-12-01 | 1TB04400-005C13-NSC-LTR-0214 | 2023-01-05 | 15533627.13 | 6794897.65 | -1358979.53 | -679489.765 | 4756428.355 | 8 | 1TB04400-031D03-WSP-LTR-0076 | 2023-01-25 | 2023-02-02 | 8 | 5046199.81 | 35326.31 | -7065.262 | -3532.631 | 24728.417 |  |  | 2023-02-21 | 2023-03-02 | 9 | 24728.417 | 4769.0518 | 29497.4688 | 5391584.4834
9 | IPA No. 09 | 2023-01-01 | 1TB04400-005C13-NSC-LTR-0249 | 2023-02-08 | 19538516.75 | 4004889.62 | -800977.924 | -400488.962 | 2803422.734 | 9 | WSP-LTR-0081 | 2023-02-20 | 2023-03-08 | 16 | 9013675.2 | 3967475.39 | -793495.078 | -396747.539 | 2777232.773 |  |  | 2023-03-22 | 2023-04-05 | 14 | 2777232.773 | 535609.1776 | 3312841.9507 | 8704426.434
10 | IPA No. 010 | 2023-02-01 | 1TB04400-005C13-NSC-LTR-0276 | 2023-03-05 | 23912589.93 | 4374073.18 | -874814.636 | -437407.318 | 3061851.226 | 10 | 1TB04400-031D03-WSP-LTR-0095 | 2023-03-20 | 2023-04-02 | 13 | 16707321.85 | 7693646.65 | -1538729.33 | -769364.665 | 5385552.655 |  |  | 2023-04-30 | 2023-04-30 | 0 | 5385552.655 | 1038642.2978 | 6424194.9528 | 15128621.3868
11 | IPA No. 011 | 2023-03-23 | 1TB04400-005C13-NSC-LTR-0306 | 2023-04-06 | 24257369.89 | 344779.96 | -68955.992 | -34477.996 | 241345.972 | 11 | WSP-LTR-0106 | 2023-05-06 | 2023-05-04 | -2 | 17019819.92 | 312498.07 | -62499.614 | -31249.807 | 218748.649 |  |  | 2023-05-29 | 2023-06-01 | 3 | 218748.649 | 42187.2395 | 260935.8884 | 15389557.2752
12 | IPA No. 012 | 2023-04-23 | NSC-LTR-000328 | 2023-05-06 | 24978446.68 | 721076.79 | -144215.358 | -72107.679 | 504753.753 | 12 | WSP-LTR-0113 | 2023-05-29 | 2023-06-03 | 5 | 17707567.65 | 687747.73 | -137549.546 | -68774.773 | 481423.411 |  |  | 2023-07-09 | 2023-07-01 | -8 | 481423.411 | 92845.9435 | 574269.3546 | 15963826.6298
13 | IPA No. 013 | 2023-05-23 | NSC-LTR-000345 | 2023-06-07 | 25221720.36 | 243273.68 | -48654.736 | -24327.368 | 170291.576 | 13 | WSP-LTR-0123 | 2023-07-13 | 2023-07-05 | -8 | 17983112.4 | 275544.75 | -55108.95 | -27554.475 | 192881.325 |  |  | 2023-08-09 | 2023-08-02 | -7 | 192881.325 | 37198.5412 | 230079.8662 | 16193906.496
14 | IPA No. 014 | 2023-06-23 | NSC-LTR-000355 | 2023-07-08 | 25487459.36 | 265739 | -53147.8 | -26573.9 | 186017.3 | 14 | WSP04400-GENCORR-000389 | 2023-07-20 | 2023-08-05 | 16 | 17983112.4 | 0 | 0 | 0 | 0 |  |  | 2023-09-18 | 2023-09-02 | -16 | 0 | 0 | 0 | 16193906.496
15 | IPA No. 015 | 2023-07-23 | NSC-LTR-000372 | 2023-08-09 | 25502579.24 | 15119.88 | -3023.976 | -1511.988 | 10583.916 | 15 | 1TB04400-031D03-WSP-LTR-0131 | 2023-09-07 | 2023-09-06 | -1 | 18263971.28 | 280858.88 | -802422.08 | -28085.89 | -549649.09 |  |  | 2023-11-14 | 2023-10-04 | -41 | -549649.09 | 37915.9485 | -511733.1415 | 15682173.3545
16 | IPA No. 016 | 2023-08-23 | NSC-LTR-0382 | 2023-09-10 | 25502579.24 | 0 | 657169.488 | 1088143.62 | 1745313.108 | 16 | 1TB04400-031D03-WSP-LTR-0133 | 2023-09-19 | 2023-10-08 | 19 | 18263971.28 | 0 | -88603.6 | 0 | -88603.6 |  |  | 2023-11-14 | 2023-11-05 | -9 | -88603.6 | 0 | -88603.6 | 15593569.7545
17 | IPA No. 017 | Sep & Oct-23 | NSC-LTR-0394 | 2023-10-30 | 25502579.24 | 0 | -44301.8 | 0 | -44301.8 | 17 | 1TB04400-031D03-WSP-LTR-0141 | 2023-12-05 | 2023-11-27 | -8 | 18263971.28 | 0 | 0 | 726213.23 | 726213.23 |  |  | 2023-12-25 | 2023-12-25 | 0 | 726213.23 | 108931.9845 | 835145.2145 | 16428714.969
18 | IPA No. 018 | 2024-06-24 | 1TB04400-005C13-NSC-LTR-0402-0 | 2024-06-26 | 14907664.46 | 383400 | 0 | -19170 | 364230 | 18 | 1TB04400-400000-AMA-LTR-0053 | 2024-07-09 | 2024-07-24 | 15 | 18647371.28 | 383400 | 0 | -19170 | 364230 |  |  | 2024-09-18 | 2024-08-21 | -28 | 364230 | 54634.5 | 418864.5 | 16847579.469
19 | IPA No. 019 | 2024-08-24 | 1TB04400-005C13-NSC-LTR-0405 | 2024-09-03 | 14907664.46 | 0 | 0 | 0 | 0 | 19 | 1TB04400-400000-AMA-LTR-0054 | 2024-09-16 | 2024-10-01 | 15 | 18647371.28 | 0 | 0 | 0 | 0 |  |  | 2024-10-31 | 2024-10-29 | -2 | 0 | 0 | 0 | 16847579.469
20 | IPA No. 020 | 2024-10-24 | 1TB04400-005C13-NSC-LTR-0408 | 2024-10-14 | 16458381.51 | 1550717.05 | 0 | 745383.23 | 2296100.28 | 20 | 1TB04400-400000-AMA-LTR-0057 | 2024-12-09 | 2024-11-11 | -28 | 20198088.33 | 1550717.05 | 0 | 745383.23 | 2296100.28 |  |  | 2024-12-09 | 2024-12-09 | 0 | 2296100.28 | 344415.042 | 2640515.322 | 19488094.791 |  |  | 56
TOTAL (SAR) | [5 empty] | 27436696.29 | -3739706.8 | -361930.394 | 23335059.096 | TOTAL (SAR) | [5 empty] | 20198088.33 | -3739706.8 | 0.01 | 16458381.54 | TOTAL (SAR) |  |  |  |  | 16458381.54 | 3029713.251 | 19488094.791 | 19488094.791 | 700172.06 | 15963826.6298
13881588.3737
PLOT TB - 04.3 MARINA B&M
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | NSCC Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | WSP Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (28days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | AMAALA ACONEX REF FOR INV APPROVAL | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (56days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 20% | 10% | SAR |  |  | Date | Cl. 14.6.1 | + / - | SAR | SAR | 20% | 10% | SAR |  | Date | Date | Cl.14.7(b)(i) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 28 | d = c- d | e | f | g = f * 10% | h = f * 10% | i = f + g + h |  |  | j | k = a + 56 | l = k - j | m = i | n = ( f + h ) * 15% | O = M + N
1 | IPA No. 01 Adv Pay | Advance Payment | NSC-LTR-000010 | 2022-04-26 | 5912918 | 5912918 | 0 | 0 | 5912918 | 1 | WSP-TRAN-000502 | 2022-05-17 | 2022-05-10 | -7 | 5912918 | 5912918 | 0 | 0 | 5912918 | AMA-WTRAN-000703 | 2021-06-12 | 2022-06-02 | 2022-05-10 | -23 | 5912918 | 886937.7 | 6799855.7 | 6799855.7
2 | IPA No. 02 | 2022-06-01 | NSC-GENCORR-000027 | 2022-07-26 | 6766315.174 | 853397.174 | -170679.4348 | -85339.7174 | 597378.0218 | 2 | WSP-LTR-000024 | 2022-08-17 | 2022-08-23 | 6 | 6690473.56 | 777555.56 | -155511.112 | -77755.556 | 544288.892 | 0 |  | 2022-09-28 | 2022-09-20 | -8 | 544288.892 | 104970.0006 | 649258.8926 | 7449114.5926
3 | IPA No. 03 | 2022-07-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 7086253.398 | 319938.224 | -63987.6448 | -31993.8224 | 223956.7568 | 3 | WSP-LTR-0033 | 2022-10-29 | 2022-11-15 | 17 | 7086253.4 | 395779.84 | -79155.968 | -39577.984 | 277045.888 | 0 |  | 2022-12-13 | 2022-12-13 | 0 | 277045.888 | 53430.2784 | 330476.1664 | 7779590.759
4 | IPA No. 04 | 2022-08-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 7086253.398 | 0 | 0 | 0 | 0 | 4 | WSP-LTR-0034 | 2022-10-29 | 2022-11-15 | 17 | 7300583.21 | 214329.81 | -42865.962 | -21432.981 | 150030.867 | 0 |  | 2022-12-13 | 2022-12-13 | 0 | 150030.867 | 28934.5243 | 178965.3913 | 7958556.1503
5 | IPA No. 05 | 2022-09-01 | NSC-TRANSMIT-000067 | 2022-10-18 | 7086253.398 | 0 | 0 | 0 | 0 | 5 | WSP-LTR-0035 | 2022-10-29 | 2022-11-15 | 17 | 7533880.26 | 233297.05 | -46659.41 | -23329.705 | 163307.935 |  |  | 2022-12-13 | 2022-12-13 | 0 | 163307.935 | 31495.1017 | 194803.0367 | 8153359.1871
6 | IPA No. 06 | 2022-10-01 | ITB04400-005C13-NSC-LTR-0155 | 2022-11-05 | 9056026.919 | 1969773.521 | -393954.7042 | -196977.3521 | 1378841.4647 | 6 | WSP-LTR-0047 | 2022-12-07 | 2022-12-03 | -4 | 7569689.5 | 35809.24 | -7161.848 | -3580.924 | 25066.468 | 0 | 0 | 2023-01-09 | 2022-12-31 | -9 | 25066.468 | 4834.2474 | 29900.7154 | 8183259.9025
7 | IPA No. 07 | 2022-11-01 | 1TB04400-005C13-NSC-LTR-0175 | 2022-12-05 | 9292485.17 | 236458.251 | -47291.6502 | -23645.8251 | 165520.7757 | 7 | WSP-LTR-0065 | 2023-01-04 | 2023-01-02 | -2 | 7561238.73 | -8450.77 | 1690.154 | 845.077 | -5915.539 | AMA-WTRAN-001848 | 2023-01-22 | 2023-01-22 | 2023-01-30 | 8 | -5915.539 | -1140.8539 | -7056.3929 | 8176203.5096
8 | IPA No. 08 | 2022-12-01 | 1TB04400-005C13-NSC-LTR-0214 | 2023-01-05 | 11364136.02 | 2071650.85 | -414330.17 | -207165.085 | 1450155.595 | 8 | 1TB04400-031D03-WSP-LTR-0076 | 2023-01-25 | 2023-02-02 | 8 | 7579520.32 | 18281.59 | -3656.318 | -1828.159 | 12797.113 |  |  | 2023-02-21 | 2023-03-02 | 9 | 12797.113 | 2468.0147 | 15265.1277 | 8191468.6372
9 | IPA No. 09 | 2023-01-01 | 1TB04400-005C13-NSC-LTR-0249 | 2023-02-08 | 11548441.52 | 184305.5 | -36861.1 | -18430.55 | 129013.85 | 9 | WSP-LTR-0081 | 2023-02-20 | 2023-03-08 | 16 | 7701731.24 | 122210.92 | -24442.184 | -12221.092 | 85547.644 |  |  | 2023-03-22 | 2023-04-05 | 14 | 85547.644 | 16498.4742 | 102046.1182 | 8293514.7554
10 | IPA No. 010 | 2023-02-01 | 1TB04400-005C13-NSC-LTR-0276 | 2023-03-05 | 13641305.65 | 2092864.13 | -418572.826 | -209286.413 | 1465004.891 | 10 | 1TB04400-031D03-WSP-LTR-0095 | 2023-03-20 | 2023-04-02 | 13 | 7817104.55 | 115373.31 | -23074.662 | -11537.331 | 80761.317 |  |  | 2023-04-30 | 2023-04-30 | 0 | 80761.317 | 15575.3968 | 96336.7139 | 8389851.4693
11 | IPA No. 011 | 2023-03-23 | 1TB04400-005C13-NSC-LTR-0306 | 2023-04-06 | 13827184 | 185878.35 | -37175.67 | -18587.835 | 130114.845 | 11 | WSP-LTR-0106 | 2023-05-06 | 2023-05-04 | -2 | 7925640.25 | 108535.7 | -21707.14 | -10853.57 | 75974.99 |  |  | 2023-05-29 | 2023-06-01 | 3 | 75974.99 | 14652.3195 | 90627.3095 | 8480478.7788
12 | IPA No. 012 | 2023-04-23 | NSC-LTR-000328 | 2023-05-06 | 24441974.96 | 10614790.96 | -2122958.192 | -1061479.096 | 7430353.672 | 12 | WSP-LTR-0113 | 2023-05-29 | 2023-06-03 | 5 | 8027338.34 | 101698.09 | -20339.618 | -10169.809 | 71188.663 |  |  | 2023-07-09 | 2023-07-01 | -8 | 71188.663 | 13729.2421 | 84917.9052 | 8565396.6839
13 | IPA No. 013 | 2023-05-23 | NSC-LTR-000345 | 2023-06-07 | 36495906 | 12053931.04 | -2410786.208 | -1205393.104 | 8437751.728 | 13 | WSP-LTR-0123 | 2023-07-13 | 2023-07-05 | -8 | 19984642.87 | 11957304.53 | -2391460.916 | -1195730.453 | 8370113.161 |  |  | 2023-08-09 | 2023-08-02 | -7 | 8370113.161 | 1614236.1115 | 9984349.2725 | 18549745.9565
14 | IPA No. 014 | 2023-06-23 | NSC-LTR-000355 | 2023-07-08 | 45411121.79 | 8915215.79 | -1783043.158 | -891521.579 | 6240651.053 | 14 | WSP04400-GENCORR-000389 | 2023-07-20 | 2023-08-05 | 16 | 27256556.74 | 7271913.87 | 0 | -727191.387 | 6544722.483 |  |  | 2023-09-18 | 2023-09-02 | -16 | 6544722.483 | 981708.3724 | 7526430.8554 | 26076176.8119
15 | IPA No. 015 | 2023-07-23 | NSC-LTR-000372 | 2023-08-09 | 46237089.38 | 825967.59 | -165193.518 | -82596.759 | 578177.313 | 15 | 1TB04400-031D03-WSP-LTR-0131 | 2023-09-07 | 2023-09-06 | -1 | 29849670.46 | 2593113.72 | -2819922.09 | -259311.38 | -486119.75 |  |  | 2023-11-14 | 2023-10-04 | -41 | -486119.75 | 350070.351 | -136049.399 | 25940127.4129
16 | IPA No. 016 | 2023-08-23 | NSC-LTR-0382 | 2023-09-10 | 47155677.04 | 918587.66 | 2291241.746 | 1970279.184 | 5180108.59 | 16 | 1TB04400-031D03-WSP-LTR-0133 | 2023-09-19 | 2023-10-08 | 19 | 30768326.96 | 918656.5 | -183731.3 | -91865.65 | 643059.55 |  |  | 2023-11-14 | 2023-11-05 | -9 | 643059.55 | 124018.6275 | 767078.1775 | 26707205.5904
17 | IPA No. 017 | Sep & Oct-23 | NSC-LTR-0394 | 2023-10-30 | 47931426 | 775748.96 | -139325.47 | -38787.446 | 597636.044 | 17 | 1TB04400-031D03-WSP-LTR-0141 | 2023-12-05 | 2023-11-27 | -8 | 31568232.54 | 799905.58 | -94919.63 | 1202775.18 | 1907761.13 |  |  | 2023-12-25 | 2023-12-25 | 0 | 1907761.13 | 300402.114 | 2208163.244 | 28915368.8344
18 | IPA No. 018 | 2024-06-24 | 1TB04400-005C13-NSC-LTR-0402-0 | 2024-06-26 | 31734099.53 | 930750 | 0 | -46537.5 | 884212.5 | 18 | 1TB04400-400000-AMA-LTR-0053 | 2024-07-09 | 2024-07-24 | 15 | 32498982.54 | 930750 | 0 | -46537.5 | 884212.5 |  |  | 2024-09-18 | 2024-08-21 | -28 | 884212.5 | 132631.875 | 1016844.375 | 29932213.2094
19 | IPA No. 019 | 2024-08-24 | 1TB04400-005C13-NSC-LTR-0405 | 2024-09-03 | 31734099.53 | 5148035 | 0 | -257401.75 | 4890633.25 | 19 | 1TB04400-400000-AMA-LTR-0054 | 2024-09-16 | 2024-10-01 | 15 | 37647017.54 | 5148035 | 0 | -257401.75 | 4890633.25 |  |  | 2024-10-31 | 2024-10-29 | -2 | 4890633.25 | 733594.9875 | 5624228.2375 | 35556441.4469
20 | IPA No. 020 | 2024-10-24 | 1TB04400-005C13-NSC-LTR-0408 | 2024-10-14 | 34014498.11 | 2280398.58 | 0 | 1586704.98 | 3867103.56 | 20 | 1TB04400-400000-AMA-LTR-0057 | 2024-12-09 | 2024-11-11 | -28 | 39927416.12 | 2280398.58 | 0 | 1586704.98 | 3867103.56 |  |  | 2024-10-31 | 2024-12-09 | 39 | 3867103.56 | 580065.534 | 4447169.094 | 40003610.5409
TOTAL (SAR) | [5 empty] | 56290609.58 | -5912918 | -818159.67 | 49559531.91 | TOTAL (SAR) | [5 empty] | 39927416.12 | -5912918.004 | 0.006 | 34014498.122 | TOTAL (SAR) |  |  |  |  | 34014498.122 | 5989112.4189 | 40003610.5409 | 40003610.5409
[19 empty] | 16458381.53 | [10 empty] | 15269747.2111
[19 empty] | 22369868.06 | -11644630.062
[17 empty] | -2793572.17 | -1396786.085 | 13517209.395 | [5 empty] | 38664502.1505 | 7158940.71 | 15389557.2752
[19 empty] | 14913995.48 | [5 empty] | 24973123 | 9299440.83
[17 empty] | -2656022.624 | -1328011.312 | 13035785.984 | [5 empty] | -13691379.1505
14363797.296
18104219.694
22369868.06
38664502.1505
[25 empty] | 38664502.1505 | TOTAL Payment To Date
27545100.76
Formulas:
Payment Date as per Contract (56days) = +[Date Aconex Letter]+56
Issue date of IPC per Contract (28days) = [Date Aconex Letter]+28
Note on E41: Vaseef Shaikh: Orginal date = 3rd of July 2022 - NSC-LTR-000045
Note on E42: Blake Lombard: Original Date was dated 3 August 2022.
Note on E43: Blake Lombard: Original Date was dated 3 August 2022.
Note on E44: Blake Lombard: Original Date was dated 3 August 2022.
Note on E45: Blake Lombard: Original Date was dated 3 August 2022.

## Schedule H SAB
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
SAUDI ARABIAN BAYTUR (PO 2230023)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [10 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | Payment Held | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 10% | 10% | SAR |  |  | Date | Cl. 14.5.1 | + / - | SAR | SAR | 10% | 10% |  | SAR |  |  | Date | Date | Cl.14.6.1(b) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 10% | h = f * 10% | i | j = f + g + h + i |  | k |  | l | m = k + 30 | n = m - l | o = j | p = ( f + h + i ) * 15% | q = o + p
1 | IPA - 1 | Adv. Payment | AMA01003-PAYAP-000099 | 2023-06-07 | 26095541.44 | 26095541.44 | 0 | 0 | 26095541.44 | 1 | AMA01003-PC-000014 | 2023-06-07 | 2023-06-28 | 21 | 26095541.44 | 26095541.44 | 0 | 0 |  | 26095541.44 | SAB01003-RIA-000001 | 2023-06-08 |  | 2023-06-11 | 2023-07-08 | 27 | 26095541.44 | 3914331.216 | 30009872.656 | 30009872.656 | 30009872.656
2 | IPA - 2 | 2023-05-01 | Email | 2023-06-13 | 38315174.25 | 12219632.81 | -1221963.281 | -1221963.281 | 9775706.248 | 2 | 1TB01003-003C03-AMA-LTR-0036 | 2023-06-14 | 2023-07-04 | 20 | 33569822.16 | 7474280.72 | -747428.072 | -747428.072 |  | 5979424.576 | SAB01003-RIA-000002 | 2023-07-23 |  | 2023-08-03 | 2023-08-22 | 19 | 5979424.576 | 1009027.8972 | 6988452.4732 | 36998325.1292
3 | IPA - 3 | 2023-06-01 | SAB01003-GENCORR-000038 | 2023-06-22 | 41270325.75 | 2955151.5 | -295515.15 | -295515.15 | 2364121.2 | 3 | 1TB01003-003C03-AMA-LTR-0045 | 2023-07-20 | 2023-07-13 | -7 | 35160374.67 | 1590552.51 | -159055.251 | -159055.251 |  | 1272441.998 | SAB01003-RIA-000003 | 2023-07-29 |  | 2023-08-09 | 2023-08-28 | 19 | 1272441.998 | 214724.5888 | 1487166.5868 | 38485491.716
4 | IPA - 4 | 2023-07-01 | SAB01003-GENCORR-000041 | 2023-08-06 | 50285467.51 | 9015141.76 | -901514.176 | -901514.176 | 7212113.408 | 4 | 1TB01003-003C03-AMA-LTR-0053 | 2023-08-12 | 2023-08-27 | 15 | 42309969.56 | 7149594.89 | -714959.489 | -714959.489 |  | 5719675.902 | SAB01003-RIA-000004 | 2023-08-27 |  | 2023-08-30 | 2023-09-26 | 27 | 5719675.902 | 965195.3102 | 6684871.2122 | 45170362.9282
5 | IPA - 5 | 2023-08-01 | SAB01003-GENCORR-000046 | 2023-09-02 | 62828278.55 | 12542811.04 | -1254281.104 | -1254281.104 | 10034248.832 | 5 | 1TB01003-003C03-AMA-LTR-0065 | 2023-09-12 | 2023-09-23 | 11 | 57614561.45 | 15304591.89 | -1530459.189 | -1530459.189 |  | 12243673.502 | SAB01003-RIA-000005 | 2023-09-28 |  | 2023-10-08 | 2023-10-28 | 20 | 12243673.502 | 2066119.9052 | 14309793.4072 | 59480156.3353
6 | IPA - 6 | 2023-09-01 | SAB01003-GENCORR-000051 | 2023-10-01 | 71042424.66 | 8214146.11 | -821414.611 | -821414.611 | 6571316.888 | 5 | 1TB01003-003C03-AMA-LTR-0073 | 2023-10-05 | 2023-10-22 | 17 | 64715031.15 | 7100469.7 | -710046.97 | -710046.97 |  | 5680375.76 | SAB01003-RIA-000006 | 2023-10-14 |  | 2023-10-22 | 2023-11-13 | 22 | 5680375.76 | 958563.4095 | 6638939.1695 | 66119095.5049
7 | IPA - 7 | Long Lead Items | SAB01003-GENCORR-000052 | 2023-10-28 | 116136343.69 | 45093919.03 | 0 | 0 | 45093919.03 | 7 | 1TB01003-003C03-AMA-LTR-0081 | 2023-11-01 | 2023-11-18 | 17 | 109808950.18 | 45093919.03 | 0 | 0 |  | 45093919.03 | SAB01003-RIA-000007 | 2023-11-12 |  | 2023-11-14 | 2023-12-12 | 28 | 45093919.03 | 6764087.8545 | 51858006.8845 | 117977102.3893 | 48171310.414
8 | IPA - 8 | 2023-10-01 | SAB01003-GENCORR-000053 | 2023-11-01 | 121868879.47 | 5732535.78 | -573253.578 | -573253.578 | 4586028.624 | 8 | 1TB01003-003C03-AMA-LTR-0085 | 2023-11-15 | 2023-11-22 | 7 | 113655689.41 | 3846739.23 | -384673.923 | -384673.923 |  | 3077391.384 | SAB01003-RIA-000008 | 2023-11-23 |  | 2023-12-04 | 2023-12-23 | 19 | 3077391.384 | 519309.7961 | 3596701.1801 | 121573803.5694
9 | IPA - 9 | 2023-11-01 | SAB01003-GENCORR-000059 | 2023-12-03 | 130186103.4919 | 8317224.0219 | -831722.4022 | -831722.4022 | 6653779.2175 | 9 | 1TB01003-003C03-AMA-LTR-0098 | 2023-12-13 | 2023-12-24 | 11 | 119250983.335 | 5595293.925 | -559529.4 | -559529.4 | -535936.5 | 3940298.625 | SAB01003-RIA-000009 | 2023-12-20 |  | 2024-01-22 | 2024-01-19 | -3 | 3940298.625 | 674974.2037 | 4615272.8287 | 126189076.3981
10 | IPA - 10 | 2023-12-01 | SAB01003-GENCORR-000063 | 2024-01-01 | 135913528.4369 | 5727424.945 | -572742.49 | -572742.49 | 4581939.965 | 10 | 1TB01003-003C03-AMA-LTR-0117 | 2024-01-24 | 2024-01-22 | -2 | 122356423.945 | 3105440.61 | -310544.06 | -310544.06 |  | 2484352.49 | SAB01003-RIA-000010 | 2024-02-04 |  | 2024-02-14 | 2024-03-05 | 20 | 2484352.49 | 419234.4825 | 2903586.9725 | 129092663.3706
11 | IPA - 11 | 2024-01-01 | SAB01003-GENCORR-000068 | 2024-02-01 | 142624045.7027 | 6710517.2658 | -671051.7266 | -671051.7266 | 5368413.8126 | 11 | 1TB01003-003C03-AMA-LTR-0136 | 2024-02-24 | 2024-02-22 | -2 | 125881687.595 | 3525263.65 | -352526.36 | -352526.36 |  | 2820210.93 | SAB01003-RIA-000011 | 2024-03-06 |  | 2024-03-14 | 2024-04-05 | 22 | 2820210.93 | 475910.5935 | 3296121.5235 | 132388784.8941
12 | IPA - 12 | 2024-02-01 | SAB01003-GENCORR-000076 | 2024-03-03 | 152735805.1927 | 10111759.49 | -1011175.95 | -1011175.95 | 8089407.59 | 12 | 1TB01003-003C03-AMA-LTR-0143 | 2024-03-16 | 2024-03-24 | 8 | 132104439.925 | 6222752.33 | -622275.24 | -622275.24 |  | 4978201.85 | SAB01003-RIA-000012 | 2024-03-24 |  | 2024-03-27 | 2024-04-23 | 27 | 4978201.85 | 840071.5635 | 5818273.4135 | 138207058.3076
13 | IPA - 13 | Payment to Specialist Contractors (SAMIF & MEDTEL) | 1TB01003-003C03-SAB-LTR-0106 | 2024-07-22 | 159440948.6727 | 6705143.48 | 0 | 0 | 6705143.48 | 13 | 1TB01003-003C03-AMA-LTR-0183 | 2024-07-22 | 2024-08-12 | 21 | 138809583.405 | 6705143.48 | 0 | 0 |  | 6705143.48 | SAB01003-RIA-000013 | 2024-07-29 |  | 2024-07-31 | 2024-08-28 | 28 | 6705143.48 | 1005771.522 | 7710915.002 | 145917973.3097
14 | IPA - 14 | On Account Payment | SAB01003-GENCORR-000103 | 2024-07-25 | 186428169.9127 | 26987221.24 | 0 | 0 | 26987221.24 | 14 | 1TB01003-003C03-AMA-LTR-0188 | 2024-07-25 | 2024-08-15 | 21 | 165796804.645 | 26987221.24 | 0 | 0 |  | 26987221.24 | SAB01003-RIA-000014 | 2024-07-30 |  | 2024-07-31 | 2024-08-29 | 29 | 26987221.24 | 4048083.186 | 31035304.426 | 176953277.7357
15 | IPA - 15 | On Account Payment | SAB01003-GENCORR-000118 | 2024-08-19 | 223936215.9427 | 37508046.03 | 0 | 0 | 37508046.03 | 15 | 1TB01003-003C03-AMA-LTR-0215 | 2024-09-02 | 2024-09-09 | 7 | 203304850.675 | 37508046.03 | 0 | 0 |  | 37508046.03 | SAB01003-RIA-000015 | 2024-09-19 |  | 2024-09-26 | 2024-10-19 | 23 | 37508046.03 | 5626206.9045 | 43134252.9345 | 220087530.6702
16 | IPA - 16 | 2024-10-24 | SAB01003-GENCORR-000118 | 2024-10-17 | 290395321.7627 | 66459105.82 | -6645910.58 | -6645910.58 | 53167284.66 | 16 | 1TB01003-003C03-AMA-LTR-0242 | 2024-12-24 | 2024-11-07 | -47 | 220061073.605 | 16756222.93 | -6276926.07 | -6276926.07 |  | 4202370.79 | SAB01003-RIA-000015 | 2025-01-04 |  | 2025-01-15 | 2025-02-03 | 19 | 4202370.79 | 1571894.529 | 5774265.319 | 225861795.9892
17 | IPA - 17 | 2024-12-24 | SAB01003-GENCORR-000437 | 2025-01-19 | 308187474.8227 | 17792153.06 | -2165698.57 | -2165698.57 | 13460755.92 | 17 | 1TB01003-003C03-AMA-LTR-0261 | 2025-01-20 | 2025-02-09 | 20 | 237853226.665 | 17792153.06 | -2165698.57 | -2165698.57 |  | 13460755.92 | SAB01003-RIA-000017 | 2025-01-26 |  | 2025-01-28 | 2025-02-25 | 28 | 13460755.92 | 2343968.1735 | 15804724.0935 | 241666520.0827
TOTAL (SAR) | [5 empty] | 308187474.8227 | -16966243.6188 | -16966243.6188 | 274254987.5851 | TOTAL (SAR) | [5 empty] | 237853226.665 | -14534122.594 | -14534122.594 | -535936.5 | 208249044.947 | TOTAL (SAR) | [5 empty] | 208249044.947 | 33417475.1357 | 241666520.0827 | 241666520.0827
[21 empty] | TOTAL PAYMENT: | [5 empty] | 208249044.947
Less:
[21 empty] | Encashed Performance Bond: | [5 empty] | -26095541.44
[21 empty] | Encashed Advance Bond: | [5 empty] | -11561418.85
[21 empty] | NET PAYMENT MADE: | [5 empty] | 170592084.657
-37656960.29
222783167.541
0.036364
|  |  |  | 2021-01-01 | [11 empty] | 109808950.18 | [8 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [20 empty] | 2020-08-06
2020-06-04
Cashflow
[27 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21days) = [Date Aconex Letter]+21
Payment Date as per Contract (30days) = +[INVOICE DATE]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H Medtel
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
MEDTEL (PO 2230075)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 10% | 10% | SAR |  |  | Date | No Provision | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.11.4.1 | + / - |  | -5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 0% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = ( f + h ) * -5% (Installation) | P = N + O
1 | IPA - 1 | 2023-08-23 | AMA01003-PAYAP-000156 | 2023-09-10 | 819298.55 | 819298.55 | 0 | 0 | 819298.55 | 1 | AMA01003-PC-000029 | 2023-09-25 | 2023-10-01 | 6 | 819298.55 | 819298.55 | 0 | 0 | 819298.55 | MWW01003-RIA-000002 | 2023-10-09 |  | 2023-11-06 | 2023-11-08 | 2 | 819298.55 | -15605.82 | 803692.73 | 803692.73 | 942193.3325
TOTAL (SAR) | [5 empty] | 819298.55 | 0 | 0 | 819298.55 | TOTAL (SAR) | [5 empty] | 819298.55 | 0 | 0 | 819298.55 | TOTAL (SAR) | [5 empty] | 819298.55 | -15605.82 | 803692.73 | 803692.73
819298.55
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract = [Date Aconex Letter]+21
Payment Date as per Contract (30days) = +[INVOICE DATE]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H ESCCO
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
ESCCO (PO 2230178)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [10 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | Payment Held | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 30% | 10% | SAR |  |  | Date | No Provision | + / - | SAR | SAR | 30% | 10% |  | SAR |  |  | Date | Date | Cl.11.4.1 | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 10% | h = f * 10% | i | j = f + g + h + i |  | k |  | l | m = k + 30 | n = m - l | o = j | p = ( f + h + i ) * 15% | q = o + p
1 | IPA - 1 | Adv. Payment | AMA01003-PAYAP-000219 | 2023-12-14 | 685941.9 | 685941.9 | 0 | 0 | 685941.9 | 1 | AMA01003-PC-000038 | 2023-12-17 | 2024-01-04 | 18 | 685941.9 | 685941.9 | 0 | 0 |  | 685941.9 | ESC01003-RIA-000001 | 2023-12-17 |  | 2023-12-21 | 2024-01-16 | 26 | 685941.9 | 102891.285 | 788833.185 | 788833.185 | 788833.185
2 | IPA - 2 | 2024-09-24 | ESC01003-GENCORR-000007 | 2024-10-09 | 1177229.8 | 491287.9 | -147386.37 | -49128.79 | 294772.74 | 2 | 1TB01003-003F03-AMA-LTR-0022 | 2024-10-17 | 2024-10-30 | 13 | 1177229.8 | 491287.9 | -147386.37 | -49128.79 |  | 294772.74 | ESC01003-RIA-000002 | 2024-10-21 |  | 2024-10-31 | 2024-11-20 | 20 | 294772.74 | 44215.911 | 338988.651 | 1127821.836
3 | IPA - 3 | 2024-10-24 | ESC01003-GENCORR-000013 | 2024-11-17 | 1991193.79 | 813963.99 | -244189.2 | -81396.4 | 488378.39 | 3 | 1TB01003-003F03-AMA-LTR-0024 | 2024-11-21 | 2024-12-08 | 17 | 1977860.19 | 800630.39 | -240189.12 | -80063.04 |  | 480378.23 | ESC01003-RIA-000003 | 2024-12-05 |  | 2024-12-18 | 2025-01-04 | 17 | 480378.23 | 72056.7345 | 552434.9645 | 1680256.8005
4 | IPA - 4 | 2025-01-01 | ESC01003-GENCORR-000016 | 2025-01-16 | 2175832.41 | 184638.62 | -55391.59 | -18463.86 | 110783.17 | 4 | 1TB01003-003F03-AMA-LTR-0032 | 2025-03-18 | 2025-02-06 | -40 | 2162498.81 | 184638.62 | -55391.59 | -18463.86 |  | 110783.17 | ESC01003-RIA-000004 | 2025-04-23 |  | 2025-06-03 | 2025-05-23 | -11 | 110783.17 | 16617.4755 | 127400.6455 | 1807657.446
5 | IPA - 5 | 2025-09-01 | ESC01003-GENCORR-000028 | 2025-09-25 | 2488723.51 | 312891.1 | -93867.33 | -31289.11 | 187734.66 | 5 | 1TB01003-003F03-AMA-LTR-0039 | 2025-09-29 | 2025-10-16 | 17 | 2475389.91 | 312891.1 | -93867.33 | -31289.11 |  | 187734.66 | ESC01003-RIA-000006 | 2025-10-05 |  |  | 2025-11-04 |  | 187734.66 | 28160.199 | 215894.859 | 2023552.305
6 | IPA - 6 | 2025-11-01 | ESC01003-GENCORR-000030 | 2025-12-02 | 2605384.36 | 116660.85 | -34998.26 | -11666.09 | 69996.5 | 6 | 1TB01003-003F03-AMA-LTR-0040 | 2025-12-15 | 2025-12-23 | 8 | 2592050.76 | 116660.85 | -34998.26 | -11666.09 |  | 69996.5 | ESC01003-RIA-000007 | 2025-10-09 |  |  | 2025-11-08 |  | 69996.5 | 10499.475 | 80495.975 | 2104048.28
7 | IPA - 7 | 2025-12-01 | ESC01003-GENCORR-000032 | 2026-01-19 | 2692609.76 | 87225.4 | -26167.62 | -8722.54 | 52335.24 | 7 | 1TB01003-003F03-AMA-LTR-0042 | 2026-01-29 | 2026-02-09 | 11 | 2679276.16 | 87225.4 | -26167.62 | -8722.54 |  | 52335.24 | ESC01003-RIA-000009 | 2026-02-09 |  |  | 2026-03-11 |  | 52335.24 | 7850.286 | 60185.526 | 2164233.806 | 60185.526
8 | IPA - 8 | 2026-02-01 | ESC01003-GENCORR-000035 | 2026-03-31 | 2901872.92 | 209263.16 | -87941.62 | -20926.316 | 100395.224 | 8 | 1TB01003-003F03-AMA-LTR-0047 | 2026-04-05 | 2026-04-21 | 16 | 2888539.32 | 209263.16 | -87941.62 | -20926.316 |  | 100395.224 | ESC01003-RIA-000010 | 2026-05-14 |  |  | 2026-06-13
TOTAL (SAR) | [5 empty] | 2901872.92 | -689941.99 | -221593.106 | 1990337.824 | TOTAL (SAR) | [5 empty] | 2888539.32 | -685941.91 | -220259.746 |  | 1982337.664 | TOTAL (SAR) | [5 empty] | 1881942.44 | 282291.366 | 2164233.806 | 1807657.446
2202597.41
0.036364
|  |  |  | 2021-01-01 | [11 empty] | 2679276.16 | [8 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [20 empty] | 2020-08-06
2020-06-04
Cashflow
[27 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract = [Date Aconex Letter]+21
Payment Date as per Contract (30days) = +[INVOICE DATE]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H RAQTAN
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
RAQTAN (PO 2230205)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [10 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | Payment Held | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 35% | 10% | SAR |  |  | Date | Cl. 14.5.1 | + / - | SAR | SAR | 35% | 10% |  | SAR |  |  | Date | Date | Cl.14.6.1(b) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 10% | h = f * 10% | i | j = f + g + h + i |  | k |  | l | m = k + 30 | n = m - l | o = j | p = ( f + h + i ) * 15% | q = o + p
1 | IPA - 1 | Adv. Payment | AMA01003-PAYAP-000190 | 2023-11-01 | 1643323.15 | 1643323.15 | 0 | 0 | 1643323.15 | 1 | AMA01003-PC-000035 | 2023-11-08 | 2023-11-22 | 14 | 1643323.15 | 1643323.15 | 0 | 0 |  | 1643323.15 | Tax Invoice SIN_00657 | 2023-11-16 |  | 2023-11-16 | 2023-12-16 | 30 | 1643323.15 | 246498.4725 | 1889821.6225 | 1889821.6225 | 1889821.6225
2 | IPA - 2 | 2024-04-01 | RQN01003-GENCORR-000011 | 2024-05-15 | 2326387.15 | 683064 | -239072.4 | -68306.4 | 375685.2 | 2 | 1TB01003-003C08-AMA-LTR-0015 | 2024-06-03 | 2024-06-05 | 2 | 2326387.15 | 683064 | -239072.4 | -68306.4 |  | 375685.2 | RQN01003-RIA-000003 | 2024-07-17 |  | 2024-07-31 | 2024-08-16 | 16 | 375685.2 | 92213.64 | 467898.84 | 2357720.4625
3 | IPA - 3 | 2024-06-01 | RQN01003-GENCORR-000014 | 2024-07-14 | 6048086.35 | 3721699.2 | -1302594.72 | -279680.7 | 2139423.78 | 3 | 1TB01003-003C08-AMA-LTR-0018 | 2024-07-24 | 2024-08-04 | 11 | 3256186.95 | 929799.8 | -325429.93 | -92979.98 |  | 511389.89 | RQN01003-RIA-000004 | 2024-08-08 |  | 2024-08-19 | 2024-09-07 | 19 | 511389.89 | 125522.973 | 636912.863 | 2994633.3255
4 | IPA - 4 | 2024-08-24 | RQN01003-GENCORR-000018 | 2024-09-10 | 6112478.35 | 64392 | -22537.2 | -6439.2 | 35415.6 | 4 | 1TB01003-003C08-AMA-LTR-0023 | 2024-09-29 | 2024-10-01 | 2 | 3320578.95 | 64392 | -22537.2 | -6439.2 |  | 35415.6 | RQN01003-RIA-000005 | 2024-11-20 |  | 2024-11-28 | 2024-12-20 | 22 | 35415.6 | 8692.92 | 44108.52 | 3038741.8455
5 | IPA - 5 | 2024-11-01 | RQN01003-GENCORR-000023 | 2024-11-28 | 6467355.88 | 354877.53 | -124207.14 | -35487.75 | 195182.64 | 5 | 1TB01003-003C08-AMA-LTR-0026 | 2024-12-15 | 2024-12-19 | 4 | 3685820.55 | 365241.6 | -127834.56 | -36524.16 |  | 200882.88 | RQN01003-RIA-000006 | 2025-01-12 |  | 2025-01-26 | 2025-02-11 | 16 | 200882.88 | 49307.616 | 250190.496 | 3288932.3415
6 | IPA - 6 | 2025-05-01 | RQN01003-GENCORR-000034 | 2025-05-15 | 7048173.88 | 580818 | -203286.3 | -58081.8 | 319449.9 | 6 | 1TB01003-003C08-AMA-LTR-0034 | 2025-06-10 | 2025-06-05 | -5 | 4040925.15 | 355104.6 | -124286.61 | -35510.46 |  | 195307.53 | RQN01003-RIA-000007 | 2025-06-18 |  | 2025-07-20 | 2025-07-18 | -2 | 195307.53 | 47939.121 | 243246.651 | 3532178.9925
7 | IPA - 7 | 2025-09-25 | RQN01003-GENCORR-000038 | 2025-09-28 | 7560532.88 | 512359 | -179325.65 | -51235.9 | 281797.45 | 7 | 1TB01003-003C08-AMA-LTR-0038 | 2025-09-30 | 2025-10-19 | 19 | 4553284.15 | 512359 | -179325.65 | -51235.9 |  | 281797.45 | RQN01003-RIA-000008 | 2025-10-09 |  |  | 2025-11-08 |  | 281797.45 | 69168.465 | 350965.915 | 3883144.9075
8 | IPA - 8 | 2025-10-01 | RQN01003-GENCORR-000041 | 2025-11-05 | 8374306.83 | 813773.95 | -284820.88 | -81377.4 | 447575.67 | 8 | 1TB01003-003C08-AMA-LTR-0040 | 2025-11-18 | 2025-11-26 | 8 | 5367058.1 | 813773.95 | -284820.88 | -81377.4 |  | 447575.67 | RQN01003-RIA-000009 | 2025-11-30 |  |  | 2025-12-30 |  | 447575.67 | 109859.4825 | 557435.1525 | 4440580.06
9 | IPA - 9 | 2025-11-01 | RQN01003-GENCORR-000042 | 2025-11-26 | 8899552.43 | 525245.6 | -183835.96 | -52524.56 | 288885.08 | 9 | 1TB01003-003C08-AMA-LTR-0042 | 2025-12-15 | 2025-12-17 | 2 | 5817551 | 450492.9 | -340015.92 | -45049.29 |  | 65427.69 | RQN01003-RIA-000010 | 2025-12-24 |  |  | 2026-01-23 |  | 65427.69 | 60816.5415 | 126244.2315 | 4566824.2915
10 | IPA - 10 | 2025-12-01 | RQN01003-GENCORR-000044 | 2025-12-29 | 9371719.78 | 472167.35 |  | -47216.735 | 424950.615 | 10 | 1TB01003-003C08-AMA-LTR-0043 | 2026-01-24 | 2026-01-19 | -5 | 5907264.6 | 89713.6 |  | -8971.36 |  | 80742.24
TOTAL (SAR) | [5 empty] | 9371719.78 | -2539680.25 | -680350.445 | 6151689.085 | TOTAL (SAR) | [5 empty] | 5907264.6 | -1643323.15 | -426394.15 |  | 3837547.3 | TOTAL (SAR) | [5 empty] | 3756805.06 | 810019.2315 | 4566824.2915 | 3532178.9925
4263941.45
0.036364
|  |  |  | 2021-01-01 | [11 empty] | 4553284.15 | [8 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [20 empty] | 2020-08-06
2020-06-04
Cashflow
[27 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21days) = [Date Aconex Letter]+21
Payment Date as per Contract (30days) = +[INVOICE DATE]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H DEPA
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
CN.003C09 - DEPA Interior Fitout
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (14days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | N/A | 15% | SAR |  |  | Date | Cl. 14.5.1 | + / - | SAR | SAR | N/A | 15% | SAR |  |  | Date | Date | Cl.14.6.1(b) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 14 | d = c- d | e | f | g = N//A | h = f * 10% | j = f + g + h + i |  | k |  | l | m = k + 30 | n = m - l | o = j | p = ( o - i ) * 15% | q = o + p
1 | IPA - 1 | 2024-03-01 | DCC01003-GENCORR-000002 | 2024-04-04 | 10908108.55 | 10908108.55 | 0 | -1636216.2825 | 9271892.2675 | 1 | 1TB01003-003C09-AMA-LTR-0034 | 2024-04-21 | 2024-04-18 | -3 | 10489133.3 | 10489133.3 | 0 | -1573369.995 | 8915763.305 | DCC01003-RIA-000001 | 2024-05-12 |  | 2024-05-19 | 2024-06-11 | 23 | 8915763.305 | 1573369.995 | 10489133.3 | 10489133.3 | 10253127.8007 | -236005.4992
2 | IPA - 2 | 2024-04-01 | DCC01003-GENCORR-000022 | 2024-05-15 | 15374838.19 | 4466729.64 | 0 | -670009.446 | 3796720.194 | 2 | 1TB01003-003C09-AMA-LTR-0042 | 2024-05-19 | 2024-05-29 | 10 | 14349533.34 | 3860400.04 | 0 | -579060.006 | 3281340.034 | DCC01003-RIA-000002 | 2024-06-10 |  | 2024-06-13 | 2024-07-10 | 27 | 3281340.034 | 579060.006 | 3860400.04 | 14349533.34 |  | 1809375.4942
3 | IPA - 3 | 2024-05-01 | DCC01003-GENCORR-000150 | 2024-06-26 | 18992642.1 | 3617803.91 | 0 | -542670.5865 | 3075133.3235 | 3 | 1TB01003-003C09-AMA-LTR-0050 | 2024-06-30 | 2024-07-10 | 10 | 16969455.1 | 2619921.76 | 0 | -392988.264 | 2226933.496 | DCC01003-RIA-000003 | 2024-07-16 |  | 2024-07-17 | 2024-08-15 | 29 | 2226933.496 | 392988.264 | 2619921.76 | 16969455.1
4 | IPA - 4 | 2024-06-01 | DCC01003-GENCORR-000239 | 2024-08-08 | 20887242.09 | 1894599.99 | 0 | -284190 | 1610409.99 | 4 | 1TB01003-003C09-AMA-LTR-0061 | 2024-08-12 | 2024-08-22 | 10 | 17872001.51 | 902546.41 | 0 | -135381.9615 | 767164.4485 | DCC01003-RIA-000004 | 2024-09-09 |  | 2024-09-21 | 2024-10-09 | 18 | 767164.4485 | 135381.9615 | 902546.41 | 17872001.51
5 | IPA - 5 | 2024-07-01 | DCC01003-GENCORR-000267 | 2024-08-19 | 23051395.3 | 2164153.21 | 0 | -324622.98 | 1839530.23 | 5 | 1TB01003-003C09-AMA-LTR-0064 | 2024-09-07 | 2024-09-02 | -5 | 18998753.37 | 1126751.86 | 0 | -169012.779 | 957739.081 | DCC01003-RIA-000006 | 2024-10-02 |  | 2024-10-17 | 2024-11-01 | 15 | 957739.081 | 169012.779 | 1126751.86 | 18998753.37
6 | IPA - 6 | 2024-08-01 | DCC01003-GENCORR-000313 | 2024-10-05 | 25137103.02 | 2085707.72 | 0 | -324622.98 | 1761084.74 | 5 | 1TB01003-003C09-AMA-LTR-0084. | 2024-10-10 | 2024-10-19 | 9 | 19813375.38 | 814622.01 | 0 | -122193.3 | 692428.71 | DCC01003-RIA-000007 | 2024-10-22 |  | 2024-10-31 | 2024-11-21 | 21 | 692428.71 | 122193.3015 | 814622.0115 | 19813375.3815
7 | IPA - 7 | 2024-09-01 | DCC01003-GENCORR-000320 | 2024-10-09 | 28959575.37 | 3822472.35 | 0 | -573370.85 | 3249101.5 | 7 | 1TB01003-003C09-AMA-LTR-0085. | 2024-10-13 | 2024-10-23 | 10 | 22167964.91 | 2354589.53 | 0 | -353188.43 | 2001401.1 | DCC01003-RIA-000008 | 2024-10-22 |  | 2024-11-18 | 2024-11-21 | 3 | 2001401.1 | 353188.4295 | 2354589.5295 | 22167964.911
8 | IPA - 8 | 2024-10-24 | DCC01003-GENCORR-000380 | 2024-10-31 | 31718113.4 | 2758538.03 | 0 | -413780.7 | 2344757.33 | 8 | 1TB01003-003C09-AMA-LTR-0091 | 2024-11-07 | 2024-11-14 | 7 | 24069232.4 | 1901267.49 | 0 | -285190.12 | 1616077.37 | DCC01003-RIA-000009 | 2024-11-20 |  | 2024-12-09 | 2024-12-20 | 11 | 1616077.37 | 285190.1235 | 1901267.4935 | 24069232.4045
9 | IPA - 9 | 2024-11-24 | DCC01003-GENCORR-000452 | 2024-12-01 | 36005151.8 | 4287038.4 | 0 | -643055.76 | 3643982.64 | 9 | TB01003-003C09-AMA-LTR-0099 |  | 2024-12-15 |  | 27462520.91 | 3393288.51 | 0 | -508993.28 | 2884295.23 | DCC01003-RIA-000010 | 2025-01-05 |  | 2025-01-26 | 2025-02-04 | 9 | 2884295.23 | 508993.2765 | 3393288.5065 | 27462520.911
10 | IPA - 10 | 2024-12-01 | DCC01003-GENCORR-000540 | 2025-01-01 | 41682277.31 | 5677125.51 | 0 | -851568.83 | 4825556.68 | 10 | 1TB01003-003C09-AMA-LTR-0106 | 2025-01-27 | 2025-01-15 | -12 | 31809208.84 | 4346687.93 | 0 | -652003.19 | 3694684.74 | DCC01003-RIA-000011 | 2025-02-05 |  | 2025-03-26 | 2025-03-07 | -19 | 3694684.74 | 652003.1895 | 4346687.9295 | 31809208.8405
11 | IPA - 11 | 2025-01-01 | DCC01003-GENCORR-000605 | 2025-02-02 | 46805429.95 | 5123152.64 | 0 | -768472.9 | 4354679.74 | 11 | 1TB01003-003C09-AMA-LTR-0116 | 2025-03-03 | 2025-02-16 | -15 | 35734472.99 | 3925264.15 | 0 | -588789.62 | 3336474.53 | DCC01003-RIA-000012 | 2025-03-26 |  | 2025-05-12 | 2025-04-25 | -17 | 3336474.53 | 588789.6225 | 3925264.1525 | 35734472.993
12 | IPA - 12 | 2025-02-01 | DCC01003-GENCORR-000609 | 2025-03-02 | 52100744.19 | 5295314.24 | 0 | -794297.14 | 4501017.1 | 12 | 1TB01003-003C09-AMA-LTR-0118 | 2025-03-18 | 2025-03-16 | -2 | 39724769.64 | 3990296.65 | 0 | -598544.5 | 3391752.15 | DCC01003-RIA-000013 | 2025-04-06 |  | 2025-05-12 | 2025-05-06 | -6 | 3391752.15 | 598544.4975 | 3990296.6475 | 39724769.6405
13 | IPA-13 | 2025-03-01 | DCC01003-GENCORR-000699 | 2025-04-03 | 57873035.19 | 5772291 | 0 | -865843.65 | 4906447.35 | 13 | 1TB01003-003C09-AMA-LTR-0125 | 2025-04-17 | 2025-04-17 | 0 | 43795076.76 | 4070307.12 | 0 | -610546.07 | 3459761.05 | DCC01003-RIA-000014 | 2025-06-26 |  | 2025-07-08 | 2025-07-26 | 18 | 3459761.05 | 610546.068 | 4070307.118 | 43795076.7585
14 | IPA-14 | 2025-04-01 | DCC01003-GENCORR-000767 | 2025-05-03 | 61951557.71 | 4078522.52 | 0 | -611778.38 | 3466744.14 | 14 | 1TB01003-003C09-AMA-LTR-0135 | 2025-06-10 | 2025-05-17 | -24 | 45880271.12 | 2085194.36 | 0 | -312779.15 | 1772415.21 | DCC01003-RIA-000015 | 2025-07-01 |  | 2025-07-20 | 2025-07-31 | 11 | 1772415.21 | 312779.154 | 2085194.364 | 45880271.1225
15 | IPA-15 | 2025-05-01 | DCC01003-GENCORR-000870 | 2025-06-02 | 66838837.39 | 4887279.68 | 0 | -733091.95 | 4154187.73 | 15 | 1TB01003-003C09-AMA-LTR-0140 | 2025-06-30 | 2025-06-16 | -14 | 49037298.55 | 3157027.43 | 0 | -473554.11 | 2683473.32 | DCC01003-RIA-000016 | 2025-07-24 |  | 2025-07-31 | 2025-08-23 | 23 | 2683473.32 | 473554.1145 | 3157027.4345 | 49037298.557
16 | IPA-16 | 2025-06-01 | DCC01003-GENCORR-000983 | 2025-07-04 | 71044652.25 | 4205814.86 | 0 | -630872.23 | 3574942.63 | 16 | 1TB01003-003C09-AMA-LTR-0146 | 2025-08-05 | 2025-07-18 | -18 | 52071883.6 | 3034585.05 | 0 | -455187.76 | 2579397.29 | DCC01003-RIA-000017 | 2025-08-19 |  | 2025-08-31 | 2025-09-18 | 18 | 2579397.29 | 455187.7575 | 3034585.0475 | 52071883.6045
17 | IPA-17 | 2025-07-01 | DCC01003-GENCORR-001032 | 2025-08-02 | 75916581.03 | 4871928.78 | 0 | -730789.32 | 4141139.46 | 17 | 1TB01003-003C09-AMA-LTR-0153 | 2025-08-19 | 2025-08-16 | -3 | 55223620.78 | 3151737.18 | 0 | -472760.58 | 2678976.6 | DCC01003-RIA-000018 | 2025-09-02 |  | 2025-09-24 | 2025-10-02 | 8 | 2678976.6 | 472760.577 | 3151737.177 | 55223620.7815
18 | IPA-18 | 2025-08-01 | DCC01003-GENCORR-001060 | 2025-09-01 | 80931703.34 | 5015122.31 | 0 | -730789.32 | 4284332.99 | 18 | 1TB01003-003C09-AMA-LTR-0159 | 2025-09-24 | 2025-09-15 | -9 | 58361610.36 | 3137989.58 | 0 | -470698.43 | 2667291.15 | DCC01003-RIA-000019 | 2025-09-30 |  |  | 2025-10-30 |  | 2667291.15 | 470698.437 | 3137989.587 | 58361610.3685
19 | IPA-19 | 2025-09-01 | DCC01003-GENCORR-001067 | 2025-09-22 | 85239336.44 | 4307633.1 | 0 | -730789.32 | 3576843.78 | 19 | 1TB01003-003C09-AMA-LTR-0160 | 2025-09-24 | 2025-10-06 | 12 | 61376701.57 | 3015091.21 | 0 | -452263.69 | 2562827.52 | DCC01003-RIA-000020 | 2025-10-05 |  |  | 2025-11-04 |  | 2562827.52 | 452263.6815 | 3015091.2015 | 61376701.57
20 | IPA-20 | 2025-10-01 | DCC01003-GENCORR-001096 | 2025-11-01 | 90713702.59 | 5474366.15 | 0 | -821154.92 | 4653211.23 | 20 | 1TB01003-003C09-AMA-LTR-0180 | 2025-11-24 | 2025-11-15 | -9 | 64747181.35 | 3370479.78 | 0 | -505571.96 | 2864907.82 | DCC01003-RIA-000023 | 2025-12-07 |  |  | 2026-01-06 |  | 2864907.82 | 505571.967 | 3370479.787 | 64747181.357
21 | IPA-21 | 2025-11-01 | DCC01003-GENCORR-001108 | 2025-12-02 | 97637356.05 | 6923653.46 | 0 | -1038548.02 | 5885105.44 | 21 | 1TB01003-003C09-AMA-LTR-0197 | 2025-12-15 | 2025-12-16 | 1 | 68859769.47 | 4112588.12 | 0 | -618388.22 | 3494199.9 | DCC01003-RIA-000022 | 2025-12-25 |  |  | 2026-01-24 |  | 3494199.9 | 616888.218 | 4111088.118 | 68858269.475
22 | IPA-22 | 2026-01-01 | DCC01003-GENCORR-001130 | 2026-02-01 | 101433292.07 | 3795936.02 | 0 | -569390.4 | 3226545.62 | 22 | 1TB01003-003C09-AMA-LTR-0224 | 2026-03-01 | 2026-02-15 | -14 | 72655705.49 | 3795936.02 | 0 | -569390.4 | 3226545.62 | DCC01003-RIA-000023 | 2026-03-13 |  | 2026-04-04 | 2026-04-12 |  | 3226545.62 | 569390.403 | 3795936.023 | 72654205.498
23 | IPA-23 | 2026-02-02 | DCC01003-GENCORR-001175 | 2026-03-01 | 106483245.09 | 5049953.02 | 0 | -757492.95 | 4292460.07 | 23 | 1TB01003-003C09-AMA-LTR-0223 | 2026-04-12 | 2026-03-15 | -28 | 74975529.06 | 2319823.57 | 0 | -347973.5355 | 1971850.0345 | DCC01003-RIA-000025 | 2026-06-08 |  |  | 2026-07-08
24 | IPA-24 | 2026-06-01 | DCC01003-GENCORR-001206 | 2026-07-15 | 108065923.04 | 1582677.95 | 0 | -757492.95 | 825185 | 24 | 1TB01003-003C09-AMA-LTR-0259 | 2026-07-21 | 2026-07-29 | 8 | 76558197.01 | 1582667.95 | 0 | -237400.1925 | 1345267.7575 | DCC01003-RIA-000026 | 2026-08-23 |  |  | 2026-09-22
TOTAL (SAR) | [5 empty] | 108065923.04 | 0 | -16804911.865 | 91261011.175 | TOTAL (SAR) | [5 empty] | 76558197.01 | 0 | -11485229.5435 | 65072967.4665 | TOTAL (SAR) | [5 empty] | 61755849.6745 | 10898355.8235 | 72654205.498 | 55223620.7815
76558197.01
[11 empty] | 0.036364 | [14 empty] | 1650167.791
|  |  |  | 2021-01-01 | [11 empty] | 22167964.91 | [7 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
60238743.09
55223620.78
5015122.31
Formulas:
Issue date of IPC per Contract (14days) = [Date Aconex Letter]+14
Payment Date as per Contract (30days) = +[INVOICE DATE]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H AREEN
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
FFEOSE.003F06 - FF&E and OSE Procurement Agent (Areen Design Ltd)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONSULTANT INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WITHOLDING TAX AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | N/A | N/A | SAR |  |  | Date | Cl. 22.5 | + / - | SAR | SAR | N/A | N/A | SAR |  |  | Date | Date | Payment Schedule | + / - |  | -5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 0% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = ( f + h ) *- 15% | P = N + O
1 | IPA - 1 | Seed Fund1 | AMA01003-PAYAP-000361 | 2024-08-29 | 8437500 | 8437500 | 0 | 0 | 8437500 | 1 | AMA01003-PC-000060 | 2024-09-16 | 2024-09-19 | 3 | 8437500 | 8437500 | 0 | 0 | 8437500 | ADL01003-RIA-000002 | 2024-09-30 |  | 2024-09-30 | 2024-10-30 | 30 | 8437500 | 0 | 8437500 | 8437500 | 9703125 | 0
2 | IPA - 2 | Jan to May 24 | AMA01003-PAYAP-000376 | 2024-09-10 | 8935900 | 498400 | 0 | 0 | 498400 | 2 | AMA01003-PC-000063 | 2024-09-19 | 2024-10-01 | 12 | 8935900 | 498400 | 0 | 0 | 498400 | ADL01003-RIA-000001 | 2024-09-26 |  | 2024-10-14 | 2024-10-26 | 12 | 498400 | -74760 | 423640 | 8861140 |  | 0
3 | IPA - 3 | May to Sep 24 | ADL01003-GENCORR-000011 | 2024-11-20 | 9083825.62 | 147925.62 | 0 | 0 | 147925.62 | 3 | 1TB01003-003F06-AMA-LTR-0004 | 2024-11-25 | 2024-12-11 | 16 | 9083825.62 | 147925.62 | 0 | 0 | 147925.62 | ADL01003-RIA-000005 | 2025-02-18 |  | 2025-05-06 | 2025-03-20 | -47 | 147925.62 | -22188.843 | 125736.777 | 8986876.777 | -0.15
4 | IPA - 4 | Oct to Dec 24 | AMA01003-GENCORR-001016 | 2025-02-24 | 9241122.59 | 157296.97 | 0 | 0 | 157296.97 | 4 | 1TB01003-003F06-AMA-LTR-0005 | 2025-03-10 | 2025-03-17 | 7 | 9241122.59 | 157296.97 | 0 | 0 | 157296.97 | ADL01003-RIA-000006 | 2025-03-31 |  | 2025-05-06 | 2025-04-30 | -6 | 157296.97 | -23594.5455 | 133702.4245 | 9120579.2015
5 | IPA - 5 | Seed Fund 2 | ADL01003-GENCORR-000024 | 2025-03-10 | 11524587.59 | 2283465 | 0 | 0 | 2283465 | 5 | 1TB01003-003F06-AMA-LTR-0005 | 2025-03-17 | 2025-03-31 | 14 | 11524587.59 | 2283465 | 0 | 0 | 2283465 | ADL01003-RIA-000007 | 2025-04-24 |  | 2025-04-30 | 2025-05-24 | 24 | 2283465 | 0 | 2283465 | 11404044.2015
6 | IPA - 6 | 2025-01-25 | ADL01003-GENCORR-000026 | 2025-03-17 | 11615238.53 | 90650.94 | 0 | 0 | 90650.94 | 6 | 1TB01003-003F06-AMA-LTR-0007 | 2025-05-01 | 2025-04-07 | -24 | 11615238.53 | 90650.94 | 0 | 0 | 90650.94 | ADL01003-RIA-000008 | 2025-05-13 |  | 2025-06-05 | 2025-06-12 | 7 | 90650.94 | -13597.641 | 77053.299 | 11481097.5005
7 | IPA - 7 | Seed Fund 3 | ADL01003-GENCORR-000030 | 2025-04-29 | 20134372.28 | 8519133.75 | 0 | 0 | 8519133.75 | 7 | 1TB01003-003F06-AMA-LTR-0008 | 2025-06-17 | 2025-05-20 | -28 | 20134372.28 | 8519133.75 | 0 | 0 | 8519133.75 | ADL01003-RIA-000009 | 2025-07-18 |  | 2025-07-31 | 2025-08-17 | 17 | 8519133.75 | 0 | 8519133.75 | 20000231.2505
8 | IPA - 8 | 2025-04-01 | ADL01003-GENCORR-000041 | 2025-06-26 | 20176732.63 | 42360.35 | 0 | 0 | 42360.35 | 8 | 1TB01003-003F06-AMA-LTR-0009 | 2025-07-03 | 2025-07-17 | 14 | 20176732.63 | 42360.35 | 0 | 0 | 42360.35 | ADL01003-RIA-000010 | 2025-08-05 |  | 2025-08-31 | 2025-09-04 | 4 | 42360.35 | -6354.0525 | 36006.2975 | 20036237.548
9 | IPA - 9 | Jan to Jul 25 | ADL01003-GENCORR-000044 | 2025-08-20 | 20565168.13 | 388435.5 | 0 | 0 | 388435.5 | 9 | 1TB01003-003F06-AMA-LTR-0011 | 2025-08-31 | 2025-09-10 | 10 | 20565168.13 | 388435.5 | 0 | 0 | 388435.5 | ADL01003-RIA-000011 | 2025-09-17 |  |  | 2025-10-17 |  | 388435.5 | -58265.325 | 330170.175 | 20366407.723
10 | IPA - 10 | 2025-09-01 | ADL01003-GENCORR-000049 | 2025-09-22 | 20636956.76 | 71788.63 | 0 | 0 | 71788.63 | 10 | 1TB01003-003F06-AMA-LTR-0012 | 2025-09-24 | 2025-10-13 | 19 | 20685331.63 | 120163.5 | 0 | 0 | 120163.5 | ADL01003-RIA-000012 | 2025-10-02 |  |  | 2025-11-01 |  | 120163.5 | -18024.525 | 102138.975 | 20468546.698
11 | IPA - 11 | 2025-10-01 | ADL01003-GENCORR-000051 | 2025-11-10 | 20704628.07 | 67671.31 | 0 | 0 | 67671.31 | 11 | 1TB01003-003F06-AMA-LTR-0013 | 2025-11-24 | 2025-12-01 | 7 | 20753002.94 | 67671.31 | 0 | 0 | 67671.31 | ADL01003-RIA-000013 | 2025-12-04 |  |  | 2026-01-03 |  | 67671.31 | -10150.6965 | 57520.6135 | 20526067.3115
12 | IPA - 12 | Seed Fund 4 | ADL01003-GENCORR-000058 | 2026-02-16 | 25036200.57 | 4331572.5 | 0 | 0 | 4331572.5 | 12 | 1TB01003-003F06-AMA-LTR-0014 | 2026-03-01 | 2026-03-09 | 8 | 25084575.44 | 4331572.5 | 0 | 0 | 4331572.5 | ADL01003-RIA-000013 | 2025-03-13 |  | 2026-04-04 | 2025-04-12 |  | 4331572.5 | -649735.875 | 3681836.625 | 24207903.9365
13 | IPA - 13 | 2026-03-01 | ADL01003-GENCORR-000066 | 2026-04-09 | 25262308.81 | 226108.24 | 0 | 0 | 226108.24 | 13 | 1TB01003-003F06-AMA-LTR-0016 | 2026-04-23 | 2026-04-30 | 7 | 25310683.68 | 226108.24 | 0 | 0 | 226108.24 | ADL01003-RIA-000015 | 2026-05-19 |  |  | 2026-06-18
14 | IPA - 14 | 2026-04-01 | ADL01003-GENCORR-000068 | 2026-05-06 | 25284285.28 | 21976.47 | 0 | 0 | 21976.47 | 14 | 1TB01003-003F06-AMA-LTR-0017 | 2026-04-23 | 2026-05-27 | 34 | 25332660.15 | 21976.47 | 0 | 0 | 21976.47 | ADL01003-RIA-000016 | 2026-05-26 |  |  | 2026-06-25
15 | IPA - 15 | 2026-05-01 | Email | 2026-07-02 | 25319298.82 | 35013.54 | 0 | 0 | 35013.54 | 15 | 1TB01003-003F06-AMA-LTR-0020 | 2026-09-23 | 2026-07-23 | -62 | 25367673.69 | 35013.54 | 0 | 0 | 35013.54
TOTAL (SAR) | [5 empty] | 25319298.82 | 0 | 0 | 25319298.82 | TOTAL (SAR) | [5 empty] | 25367673.69 | 0 | 0 | 25367673.69 | TOTAL (SAR) | [5 empty] | 25084575.44 | -876671.5035 | 24207903.9365 | 20036237.548
25367673.69
0.036364
|  |  |  | 2021-01-01 | [11 empty] | 20134372.28 | [7 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21days) = [Date Aconex Letter]+21
Payment Date as per Contract (30days) = +[INVOICE DATE]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H ALUTEC
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
CN.003C27 - Façade & Glazing Works (Alutec)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (21days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 25% | 10% | SAR |  |  | Date | Cl. 13.5.1 | + / - | SAR | SAR | 25% | 10% | SAR |  |  | Date | Date | Cl.13.6.1(b) | + / - |  | -5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 25% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 21 | m = l - k | n = i | o = ( f + h ) * -5% (Installation) | P = N + O
1 | IPA - 1 | Advance Payment | ATA01003-TRANSMIT-000034 | 2024-08-29 | 7474917.64 | 7474917.64 | 0 | 0 | 7474917.64 | 1 | 1TB01003-003C27-AMA-LTR-0015 | 2024-09-08 | 2024-09-19 | 11 | 819298.55 | 7474917.64 | 0 | 0 | 7474917.64 | ATA01003-RIA-000001 | 2024-09-19 |  | 2024-10-17 | 2024-10-10 | -7 | 7474917.64 | -19129.03 | 7455788.61 | 7455788.61 | 8596155.286
2 | IPA - 2 | 2024-10-24 | ATA01003-TRANSMIT-000046 | 2024-11-10 | 8368918.04 | 894000.4 | -223500.1 | -89400.05 | 581100.25 | 2 | TB01003-003C27-AMA-LTR-0016 | 2024-11-19 | 2024-12-01 | 12 | 1713298.95 | 894000.4 | -223500.1 | -89400.05 | 581100.25 | ATA01003-RIA-000003 | 2025-01-12 |  | 2025-01-30 | 2025-02-02 | 3 | 581100.25 | -3293.33 | 577806.92 | 8033595.53 | 584393.58
3 | IPA - 3 | 2024-11-24 | ATA01003-GENCORR-000006 | 2024-12-04 | 8923214.93 | 554296.89 | -138574.22 | -55429.7 | 360292.97 | 3 | 1TB01003-003C27-AMA-LTR-0017 | 2024-12-12 | 2024-12-25 | 13 | 2098820.64 | 385521.69 | -96380.42 | -38552.17 | 250589.1 | ATA01003-RIA-000002 | 2025-01-12 |  | 2025-01-30 | 2025-02-02 | 3 | 250589.1 | -2986.99 | 247602.11 | 8281197.64 | 253576.09
4 | IPA - 4 | 2024-12-24 | ATA01003-GENCORR-000010 | 2024-12-28 | 9004943.92 | 81728.99 | -20432.25 | -8172.91 | 53123.83 | 4 | 1TB01003-003C27-AMA-LTR-0021 | 2025-01-15 | 2025-01-18 | 3 | 2180549.63 | 81728.99 | -20432.25 | -8172.88 | 53123.86 | ATA01003-RIA-000004 | 2025-01-26 |  | 2025-03-27 | 2025-02-16 | -39 | 53123.86 | -2986.99 | 50136.87 | 8331334.51
5 | IPA - 5 | 2025-01-24 | ATA01003-GENCORR-000016 | 2025-01-28 | 10170598.34 | 1165654.42 | -291413.61 | -14847.8 | 859393.01 | 5 | 1TB01003-003C27-AMA-LTR-0021 | 2025-03-17 | 2025-02-18 | -27 | 3059789.41 | 879239.78 | -219809.95 | -87923.97 | 571505.86 | ATA01003-RIA-000005 | 2025-04-04 |  | 2025-06-30 | 2025-04-25 | -66 | 571505.86 | -2986.99 | 568518.87 | 8899853.38
6 | IPA - 6 | 2025-02-24 | ATA01003-GENCORR-000019 | 2025-02-24 | 11754605.21 | 1584006.87 | -396001.71 | -158400.68 | 1029604.48 | 6 | 1TB01003-003C27-AMA-LTR-0034 | 2025-04-10 | 2025-03-17 | -24 | 3911239.13 | 851449.72 | -212862.42 | -85144.97 | 553442.33 | ATA01003-RIA-000006 | 2025-05-14 |  | 2025-06-30 | 2025-06-04 | -26 | 553442.33 | -2986.99 | 550455.34 | 9450308.72
7 | IPA - 7 | 2025-03-24 | ATA01003-GENCORR-000021 | 2025-04-08 | 12319920.76 | 565315.55 | -141328.89 | -56531.59 | 367455.07 | 7 | 1TB01003-003C27-AMA-LTR-0036 | 2025-04-17 | 2025-04-29 | 12 | 4246125.68 | 334886.55 | -83721.64 | -33488.68 | 217676.23 | ATA01003-RIA-000007 | 2025-05-14 |  | 2025-06-30 | 2025-06-04 | -26 | 217676.23 | -2986.99 | 214689.24 | 9664997.96
8 | IPA - 8 | 2025-04-24 | ATA01003-GENCORR-000026 | 2025-05-14 | 27301891.84 | 14981971.08 | -3745492.77 | -1498197.14 | 9738281.17 | 8 | 1TB01003-003C27-AMA-LTR-0041 | 2025-05-22 | 2025-06-04 | 13 | 14874139.76 | 10628014.08 | -2657003.52 | -1062801.43 | 6908209.13 | ATA01003-RIA-000008 | 2025-06-17 |  | 2025-07-02 | 2025-07-08 | 6 | 6908209.13 | -2986.99 | 6905222.14 | 16570220.1
9 | IPA - 9 | 2025-05-01 | ATA01003-GENCORR-000029 | 2025-05-22 | 29972984.63 | 2671092.79 | -667773.2 | -267109.29 | 1736210.3 | 9 | 1TB01003-003C27-AMA-LTR-0042 | 2025-06-18 | 2025-06-12 | -6 | 17545232.55 | 2671092.79 | -667773.2 | -267109.25 | 1736210.34 | ATA01003-RIA-000009 | 2025-07-13 |  | 2025-08-07 | 2025-08-03 | -4 | 1736210.34 | -5417.5 | 1730792.84 | 18301012.94
10 | IPA - 10 | 2025-06-01 | ATA01003-GENCORR-000031 | 2025-06-25 | 41055351 | 11082366.37 | -2770591.59 | -1108236.65 | 7203538.13 | 10 | 1TB01003-003C27-AMA-LTR-0045 | 2025-08-05 | 2025-07-16 | -20 | 23657272.28 | 6112039.73 | -1528009.93 | -611203.99 | 3972825.81 | ATA01003-RIA-000010 | 2025-08-17 |  | 2025-08-31 | 2025-09-07 | 7 | 3972825.81 | -8551.66 | 3964274.15 | 22265287.09
11 | IPA - 11 | 2025-07-01 | ATA01003-GENCORR-000036 | 2025-07-24 | 46721910.19 | 5666559.19 | -1416639.8 | -566655.9 | 3683263.49 | 11 | 1TB01003-003C27-AMA-LTR-0048 | 2025-08-19 | 2025-08-14 | -5 | 25712612.61 | 2055340.33 | -513835.09 | -205534.01 | 1335971.23 | ATA01003-RIA-000010 | 2025-08-27 |  | 2025-09-24 | 2025-09-17 | -7 | 1335971.23 | -1906.93 | 1334064.3 | 23599351.39
12 | IPA - 12 | 2025-08-01 | ATA01003-GENCORR-000039 | 2025-08-26 | 49684769.59 | 2962859.4 | -740714.85 | -296285.94 | 1925858.61 | 12 | 1TB01003-003C27-AMA-LTR-0050 | 2025-09-29 | 2025-09-16 | -13 | 26479884.81 | 767272.2 | -191818.05 | -76727.22 | 498726.93 | ATA01003-RIA-000012 | 2025-10-05 |  |  | 2025-10-26 |  | 498726.93 | -1906.93 | 496820 | 24096171.39
13 | IPA - 13 | 2025-09-01 | ATA01003-GENCORR-000042 | 2025-09-21 | 53302330.62 | 3617561.03 | -904390.25 | -361756.12 | 2351414.66 | 13 | 1TB01003-003C27-AMA-LTR-0051 | 2025-09-29 | 2025-10-12 | 13 | 27056062.61 | 576177.8 | -144044.45 | -57617.77 | 374515.58 | ATA01003-RIA-000013 | 2025-10-08 |  |  | 2025-10-29 |  | 374515.58 | -1906.93 | 372608.65 | 24468780.04
14 | IPA - 14 | 2025-10-01 | ATA01003-GENCORR-000044 | 2025-10-23 | 56379327.4 | 3076996.78 | -769249.19 | -307699.69 | 2000047.9 | 14 | 1TB01003-003C27-AMA-LTR-0054 | 2025-11-18 | 2025-11-13 | -5 | 28239031.41 | 1182968.8 | -915726.62 | -118296.92 | 148945.26 | ATA01003-RIA-000014 | 2025-12-07 |  |  | 2025-12-28 |  | 148945.26 | -1906.93 | 147038.33 | 24615818.37
15 | IPA - 15 | 2025-11-01 | ATA01003-GENCORR-000050 | 2025-11-26 | 58757301.586 | 2377974.186 | 0 | -237797.4 | 2140176.786 | 15 | 1TB01003-003C27-AMA-LTR-0059 | 2025-12-15 | 2025-12-17 | 2 | 29151402.54 | 912371.13 | 0 | -91237.1 | 821134.03 | ATA01003-RIA-000015 | 2026-01-05 |  |  | 2026-01-26 |  | 821134.03 | -1906.93 | 819227.1 | 25435045.47
16 | IPA - 16 | 2025-12-01 | ATA01003-GENCORR-000052 | 2025-12-17 | 60430581.8102 | 1673280.2242 | 0 | -167328.01 | 1505952.2142 | 16 | 1TB01003-003C27-AMA-LTR-0061. | 2026-01-26 | 2026-01-07 | -19 | 29477702.66 | 326300.12 | 0 | -32630.01 | 293670.11 | ATA01003-RIA-000016 | 2026-03-03 |  | 2026-04-16 | 2026-03-24 |  | 293670.11 | -1906.93 | 291763.18 | 25726808.65
17 | IPA - 17 | 2026-01-01 | ATA01003-GENCORR-000054 | 2026-01-22 | 61639220.6343 | 1208638.824 | 0 | -120863.871 | 1087774.9531 | 17 | 1TB01003-003C27-AMA-LTR-0066 | 2026-03-04 | 2026-02-12 | -20 | 29577847.18 | 100144.52 | 0 | -10014.45 | 90130.07 | ATA01003-RIA-000017 | 2026-05-11 |  |  | 2026-06-01
18 | IPA - 18 | 2025-10-01 | ATA01003-GENCORR-000056 | 2026-02-25 | 62729904.0051 | 1090683.3708 | 0 | -109068.3287 | 981615.0422 | 18 | 1TB01003-003C27-AMA-LTR-0069 | 2026-04-14 | 2026-03-18 | -27 | 29632970.69 | 55123.51 | 0 | -5512.351 | 49611.159 | ATA01003-RIA-000017 | 2026-05-11 |  |  | 2026-06-01
19 | IPA - 19 | 2026-03-01 | ATA01003-GENCORR-000061 | 2026-03-24 | 62834968.1751 | 105064.17 | 0 | -10506.417 | 94557.753 | 19 | 1TB01003-003C27-AMA-LTR-0071 | 2026-04-26 | 2026-04-14 | -12 | 29738034.86 | 105064.17 | 0 | -10506.417 | 94557.753 | ATA01003-RIA-000019 | 2026-07-12 |  |  | 2026-08-02
20 | IPA - 20 | 2026-04-01 | ATA01003-GENCORR-000061 | 2026-04-20 | 63048049.2151 | 213081.04 | 0 | -21308.104 | 191772.926 | 20 | 1TB01003-003C27-AMA-LTR-0074 | 2026-06-01 | 2026-05-11 | -21 | 29951115.9 | 213081.04 | 0 | -21308.104 | 191772.926 | ATA01003-RIA-000020 | 2026-08-18 |  |  | 2026-09-08
21 | IPA - 21 | Retention release | ATA01003-GENCORR-000067 | 2026-08-06 | 63048049.2151 | 0 | 0 | 2913181.72 | 2913181.72 | 21 | 1TB01003-003C27-AMA-LTR-0085 | 2026-06-01 | 2026-08-27 | 87 | 29951115.9 | 0 | 0 | 2913181.72 | 2913181.72 |  | 2026-09-07 |  |  | 2026-09-28
TOTAL (SAR) | [5 empty] | 63048049.2151 | -12226102.43 | -2542413.8707 | 48279532.9045 | TOTAL (SAR) | [5 empty] | 36606734.99 | -7474917.64 | -0.022 | 29131817.318 | TOTAL (SAR) | [5 empty] | 25792563.69 | -65755.04 | 25726808.65 | 23599351.39
7474917.64
[17 empty] | 0 |  | 29131817.34
[11 empty] | 0.036364 | [5 empty] | 335862.5
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [12 empty] | -267109.25 | [6 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21days) = [Date Aconex Letter]+21
Payment Date as per Contract (21days) = +[INVOICE DATE]+21
Payment Date as per Contract (21days) = [Payment Date as per Contract (21days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H MAS (Wet Works)
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
MAS (PO 2240427)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (21days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 13.5.1 | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.13.6.1(b) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 0% | i = f + g + h |  | j |  | k | l = j + 21 | m = l - k | n = i | o = n * 15% | P = N + O
1 | IPA - 1 | 2024-11-09 | MEC01003-TRANSMIT-000001 | 2024-11-20 | 969150 | 969150 | 0 | 0 | 969150 | 1 | 1TB01003-003C31-AMA-LTR-0005 | 2024-12-08 | 2024-12-11 | 3 | 969150 | 969150 | 0 | 0 | 969150 | MEC01003-RIA-000001 | 2024-12-22 |  | 2024-12-29 | 2025-01-12 | 14 | 969150 | 145372.5 | 1114522.5 | 1114522.5 | 1114522.5
2 | IPA-2 | 2024-12-24 | MEC01003-TRANSMIT-000009 | 2024-12-11 | 1486800 | 517650 | 0 | 0 | 517650 | 2 | 1TB01003-003C31-AMA-LTR-0006 | 2024-12-28 | 2025-01-01 | 4 | 1486800 | 517650 | 0 | 0 | 517650 | MEC01003-RIA-000003 | 2025-01-20 |  | 2025-03-26 | 2025-02-10 | -44 | 517650 | 77647.5 | 595297.5 | 1709820
3 | IPA-3 | 2025-01-01 | MEC01003-TRANSMIT-000013 | 2025-02-10 | 2029650 | 542850 | 0 | 0 | 542850 | 3 | 1TB01003-003C31-AMA-LTR-0010 | 2024-02-22 | 2025-03-03 | 375 | 2029650 | 542850 | 0 | 0 | 542850 | MEC01003-RIA-000005 | 2025-03-06 |  | 2025-04-07 | 2025-03-27 | -11 | 542850 | 81427.5 | 624277.5 | 2334097.5
4 | IPA-4 | 2025-02-01 | MEC01003-TRANSMIT-000015 | 2025-03-18 | 3134600 | 1104950 | 0 | 0 | 1104950 | 4 | 1TB01003-003C31-AMA-LTR-0013 | 2025-04-09 | 2025-04-08 | -1 | 2820195 | 790545 | 0 | 0 | 790545 | MEC01003-RIA-000006 | 2025-04-15 |  | 2025-04-30 | 2025-05-06 | 6 | 790545 | 118581.75 | 909126.75 | 3243224.25
5 | IPA-5 | 2025-03-01 | MEC01003-TRANSMIT-000018 | 2025-04-14 | 4302340 | 1167740 | 0 | 0 | 1167740 | 5 | 1TB01003-003C31-AMA-LTR-0014 | 2025-04-27 | 2025-05-05 | 8 | 3979815 | 1159620 | 0 | 0 | 1159620 | MEC01003-RIA-000007 | 2025-05-06 |  | 2025-06-10 | 2025-05-27 | -14 | 1159620 | 173943 | 1333563 | 4576787.25
6 | IPA-6 | 2025-04-01 | MEC01003-TRANSMIT-000020 | 2025-05-17 | 6057419 | 1755079 | 0 | 0 | 1755079 | 6 | 1TB01003-003C31-AMA-LTR-0015 | 2025-06-10 | 2025-06-07 | -3 | 5723898 | 1744083 | 0 | 0 | 1744083 | MEC01003-RIA-000009 | 2025-06-28 |  | 2025-07-08 | 2025-07-19 | 11 | 1744083 | 261612.45 | 2005695.45 | 6582482.7
7 | IPA-7 | 2025-05-01 | MEC01003-TRANSMIT-000022 | 2025-06-17 | 8498048 | 2440629 | 0 | 0 | 2440629 | 7 | 1TB01003-003C31-AMA-LTR-0017 | 2025-06-29 | 2025-07-08 | 9 | 8156188 | 2432290 | 0 | 0 | 2432290 | MEC01003-RIA-000010 | 2025-07-09 |  | 2025-07-23 | 2025-07-30 | 7 | 2432290 | 364843.5 | 2797133.5 | 9379616.2
8 | IPA-8 | 2025-06-01 | MEC01003-TRANSMIT-000023 | 2025-07-06 | 10595512 | 2097464 | 0 | 0 | 2097464 | 8 | 1TB01003-003C31-AMA-LTR-0018 | 2025-07-13 | 2025-07-27 | 14 | 10263319 | 2107131 | 0 | 0 | 2107131 | MEC01003-RIA-000011 | 2025-07-19 |  | 2025-07-31 | 2025-08-09 | 9 | 2107131 | 316069.65 | 2423200.65 | 11802816.85
9 | IPA-9 | 2025-07-01 | MEC01003-TRANSMIT-000024 | 2025-08-11 | 12664016 | 2068504 | 0 | 0 | 2068504 | 9 | 1TB01003-003C31-AMA-LTR-0019 | 2025-08-19 | 2025-09-01 | 13 | 12276793 | 2013474 | 0 | 0 | 2013474 | MEC01003-RIA-000012 | 2025-09-01 |  | 2025-10-06 | 2025-09-22 | -14 | 2013474 | 302021.1 | 2315495.1 | 14118311.95
10 | IPA-10 | 2025-08-01 | MEC01003-TRANSMIT-000025 | 2025-09-04 | 15016811 | 2352795 | 0 | 0 | 2352795 | 10 | 1TB01003-003C31-AMA-LTR-0020 | 2025-09-14 | 2025-09-25 | 11 | 14576752 | 2299959 | 0 | 0 | 2299959 | MEC01003-RIA-000013 | 2025-09-24 |  |  | 2025-10-15 |  | 2299959 | 344993.85 | 2644952.85 | 16763264.8 | paid
11 | IPA-11 | 2025-09-01 | MEC01003-TRANSMIT-000032 | 2025-09-22 | 17085315 | 2068504 | 0 | 0 | 2068504 | 11 | 1TB01003-003C31-AMA-LTR-0021 | 2025-09-24 | 2025-10-13 | 19 | 16049410 | 1472658 | 0 | 0 | 1472658 | MEC01003-RIA-000015 | 2025-10-15 |  |  | 2025-11-05 |  | 1472658 | 220898.7 | 1693556.7 | 18456821.5 | paid
12 | IPA-12 | 2025-10-01 | MEC01003-TRANSMIT-000034 | 2025-10-28 | 18729701 | 1644386 | 0 | 0 | 1644386 | 12 | 1TB01003-003C31-AMA-LTR-0022 | 2025-11-18 | 2025-11-18 | 0 | 17691374 | 1641964 | 0 | 0 | 1641964 | MEC01003-RIA-000017 | 2025-12-06 |  |  | 2025-12-27 |  | 1641964 | 246294.6 | 1888258.6 | 20345080.1 | paid
13 | IPA-13 | 2025-11-01 | MEC01003-TRANSMIT-000035 | 2025-12-02 | 20788547 | 2058846 | 0 | 0 | 2058846 | 13 | 1TB01003-003C31-AMA-LTR-0025 | 2025-12-22 | 2025-12-23 | 1 | 19750220 | 2058846 | 0 | 0 | 2058846 | MEC01003-RIA-000018 | 2026-01-17 |  |  | 2026-02-07 |  | 2058846 | 308826.9 | 2367672.9 | 22712753
14 | IPA-14 | 2025-12-01 | MEC01003-TRANSMIT-000036 | 2026-01-01 | 21804949.21 | 1016402.21 | 0 | 0 | 1016402.21 | 14 | 1TB01003-003C31-AMA-LTR-0026 | 2026-02-10 | 2026-01-22 | -19 | 20766622.21 | 1016402.21 | 0 | 0 | 1016402.21 | MEC01003-RIA-000019 | 2026-02-28 |  |  | 2026-03-21
15 | IPA-15 | 2026-01-01 | MEC01003-GENCORR-000031 | 2026-03-05 | 23229583.21 | 1424634 | 0 | 0 | 1424634 | 15 | 1TB01003-003C31-AMA-LTR-0029 | 2026-04-05 | 2026-03-26 | -10 | 22191256.21 | 1424634 | 0 | 0 | 1424634 | MEC01003-RIA-000020 | 2026-04-30 |  |  | 2026-05-21
16 | IPA-16 | 2026-04-01 | MEC01003-TRANSMIT-000038 | 2026-04-27 | 23384183.21 | 154600 | 0 | 0 | 154600 | 15 | 1TB01003-003C31-AMA-LTR-0029 | 2026-04-05 | 2026-05-18 | 43 | 22345856.21 | 154600 | 0 | 0 | 154600 | MEC01003-RIA-000020 | 2026-07-23 |  |  | 2026-08-13
TOTAL (SAR) | [5 empty] | 23384183.21 | 0 | 0 | 23384183.21 | TOTAL (SAR) | [5 empty] | 22345856.21 | 0 | 0 | 22345856.21 | TOTAL (SAR) | [5 empty] | 19750220 | 2962533 | 22712753 | 14118311.95
22345856.21
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
|  |  |  | 12331823 | [21 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
|  |  |  | 10263319 | [21 empty] | 11439880.26
2068504
14629588
12276793
2352795
Formulas:
Issue date of IPC per Contract (21days) = [Date Aconex Letter]+21
Payment Date as per Contract (21days) = +[INVOICE DATE]+21
Payment Date as per Contract (21days) = [Payment Date as per Contract (21days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H MAS (Amphitheatre)
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
MAS (PO 2240461)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (21days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 10% | SAR |  |  | Date | Cl. 13.5.1 | + / - | SAR | SAR | 0% | 10% | SAR |  |  | Date | Date | Cl.13.6.1(b) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 21 | m = l - k | n = i | o = n * 15% | P = N + O
1 | IPA - 1 | Advance Payment | MEC01003-TRANSMIT-000002 | 2024-11-20 | 914924.96 | 914924.96 | 0 | -91492.496 | 823432.464 | 1 | 1TB01003-003C32-AMA-LTR-0006 | 2024-12-02 | 2024-12-11 | 9 | 836682.35 | 836682.35 | 0 | -83668.235 | 753014.115 | MEC01003-RIA-000002 | 2024-12-23 |  | 2025-01-28 | 2025-01-13 | -15 | 753014.115 | 112952.1172 | 865966.2323 | 865966.2323 | 865966.2322
2 | IPA - 2 | 2024-12-12 | MEC01003-TRANSMIT-000010 | 2024-12-11 | 1157134.88 | 242209.92 | 0 | -24220.992 | 217988.928 | 2 | 1TB01003-003C32-AMA-LTR-0007 | 2025-01-05 | 2025-01-01 | -4 | 1020572.27 | 183889.92 | 0 | -18388.992 | 165500.928 | MEC01003-RIA-000004 | 2025-01-20 |  | 2025-04-23 | 2025-02-10 | -72 | 165500.928 | 24825.1392 | 190326.0672 | 1056292.2995
3 | IPA - 3 | 2025-03-01 | MEC01003-TRANSMIT-000016 | 2025-03-18 | 1421112.96 | 263978.08 | 0 | -26397.808 | 237580.272 | 3 | 1TB01003-003C32-AMA-LTR-0014 | 2025-04-21 | 2025-04-08 | -13 | 1216710.35 | 196138.08 | 0 | -19613.808 | 176524.272 | MEC01003-RIA-000008 | 2025-05-29 |  | 2025-06-29 | 2025-06-19 | -10 | 176524.272 | 26478.6408 | 203002.9128 | 1259295.2123
4 | IPA - 4 | 2025-10-01 | MEC01003-TRANSMIT-000033 | 2025-10-18 | 1479432.96 | 58320 | 0 | 57919.52 | 116239.52 | 4 | 1TB01003-003C32-AMA-LTR-0015 | 2025-10-27 | 2025-11-08 | 12 | 1294644.16 | 77933.81 | 0 | 38305.71 | 116239.52 | MEC01003-RIA-000016 | 2025-11-05 |  |  | 2025-11-26 |  | 116239.52 | 17435.928 | 133675.448 | 1392970.6603
TOTAL (SAR) | [5 empty] | 1479432.96 | 0 | -84191.776 | 1395241.184 | TOTAL (SAR) | [5 empty] | 1294644.16 | 0 | -83365.325 | 1211278.835 | TOTAL (SAR) | [5 empty] | 1211278.835 | 181691.8252 | 1392970.6603 | 1259295.2123
1294644.16
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
[6 empty] | 1284550.35 | [19 empty] | Cashflow
[6 empty] | 1020572.27 | [19 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
[6 empty] | 263978.08 | [19 empty] | 11439880.26
Formulas:
Issue date of IPC per Contract (21days) = [Date Aconex Letter]+21
Payment Date as per Contract (21days) = +[INVOICE DATE]+21
Payment Date as per Contract (21days) = [Payment Date as per Contract (21days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H AL FANAR
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
CN.003C34 - Al Fanar - MEP Labour Supply
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 19.4 | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.19.7 (Payment Schedule) | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = n * 15% | P = N + O
1 | IPA-01 | Sep to Oct 2024 | Alfanar VAT No : 300050206400003 | 2024-12-18 | 19919915.22 | 19919915.22 | 0 | 0 | 19919915.22 | 1 | 1TB01003-003C34-AMA-LTR-0009 | 2024-12-28 | 2025-01-08 | 11 | 18765256.3 | 18765256.3 | 0 | 0 | 18765256.3 | ACY01003-RIA-000001 | 2025-01-27 |  | 2025-03-25 | 2025-02-26 | -27 | 18765256.3 | 2814788.445 | 21580044.745 | 21580044.745 | 21580044.745
2 | IPA-02 | 24 Nov 24 to 24 Feb 25 | ACY01003-GENCORR-000009 | 2025-01-08 | 41674804.92 | 21754889.7 | 0 | 0 | 21754889.7 | 2 | 1TB01003-003C34-AMA-LTR-0019 | 2025-03-16 | 2025-01-29 | -46 | 40520146 | 21754889.7 | 0 | 0 | 21754889.7 | ACY01003-RIA-000002 | 2025-04-15 |  | 2025-04-23 | 2025-05-15 | 22 | 21754889.7 | 3263233.455 | 25018123.155 | 46598167.9
3 | IPA-03 | 25 Feb to 24 Mar 25 | ACY01003-GENCORR-000014 | 2025-03-27 | 60167760.1741 | 18492955.2541 | 0 | 0 | 18492955.2541 | 3 | 1TB01003-003C34-AMA-LTR-0020 | 2025-04-27 | 2025-04-17 | -10 | 42914917 | 2394771 | 0 | 0 | 2394771 | ACY01003-RIA-000003 | 2025-05-14 |  | 2025-05-28 | 2025-06-13 | 16 | 2394771 | 359215.65 | 2753986.65 | 49352154.55
4 | IPA-04 | 25 Mar to 24 Apr 25 | ACY01003-GENCORR-000016 | 2025-05-11 | 67939560.1741 | 7771800 | 0 | 0 | 7771800 | 4 | 1TB01003-003C34-AMA-LTR-0022 | 2025-05-20 | 2025-06-01 | 12 | 45816977.5 | 2902060.5 | 0 | 0 | 2902060.5 | ACY01003-RIA-000004 | 2025-06-15 |  | 2025-06-29 | 2025-07-15 | 16 | 2902060.5 | 435309.075 | 3337369.575 | 52689524.125
5 | IPA-05 | 25 April to 25 MAy 25 | ACY01003-GENCORR-000017 | 2025-05-26 | 76209513.1741 | 8269953 | 0 | 0 | 8269953 | 5 | 1TB01003-003C34-AMA-LTR-0024 | 2025-06-10 | 2025-06-16 | 6 | 50069966.5 | 4252989 | 0 | 0 | 4252989 | ACY01003-RIA-000005 | 2025-06-26 |  | 2025-06-30 | 2025-07-26 | 26 | 4252989 | 637948.35 | 4890937.35 | 57580461.475
6 | IPA-06 | Dec, Jan & Feb Adjustment | ACY01003-GENCORR-000021 | 2025-06-22 | 83256947.1741 | 7047434 | 0 | 0 | 7047434 | 6 | 1TB01003-003C34-AMA-LTR-0029 | 2025-07-24 | 2025-07-13 | -11 | 54149805 | 4079838.5 | 0 | 0 | 4079838.5 | ACY01003-RIA-000006 | 2025-08-05 |  | 2025-09-30 | 2025-09-04 | -26 | 4079838.5 | 611975.775 | 4691814.275 | 62272275.75
7 | IPA-07 | Materials | ACY01003-GENCORR-000028 | 2025-07-27 | 93160343.6841 | 9903396.51 | 0 | 0 | 9903396.51 | 7 | 1TB01003-003C34-AMA-LTR-0032 | 2025-08-19 | 2025-08-17 | -2 | 59908608.28 | 5758803.28 | 0 | 0 | 5758803.28 | ACY01003-RIA-000007 | 2025-09-01 |  | 2025-09-30 | 2025-10-01 | 1 | 5758803.28 | 863820.492 | 6622623.772 | 68894899.522
8 | IPA-08 | from 25 May to 24 Aug & materials | ACY01003-GENCORR-000032 | 2025-09-11 | 106952156.8341 | 13791813.15 | 0 | 0 | 13791813.15 | 8 | 1TB01003-003C34-AMA-LTR-0038 | 2025-09-24 | 2025-10-02 | 8 | 72073397.31 | 12164789.03 | 0 | 0 | 12164789.03 | ACY01003-RIA-000008 | 2025-10-12 |  |  | 2025-11-11 |  | 12164789.03 | 1824718.3545 | 13989507.3845 | 82884406.9065
9 | IPA-09 | 25 Aug to 24 Sep 25 | ACY01003-GENCORR-000037 | 2025-11-02 | 111632672.1441 | 4680515.31 | 0 | 0 | 4680515.31 | 9 | 1TB01003-003C34-AMA-LTR-0044 | 2026-02-05 | 2025-11-23 | -74 | 75431356.84 | 3357959.53 | 0 | 0 | 3357959.53 | ACY01003-RIA-000009 | 2026-02-28 |  |  | 2026-03-30 |  | 3357959.53 | 503693.9295 | 3861653.4595 | 86746060.366
10 | IPA-10 | Oct 25 | ACY01003-GENCORR-000038 | 2025-11-06 | 113381370.6441 | 1748698.5 | 0 | 0 | 1748698.5 | 10 | 1TB01003-003C34-AMA-LTR-0046 | 2026-02-05 | 2025-11-27 | -70 | 77403384.84 | 1972028 | 0 | 0 | 1972028 | ACY01003-RIA-000010 | 2026-02-28 |  |  | 2026-03-30 |  | 1972028 | 295804.2 | 2267832.2 | 89013892.566
11 | IPA-11 | Nov & Dec 25 | ACY01003-GENCORR-000046 | 2026-01-28 | 119921218.3441 | 6539847.7 | 0 | 0 | 6539847.7 | 11 | 1TB01003-003C34-AMA-LTR-0046 | 2026-03-01 | 2026-02-18 | -11 | 82146350.2 | 4742965.36 | 0 | 0 | 4742965.36 | ACY01003-RIA-000011 | 2026-03-14 |  | 2026-04-04 | 2026-04-13 |  | 4742965.36 | 711444.804 | 5454410.164 | 94468302.73
12 | IPA-12 | Jan 26 | ACY01003-GENCORR-000049 | 2026-02-10 | 121846508.8441 | 1925290.5 | 0 | 0 | 1925290.5 | 12 | 1TB01003-003C34-AMA-LTR-0051 | 2026-02-24 | 2026-03-03 | 7 | 82985497.7 | 839147.5 | 0 | 0 | 839147.5 | ACY01003-RIA-000012 | 2026-04-27 |  |  | 2026-05-27
13 | IPA-13 | 2026-04-01 | ACY01003-GENCORR-000069 | 2026-05-05 | 125128833.8641 | 3282325.02 | 0 | 0 | 3282325.02 | 13 | 1TB01003-003C34-AMA-LTR-0051 | 2026-02-24 | 2026-05-26 | 91 | 86267822.72 | 3282325.02 | 0 | 0 | 3282325.02 | ACY01003-RIA-000013 | 2026-08-06 |  |  | 2026-09-05
14 | IPA-14 | 2026-06-01 | ACY01003-GENCORR-000078 | 2026-07-07 | 128789993.5241 | 3661159.66 | 0 | 0 | 3661159.66 | 14 | 1TB01003-003C34-AMA-LTR-0067 | 2026-08-17 | 2026-07-28 | -20 | 89928982.38 | 3661159.66 | 0 | 0 | 3661159.66 | ACY01003-RIA-000014 | 2026-09-13 |  |  | 2026-10-13
15 | IPA-15 | 2026-09-01 | ACY01003-GENCORR-000084 | 2026-08-25 | 131213586.2341 | 2423592.71 | 0 | 0 | 2423592.71 | 15 | 1TB01003-003C34-AMA-LTR-0070 | 2026-09-19 | 2026-09-15 | -4 | 92352575.09 | 2423592.71 | 0 | 0 | 2423592.71
TOTAL (SAR) | [5 empty] | 131213586.2341 | 0 | 0 | 131213586.2341 | TOTAL (SAR) | [5 empty] | 92352575.09 | 0 | 0 | 92352575.09 | TOTAL (SAR) | [5 empty] | 82146350.2 | 12321952.53 | 94468302.73 | 82884406.9065
92352575.09
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
[6 empty] | 57117400.5 | [19 empty] | 11439880.26
50069966.5
7047434
64053201.51
54149805
9903396.51
73700421.43
59908608.28
13791813.15
Formulas:
Issue date of IPC per Contract (21days) = [Date Aconex Letter]+21
Payment Date as per Contract (30days) = +[INVOICE DATE]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H CML
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
PS.003F08 - CML (Independent Commissioning Agent) COO 7
STAGE 1 - PAYMENT APPLICATION | [10 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) |  | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONSULTANT INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | N/A | N/A | SAR |  |  |  | Date | Cl. 24.2 | + / - | SAR | SAR | N/A | N/A | SAR |  |  | Date | Date | Cl. 24.5 (Schedule 3) | + / - |  | 15% | Date | Date
|  |  |  | a | [8 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 0% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = ( f + h ) * 15% | P = N + O
1 | IPA - 1 | 2024-11-01 | CIL01003-GENCORR-000027 | 2024-12-17 | 118750 | 118750 | 0 | 0 | 118750 |  | 1 | 1TB01003-003F08-AMA-LTR-0005 | 2025-01-11 | 2025-01-07 | -4 | 118750 | 118750 | 0 | 0 | 118750 | CIL01003-RIA-000001 | 2025-01-22 |  | 2025-04-21 | 2025-02-21 | -59 | 118750 | 17812.5 | 136562.5 | 136562.5 | 136562.5
2 | IPA - 2 | 2024-12-01 | CIL01003-GENCORR-000058 | 2025-01-07 | 310538.89 | 191788.89 | 0 | 0 | 191788.89 | 2 | 2 | 1TB01003-003F08-AMA-LTR-0006 | 2025-01-15 | 2025-01-28 | 13 | 310545 | 191795 | 0 | 0 | 191795 | CIL01003-RIA-000002 | 2025-01-22 |  | 2025-04-21 | 2025-02-21 | -59 | 191795 | 28769.25 | 220564.25 | 357126.75 | 220564.25
3 | IPA - 3 | 2025-01-01 | CIL01003-GENCORR-000072 | 2025-01-30 | 508438.89 | 197900 | 0 | 0 | 197900 |  | 3 | 1TB01003-003F08-AMA-LTR-0007 | 2025-02-17 | 2025-02-20 | 3 | 508445 | 197900 | 0 | 0 | 197900 | CIL01003-RIA-000003 | 2025-03-03 |  | 2025-05-19 | 2025-04-02 | -47 | 197900 | 29685 | 227585 | 584711.75
4 | IPA - 4 | 2025-02-01 | CIL01003-GENCORR-000078 | 2025-03-05 | 686658.68 | 178219.79 | 0 | 0 | 178219.79 |  | 4 | 1TB01003-003F08-AMA-LTR-0008 | 2025-03-01 | 2025-03-26 | 25 | 686664.79 | 178219.79 | 0 | 0 | 178219.79 | CIL01003-RIA-000004 | 2025-04-03 |  | 2025-05-19 | 2025-05-03 | -16 | 178219.79 | 26732.9685 | 204952.7585 | 789664.5085
5 | IPA - 5 | 2025-03-01 | CIL01003-GENCORR-000082 | 2025-04-03 | 929971.18 | 243312.5 | 0 | 0 | 243312.5 |  | 5 | 1TB01003-003F08-AMA-LTR-0009 | 2025-04-27 | 2025-04-24 | -3 | 929977.29 | 243312.5 | 0 | 0 | 243312.5 | CIL01003-RIA-000005 | 2025-05-06 |  | 2025-06-05 | 2025-06-05 | 0 | 243312.5 | 36496.875 | 279809.375 | 1069473.8835
6 | IPA - 6 | 2025-04-01 | CIL01003-GENCORR-000087 | 2025-05-05 | 1162716.18 | 232745 | 0 | 0 | 232745 |  | 6 | 1TB01003-003F08-AMA-LTR-0010 | 2025-05-08 | 2025-05-26 | 18 | 1162722.29 | 232745 | 0 | 0 | 232745 | CIL01003-RIA-000006 | 2025-05-12 |  | 2025-06-05 | 2025-06-11 | 6 | 232745 | 34911.75 | 267656.75 | 1337130.6335
7 | IPA - 7 | 2025-05-01 | CIL01003-GENCORR-000102 | 2025-06-04 | 1389983.93 | 227267.75 | 0 | 0 | 227267.75 |  | 7 | 1TB01003-003F08-AMA-LTR-0011 | 2025-06-24 | 2025-06-25 | 1 | 1389990.04 | 227267.75 | 0 | 0 | 227267.75 | CIL01003-RIA-000007 | 2025-07-02 |  | 2025-07-23 | 2025-08-01 | 9 | 232745 | 34911.75 | 267656.75 | 1604787.3835
8 | IPA - 8 | 2025-06-01 | CIL01003-GENCORR-000105 | 2025-07-04 | 1593009.43 | 203025.5 | 0 | 0 | 203025.5 |  | 8 | 1TB01003-003F08-AMA-LTR-0012 | 2025-07-13 | 2025-07-25 | 12 | 1593015.54 | 203025.5 | 0 | 0 | 203025.5 | CIL01003-RIA-000008 | 2025-08-05 |  | 2025-08-31 | 2025-09-04 | 4 | 203025.5 | 30453.825 | 233479.325 | 1838266.7085
9 | IPA - 9 | 2025-07-01 | CIL01003-GENCORR-000112 | 2025-08-04 | 1835720.54 | 242711.11 | 0 | 0 | 242711.11 |  | 9 | 1TB01003-003F08-AMA-LTR-0014 | 2025-08-19 | 2025-08-25 | 6 | 1835726.65 | 242711.11 | 0 | 0 | 242711.11 | CIL01003-RIA-000009 | 2025-09-02 |  | 2025-10-06 | 2025-10-02 | -4 | 242711.11 | 36406.6665 | 279117.7765 | 2117384.485
10 | IPA - 10 | 2025-08-01 | CIL01003-GENCORR-000119 | 2025-09-02 | 2056017.04 | 220296.5 | 0 | 0 | 220296.5 |  | 10 | 1TB01003-003F08-AMA-LTR-0015 | 2025-09-14 | 2025-09-23 | 9 | 2056023.15 | 220296.5 | 0 | 0 | 220296.5 | CIL01003-RIA-0000010 | 2025-09-22 |  |  | 2025-10-22 |  | 242711.11 | 36406.6665 | 279117.7765 | 2396502.2615
11 | IPA - 11 | 2025-09-01 | CIL01003-GENCORR-000123 | 2025-09-22 | 2299517.04 | 243500 | 0 | 0 | 243500 |  | 11 | 1TB01003-003F08-AMA-LTR-0016 | 2025-09-24 | 2025-10-13 | 19 | 2299523.15 | 243500 | 0 | 0 | 243500 | CIL01003-RIA-0000011 | 2025-10-03 |  |  | 2025-11-02 |  | 242711.11 | 36406.6665 | 279117.7765 | 2675620.038
12 | IPA - 12 | 2025-10-01 | CIL01003-GENCORR-000133 | 2025-11-05 | 2552011.87 | 252494.83 | 0 | 0 | 252494.83 |  | 12 | 1TB01003-003F08-AMA-LTR-0017 | 2025-11-18 | 2025-11-26 | 8 | 2552017.98 | 252494.83 | 0 | 0 | 252494.83 | CIL01003-RIA-000012 | 2025-12-08 |  |  | 2026-01-07 |  | 242711.11 | 36406.6665 | 279117.7765 | 2954737.8145
13 | IPA - 13 | 2025-11-01 | CIL01003-GENCORR-000138 | 2025-12-09 | 2768534.95 | 216523.08 | 0 | 0 | 216523.08 |  | 13 | 1TB01003-003F08-AMA-LTR-0018 | 2025-12-22 | 2025-12-30 | 8 | 2768541.06 | 216523.08 | 0 | 0 | 216523.08 | CIL01003-RIA-000013 | 2026-01-15 |  |  | 2026-02-14 |  | 242711.11 | 36406.6665 | 279117.7765 | 3233855.591
14 | IPA - 14 | 2025-12-01 | CIL01003-GENCORR-000141 | 2026-01-06 | 2970523.84 | 201988.89 | 0 | 0 | 201988.89 |  | 14 | 1TB01003-003F08-AMA-LTR-0020 | 2026-01-24 | 2026-01-27 | 3 | 2970529.95 | 201988.89 | 0 | 0 | 201988.89 | CIL01003-RIA-000014 | 2026-02-10 |  | 2026-04-04 | 2026-03-12 |  | 201988.89 | 30298.3335 | 232287.2235 | 3466142.8145
15 | IPA - 15 | 2026-01-01 | CIL01003-GENCORR-000147 | 2026-02-04 | 3134777.69 | 164253.85 | 0 | 0 | 164253.85 |  | 15 | 1TB01003-003F08-AMA-LTR-0022 | 2026-02-10 | 2026-02-25 | 15 | 3134783.8 | 164253.85 | 0 | 0 | 164253.85 | CIL01003-RIA-000015 | 2026-02-25 |  | 2026-04-04 | 2026-03-27 |  | 164253.85 | 24638.0775 | 188891.9275 | 3655034.742
16 | IPA - 16 | 2026-02-01 | CIL01003-GENCORR-000151 | 2026-03-08 | 3278002.69 | 143225 | 0 | 0 | 143225 |  | 16 | 1TB01003-003F08-AMA-LTR-0023 | 2026-04-12 | 2026-03-29 | -14 | 3278008.8 | 143225 | 0 | 0 | 143225 | CIL01003-RIA-000016 | 2026-04-24 |  |  | 2026-05-24
17 | IPA - 17 | 2026-03-01 | CIL01003-GENCORR-000157 | 2026-04-08 | 3430824.91 | 152822.22 | 0 | 0 | 152822.22 |  | 17 | 1TB01003-003F08-AMA-LTR-0024 | 2026-04-23 | 2026-04-29 | 6 | 3430831.02 | 152822.22 | 0 | 0 | 152822.22 | CIL01003-RIA-000017 | 2026-05-04 |  |  | 2026-06-03
18 | IPA - 18 | 2026-04-01 | CIL01003-GENCORR-000160 | 2026-05-06 | 3597732.6 | 166907.69 | 0 | 0 | 166907.69 |  | 18 | 1TB01003-003F08-AMA-LTR-0026 | 2026-05-12 | 2026-05-27 | 15 | 3597738.71 | 166907.69 | 0 | 0 | 166907.69 | CIL01003-RIA-000018 | 2026-06-25 |  |  | 2026-07-25
19 | IPA - 19 | 2026-05-01 | CIL01003-GENCORR-000163 | 2026-06-05 | 3733359.52 | 135626.92 | 0 | 0 | 135626.92 |  | 19 | 1TB01003-003F08-AMA-LTR-0028 | 2026-06-25 | 2026-06-26 | 1 | 3733365.63 | 135626.92 | 0 | 0 | 135626.92 | CIL01003-RIA-000019 | 2026-07-23 |  |  | 2026-08-22
20 | IPA - 20 | 2026-07-01 | CIL01003-GENCORR-000165 | 2026-07-02 | 3831359.52 | 98000 | 0 | 0 | 98000 |  | 20 | 1TB01003-003F08-AMA-LTR-0029 | 2026-07-11 | 2026-07-23 | 12 | 3831365.63 | 98000 | 0 | 0 | 98000 | CIL01003-RIA-000020 | 2026-08-17 |  |  | 2026-09-16
21 | IPA - 21 | 2026-08-01 | CIL01003-GENCORR-000165 | 2026-08-10 | 3853996.24 | 22636.72 | 0 | 0 | 22636.72 |  | 21 | 1TB01003-003F08-AMA-LTR-0032 | 2026-08-17 | 2026-08-31 | 14 | 3854002.35 | 22636.72 | 0 | 0 | 22636.72 | CIL01003-RIA-000021 | 2026-09-11 |  |  | 2026-10-11
22 | IPA - 22 | 2026-08-01 | CIL01003-GENCORR-000171 | 2026-09-03 | 3873841.76 | 19845.52 | 0 | 0 | 19845.52 |  | 22 | 1TB01003-003F08-AMA-LTR-0033 | 2026-09-08 | 2026-09-24 | 16 | 3873847.87 | 19845.52 | 0 | 0 | 19845.52 | CIL01003-RIA-000022 | 2026-09-28 |  |  | 2026-10-28
TOTAL (SAR) | [5 empty] | 3873841.76 | 0 | 0 | 3873841.76 |  | TOTAL (SAR) | [5 empty] | 3873847.87 | 0 | 0 | 3873847.87 | TOTAL (SAR) | [5 empty] | 3178291.08 | 476743.662 | 3655034.742 | 2117384.485
267656.75
[12 empty] | 0.036364 | [7 empty] | 421532.29
|  |  |  | 2021-01-01 | [15 empty] | 484762.1335 |  |  |  |  | 2020-09-20
|  |  |  | 2020-11-17 | [20 empty] | 2020-08-06
2020-06-04
2025-06-04
51
2025-07-25
Formulas:
Issue date of IPC per Contract (21days) = [Date Aconex Letter]+21
Payment Date as per Contract (30days) = +[INVOICE DATE]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45
AMAALA CM TEAM Aconex Letter Ref. = +[AMAALA CM TEAM Aconex Letter Ref., row above]+M45

## Schedule H EURO
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
PS.003F07 - Euro Consult (COO 6)
STAGE 1 - PAYMENT APPLICATION | [10 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) |  | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONSULTANT INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | N/A | N/A | SAR |  |  |  | Date | Cl. 24.2 | + / - | SAR | SAR | N/A | N/A | SAR |  |  | Date | Date | Cl. 24.5 (Schedule 3) | + / - |  | 15% | Date | Date
|  |  |  | a | [8 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 0% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = ( f + h ) * 15% | P = N + O
1 | IPA - 1 | 2024-12-25 | ECC01003-GENCORR-000001 | 2025-01-12 | 16136.06 | 16136.06 | 0 | 0 | 16136.06 |  | 1 | 1TB01003-003F07-AMA-LTR-0005 | 2025-01-20 | 2025-02-02 | 13 | 16136.06 | 16136.06 | 0 | 0 | 16136.06 | ECC01003-RIA-000001 | 2025-02-25 |  | 2025-04-21 | 2025-03-27 | -25 | 16136.06 | 2420.409 | 18556.469 | 18556.469 | 18556.469
2 | IPA - 2 | 2025-01-25 | ECC01003-GENCORR-000003 | 2025-01-28 | 54739.36 | 38603.3 | 0 | 0 | 38603.3 | 2 | 2 | 1TB01003-003F07-AMA-LTR-0006 | 2025-02-17 | 2025-02-18 | 1 | 54739.36 | 38603.3 | 0 | 0 | 38603.3 | ECC01003-RIA-000002 | 2025-03-17 |  | 2025-04-26 | 2025-04-16 | -10 | 38603.3 | 5790.495 | 44393.795 | 62950.264 | 44393.795
3 | IPA - 3 | 2025-02-05 | ECC01003-GENCORR-000006 | 2025-03-18 | 64000.42 | 9261.06 | 0 | 0 | 9261.06 |  | 3 | 1TB01003-003F07-AMA-LTR-0007 | 2025-04-15 | 2025-04-08 | -7 | 64000.42 | 9261.06 | 0 | 0 | 9261.06 | ECC01003-RIA-000003 | 2025-05-12 |  | 2025-06-30 | 2025-06-11 | -19 | 9261.06 | 1389.159 | 10650.219 | 73600.483
4 | IPA - 4 | 2025-06-01 | ECC01003-GENCORR-000011 | 2025-07-17 | 84414 | 20413.58 | 0 | 0 | 20413.58 |  | 4 | 1TB01003-003F07-AMA-LTR-0008 | 2025-08-05 | 2025-08-07 | 2 | 84414 | 20413.58 | 0 | 0 | 20413.58 | ECC01003-RIA-000006 | 2025-08-19 |  | 2025-08-31 | 2025-09-18 | 18 | 20413.58 | 3062.037 | 23475.617 | 97076.1
5 | IPA - 5 | 2026-03-01 | ECC01003-GENCORR-000018 | 2026-04-12 | 128677.64 | 44263.64 | 0 | 0 | 44263.64 |  | 5 | 1TB01003-003F07-AMA-LTR-0009 | 2026-04-23 | 2026-05-03 | 10 | 128677.64 | 44263.64 | 0 | 0 | 44263.64 | ECC01003-RIA-000008 | 2026-05-13 |  |  | 2026-06-12
TOTAL (SAR) | [5 empty] | 128677.64 | 0 | 0 | 128677.64 |  | TOTAL (SAR) | [5 empty] | 128677.64 | 0 | 0 | 128677.64 | TOTAL (SAR) | [5 empty] | 84414 | 12662.1 | 97076.1 | 97076.1
0
[12 empty] | 0.036364 | [7 empty] | 64677.22
|  |  |  | 2021-01-01 | [15 empty] | 74378.803 |  |  |  |  | 2020-09-20
|  |  |  | 2020-11-17 | [20 empty] | 2020-08-06
2020-06-04
Formulas:
Issue date of IPC per Contract (21days) = [Date Aconex Letter]+21
Payment Date as per Contract (30days) = +[INVOICE DATE]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H EURO CO027
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
PS.003F09 - Euro Consult (COO 27)
STAGE 1 - PAYMENT APPLICATION | [10 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) |  | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONSULTANT INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | N/A | N/A | SAR |  |  |  | Date | Cl. 24.2 | + / - | SAR | SAR | N/A | N/A | SAR |  |  | Date | Date | Cl. 24.5 (Schedule 3) | + / - |  | 15% | Date | Date
|  |  |  | a | [8 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 0% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = ( f + h ) * 15% | P = N + O
1 | IPA - 1 | 2025-02-01 | ECC01003-GENCORR-000005 | 2025-02-16 | 24000 | 24000 | 0 | 0 | 24000 |  | 1 | 1TB01003-003F09-AMA-LTR-0001 | 2025-04-15 | 2025-03-09 | -37 | 24000 | 24000 | 0 | 0 | 24000 | ECC01003-RIA-000004 | 2025-06-19 |  | 2025-07-23 | 2025-07-19 | -4 | 24000 | 3600 | 27600 | 27600 | 27600
2 | IPA - 2 | 2025-05-01 | ECC01003-GENCORR-000009 | 2025-06-02 | 36000 | 12000 | 0 | 0 | 12000 | 2 | 2 | 1TB01003-003F09-AMA-LTR-0002 | 2025-06-24 | 2025-06-23 | -1 | 36000 | 12000 | 0 | 0 | 12000 | ECC01003-RIA-000005 | 2025-07-09 |  | 2025-08-07 | 2025-08-08 | 1 | 12000 | 1800 | 13800 | 41400 | 13800
3 | IPA - 3 | June to August 25 | ECC01003-GENCORR-000013 | 2025-09-08 | 45000 | 9000 | 0 | 0 | 9000 |  | 3 | 1TB01003-003F09-AMA-LTR-0003 | 2025-09-14 | 2025-09-29 | 15 | 45000 | 9000 | 0 | 0 | 9000 | ECC01003-RIA-000007 | 2025-09-27 |  | 2025-08-07 | 2025-10-27 | 81 | 9000 | 1350 | 10350 | 51750
4 | IPA - 4 | 2026-03-01 | ECC01003-GENCORR-000019 | 2026-04-12 | 54000 | 9000 | 0 | 0 | 9000 |  | 3 | 1TB01003-003F09-AMA-LTR-0004 | 2026-04-23 | 2026-05-03 | 10 | 54000 | 9000 | 0 | 0 | 9000 | ECC01003-RIA-000009 | 2026-05-13 |  |  | 2026-06-12
TOTAL (SAR) | [5 empty] | 54000 | 0 | 0 | 54000 |  | TOTAL (SAR) | [5 empty] | 54000 | 0 | 0 | 54000 | TOTAL (SAR) | [5 empty] | 45000 | 6750 | 51750 | 41400
0
[12 empty] | 0.036364 | [7 empty] | 9000
|  |  |  | 2021-01-01 | [15 empty] | 10350 |  |  |  |  | 2020-09-20
|  |  |  | 2020-11-17 | [20 empty] | 2020-08-06
2020-06-04
Formulas:
Issue date of IPC per Contract (21days) = [Date Aconex Letter]+21
Payment Date as per Contract (30days) = +[INVOICE DATE]+30
Payment Date as per Contract (30days) = [Payment Date as per Contract (30days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H ARMETAL
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
ARMETAL (PO 2250084)
STAGE 1 - PAYMENT APPLICATION | [10 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) |  | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (15 days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (21days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 5% | SAR |  |  |  | Date | Cl. 12.3.3 | + / - | SAR | SAR | 0% | 5% | SAR |  |  | Date | Date | Cl.12.4.1 | + / - |  | 15% | Date | Date
|  |  |  | a | [8 empty] | b | c = a + 15 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 21 | m = l - k | n = i | o = n * 15% | P = N + O
1 | IPA - 1 | 35% Mobilization | AMI01003-TRANSMIT-000004 | 2025-01-23 | 2495482.5 | 2495482.5 | 0 | -124774.13 | 2370708.37 |  | 1 | 1TB01003-003C33-AMA-LTR-0006 | 2025-02-26 | 2025-02-07 | -19 | 2495482.5 | 2495482.5 | 0 | -124774.13 | 2370708.37 | AMI01003-RIA-000001 | 2025-04-07 |  | 2025-04-21 | 2025-04-28 | 7 | 2370708.37 | 355606.2555 | 2726314.6255 | 2726314.6255 | 2726314.6255
2 | IPA - 2 | Shopdrawings & Delivered Raw Materials | AMI01003-TRANSMIT-000007 | 2025-04-29 | 4277970 | 1782487.5 | 0 | -89124.37 | 1693363.13 |  | 2 | 1TB01003-003C32-AMA-LTR-0009 | 2025-06-29 | 2025-05-14 | -46 | 4277970 | 1782487.5 | 0 | -89124.37 | 1693363.13 | AMI01003-RIA-000002 | 2025-07-16 |  | 2025-07-28 | 2025-08-06 | 9 | 1693363.13 | 254004.4695 | 1947367.5995 | 4673682.225
3 | IPA - 3 | Delivery of Fabricated SST Panels to the Jobsite | AMI01003-GENCORR-000025 | 2025-07-29 | 5176343.7 | 898373.7 | 0 | -44918.69 | 853455.01 |  | 3 | 1TB01003-003C32-AMA-LTR-0010 | 2025-08-18 | 2025-08-13 | -5 | 5176343.7 | 898373.7 | 0 | -44918.69 | 853455.01 | AMI01003-RIA-000003 | 2025-08-26 |  | 2025-10-06 | 2025-09-16 | -20 | 853455.01 | 128018.2515 | 981473.2615 | 5655155.4865
4 | IPA - 4 | 2025-09-01 | AMI01003-GENCORR-000033 | 2025-09-21 | 6702153 | 1525809.3 | 0 | -76290.46 | 1449518.84 | 4 | 4 | 1TB01003-003C32-AMA-LTR-0011 | 2025-09-22 | 2025-10-06 | 14 | 6702153 | 1525809.3 | 0 | -76290.46 | 1449518.84 | AMI01003-RIA-000004 | 2025-10-05 |  |  | 2025-10-26 |  | 1449518.84 | 217427.826 | 1666946.666 | 7322102.1525
5 | IPA - 5 | 2025-12-01 | AMI01003-GENCORR-000043 | 2026-04-05 | 6915493 | 213340 | 0 | -10667 | 202673 | 9 | 5 | 1TB01003-003C32-AMA-LTR-0017 | 2026-04-29 | 2026-04-20 | -9 | 6915493 | 213340 | 0 | -10667 | 202673
6 | IPA - 6 | 2026-06-01 | AMI01003-GENCORR-000057 | 2026-07-12 | 6982571.39 | 67078.39 | 0 | -3353.9195 | 63724.4705 | 15 | 6 | 1TB01003-003C32-AMA-LTR-0019 | 2026-04-29 | 2026-07-27 | 89 | 6982571.39 | 67078.39 | 0 | -3353.9195 | 63724.4705 | AMI01003-RIA-000006 | 2026-08-18 |  |  | 2026-09-08
TOTAL (SAR) | [5 empty] | 6982571.39 | 0 | -349128.5695 | 6633442.8205 |  | TOTAL (SAR) | [5 empty] | 6982571.39 | 0 | -349128.5695 | 6633442.8205 | TOTAL (SAR) | [5 empty] | 6367045.35 | 955056.8025 | 7322102.1525 | 5655155.4865
6982571.39
0.036364
|  |  |  | 2021-01-01 | [20 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [20 empty] | 2020-08-06
2020-06-04
Cashflow
[27 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (15 days) = [Date Aconex Letter]+15
Payment Date as per Contract (21days) = +[INVOICE DATE]+21
Payment Date as per Contract (21days) = [Payment Date as per Contract (21days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H HAM
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
HASSAN ALLAM (PO 2250145)
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21 days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30 days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | VAT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 19.4 | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.19.7 | + / - |  | 15% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = n * 15% | P = N + O
1 | IPA - 1 | 2025-05-01 | HAM01003-GENCORR-000002 | 2025-07-10 | 1425959.08 | 1425959.08 | 0 | 0 | 1425959.08 | 1 | 1TB01003-003C37-AMA-LTR-0006 | 2025-07-16 | 2025-07-31 | 15 | 1425959.08 | 1425959.08 | 0 | 0 | 1425959.08 | AMA01003-RIA-000092 | 2025-08-05 |  | 2025-08-31 | 2025-09-04 | 4 | 1425959.08 | 213893.862 | 1639852.942 | 1639852.942 | 1639852.942
2 | IPA - 2 | 2025-08-01 | Email | 2025-08-25 | 1774248.92 | 348289.84 | 0 | 0 | 348289.84 | 2 | 1TB01003-003C37-AMA-LTR-0007 | 2025-10-05 | 2025-09-15 | -20 | 1774248.92 | 348289.84 | 0 | 0 | 348289.84 | HAM01003-RIA-000001 | 2025-12-20 |  |  | 2026-01-19 |  | 348289.84 | 52243.476 | 400533.316 | 400533.316
3 | IPA - 3 | Sep-25 (Final) | HAM01003-GENCORR-000006 | 2025-11-17 | 3096124.9 | 1321875.98 | 0 | 0 | 1321875.98 | 3 | 1TB01003-003C37-AMA-LTR-0008 | 2026-01-24 | 2025-12-08 | -47 | 3096124.9 | 1321875.98 | 0 | 0 | 1321875.98 | HAM01003-RIA-000001 | 2026-02-18 |  |  | 2026-03-20
TOTAL (SAR) | [5 empty] | 3096124.9 | 0 | 0 | 3096124.9 | TOTAL (SAR) | [5 empty] | 3096124.9 | 0 | 0 | 3096124.9 | TOTAL (SAR) | [5 empty] | 1774248.92 | 266137.338 | 2040386.258 | 1639852.942
3096124.9
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21 days) = [Date Aconex Letter]+21
Payment Date as per Contract (30 days) = +[INVOICE DATE]+30
Payment Date as per Contract (30 days) = [Payment Date as per Contract (30 days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H GST
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
PS.003F12 - GST - Sustainability Accreditation Services
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21 days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30 days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 19.4 | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.19.7 | + / - |  | 5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = n * 15% | P = N + O
1 | IPC-01 | 2025-11-01 | AMA01003-PAYAP-002344 | 2026-02-23 | 0 | 0 | 0 | 0 | 0 |  | Revision requested |  |  |  | 0 |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
2 | IPC -01 | 2025-11-01 | AMA01003-PAYAP-002025 | 2025-11-25 | 63250 | 63250 | 0 | 0 | 63250 | IPC-02 | AMA01003-RAOP-002041 | 2025-12-03 | 2025-12-16 | 13 | 63250 | 63250 | 0 | 0 | 63250 | GST-RIA-000001 | 2025-12-04 |  |  | 2026-01-03 |  | 63250 | -3162.5 | 60087.5 | 60087.5
3 | IPC-02 | 2026-03-01 | AMA01003-PAYAP-002377 | 2026-04-06 | 101200 | 37950 | 0 | 0 | 37950 | IPC-03 | 1TB01003-003F12-AMA-LTR-0001 | 2026-05-10 | 2026-04-27 | -13 | 101200 | 37950 | 0 | 0 | 37950 | GST-RIA-000003 | 2026-06-25 |  |  | 2026-07-25
4 | IPC-03 | 2026-09-01 | GST01003-GENCORR-000004 | 2026-09-14 | 126500 | 25300 | 0 | 0 | 25300 | IPC-04 | 1TB01003-003F12-AMA-LTR-0002 | 2026-09-21 | 2026-10-05 | 14 | 126500 | 25300 | 0 | 0 | 25300
TOTAL (SAR) | [5 empty] | 126500 | 0 | 0 | 126500 | TOTAL (SAR) | [5 empty] | 126500 | 0 | 0 | 126500 | TOTAL (SAR) | [5 empty] | 63250 | -3162.5 | 60087.5 | 0
126500
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21 days) = [Date Aconex Letter]+21
Payment Date as per Contract (30 days) = [INVOICE DATE]+30
Payment Date as per Contract (30 days) = [Payment Date as per Contract (30 days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H BIRCH
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
FFEOSE.003D07 - Birch Street
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21 days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30 days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 19.4 | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.19.7 | + / - |  | 5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = n * 15% | P = N + O
1 | Final IPC 1 | 2026-04-01 | AMA01003-PAYAP-002380 | 2026-04-09 | 0 | 115998.975 | 0 | 0 | 115998.975 | IPC 1 | 1TB01003-003D07-AMA-LTR-0001 | 2026-04-23 | 2026-04-30 | 7 | 115998.975 | 115998.975 | 0 | 0 | 115998.975 | BIRCHSTR-RAI-000001 | 2026-06-25 |  |  | 2026-07-25 | [5 empty] | 0
TOTAL (SAR) | [5 empty] | 115998.975 | 0 | 0 | 115998.975 | TOTAL (SAR) | [5 empty] | 115998.975 | 0 | 0 | 115998.975 | TOTAL (SAR) | [5 empty] | 0 | 0 | 0 | 0
115998.975
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
[6 empty] | 30933.06 | [19 empty] | Cashflow
[6 empty] | 4639.959 | [19 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
[6 empty] | 26293.101 | [19 empty] | 11439880.26
Formulas:
Issue date of IPC per Contract (21 days) = [Date Aconex Letter]+21
Payment Date as per Contract (30 days) = [INVOICE DATE]+30
Payment Date as per Contract (30 days) = [Payment Date as per Contract (30 days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H Saudico
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
FFEOSE.003D15 - Saudico Electronic Systems
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21 days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30 days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 19.4 | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.19.7 | + / - |  | 5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = n * 15% | P = N + O
1 | Final IPC 1 | 2026-04-01 | AMA01003-FINSTAT-000017 | 2026-02-10 | 0 | 34719 | 0 | 0 | 34719 | IPC 1 | 1TB01003-003D15-AMA-LTR-0001 | 2026-02-10 | 2026-03-03 | 21 | 34719 | 34719 | 0 | 0 | 34719 | SAUDICOE-RIA-000001 | 2026-04-21 |  |  | 2026-05-21 | [5 empty] | 0
TOTAL (SAR) | [5 empty] | 34719 | 0 | 0 | 34719 | TOTAL (SAR) | [5 empty] | 34719 | 0 | 0 | 34719 | TOTAL (SAR) | [5 empty] | 0 | 0 | 0 | 0
34719
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21 days) = [Date Aconex Letter]+21
Payment Date as per Contract (30 days) = [INVOICE DATE]+30
Payment Date as per Contract (30 days) = [Payment Date as per Contract (30 days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H Saudico (2)
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
FFEOSE.003D09 - Saudico Electronic Systems
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21 days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30 days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 19.4 | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.19.7 | + / - |  | 5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = n * 15% | P = N + O
1 | Final IPC 1 | 2026-04-01 | AMA01003-FINSTAT-000018 | 2026-02-10 | 0 | 353487.06 | 0 | 0 | 353487.06 | IPC 1 | 1TB01003-003D09-AMA-LTR-0001 | 2026-02-10 | 2026-03-03 | 21 | 353487.06 | 353487.06 | 0 | 0 | 353487.06 | SAUDICOE-RIA-000002 | 2026-05-05 |  |  | 2026-06-04 | [5 empty] | 0
TOTAL (SAR) | [5 empty] | 353487.06 | 0 | 0 | 353487.06 | TOTAL (SAR) | [5 empty] | 353487.06 | 0 | 0 | 353487.06 | TOTAL (SAR) | [5 empty] | 0 | 0 | 0 | 0
353487.06
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21 days) = [Date Aconex Letter]+21
Payment Date as per Contract (30 days) = [INVOICE DATE]+30
Payment Date as per Contract (30 days) = [Payment Date as per Contract (30 days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H PeopleVine
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
FFEOSE.003D16 - PeopleVine Implementation
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21 days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30 days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 19.4 | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.19.7 | + / - |  | 5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = n * 15% | P = N + O
1 | Advance Payment | 2026-04-01 | AMA01003-PAYAP-002542 | 2026-06-06 | 0 | 146306.25 | 0 | 0 | 146306.25 | IPC 1 | 1TB01003-003D16-AMA-LTR-0001 | 2026-06-09 | 2026-06-27 | 18 | 146306.25 | 146306.25 | 0 | 0 | 146306.25 | AMA01003-RIA-000254 | 2026-06-14 |  |  | 2026-07-14 | [5 empty] | 0
TOTAL (SAR) | [5 empty] | 146306.25 | 0 | 0 | 146306.25 | TOTAL (SAR) | [5 empty] | 146306.25 | 0 | 0 | 146306.25 | TOTAL (SAR) | [5 empty] | 0 | 0 | 0 | 0
146306.25
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21 days) = [Date Aconex Letter]+21
Payment Date as per Contract (30 days) = [INVOICE DATE]+30
Payment Date as per Contract (30 days) = [Payment Date as per Contract (30 days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H Reachware
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
FFEOSE.003D14 - TRA - Zatca Integration with Reachware
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21 days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30 days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 19.4 | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.19.7 | + / - |  | 5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = n * 15% | P = N + O
1 | IPC 01 | 2026-06-01 | Email - Invoices | 2026-07-07 | 0 | 37477.5 | 0 | 0 | 37477.5 | IPC 1 | 1TB01003-003D14-AMA-LTR-0001 | 2026-07-11 | 2026-07-28 | 17 | 37477.5 | 37477.5 | 0 | 0 | 37477.5 | FADAA-RIA-000001 | 2026-08-16 |  |  | 2026-09-15 | [5 empty] | 0
TOTAL (SAR) | [5 empty] | 37477.5 | 0 | 0 | 37477.5 | TOTAL (SAR) | [5 empty] | 37477.5 | 0 | 0 | 37477.5 | TOTAL (SAR) | [5 empty] | 0 | 0 | 0 | 0
37477.5
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21 days) = [Date Aconex Letter]+21
Payment Date as per Contract (30 days) = [INVOICE DATE]+30
Payment Date as per Contract (30 days) = [Payment Date as per Contract (30 days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H Deep Cleaning
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
CN.003F13 - Enviro - Deep Cleaning
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21 days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30 days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 19.4 | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.19.7 | + / - |  | 5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = n * 15% | P = N + O
1 | IPC 01 | 2026-06-01 | EFM01003-GENCORR-000001 | 2026-06-25 | 0 | 792132.29 | 0 | 0 | 792132.29 | IPC 1 | 1TB01003-003F13-AMA-LTR-0001 | 2026-07-11 | 2026-07-16 | 5 | 792132.29 | 792132.29 | 0 | 0 | 792132.29 |  |  |  |  | 1900-01-29 | [5 empty] | 0
TOTAL (SAR) | [5 empty] | 792132.29 | 0 | 0 | 792132.29 | TOTAL (SAR) | [5 empty] | 792132.29 | 0 | 0 | 792132.29 | TOTAL (SAR) | [5 empty] | 0 | 0 | 0 | 0
792132.29
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21 days) = [Date Aconex Letter]+21
Payment Date as per Contract (30 days) = [INVOICE DATE]+30
Payment Date as per Contract (30 days) = [Payment Date as per Contract (30 days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H Info Cor
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
CN.003F13 - Infor Saudi Arabia Limited
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21 days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30 days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 19.4 | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.19.7 | + / - |  | 5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = n * 15% | P = N + O
1 | IPC 01 - Final | 2026-07-01 | Email | 2026-08-05 | 0 | 58307.19 | 0 | 0 | 58307.19 | IPC 1 | 1TB01003-003D12-AMA-LTR-0001 | 2026-08-11 | 2026-08-26 | 15 | 58307.19 | 58307.19 | 0 | 0 | 58307.19 | AMA01003-RIA-000255 | 2026-08-19 |  |  | 2026-09-18 | [5 empty] | 0
TOTAL (SAR) | [5 empty] | 58307.19 | 0 | 0 | 58307.19 | TOTAL (SAR) | [5 empty] | 58307.19 | 0 | 0 | 58307.19 | TOTAL (SAR) | [5 empty] | 0 | 0 | 0 | 0
58307.19
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21 days) = [Date Aconex Letter]+21
Payment Date as per Contract (30 days) = [INVOICE DATE]+30
Payment Date as per Contract (30 days) = [Payment Date as per Contract (30 days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule H Al Futaim
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
CN.003F13 - Al Futtaim Pioneer Elevators - Al Futtaim Pioneer
STAGE 1 - PAYMENT APPLICATION | [9 empty] | STAGE 2 - CERTIFICATION | [9 empty] | STAGE 3 - PAYMENT
SR Nr. | PAYMENT APPLICATION | MONTH | Aconex Letter Ref. | Date Aconex Letter | CUMMULATIVE CLAIMED AMT (Excl. VAT) | GROSS CLAIMED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CLAIMED AMT FOR THE MONTH (Excl. VAT) | IPC Nr. | AMAALA CM TEAM Aconex Letter Ref. | Date Aconex Letter | Issue date of IPC per Contract (21 days) | Differ Days | CUMMULATIVE CERTIFIED AMT (Excl. VAT) | GROSS CERTIFIED AMT FOR THE MONTH (Excl. VAT) | ADV RECOVERY | RETENTION | NET CERTIFIED AMT FOR THE MONTH (Excl. VAT) | CONTRACTOR INVOICE ACONEX REF | INVOICE DATE | DATE AMAALA ACONEX REF FOR INV APPROVAL | PAID BY FINANCE DATE | Payment Date as per Contract (30 days) | Differ Days | NET PAYMENT FOR THE MONTH (Excl. VAT) | WHT AMOUNT FOR THE MONTH | FINAL AMT TO BE PAID FOR THE MONTH | CUMMUALTIVE PAID AMT
|  |  |  | Date | SAR | SAR | 0% | 0% | SAR |  |  | Date | Cl. 19.4 | + / - | SAR | SAR | 0% | 0% | SAR |  |  | Date | Date | Cl.19.7 | + / - |  | 5% | Date | Date
|  |  |  | a | [7 empty] | b | c = a + 21 | d = c- d | e | f | g = f * 0% | h = f * 10% | i = f + g + h |  | j |  | k | l = j + 30 | m = l - k | n = i | o = n * 15% | P = N + O
1 | IPC 01 - Adv | 2026-08-01 | FUE01003- GENCORR-000001 | 2026-08-05 | 0 | 103793.25 | 0 | 0 | 103793.25 | IPC 1 | 1TB01003-003C328-AMA-LTR-0006 | 2026-08-13 | 2026-08-26 | 13 | 103793.25 | 103793.25 | 0 | 0 | 103793.25 |  |  |  |  | 1900-01-29 | [5 empty] | 0
2 | IPC 02 | 2026-08-01 | FUE01003- GENCORR-000004 | 2026-08-30 | 311379.75 | 207586.5 | 0 | 0 | 207586.5 | IPC 2 | 1TB01003-003C328-AMA-LTR-0006 | 2026-08-13 | 2026-09-20 | 38 | 103793.25 | 207586.5 | 0 | 0 | 207586.5
TOTAL (SAR) | [5 empty] | 311379.75 | 0 | 0 | 311379.75 | TOTAL (SAR) | [5 empty] | 311379.75 | 0 | 0 | 311379.75 | TOTAL (SAR) | [5 empty] | 0 | 0 | 0 | 0
311379.75
0.036364
|  |  |  | 2021-01-01 | [19 empty] | 2020-09-20
|  |  |  | 2020-11-17 | [19 empty] | 2020-08-06
2020-06-04
Cashflow
[26 empty] | 2023-10-23 | 2023-11-23 | 2023-12-23
11439880.26
Formulas:
Issue date of IPC per Contract (21 days) = [Date Aconex Letter]+21
Payment Date as per Contract (30 days) = [INVOICE DATE]+30
Payment Date as per Contract (30 days) = [Payment Date as per Contract (30 days), row above]-45
Date Aconex Letter = [Date Aconex Letter, row above]-45

## Schedule I
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
#REF!
Transaction Number | Supplier Name | Line Description | New AMD Coding | CBS | Program Name | Program No. | Forecast May-22 | Actual May-22 | Difference | Forecast Jun-22 | Actual june-22 | Difference | Forecast Jul-22 | Actual Jul-22 | Difference | Forecast Aug-22 | Actual Aug-22 | Difference | Forecast Sep-22 | Actual Sep-22 | Difference | Forecast Oct-22 | Actual Oct-22 | Difference | Forecast Nov-22 | Actual Nov-22 | Difference | Forecast Dec-22 | Actual Dec-22 | Difference | Forecast Jan-23 | Actual Jan-23 | Difference | Forecast Feb-23 | Actual Feb-23 | Difference | Forecast Mar-23 | Actual Mar-23 | Difference | Forecast Apr-23 | Actual Apr-23 | Difference | Forecast May-23 | Actual May-23 | Difference | Forecast Jun-23 | Actual Jun-23 | Difference | Forecast Jul-23 | Actual Jul-23 | Difference | Forecast Aug-23 | Actual Aug-23 | Difference | Forecast Sep-23 | Actual Sep-23 | Difference | Forecast Oct-23 | Actual Oct-23 | Difference | Forecast Nov-23 | Actual Nov-23 | Difference | Forecast Dec-23 | Actual Dec-23 | Difference | Forecast Jan-24 | Actual Jan-24 | Difference | Forecast Feb-24 | Actual Feb-24 | Difference | Forecast Mar-24 | Actual Mar-24 | Difference | Forecast April-24 | Actual April-24 | Difference | Forecast May-24 | Actual May-24 | Difference | Forecast Jun-24 | Actual Jun-24 | Difference | Forecast July-24 | Actual July-24 | Difference | Forecast Aug-24 | Actual Aug-24 | Difference | Forecast Sep-24 | Actual Sep-24 | Difference | Forecast Oct-24 | Actual Oct-24 | Difference | Forecast Nov-24 | Actual Nov-24 | Difference | Forecast Dec-24 | Actual Dec-24 | Difference | Forecast Jan-25 | Actual Jan-25 | Difference | Forecast Feb-25 | Actual Feb-25 | Difference | Forecast Mar-25 | Actual Mar-25 | Difference | Forecast Apr-25 | Actual Apr-25 | Difference | Forecast May-25 | Actual May-25 | Difference | Forecast Jun-25 | Actual Jun-25 | Difference | Forecast Jul-25 | Actual Jul-25 | Difference | Forecast Aug-25 | Actual Aug-25 | Difference | Forecast Sep-25 | Actual Sep-25 | Difference | Forecast Oct-25 | Actual Oct-25 | Difference | Forecast Nov-25 | Actual Nov-25 | Difference | Forecast Dec-25 | Actual Dec-25 | Difference | Forecast Jan-26 | Actual Jan-26 | Difference | Forecast Feb-26 | Actual Feb-26 | Difference | Forecast Mar-26 | Forecast Apr-26 | Forecast May-26 | Total Cashflow Amount | 0 | 218748.65 | 481423.411
2220032 | NSCC International Saudi Contracting | Piling Works - AYC | 1TB.01.003.01 | CN | Marina Village | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 556920.413 | 556920.413 | 0 | 0 | 0 | 0 | 613807.099 | 0 | 613807.099 | 319906.587 | 319906.587 | 0 | 45414.85 | 12989.69 | 32425.16 | 0 | 0 | 0 | 24782.42 | 2802015.19 | -2777232.77 | 5385552.66 | 5385552.655 | 0.005 | 0 | 218748.649 | -218748.649 | 0 | 0 | 0 | 0 | 481423.411 | -481423.411 |  | 0 | 0 | 0 | 0 | [7 empty] | 0 | 726213.23 | -726213.23 | [25 empty] | 364230 | -364230 | [7 empty] | 2296100.28 | -2296100.28 | [7 empty] | 0 | 0 | [7 empty] | 0 | 0 | [7 empty] | 0 | 0 | [7 empty] | 0 | 0 | [9 empty] | 0 | 481423.411 | 218748.65 | 481423.411
2200445 | Dewan Architects & Engineers | Triple Bay Yacht Club Lead Consultant Detailed Design | 1TB.01.003.01 | CN | Marina Village | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1135879.458 | 1135879.458 | 0 | 0 | 0 | 0 | 45604.9 | 0 | 45604.9 | 66000 | 66000 | 9.3132e-10 | 288452.4 | 238952.4 | 49500 | 0 | 0 | 0 | 717704.8 | 717704.8 | 0 | 337720 | 169552 | 168168 | 200868 | 274405.15 | -73537.15 | 0 | 249405.15 | -249405.15 | 12800 | 0 | 12800 | 103400 | 45250 | 58150 | 21450 | 0 | 21450 | 181592 | 0 | 181592 | 140000 | 165273.6 | -25273.6 | 453000 |  | 453000 | 305584.35 | 77920 | 227664.35 | 16500 | 0 | 16500 | 145792.8 | 0 | 145792.8 |  |  |  |  | 0 | 0 |  |  |  |  | 184752.8 | -184752.8 | 107789.05 | 77920 | 29869.05 | 44301.9 | 0 | 44301.9 |  |  |  |  | 0 | 0 | 74170.95 | 29869.05 | 44301.9 | 466536 | 0 | 466536 | 38500 | 0 | 38500 | 60500 | 0 | 60500 |  | 816870.6 | -816870.6 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 42669.05 | 194386.2 | 48019.05
2210224 | Soil Improvement Contracting Co. | Triple Bay Ground Improvement | 1TB.01.003.01 | CN | Marina Village | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17100 | -17100 | 75600 | 59850 | 15750 | 0 |  | 0 | 0 |  |  | 0 |  |  |  | 23666.4 | -23666.4 | 0 | 0 | 0 | 6000 | 0 | 6000 | 6000 | 0 | 6000 | 6000 | 3522.6 | 2477.4 | [7 empty] | 6104.7 | -6104.7 |  |  |  |  | 8221.5 | -8221.5 |  |  | 0 |  |  |  |  | 4212 | -4212 | [15 empty] | 0 | 8221.5 | -8221.5 | [48 empty] | 0 | 6000
2220038 | Green Business Certification Inc. | Sustainability Accreditation, third party technical reviews and verification of LEED-registered AMMLA Projects | 1TB.01.003.01 | CN | Marina Village | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 13500.1125 | -13500.1125 | [8 empty] | 0 | [81 empty] | 0 | 0
220010 | HKS Architects Ltd - Design Competition Fees | Triple Bay Marine Yacht Club - Design Architect Services | 1TB.01.003.01 | PS | Marina Village | 1 | 0 | 0 | 0 | 2180000 | 2180000 | 0 | 545000 | 545000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [8 empty] | 0 | [81 empty] | 0 | 0
2200375 | HKS Architects Ltd - Design Architect Services | Triple Bay Marine Yacht Club - Design Architect Services | 1TB.01.003.01 | PS | Marina Village | 1 | 513480 | 513480 | 0 | 0 | 0 | 0 | 2542470.48 | 2542470.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350947.872 | 350947.872 | 0 | 0 | 0 | 0 |  |  | 0 | 177511.93 |  | 177511.93 | 177511.93 | 0 | 177511.93 | 177511.93 | 0 | 177511.93 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  |  |  | 87736.39 | -87736.39 |  |  | 0 | [81 empty] | 0 | #REF! | 0 | 0
2210167 | Applied Technology and Management Inc (Dubai BR) | Rapid Peer Review of AMAALA Existing Design of Yachting and Marina Facilities | 1TB.01.003.01 | CN | Marina Village | 1 | 0 | 0 | 0 | 0 | 4500 | -4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [8 empty] | 0 | [81 empty] | 0 | 0
2230023 | SAB - AMAALA Yacht Club Construction Contract | Structural Concrete, Wet Trades, BOH Fit out, Pools and Water Features, Structural Steel, Glazing, Glass Balustrades, Aluminum Soffits, SFS and GRC, Render Façade, Roof Waterproofing, MEP, ICT/ELV | 1TB.01.003.01 | CN | Marina Village | 1 | [30 empty] | 26095541.44 | 0 | 26095541.44 | 26095541.44 | 0 | 26095541.44 |  |  | 0 | 26095541.44 | 26095541.44 | 0 | 5979424 | 0 | 5979424 |  | 12971542.49 | -12971542.49 | 5055385.55 | 0 | 5055385.55 | 12243673.52 | 5680375.76 | 6563297.76 | 6080555.8248 | 48171310.414 | -42090754.5892 | 10214407.898 | 3077391.384 | 7137016.514 | 3596701 | 0 | 3596701 | 5231600 | 2484352.49 | 2747247.51 | 5075060.9 | 4978201.85 | 96859.05 | 3750000 | 0 | 3750000 | 0 | 0 |  |  |  |  | 0 | 33692364.72 | -33692364.72 | 0 |  |  |  | 37508046.03 | -37508046.03 | 0 | 0 | 0 | [6 empty] | 14629962.7255 | 17663126.71 | -3033163.9845 | 9526208.68 | 0 | 9526208.68 | 8691997.07 | 0 | 8691997.07 | 7151294 | 7775637.5478 | -624343.5478 | 3498261.74 | 5114250.087 | -1615988.347 | 4197914.09 | 3862121.507 | 335792.583 | 4081475.02 | 1873214.39 | 2208260.63 | 3899538.47 | 2241917.6783 | 1657620.7917 | 5755976.9 | 4666401.513 | 1089575.387 | 5755976.9 | 10309315.076 | -4553338.176 | 5755976.9 | 4213176.8348 | 1542800.0652 | 5755976.9 | 0 | 5755976.9 |  | 2856041.1304 | -2856041.1304 |  | 3483605.7739 | -3483605.7739 |  | 1787346 | 1787346 | 3574692 | 5979424.58 | 26095541.44 | 6624822.6
2230042 | LANGAN International UK, LTD | Geotechnical Consultant | 1TB.01.003.01 | PS | Marina Village | 1 | [36 empty] | 160000 | 0 | 160000 | 0 |  | 0 |  |  | 0 |  | 168421.05 | -168421.05 |  |  | 0 | [8 empty] | 0 | [81 empty] | 0 | 0
2230075 | Medtel - W.N. WLL | STO Façade Mock-up | 1TB.01.003.01 | CN | Marina Village | 1 | [36 empty] | 166859.71 | 0 | 166859.71 | 0 |  | 0 |  |  | 0 | 834298.55 | 0 | 834298.55 |  | 0 | 0 | 819298.55 | 0 | 819298.55 |  | 819298.55 | -819298.55 |  |  | 0 | [81 empty] | 0 |  | 667438.84
2230205 | Raqtan - Kitchen and Laundry Works | Kitchen and Laundry Works | 1TB.01.003.01 | CN | Marina Village | 1 | [39 empty] | 0 |  | 0 |  | 0 | 0 | 1643323.15 |  | 1643323.15 |  | 0 | 0 | 1643323.15 | 0 | 1643323.15 | [5 empty] | 0 | [18 empty] | 375685.2 | 375685.2 | 0 | 250000 | 511389.89 | -261389.89 | 250000 | 0 | 250000 |  |  |  | 35415.6 | 35415.6 | 0 |  |  |  | 737236.976 | 200882.88 | 536354.096 | 737236.976 | 0 | 737236.976 | 368618.488 | 0 | 368618.488 | 358485.62 | 0 | 358485.62 | 348091.74 | 0 | 348091.74 | 460910.09 | 0 | 460910.09 | 482718.714 | 195307.53 | 287411.184 | 514899.9616 | 0 | 514899.9616 | 611443.7044 | 0 | 611443.7044 | 611443.7044 | Awaiting info. | 0 | 611443.7044 | Awaiting info. | 0 | 153337 | Awaiting info. |  | 159337 | Awaiting info. | 0 | 159337 | Awaiting info. | 0 | 159337 |  |  | 159337 | 1643323.15 | 380000 | 449935
2230178 | ESCCO - Vertical Transportation Works | Vertical Transportation Works | 1TB.01.003.01 | CN | Marina Village | 1 | [44 empty] | 0 |  |  | 0 |  | 0 | 0 | 685941 | 0 | 685941 |  |  |  |  | 685941.9 | -685941.9 | [21 empty] | 94659.9822 | 0 | 94659.9822 | 94659.9822 | 0 | 94659.9822 |  | 294772.74 | -294772.74 | 298772 | 0 | 298772 | 384713.028 | 480378.23 | -95665.202 | 305554.0922 | 0 | 305554.0922 | 446662.1402 | 0 | 446662.1402 | 178556.849 | 0 | 178556.849 |  | 0 | 0 | 573941.46 | 0 | 573941.46 | 491574.6 | 110783.17 | 380791.43 | 393234 | 0 | 393234 | 393234 | 0 | 393234 | 393234 | 0 | 393234 | 393234 | Awaiting info. | 0 | 393234 | Awaiting info. | 0 | 393234 | Awaiting info. |  |  | Awaiting info. | 0 | 249802.7 | Awaiting info. | 0 | 334075.28 | 52335.24 | 125557.9 | 511968.42
2230031 | Khatib & Alami | Management Supervision | 1TB.01.003.01 | MS | Marina Village | 1 | 0 | 0 | 0 | 0 | 48862 | -48862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [5 empty] | 1182400 | 0 | 1182400 | 0 |  | 0 |  | 0 | 0 | 2012335 | 0 | 2012335 | 613667 | 0 | 613667 | 495000 | 0 | 495000 | 495000 | 0 | 495000 | 495000 | 3716548 | -3221548 | 408115 | 455307 | -47192 | 396575 | 0 | 396575 | 368812 | 0 | 368812 | 395420 | 0 | 395420 | 395000 | 0 | 395000 | [6 empty] | 2797323 | 2613481 | 183842 | 508000 | 0 | 508000 | 451900 | 0 | 451900 | 451900 | 0 | 451900 | 444900 | 389586 | 55314 | 431000 | 0 | 431000 | 294000 | 0 | 294000 | 294000 | 0 | 294000 | 423000 | 474949 | -51949 | 433000 | 0 | 433000 | 422000 | 2315115 | -1893115 | 435000 | 426581 | 8419 | 435000 | 278956 | 156044 | 418250 | 0 | 418250 | 418250 | Awaiting info. | 0 | 418250 | Awaiting info. | 0 | 418250 | Awaiting info. |  | 226185 | Awaiting info. | 0 | 70000 | Awaiting info. | 0 |  | 78720 | 72977 | 151697 | 2012335
2230416 | DEPA - Interior Fitout | Management Supervision | 1TB.01.003.01 | CN | Marina Village | 1 | [60 empty] | 3798460 | 0 | 3798460 | 2225032 | 0 | 2225032 | 3998460 | 0 | 3998460 | 2579791.8 | 0 | 2579791.8 | 7098257.67 | 8915763.305 | -1817505.635 | 3281340.034 | 2226933.496 | 1054406.538 | 2226933.49 | 2226933.496 | -0.006 | 1500000 | 0 | 1500000 | 1500000 | 767164.4485 | 732835.5515 | 957739.08 | 1650167.791 | -692428.711 | 536353.42 | 0 | 536353.42 | 2049307.1 | 1616077.37 | 433229.73 | 6568002.4 | 2884295.23 | 3683707.17 | 9194227.84 | 0 | 9194227.84 | 13878229.99 | 3694684.74 | 10183545.25 | 5793001.6 | 0 | 5793001.6 | 7187938.99 | 6728226.68 | 459712.31 | 7681675.02 | 0 | 7681675.02 | 6011684.05 | 7915649.58 | -1903965.53 | 7776985.98 | 4141139.46 | 3635846.52 | 5206588.88 | 2678976.6 | 2527612.28 | 5206588.88 | Awaiting info. | 0 | 5206588.88 | Awaiting info. | 0 | 5206588.88 | Awaiting info. |  | 4553702.8 | Awaiting info. | 0 | 4347525 | Awaiting info. | 0 | 1737945 | 3226545.62 | 2252014.44 | 7216505.06
2240110 | ALUTEC |  |  | CN | Marina Village | 1 | [88 empty] | 7474917.64 | -7474917.64 | 7474917.64 | 253576.09 | 7221341.55 |  |  |  | 9593398.8 | 831689.35 | 8761709.45 | 8792725.3 | 0 | 8792725.3 | 8880940.6 | 53123.86 | 8827816.74 | 571505.86 | 0 | 571505.86 | 671881.52 | 0 | 671881.52 |  | 1342624.42 | -1342624.42 | 2007730.4873 | 6908209.13 | -4900478.6427 | 2308890.0604 | 3683263.49 | -1374373.4296 | 1706570.9142 | 1335971.23 | 370599.6842 | 1706570.9142 | Awaiting info. | 0 | 1706570.9142 | Awaiting info. | 0 | 1706570.9142 | Awaiting info. |  | 938908 | Awaiting info. | 0 | 80010 | Awaiting info. | 0 |  | 49611.16 | 584517.12 | 634128.28
2240202 | AREEN Design | Management Supervision | 1TB.01.003.01 | FF&E | Marina Village | 1 | [60 empty] | 3798460 | 0 | 3798460 | 2225032 | 0 | 2225032 | 3998460 | 0 | 3998460 | 2579791.8 | 0 | 2579791.8 | 7098257.67 | 8915763.305 | -1817505.635 | 3281340.034 | 2226933.496 | 1054406.538 | [7 empty] | 8437500 | -8437500 |  | 498400 | -498400 | 498400 | 0 | 498400 | [13 empty] | 2283465 | -2283465 |  | 305222.59 | -305222.59 |  | 90650.94 | -90650.94 |  | 8519133.75 | -8519133.75 | 328353.75 | 0 | 328353.75 | 60081.75 | 0 | 60081.75 | 60081.75 | Awaiting info. | 0 | 60081.75 | Awaiting info. | 0 | 60081.75 | Awaiting info. |  |  | Awaiting info. | 0 |  | Awaiting info. | 0 |  | 4331572.5 | 226108.24 | 4557680.74
2240427 | MAS Labour |  |  | CN | Marina Village | 1 | [94 empty] | 969150 | -969150 | 517650 | 0 | 517650 | 1449700 | 0 | 1449700 | 1006635 | 517650 | 488985 | 893025 | 790545 | 102480 | 1105650 | 0 | 1105650 | 1020600 | 1159620 | -139020 | 1138590 | 2107131 | -968541 | 838760 | 0 | 838760 | 719680 | 0 | 719680 | 719680 | Awaiting info. | 0 | 719680 | Awaiting info. | 0 | 719680 | Awaiting info. |  | 1072642 | Awaiting info. | 0 |  | Awaiting info. | 0 |  | 1016402.21 |  | 1016402.21
2240461 | MAS Amphitheatre |  |  | CN | Marina Village | 1 | [96 empty] | 753014.11 | 0 | 753014.11 | 165500.93 | 0 | 165500.93 | 160377.23 |  |  |  | 165500.928 | -165500.928 |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 |  |  |  |  | 0 | 0 | [8 empty] | 0 | [6 empty] | 0
2250012 | Al Fanar Labour |  |  | CN | Marina Village | 1 | [96 empty] | 6667520 | 0 | 6667520 | 5262630 | 0 | 5262630 | 6667520 | 18765256.3 | -12097736.3 | 3056191.62 | 21754889.7 | -18698698.08 | 2926717.86 | 2394771 | 531946.86 | 1668861.87 | 7155049.5 | -5486187.63 | 4691360.77 | 0 | 4691360.77 | 7386180 | 0 | 7386180 | 4713050 | 5758803.28 | -1045753.28 | 4713050 | 12164789.03 | -7451739.03 | 4713050 | Awaiting info. | 0 | 4713050 | Awaiting info. |  | 3357959.53 | Awaiting info. |  | 1972028 | Awaiting info. | 0 | 1972028 |  |  | 1972028
2240377 | CML |  |  | PS | Marina Village | 1 | [96 empty] | 165000 | 0 | 165000 | 198125 | 0 | 198125 | 211875 |  |  | 243500 | 310545 | -67045 | 244700 | 376119.79 | -131419.79 | 243500 | 476057.5 | -232557.5 | 241021.25 | 232745 | 8276.25 | 229311.5 | 0 | 229311.5 | 243500 | 0 | 243500 | 243500 | Awaiting info. | 0 | 243500 | Awaiting info. | 0 | 243500 | Awaiting info. |  | 239333.33 | Awaiting info. | 0 | 244700 | Awaiting info. | 0 | 241100 | 164253.85 | 143225 | 548578.85
2240357 | EuroConsult |  |  | PS | Marina Village | 1 | [96 empty] | 14950.1 | 0 | 14950.1 | 14950.1 | 0 | 14950.1 | 14950.1 |  |  | 14950.1 | 54739.36 | -39789.26 | 14950.1 | 0 | 14950.1 | 29900.2 | 9261.06 | 20639.14 | 14950.1 | 0 | 14950.1 | 14950.1 | 0 | 14950.1 | 14950.1 | 20413.58 | -5463.48 | 14950.1 | Awaiting info. | 0 | 14950.1 | Awaiting info. | 0 | 14950.1 | Awaiting info. |  | 15762.54 | Awaiting info. | 0 | 15762.54 | Awaiting info. | 0 | 15762.54 | 0 |  | 15762.54
2250063 | EuroConsult (Accom and Transport) |  |  | PS | Marina Village | 1 | [114 empty] | 3000 | 0 |  | 3000 | 12000 | -9000 | 3000 | 0 | 3000 | 3000 | Awaiting info. | 0 | 3000 | Awaiting info. | 0 | 3000 | Awaiting info. |  |  | Awaiting info. | 0 |  | Awaiting info. | 0 |  |  |  | 0
2250145 | Hassan Allam |  |  | CN | Marina Village | 1 | [105 empty] | 0 | 2370708.37 | -2370708.37 | [6 empty] | 1639852.9428 | 1425959.08 | 213893.8628 | 200266.6572 | 0 | 200266.6572 | 200266.6572 | 1425959.08 | -1225692.4228 | 200266.6572 | Awaiting info. | 0 | 200266.6572 | Awaiting info. | 0 | 200266.6572 | Awaiting info. |  |  | Awaiting info. | 0 | 1321875.98 | Awaiting info. | 0 |  |  |  | 0
2250084 | ARMetal |  |  | CN | Marina Village | 1 | [114 empty] | 712995 | 1693363.13 | -980368.13 | 712995 | 0 | 712995 | 1425990 | 0 |  | 1425990 | Awaiting info. | 0 | 1425990 | Awaiting info. | 0 | 1425990 | Awaiting info. |  |  | Awaiting info. | 0 | 213117.15 | Awaiting info. | 0 |  |  |  | 0
[7 empty] | TOTAL SAR |  | 0 | TOTAL SAR |  | -53362 | TOTAL SAR |  | 0 | TOTAL SAR |  | 0 | TOTAL SAR |  | 0 | TOTAL SAR |  | 0 | TOTAL SAR |  | 659411.999 | TOTAL SAR |  | -17100 | TOTAL SAR |  | 97675.16 | TOTAL SAR |  | 0 | TOTAL SAR |  | 23495820.6 | TOTAL SAR |  | 26441221.375 | TOTAL SAR |  | 1370819.441 | TOTAL SAR |  | -249405.15 | TOTAL SAR |  | 5516800.589 | TOTAL SAR |  | -8585856.84 | TOTAL SAR |  | 5679479.8375 | TOTAL SAR |  | 10388452.46 | TOTAL SAR |  | -42528063.1292 | TOTAL SAR |  | 2950208.684 | TOTAL SAR |  | 7575633.35 | TOTAL SAR |  | 5377133.01 | TOTAL SAR |  | 4609923.85 | TOTAL SAR |  | 6725211.8 | TOTAL SAR |  | -1426717.635 | TOTAL SAR |  | 1054406.538 | TOTAL SAR |  | -33877117.526 | TOTAL SAR |  | 1546981.1422 | TOTAL SAR |  | -44679978.5963 | TOTAL SAR |  | -8508619.091 | TOTAL SAR |  | 8998545.47 | TOTAL SAR |  | -2828069.852 | TOTAL SAR |  | 19269831.0337 | TOTAL SAR |  | 36120466.9662 | TOTAL SAR |  | 16996283.097 | TOTAL SAR |  | -18292896.7058 | TOTAL SAR |  | 2086543.263 | TOTAL SAR |  | -304347.227 | TOTAL SAR |  | -9446681.256 | TOTAL SAR |  | 14685088.8509 | TOTAL SAR |  | 4160067.6228 | TOTAL SAR |  | -12005077.206 | TOTAL SAR |  | 1542800.0652 | TOTAL SAR |  | 5755976.9 | TOTAL SAR |  | -2856041.1304 | TOTAL SAR |  | -3483605.7739
[43 empty] | 1887639.64 | [8 empty] | 4599356.7 | [8 empty] | 6715555.8248 |  |  | 11162407.898 | [5 empty] | 5644675 |  |  | 9588125.7 | [11 empty] | 2602618.69 | [8 empty] | 1409639.08 | [8 empty] | 23138292.1937
[31 empty] | 409467.25 | 311792.09 |  | 0 | [8 empty] | 3775279.28 | [8 empty] | 9198713.4 | [8 empty] | 13431111.6495 | [8 empty] | 15739414
#REF!
[55 empty] | 5696502.55 |  |  | 16068828.22 | [5 empty] | 11162407.898 | [8 empty] | 5589665.7 | [75 empty] | #REF!
[29 empty] | 659411.999 | -17100 | 311792.09 | 838512.552
Note on AL18: 10% Advance Payment
Note on BK18: Including Payment to Long Lead Items (Approved RFA)
Note on DJ18: This is Direct Payment to SAB's Subcontractors and Suppliers.
Note on DM18: Jose Chavenia: Direct Payment
Note on DP18: Jose Chavenia: Direct Payments
Note on DS18: Direct Payment made for August 2025
Note on DY18: Jose Chavenia: Direct Payments
Note on EB18: Direct Payments released in October 2025
Note on EH18: Jose Chavenia: Direct Payments
Note on CR25: Advance Payment
Note on CT25: Advance Payment

## Schedule K
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01 |  |  |  |  | T&T submission #### reconciling all the errors identified in their priced BOQ
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
100%
ITEM | PACKAGE | BASELINE BUDGET | BUDGET TRANSFERS | REVISED BASELINE BUDGET | LATEST COST PLAN | VARIANCE | COMMENTS
CONSTRUCTION WORKS
1 | Piling, Shoring & Associated works | 18698534 | 0 | 18698534 | 18698534 | 2.6077e-08 | Contract Awarded - EW not Applicable |  | 0.025816
2 | Structural Concrete, Wet Trades, BOH Fit out, Pools and Water Features, Structural Steel, Glazing, Glass Balustrades, Aluminum Soffits, SFS and GRC, Render Façade, Roof Waterproofing, MEP, ICT/ELV | 174247542.3 | 86707872.4 | 260955414.7 | 260955414.7 | 0 | Contract Awarded - EW not Applicable |  | 0.025795
2a | Early Works - GBC - Sustainability Accreditation 3rd Party | 4500 | 0 | 4500 | Not Applicable | N/A |  |  | 7458065.0684 | 2610322.7739 | Adjustment to Landscape
2b | Early Works - SOI TB Ground Improvement Works | 3082689 | 0 | 3082689 | Not Applicable | N/A |  |  | 3729032.53 | Adjustment to Landscape and FF&E
3 | Lifts / Vertical Transport Supply | 2210880 | 464592.9955 | 2675472.9955 | 2675472.9955 | 0 | Contract Awarded - EW not Applicable | 2675473 | 4473000
4 | Hard and Soft Scape | 13682040 | 6064220.64 | 19746260.64 | 19746260.64 | 0 | EW No 5 - Re-reported. Transfer budget from Landscape to Interior Fitout to fund the Contract Award to DEPA. | (-SAR 310,140 adjustment for mass concrete transferred to SAB) | 1797527.0045 | 7622348.7768 | Early Warning (Feb 2024 Report)
5 | Interior Fit-Out | 28206303 | 47762924 | 75969227 | 75969227 | 0 | Based on the Contract Award Value to Depa | 75969227 | 62092796 | 68345239.6032 | -7623987.3968 | -7622348.7768
FF&E and OS&E
6 | Kitchen & Laundry Works | 5907720 | -1212511 | 4695209 | 4695209 | 0 | Contract Awarded - EW not Applicable | -522340 | 4695209 | -1212511
7 | a. Loose FF&E items (FOH) | 12800000 | 12758750 | 25558750 | 25558750 | 0 | EW No 9 - Reported. The approved additional budget transfer funds the EW value. |  | 2319040
8 | b. Loose FF&E items (BOH) | 340000 | 130000 | 470000 | 470000 | 0 | EW No 8 - Reported. The approved additional budget transfer funds the EW value. | 130000 | 5139025.07
9 | c. OS&E items | 3543829 | 5137345.56 | 8681174.56 | 8681174.56 | 0
10 | d. Art Work | 2400000 | 474723 | 2874723 | 2874723 | 0 | EW No 9 - Reported. The approved additional budget transfer funds the EW value.
| TOTALS | 265124037.3 | 158287917.5955 | 423411954.8955 | 420324765.8955 | 0
407731886.4055
-12592879.49
7458065.07
|  |  | 37584647.56 | 22998647.56 | 3729032.535
|  |  |  | 37584647.56 | 418047738.1045 | 207473655.83
5137345.56
,

## Additional Budget Sum (19Dec) (hidden)
AMAALA Program 01 - Marina Village AMAALA Yacht Club - Project Wide Summary | Current Approved ACC Budget |  | 100% DD Cost Plan (C&B) |  | Total - Estimate At Completion |  | Early Warning Variance (Budget - EAC) |  | Comments
GEA | 7869 | m2 |  | m2 | 7932 | m2 | 63 | m2
External Area | 1644 | m2 |  | m2 | 1470 | m2 | -174 | m2
Work Elements/ Assets | SAR | % | SAR | % | SAR | % | SAR | %
Ground Improvement (SIC) | 3082689 | 0.8841% |  |  | 2299717 | 0.5116% | -782972 | -0.7765%
Piling Works (NSCC) | 16458381.51 | 4.72% |  |  | 16458381.51 | 3.662% | 0 | 0%
Sustainability Accreditation (GBC) | 22585.01 | 0.006478% |  |  | 22585.01 | 0.005025% | 0 | 0% |  | 22585.01 | 0
Structural Concrete, Wet Trades, BOH Fit out, Pools and Water Features, Structural Steel, Glazing, Glass Balustrades, Aluminum Soffits, SFS and GRC, Render Façade, Roof Waterproofing, MEP and ICT/ELV (SAB) | 158892731.19 | 45.57% |  |  | 170989417.823 | 38.04% | 12096686.633 | 12% |  | 216006606.71 | 21884331.2 | 7080175.903 | -5016510.73
STO Façade Mock-up (MEDTEL) | 819298.55 | 0.235% |  |  | 819298.55 | 0.1823% | 0 | 0%
Vertical Transporation (ESCCO) | 2773546 | 0.7955% |  |  | 3322917.05 | 0.7393% | 549371.05 | 0.5449%
Kitchen and Laundry Equipment (RAQTAN) | 4705352 | 1.35% |  |  | 6070598.45 | 1.351% | 1365246.45 | 1.354% | [5 empty] | DVO 01 & 02 Adjustment
Fitout (DEPA) | 80571297.37 | 23.11% |  |  | 92122900.29 | 20.49% | 11551602.92 | 11.46% |  | 75809169.37 | 773023.07 | 75274125 | -535044.37 | 535044.11
Aluminum and Glazing Works (ALUTEC) | 30474501.58 | 8.74% |  |  | 30853014.58 | 6.864% | 378513 | 0.3754% |  | 75274125.26 | -5297172.11 | -360715.12
Manpower for Wet Works (MAS) | 22360118 | 6.413% |  |  | 22520994.21 | 5.01% | 160876.21 | 0.1596%
Amphitheatre Works (MAS) | 1284550.35 | 0.3684% |  |  | 1275030.35 | 0.2837% | -9520 | -0.009442%
Reflective Metal Cladding (AR Metal) - Contract under process |  |  |  |  | 7197028.55 | 1.601% | 7197028.55 | 7.138%
MEP Labour and Material Supply (Al Fanar) | 23125000 | 6.632% |  |  | 95540331.69 | 21.26% | 72415331.69 | 71.82%
CN Budget Hold | 4092812.42 | 1.174% |  |  | 0 |  | -4092812.42 |  |  | 27217812.42
Total Building Works | 348662862.98 | 89.48% | 0 | 0% | 449492215.063 | 91.56% | 100829352.083 | 28.92% |  | 380550505.28 | 31887642.3 | 499601291.743 | 50109076.68
Total Construction Works (excl. Preliminaries) | 348662862.98 |  | 0 |  | 449492215.063 |  | 100829352.083 | 28.92% |  | 100829352.083
Preliminaries | Included | 0% | Included | 0% | Included | 0% | Included | 0
Total Construction Works (incl. Preliminaries) | 348662862.98 | 89.48% | 0 | 0% | 449492215.063 | 91.56% | 100829352.083 | 28.92%
Loose FF&E / OSE/ Artwork | 41006647.28 | 10.52% | 154949000 | 100% | 41435803.28 | 8.44% | 429156 | 1.047%
Total Construction Works | 389669510.26 | 100% | 154949000 | 100% | 490928018.343 | 100% | 101258508.083 | 25.99% |  | 96645322.46 |  | -3234573.277
Risks/Contingencies |  | 0% |  | 0% |  | 0%
Total Development Works | 389669510.26 | 100% | 154949000 | 31.56% | 490928018.343 | 100% | 101258508.083 | 0.25986
Proposed VE Initiatives (excl. Risks/ Contingencies) | [6 empty] | 0
Total Development Works including VE (excl. Risks/ Contingencies) | 389669510.26 |  | 154949000 |  | 490928018.343 |  | 101258508.083 | 0.25986
Proposed VE Initiatives (incl. Risks/ Contingencies) | [6 empty] | 0
Total Development Works including VE (incl. Risks/ Contingencies) | 389669510.26 |  | 154949000 |  | 490928018.343 |  | 101258508.083 | 0.25986
-104493081.36
Building Works - SAR/m2 | 44308.4081 |  | 0 |  | 56668.2066 |  |  |  |  | 26065181.95 |  | 347793.9
[10 empty] | -75193326.133 |  | 569838.42
Construction Works - SAR/m2 excl. FFE | 44308.4081 |  | 0 |  | 56668.2066 | [6 empty] | 917632.32
-103575449.04
Construction Works - SAR/m2 incl. FFE | 49519.5718 |  | 0 |  | 61892.085
Construction Works including VE - SAR/m2 | 0 |  | 0 |  | 0
ERB_Rev 03_20240514
DONOT DELETE
1297056685
| 907387174.74 | CONST | 1227357002
|  | PRELIMS | 159566726 | 1.13
|  | TOTAL | 1386923728
|  | FFE-LOOSE | 154949000
|  | TOTAL | #REF!
|  | CHCK | #REF!
| -234720510.26 | ID - FOH CP OVERRUN | #REF! |  |  |  | #REF!
|  | ID - FOH CP OVERRUN (INCL PRELIMS) | #REF!
|  | ID OVERRUN | #REF!
|  | TOTAL | #REF!
| 1527651573 |  | #REF!
1137982062.74
[10 empty] | PS Budget Hold | 347793.9
[10 empty] | MS Budget Hold | 569838.42
917632.32
100340875.763
-4956647.977
-105297523.74

## Additional Budget - Det (19Dec) (hidden)
Ref | Overrun Items Descriptions |  | Variance |  | Current BT Summary Breakdown | Estimated Commitment Date
|  | Contractor | Budget V Cost
|  |  | SAR | % | SAR
1 | Early Warning for Future Awards |  | -4092812.42 | -88.72% | 0
1.a | Item No. - 79 - Reflective Ceiling (Award to Armetal) | ARMETAL | 0 | 0% |  | 2024-11-17
1.b | Construction (CN) Budget Hold - REMAINING |  | -4092812.42 | -88.72% |  | 2024-11-17
2 | Early Warning on Awarded Packages |  | 8705998.043 | 188.7% | 0
2.a | Item No. - 22 - Omission of Surveying Equipment from SAB Contract | SAB | -7890 | -0.171% |  | Final Account |  | 7070995.903 | 12096686.633 | -5025690.73
2.b | Item No. - 24 - Omission of food and welfare provision to AMAALA Staff from SAB Contract. | SAB | -90000 | -1.951% |  | Final Account
2.c | Item No.-25 - Cost saving to Site Office Monthly Running Cost due to late installation of the Office Establishment by SAB. | SAB | -200000 | -4.335% |  | Final Account
2.d | Item No. - 64 - Potential Contract Cost Adjustment | SAB | 0 | 0% |  | Management to Advise
2.e | Item No. - 70b - Cancellation of Amphitheatre Works issued to MAS - Process not followed | SAB | -1108000 | -24.02% |  | Final Account
2.f | Item No. - 71b - Recovery of Remaining Block work, Plaster work and Paint Work to be carried out by MAS - Process not followed | SAB | -4004000 | -86.79% |  | Final Account
2.g | Item No. - 75 - Deployment of Seven (7) Surveyors | SAB | 201600 | 4.37% |  | 2024-11-30
2.h | Item No. - 78 - Scaffolding works for Secondary Steel and Façade (Design) | SAB | 75000 | 1.626% |  | 2024-12-15
2.i | Item No. - 80 - Reflective Ceiling (Omission from SAB) | SAB | 0 | 0% |  | 2024-11-30
2.j | Item No. - 59 - Grand Stair Balustrade Revision to Avoid Fall Hazard (Construction) | SAB | 180170 | 3.906% |  | 2024-11-30
2.k | Item No. - 55 - Relocation Marina Offices and Regeneration Kitchen (Construction plus abortive Works) | SAB | 2230142.99 | 48.34% |  | 2024-11-30 | Approved RFC, pending PVO
2.l | Item No. - 38 - AYC ¦ Grand Stair Structure Backfill | SAB | 166610 | 3.612% |  | 2024-11-30 | Approved RFC, pending PVO
2.m | Item No. - 72 - Alteration to finishes due to Façade Layout Changes - Process not Followed | DEPA | 69000 | 1.496% |  | 2024-11-30 |  | 96201.54 | 11551602.92 | -11455401.38
2.n | Item No. - 76 - Employer’s instruction for ID Finishes on Vertical Transportation Fixture Elements | DEPA | 0 | 0% |  | 2024-11-30
2.o | Item No. - 56 - AYC Guest Lobby Staircase Geometry & Finish Revisions (Construction) | DEPA | 0 | 0% |  | 2024-11-30
2.p | Item No. - 58 - Changes to Members Lobby and Guest Lobby Staircase Ballustrades | DEPA | 27201.54 | 0.5896% |  | 2024-11-30
2.q | Item No. - 77 - AYC – Disassembly and Reassembly of electronic items from VT fixtures | ESCCO | 0 | 0% |  | 2024-11-30 |  | 0 | 549371.05 | -549371.05
2.r | Item No. - 55 - Relocation Marina Offices and Regeneration Kitchen (Kitchen) | RAQTAN | 1109644.6 | 24.05% |  | 2024-11-30 |  | 1109644.6 | 1365246.45 | -255601.85
2.s | Item No. - 73 - Additional Porte Cochere Works to be carried out by MAS | MAS-Amphi | 0 | 0% |  | 2024-11-30
2.t | Item No. - 61 - Addition of Accessories to Existing Artwork Proposal - Change Decision Pack_Artwork Package | Areen | 429156 | 9.303% |  | 2024-11-30
2.u | Item No. - 82 - Installation of MDF Platform / Ceiling | DEPA | 0 | 0% |  | 2024-12-05
2.v | Item No. - 83 - Column Dry Wall Cladding and Partitions | DEPA | 0 | 0% |  | 2024-12-05
2.w | Item No. - 84 - Column Dry Wall Cladding and Partitions (Blockworks Omission) | SAB | -9180 | -0.199% |  | 2024-12-05
2.x | Item No. - 85 - Replace the existing FOH electrical faceplates in designated areas of the Project with upgraded units meeting specifications. | Al Fanar | 0 | 0% |  | 2024-12-05 |  | 0 | 72415331.69 | -72415331.69
2.y | Item No. - 86 - Replace the existing FOH electrical faceplates in designated areas of the Project with upgraded units meeting specifications. (Omission from SAB) | SAB | -68541 | -1.486% |  | 2024-12-05
2.z | Item No. - 87 - LPG Works (Al Fanar) | Al Fanar | 0 | 0% |  | 2024-12-05
2.aa | Item No. - 88 - LPG Works (Omission from SAB) | SAB | -582220 | -12.62% |  | 2024-12-05
2.ab | Item No. - 89 - Al Fanar MEP Manpower Supply to AYC Project on behalf of SAB - Adjustment | Al Fanar | 0 | 0% |  | 2024-12-05
2.ac | Item No. - 90 - Al Fanar Allowance for Purhcasing Materials | Al Fanar | 0 | 0% |  | 2024-12-05
2.ad | Item No. - 91 - Allowance for SAB (Grankraft) works on mockup (same as advance payment amount) | SAB | 852173.913 | 18.47% |  | 2024-12-05
2.ae | Item No. - 92 - Additional Costs related to Aluminium Soffits & Cladding - Alcatop | SAB | 1026091 | 22.24% |  | 2024-12-05
2.af | Item No. - 93 - Additional Costs related to Abu Dhabi Precast - GRC Cladding | SAB | 3761897 | 81.55% |  | 2024-12-05
2.ag | Item No. - 94 - Additional Costs related to Structural Metal Work - SAMIF | SAB | 4647142 | 100.7% |  | 2024-12-05
2.ah | Item No. - 96 - Dismantling and Reinstatement of Cold Rooms (Chiller 1, Chiller 2, and Chiller 3) including coordination |  | 22250 | 0.4823% |  | 2025-12-19
2.aj | Item No. - 97 - Dismantling and Reinstatement of Cold Rooms (Chiller 1, Chiller 2, and Chiller 3) including coordination - Backcharge |  | -22250 | -0.4823% |  | 2025-12-20
0
Total Overrun |  |  | 4613185.623 | 100% | 0
ERB_Rev 03_20240514
|  |  | 101258508.083 | 96645322.46
96645322.46
|  |  | FALSE | 101258508.083
96645322.46
429156
|  | Al Fanar | 0 | 72415331.69 | 72415331.69
|  | Areen | 429156 | 429156 | 0
|  | ARMETAL | 0 | 7197028.55 | 7197028.55
|  | DEPA | 96201.54 | 11551602.92 | 11455401.38
|  | ESCCO | 0 | 549371.05 | 549371.05
|  | MAS-Amphi | 0 | -9520 | -9520
|  | RAQTAN | 1109644.6 | 1365246.45 | 255601.85
|  | SAB | #REF! | 12096686.633 | #REF!
12754372.42
12658170.88

## EI - (F1 - F2)
[9 empty] | FROM | TO
[9 empty] | 2024-06-29 | 2024-07-28
[6 empty] | JULY | 2024
1
S/N | Program | REEF PO Ref. | Vendor Name | Vendor Type | Description | CI / EI / VO Ref. | Date of Instruction | AVI / DVO Ref. | Date of AVI/DVO Agreement | Value of PVO (Planned) | Value of AVV (Actual) | No. of Calendar Days to Close AVV / DVO | Count of AVV / DVO Closed | Status | Deadline Date for Closing DVO | Remaining Days to Close Out (Red = delay) | DON’T DELETE
1 | 1 | [15 empty] | 0
2 | 1 | [15 empty] | 0
3 | 1 | [15 empty] | 0
4 | 1 | [15 empty] | 0
5 | 1 | [15 empty] | 0
6 | 1 | [15 empty] | 0
7 | 1 | [15 empty] | 0
8 | 1 | [15 empty] | 0
9 | 1 | [15 empty] | 0
10 | 1 | [15 empty] | 0
11 | 1 | [15 empty] | 0
12 | 1 | [15 empty] | 0
13 | 1 | [15 empty] | 0
14 | 1 | [15 empty] | 0
15 | 1 | [15 empty] | 0
16 | 1 | [15 empty] | 0
17 | 1 | [15 empty] | 0
18 | 1 | [15 empty] | 0
19 | 1 | [15 empty] | 0
20 | 1 | [15 empty] | 0
21 | 1 | [15 empty] | 0
22 | 1 | [15 empty] | 0
23 | 1 | [15 empty] | 0
24 | 1 | [15 empty] | 0
25 | 1 | [15 empty] | 0
26 | 1 | [15 empty] | 0
27 | 1 | [15 empty] | 0
28 | 1 | [15 empty] | 0
29 | 1 | [15 empty] | 0
30 | 1 | [15 empty] | 0
31 | 1 | [15 empty] | 0
32 | 1 | [15 empty] | 0
33 | 1 | [15 empty] | 0
34 | 1 | [15 empty] | 0
35 | 1 | [15 empty] | 0
36 | 1 | [15 empty] | 0
37 | 1 | [15 empty] | 0
38 | 1 | [15 empty] | 0
39 | 1 | [15 empty] | 0
40 | 1 | [15 empty] | 0
41 | 1 | [15 empty] | 0
42 | 1 | [15 empty] | 0
43 | 1 | [15 empty] | 0
44 | 1 | [15 empty] | 0
45 | 1 | [15 empty] | 0
46 | 1 | [15 empty] | 0
47 | 1 | [15 empty] | 0
48 | 1 | [15 empty] | 0
49 | 1 | [15 empty] | 0
50 | 1 | [15 empty] | 0
51 | 1 | [15 empty] | 0
52 | 1 | [15 empty] | 0
53 | 1 | [15 empty] | 0
54 | 1 | [15 empty] | 0
55 | 1 | [15 empty] | 0
56 | 1 | [15 empty] | 0
57 | 1 | [15 empty] | 0
58 | 1 | [15 empty] | 0
59 | 1 | [15 empty] | 0
60 | 1 | [15 empty] | 0
61 | 1 | [15 empty] | 0
62 | 1 | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
63 | 1 | [15 empty] | 0
64 | 1 | [15 empty] | 0
65 | 1 | [15 empty] | 0
66 | 1 | [15 empty] | 0
67 | 1 | [15 empty] | 0
68 | 1 | [15 empty] | 0
69 | 1 | [15 empty] | 0
70 | 1 | [15 empty] | 0
71 | 1 | [15 empty] | 0
72 | 1 | [15 empty] | 0
73 | 1 | [15 empty] | 0
74 | 1 | [15 empty] | 0
75 | 1 | [15 empty] | 0
76 | 1 | [15 empty] | 0
77 | 1 | [15 empty] | 0
78 | 1 | [15 empty] | 0
79 | 1 | [15 empty] | 0
80 | 1 | [15 empty] | 0
81 | 1 | [15 empty] | 0
82 | 1 | [15 empty] | 0
83 | 1 | [15 empty] | 0
84 | 1 | [15 empty] | 0
85 | 1 | [15 empty] | 0
86 | 1 | [15 empty] | 0
87 | 1 | [15 empty] | 0
88 | 1 | [15 empty] | 0
89 | 1 | [15 empty] | 0
90 | 1 | [15 empty] | 0
91 | 1 | [15 empty] | 0
92 | 1 | [15 empty] | 0
93 | 1 | [15 empty] | 0
94 | 1 | [15 empty] | 0
95 | 1 | [15 empty] | 0
96 | 1 | [15 empty] | 0
97 | 1 | [15 empty] | 0
98 | 1 | [15 empty] | 0
99 | 1 | [15 empty] | 0
100 | 1 | [15 empty] | 0
101 | 1 | [15 empty] | 0
102 | 1 | [15 empty] | 0
103 | 1 | [15 empty] | 0
104 | 1 | [15 empty] | 0
105 | 1 | [15 empty] | 0
106 | 1 | [15 empty] | 0
107 | 1 | [15 empty] | 0
108 | 1 | [15 empty] | 0
109 | 1 | [15 empty] | 0
110 | 1 | [15 empty] | 0
111 | 1 | [15 empty] | 0
112 | 1 | [15 empty] | 0
113 | 1 | [15 empty] | 0
114 | 1 | [15 empty] | 0
115 | 1 | [15 empty] | 0
116 | 1 | [15 empty] | 0
117 | 1 | [15 empty] | 0
118 | 1 | [15 empty] | 0
119 | 1 | [15 empty] | 0
120 | 1 | [15 empty] | 0
121 | 1 | [15 empty] | 0
122 | 1 | [15 empty] | 0
123 | 1 | [15 empty] | 0
124 | 1 | [15 empty] | 0
125 | 1 | [15 empty] | 0
126 | 1 | [15 empty] | 0
127 | 1 | [15 empty] | 0
128 | 1 | [15 empty] | 0
129 | 1 | [15 empty] | 0
130 | 1 | [15 empty] | 0
131 | 1 | [15 empty] | 0
132 | 1 | [15 empty] | 0
133 | 1 | [15 empty] | 0
134 | 1 | [15 empty] | 0
135 | 1 | [15 empty] | 0
136 | 1 | [15 empty] | 0
137 | 1 | [15 empty] | 0
138 | 1 | [15 empty] | 0
139 | 1 | [15 empty] | 0
140 | 1 | [15 empty] | 0
141 | 1 | [15 empty] | 0
142 | 1 | [15 empty] | 0
143 | 1 | [15 empty] | 0
144 | 1 | [15 empty] | 0
145 | 1 | [15 empty] | 0
146 | 1 | [15 empty] | 0
147 | 1 | [15 empty] | 0
148 | 1 | [15 empty] | 0
149 | 1 | [15 empty] | 0
150 | 1 | [15 empty] | 0
151 | 1 | [15 empty] | 0
152 | 1 | [15 empty] | 0
153 | 1 | [15 empty] | 0
154 | 1 | [15 empty] | 0
155 | 1 | [15 empty] | 0
156 | 1 | [15 empty] | 0
157 | 1 | [15 empty] | 0
158 | 1 | [15 empty] | 0
159 | 1 | [15 empty] | 0
160 | 1 | [15 empty] | 0
161 | 1 | [15 empty] | 0
162 | 1 | [15 empty] | 0
163 | 1 | [15 empty] | 0
164 | 1 | [15 empty] | 0
165 | 1 | [15 empty] | 0
166 | 1 | [15 empty] | 0
167 | 1 | [15 empty] | 0
168 | 1 | [15 empty] | 0
169 | 1 | [15 empty] | 0
170 | 1 | [15 empty] | 0
171 | 1 | [15 empty] | 0
172 | 1 | [15 empty] | 0
173 | 1 | [15 empty] | 0
174 | 1 | [15 empty] | 0
175 | 1 | [15 empty] | 0
176 | 1 | [15 empty] | 0
177 | 1 | [15 empty] | 0
178 | 1 | [15 empty] | 0
179 | 1 | [15 empty] | 0
180 | 1 | [15 empty] | 0
181 | 1 | [15 empty] | 0
182 | 1 | [15 empty] | 0
183 | 1 | [15 empty] | 0
184 | 1 | [15 empty] | 0
185 | 1 | [15 empty] | 0
186 | 1 | [15 empty] | 0
187 | 1 | [15 empty] | 0
188 | 1 | [15 empty] | 0
189 | 1 | [15 empty] | 0
190 | 1 | [15 empty] | 0
191 | 1 | [15 empty] | 0
192 | 1 | [15 empty] | 0
193 | 1 | [15 empty] | 0
194 | 1 | [15 empty] | 0
195 | 1 | [15 empty] | 0
196 | 1 | [15 empty] | 0
197 | 1 | [15 empty] | 0
198 | 1 | [15 empty] | 0
199 | 1 | [15 empty] | 0
200 | 1 | [15 empty] | 0
201 | 1 | [15 empty] | 0
202 | 1 | [15 empty] | 0
203 | 1 | [15 empty] | 0
204 | 1 | [15 empty] | 0
205 | 1 | [15 empty] | 0
206 | 1 | [15 empty] | 0
207 | 1 | [15 empty] | 0
208 | 1 | [15 empty] | 0
SELECT THE YEAR

## DVO (F1 - F2)
[9 empty] | FROM | TO
[9 empty] | 2023-12-29 | 2024-01-29
[6 empty] | JANUARY | 2024
9
S/N | Program | REEF PO Ref. | Vendor Name | Vendor Type | Description | CI / EI / VO Ref. | Date of Instruction | AVI / DVO Ref. | Date of AVI/DVO Agreement | Value of PVO (Planned) | Value of AVV (Actual) | No. of Calendar Days to Close AVV / DVO | Count of AVV / DVO Closed | Status | Deadline Date for Closing DVO | Remaining Days to Close Out (Red = delay) | DON’T DELETE
1 | 1 | [15 empty] | 0
2 | 1 | [15 empty] | 0
3 | 1 | [15 empty] | 0
4 | 1 | [15 empty] | 0
5 | 1 | [15 empty] | 0
6 | 1 | [15 empty] | 0
7 | 1 | [15 empty] | 0
8 | 1 | [15 empty] | 0
9 | 1 | [15 empty] | 0
10 | 1 | [15 empty] | 0
11 | 1 | [15 empty] | 0
12 | 1 | [15 empty] | 0
13 | 1 | [15 empty] | 0
14 | 1 | [15 empty] | 0
15 | 1 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
16 | 1 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
17 | 1 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
18 | 1 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
19 | 1 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
20 | 1 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
21 | 1 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
22 | 1 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
23 | 1 | [15 empty] | 0
24 | 1 | [15 empty] | 0
25 | 1 | [15 empty] | 0
26 | 1 | [15 empty] | 0
27 | 1 | [15 empty] | 0
28 | 1 | [15 empty] | 0
29 | 1 | [15 empty] | 0
30 | 1 | [15 empty] | 0
31 | 1 | [15 empty] | 0
32 | 1 | [15 empty] | 0
33 | 1 | [15 empty] | 0
34 | 1 | [15 empty] | 0
35 | 1 | [15 empty] | 0
36 | 1 | [15 empty] | 0
37 | 1 | [15 empty] | 0
38 | 1 | [15 empty] | 0
39 | 1 | [15 empty] | 0
40 | 1 | [15 empty] | 0
41 | 1 | [15 empty] | 0
42 | 1 | [15 empty] | 0
43 | 1 | [15 empty] | 0
44 | 1 | [15 empty] | 0
45 | 1 | [15 empty] | 0
46 | 1 | [15 empty] | 0
47 | 1 | [15 empty] | 0
48 | 1 | [15 empty] | 0
49 | 1 | [15 empty] | 0
50 | 1 | [15 empty] | 0
51 | 1 | [15 empty] | 0
52 | 1 | [15 empty] | 0
53 | 1 | [15 empty] | 0
54 | 1 | [15 empty] | 0
55 | 1 | [15 empty] | 0
56 | 1 | [15 empty] | 0
57 | 1 | [15 empty] | 0
58 | 1 | [15 empty] | 0
59 | 1 | [15 empty] | 0
60 | 1 | [15 empty] | 0
61 | 1 | [15 empty] | 0
62 | 1 | [15 empty] | 0
63 | 1 | [15 empty] | 0
64 | 1 | [15 empty] | 0
65 | 1 | [15 empty] | 0
66 | 1 | [15 empty] | 0
67 | 1 | [15 empty] | 0
68 | 1 | [15 empty] | 0
69 | 1 | [15 empty] | 0
70 | 1 | [15 empty] | 0
71 | 1 | [15 empty] | 0
72 | 1 | [15 empty] | 0
73 | 1 | [15 empty] | 0
74 | 1 | [15 empty] | 0
75 | 1 | [15 empty] | 0
76 | 1 | [15 empty] | 0
77 | 1 | [15 empty] | 0
78 | 1 | [15 empty] | 0
79 | 1 | [15 empty] | 0
80 | 1 | [15 empty] | 0
81 | 1 | [15 empty] | 0
82 | 1 | [15 empty] | 0
83 | 1 | [15 empty] | 0
84 | 1 | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
85 | 1 | [15 empty] | 0
86 | 1 | [15 empty] | 0
87 | 1 | [15 empty] | 0
88 | 1 | [15 empty] | 0
89 | 1 | [15 empty] | 0
90 | 1 | [15 empty] | 0
91 | 1 | [15 empty] | 0
92 | 1 | [15 empty] | 0
93 | 1 | [15 empty] | 0
94 | 1 | [15 empty] | 0
95 | 1 | [15 empty] | 0
96 | 1 | [15 empty] | 0
97 | 1 | [15 empty] | 0
98 | 1 | [15 empty] | 0
99 | 1 | [15 empty] | 0
100 | 1 | [15 empty] | 0
101 | 1 | [15 empty] | 0
102 | 1 | [15 empty] | 0
103 | 1 | [15 empty] | 0
104 | 1 | [15 empty] | 0
105 | 1 | [15 empty] | 0
106 | 1 | [15 empty] | 0
107 | 1 | [15 empty] | 0
108 | 1 | [15 empty] | 0
109 | 1 | [15 empty] | 0
110 | 1 | [15 empty] | 0
111 | 1 | [15 empty] | 0
112 | 1 | [15 empty] | 0
113 | 1 | [15 empty] | 0
114 | 1 | [15 empty] | 0
115 | 1 | [15 empty] | 0
116 | 1 | [15 empty] | 0
117 | 1 | [15 empty] | 0
118 | 1 | [15 empty] | 0
119 | 1 | [15 empty] | 0
120 | 1 | [15 empty] | 0
121 | 1 | [15 empty] | 0
122 | 1 | [15 empty] | 0
123 | 1 | [15 empty] | 0
124 | 1 | [15 empty] | 0
125 | 1 | [15 empty] | 0
126 | 1 | [15 empty] | 0
127 | 1 | [15 empty] | 0
128 | 1 | [15 empty] | 0
129 | 1 | [15 empty] | 0
130 | 1 | [15 empty] | 0
131 | 1 | [15 empty] | 0
132 | 1 | [15 empty] | 0
133 | 1 | [15 empty] | 0
134 | 1 | [15 empty] | 0
135 | 1 | [15 empty] | 0
136 | 1 | [15 empty] | 0
137 | 1 | [15 empty] | 0
138 | 1 | [15 empty] | 0
139 | 1 | [15 empty] | 0
140 | 1 | [15 empty] | 0
141 | 1 | [15 empty] | 0
142 | 1 | [15 empty] | 0
143 | 1 | [15 empty] | 0
144 | 1 | [15 empty] | 0
145 | 1 | [15 empty] | 0
146 | 1 | [15 empty] | 0
147 | 1 | [15 empty] | 0
148 | 1 | [15 empty] | 0
149 | 1 | [15 empty] | 0
150 | 1 | [15 empty] | 0
151 | 1 | [15 empty] | 0
152 | 1 | [15 empty] | 0
153 | 1 | [15 empty] | 0
154 | 1 | [15 empty] | 0
155 | 1 | [15 empty] | 0
156 | 1 | [15 empty] | 0
157 | 1 | [15 empty] | 0
158 | 1 | [15 empty] | 0
159 | 1 | [15 empty] | 0
160 | 1 | [15 empty] | 0
161 | 1 | [15 empty] | 0
162 | 1 | [15 empty] | 0
163 | 1 | [15 empty] | 0
164 | 1 | [15 empty] | 0
165 | 1 | [15 empty] | 0
166 | 1 | [15 empty] | 0
167 | 1 | [15 empty] | 0
168 | 1 | [15 empty] | 0
169 | 1 | [15 empty] | 0
170 | 1 | [15 empty] | 0
171 | 1 | [15 empty] | 0
172 | 1 | [15 empty] | 0
173 | 1 | [15 empty] | 0
174 | 1 | [15 empty] | 0
175 | 1 | [15 empty] | 0
176 | 1 | [15 empty] | 0
177 | 1 | [15 empty] | 0
178 | 1 | [15 empty] | 0
179 | 1 | [15 empty] | 0
180 | 1 | [15 empty] | 0
181 | 1 | [15 empty] | 0
182 | 1 | [15 empty] | 0
183 | 1 | [15 empty] | 0
184 | 1 | [15 empty] | 0
185 | 1 | [15 empty] | 0
186 | 1 | [15 empty] | 0
187 | 1 | [15 empty] | 0
188 | 1 | [15 empty] | 0
189 | 1 | [15 empty] | 0
190 | 1 | [15 empty] | 0
191 | 1 | [15 empty] | 0
192 | 1 | [15 empty] | 0
193 | 1 | [15 empty] | 0
194 | 1 | [15 empty] | 0
195 | 1 | [15 empty] | 0
196 | 1 | [15 empty] | 0
197 | 1 | [15 empty] | 0
198 | 1 | [15 empty] | 0
199 | 1 | [15 empty] | 0
200 | 1 | [15 empty] | 0
201 | 1 | [15 empty] | 0
202 | 1 | [15 empty] | 0
203 | 1 | [15 empty] | 0
204 | 1 | [15 empty] | 0
205 | 1 | [15 empty] | 0
206 | 1 | [15 empty] | 0
207 | 1 | [15 empty] | 0
208 | 1 | [15 empty] | 0
SELECT THE YEAR

## For PVO (Budget Status Table)
Control Account | Current Approved Budget | Approved Contract | Approved DVOs & Committed PVOs | Total Approved Commitments | Pending Contracts | Approved PVOs (Not Yet Committed in ACC) | Total Commitments (Approved & Pending) | This PVO | Other PVOs in circulation | Total Pending PVOs | Remaining Budget
| A | B | C | D = B + C | E | F | G = D + E + F | H | I | J = H+I | K = A-G-J
Professional Services (PS) | 24906962.8 | 20780079.36 | 4664935.12 | 25445014.48 | 0 | 101675.08 | 25546689.56 | 0 | 0 | 0 | -639726.76
Management Supervision (MS) | 13738307 | 13059930 | 1071977 | 14131907 | 0 | -53507 | 14078400 | 0 | 0 | 0 | -340093
Commercial Management (CM) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction (CN) | 505825346.56 | 479457540.54 | 2224880.47 | 481682421.01 | 0 | -18178391.66 | 463504029.35 | 0 | 0 | 0 | 42321317.21
Client Cost (CC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FF&E & OSE | 40186299.24 | 40154868.28 | 851779 | 41006647.28 | 0 | 0 | 41006647.28 | 0 | 0 | 0 | -820348.04
Savings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS | 584656915.6 | 553452418.18 | 8813571.59 | 562265989.77 | 0 | -18130223.58 | 544135766.19 | 0 | 0 | 0 | 40521149.41
-22390925.83

## Schedule J SS
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
Budget Approved - UNOFFICIALLY
ITEM | BUDGET TRANSFER DESCRIPTION |  | FROM PACKAGE | TO PACKAGE | BUDGET FROM PACKAGE | BUDGET TO PACKAGE | DATE | REPORTING PERIOD
1 | INTER PROGRAMME TRANSFER - Site Logistics budget transfer 2.547% |  | All Construction Packages | Site Logistics | -6199291.02 | 0 | 2022-08-19 | Monthly Report No 1 - Oct'22
2 | INTER PACKAGE TRANSFER - Piling NSCC to Construction Budget Hold - Contract Award |  | NSCC - Piling | Remaining budget - Construction Works | -2719369.0417 | 2719369.0417 | 2022-10-18 | Monthly Report No 1 - Oct'22 | 1
3 | ADDITIONAL BUDGET - Inline with EW Reported against PTE's to Civils package |  | External - Pre Approved | Civil and Arch Works |  | 70957643.397 | 2022-12-19 | Monthly Report No 3 - Dec'22
4 | ADDITIONAL BUDGET - Inline with EW Reported against PTE's to MEPD package |  | External - Pre Approved | MEPD |  | 27815335.598 | 2022-12-19 | Monthly Report No 3 - Dec'22
5 | ADDITIONAL BUDGET - Inline with EW Reported against PTE's to ICT / ELV package |  | External - Pre Approved | ICT / ELV |  | 4975465.6089 | 2022-12-19 | Monthly Report No 3 - Dec'22
6 | INTER PACKAGE TRANSFER - MEPD to Civils and Arch Works - Contract Award (Baytur) |  | MEPD | Civil and Arch Works | -12877723.65 | 12877723.65 | 2022-12-19 | Monthly Report No 3 - Dec'22
7 | INTER PACKAGE TRANSFER - MEPD to ICT / ELV - Contract Award (Baytur) |  | MEPD | ICT / ELV | -2819592.31 | 2819592.31 | 2022-12-19 | Monthly Report No 3 - Dec'22
8 | INTER PACKAGE TRANSFER - MEPD to Budget Hold - Contract Award (Baytur) - Saving |  | MEPD | Remaining budget - Construction Works | -12545905.62 | 12545905.62 | 2022-12-19 | Monthly Report No 3 - Dec'22 | 1
9 | INTER PACKAGE TRANSFER - MS Budget Hold to Khatib & Alami Contract Award (MS - AYC) |  | MS - Budget Hold | KAA-Mgt Fees | -13059930 | 13059930 | 2023-01-26 | Monthly Report No 4 - Jan'23
10 | INTER PACKAGE TRANSFER - PS Budget Hold to Langan Contract Award |  | PS - Budget Hold | Langan-Prf Fees | -172368.42 | 172368.42 | 2023-01-20 | Monthly Report No 4 - Jan'23
11 | INTER PACKAGE TRANSFER - PS Budget Hold to Zuhair Fayez Partnership Contract Award (PS - AYC) |  | PS - Budget Hold | ZFP-Prf Fees | -106231.5 | 106231.5 | 2023-01-26 | Monthly Report No 4 - Jan'23
33
12 | INTER PACKAGE TRANSFER - CN Budget Hold to Medtel W.N. WLL Contract Award (CN - AYC) |  | CN - Budget Hold | Medtel - STO Façade Mock-up | -834298.55 | 35 | 2023-01-26 | Monthly Report No 5 - Feb'23
13 | ADDITIONAL BUDGET - EW No.4 Reported at SAR 2,675,473 against PTE's to Vertical Transport |  | External - Pre Approved | Vertical Transport |  | 521622.03 | 2023-04-05 | Monthly Report No 7 - Apr'23
13 | INTER PACKAGE TRANSFER - PS Budget Hold to Jensen Hughes Contract Award |  | PS - Budget Hold | Jensen Hughes-Prf Fees | -127291.9 | 127291.9 | 2023-05-06 | Monthly Report No 8 - May'23
14 | INTER PACKAGE TRANSFER - Kitchen & Laundry Works to Budget Hold - Contract Award (Al Raqtan) - Saving |  | Special Kitchen | Remaining budget - FF&E and OSE | -1212511 | 1212511 | 2023-05-25 | Monthly Report No 8 - May'23
14 | INTER PACKAGE TRANSFER - PS Budget Hold to MOMRA (Tabuk) - Building Permit |  | PS - Budget Hold | MOM - Building Permit Fee | -45677.6 | 45677.6 |  | Monthly Report No 10 |  |  |  | Recent transfer to CN Hold | BTR from MH3 | Transferred budget for Kitchen Package
15 | INTER PROJECT TRANSFERS (INCOMING) |  | Approved Additional Budget | CN - Budget Hold | -104270066.6339 | 112330560.37 | 2023-07-18 | Monthly Report No 10 - Jul'23 (incl. the previous External-Pre Approved Budget. Kitchen package budget transferred under CN in ACC). |  |  | 112330560.37 | 93913586.15 | 13721765.22 | 4695209
16 | INTER PROJECT TRANSFERS (INCOMING) |  | Approved Additional Budget | FF&E OSE - Budget Hold | 0 | 33610960 | 2023-07-18 | Monthly Report No 10 - Jul'23 (transferred the budget for Kitchen to CN-Budget Hold) |  |  | 33610960 | 38306169 | -4695209
| Transfer budget to Hard and Soft Landscaping |  | CN - Budget Hold | Hard and Soft Landscaping | -12527902.4151 | 12527902.4151
| Transfer budget to Interior Fitout |  | CN - Budget Hold | Interior Fitout | -29047396.4327 | 29047396.4327
[11 empty] | 145941520.37 | Recent transfer to FFEOSE Hold | Transferred budget for Kitchen Package to CN
| TOTALS |  |  |  | -198565556.0935 | 337473554.8935
[6 empty] | 138907998.8 |  |  | transfer to Logistics |  | -6199291.02 | 132219755.15
[6 empty] | 104270066.6339 |  |  | Approved Budget Changes: |  | 139742229.35
41575298.8479
| INTER PROJECT TRANSFERS (OUTGOING) |  | PS - Budget Hold | Marina Hotel 3 - PS Hold | -6277273.42 | 0
| INTER PROJECT TRANSFERS (OUTGOING) |  | CN - Budget Hold | Marina Hotel 3 - CN Hold | -834298.55 | 0
History - related to budget transfers to appoint Baytur - due to additional budget not formally being approved as of 1 Feb 2023
ITEM | BUDGET TRANSFER DESCRIPTION | BTR APPROVAL REFERENCE | FROM PACKAGE | TO PACKAGE | BUDGET FROM PACKAGE | BUDGET TO PACKAGE | DATE | REPORTING PERIOD
1 | INTER PROGRAMME TRANSFER - Site Logistics budget transfer 2.547% | 1TB04034-034000-AMA-BTR-CM-0001-02 | CN - Budget Hold | Site Logistics | -6199291.02 | 0 | 2022-08-10 | Monthly Report No 1 - Oct'22 | from Construction Budget |  | 243418954.2 | 221633231.5
2 | INTER PACKAGE TRANSFER - PS Budget Hold to Langan Contract Award | AMA01003-BTR-000012 | PS - Budget Hold | Langan-Prf Fees | -168421.05 | 168421.05 | 2023-01-18 | Monthly Report No 4 - Jan'23
3 | INTER PACKAGE TRANSFER - PS Budget Hold to Langan Contract Award | AMA01003-RBTR-000018 | PS - Budget Hold | Langan-Prf Fees (Provisional) | -3947.37 | 3947.37 | 2023-01-22 | Monthly Report No 4 - Jan'23
4 | INTER PACKAGE TRANSFER - MS Budget Hold to PS Budget Hold | AMA01003-BTR-000037 | MS - Budget Hold | PS - Budget Hold | -172368.42 | 172368.42 | 2023-01-26 | Monthly Report No 4 - Jan'23
5 | INTER PACKAGE TRANSFER - CN Budget Hold to Saudi Baytur Contract Award | AMA01003-RBTR-000033 | CN - Budget Hold | Saudi Baytur - Main Works | -215433940.18 | 215433940.18 | 2022-01-20 | Monthly Report No 4 - Jan'23 | 260955414.4 | 174247542.3 | 174247542.3
6 | INTER PACKAGE TRANSFER - FF&E OSE Budget Hold to Saudi Baytur Contract Award | AMA01003-RBTR-000032 | FF&E OSE - Budget Hold | Saudi Baytur - Main Works | -24991549 | 24991549 | 2023-01-24 | Monthly Report No 4 - Jan'23 | 86707872.1
7 | INTER PACKAGE TRANSFER - PS Budget Hold to Saudi Baytur Contract Award | AMA01003-RBTR-000030 | PS - Budget Hold | Saudi Baytur - Main Works | -9717397.15 | 9717397.15 | 2023-01-24 | Monthly Report No 4 - Jan'23
8 | INTER PACKAGE TRANSFER - CM Budget Hold to Saudi Baytur Contract Award | AMA01003-RBTR-000034 | CM - Budget Hold | Saudi Baytur - Main Works | -1198399.55 | 1198399.55 | 2023-01-24 | Monthly Report No 4 - Jan'23
9 | INTER PACKAGE TRANSFER - MS Budget Hold to Saudi Baytur Contract Award | AMA01003-RBTR-000031 | MS - Budget Hold | Saudi Baytur - Main Works | -9614128.52 | 9614128.52 | 2023-01-24 | Monthly Report No 4 - Jan'23
10 | INTER PROJECT TRANSFER - MH3 PS Budget Hold to Zuhair Fayez Partnership Contract Award (PS - AYC) | AMA01003-WTRAN-001674 | Marina Hotel 3 - PS Hold | ZFP-Prf Fees | 0 | 106231.5 | 2023-02-08 | Monthly Report No 5 - Feb'23
11 | INTER PROJECT TRANSFER - MH3 PS Budget Hold to Khatib & Alami Contract Award (MS - AYC) | AMA01003-WTRAN-001673 | Marina Hotel 3 - PS Hold | KAA-Mgt Fees | 0 | 4870433.67 | 2023-02-08 | Monthly Report No 5 - Feb'23
12 | INTER PACKAGE TRANSFER - MS Budget Hold to Khatib & Alami Contract Award (MS - AYC) | AMA01003-WTRAN-001673 | MS - Budget Hold | KAA-Mgt Fees | -8189496.33 | 8189496.33 | 2023-02-08 | Monthly Report No 5 - Feb'23
13 | INTER PROJECT TRANSFER - MH3 PS Budget Hold to Dewan DVO 005 & DVO 006 | AMA01003-WTRAN-001799 | Marina Hotel 3 - PS Hold | DAE -Prf Fees | 0 | 367150 | 2023-02-14 | Monthly Report No 5 - Feb'23
14 | INTER PROJECT TRANSFER - MH3 PS Budget Hold to MOMRA (Building Permit Fee) | AMA01003-WTRAN-001952 | Marina Hotel 3 - PS Hold | MOM - Building Permit Fee | 0 | 45677.6 | 2023-03-01 | Monthly Report No 6 - Mar'23
15 | INTER PROJECT TRANSFER - MH3 PS Budget Hold to MOMRA (Building Permit Fee) | AMA01003-WTRAN-001952 | Marina Hotel 3 - PS Hold | Jensen Hughes-Prf Fees | 0 | 127291.9 | 2023-03-01 | Monthly Report No 6 - Mar'23
16 | INTER PROJECT TRANSFER - MH3 CN Budget Hold to Medtel Contract Award | AMA01009-WTRAN-000645 | Marina Hotel 3 - PS Hold | Medtel - STO Façade Mock-up | 0 | 834298.55 | 2023-03-05 | Monthly Report No 6 - Mar'23
17 | INTER PROJECT TRANSFER - MH3 PS Budget Hold to ESCCO Contract Award | AMA01009-WTRAN-001073 | Marina Hotel 3 - PS Hold | ESCCO - Vertical Transport | 0 | 2675473 | 2023-04-27 | Monthly Report No 7 - Apr'23
18 | INTER PROJECT TRANSFER - MH3 PS Budget Hold to RAQTAN Contract Award | AMA01009-WTRAN-001188 | Marina Hotel 3 - PS Hold | RAQTAN - Kitchen and Laundry | 0 | 4695209 | 2023-05-31 | Monthly Report No 8 - May'23
19 | BUDGET TRANSFERS (INCOMING) |  | Approved Additional Budget | CN - Budget Hold | 0 | 93913586.15 | 2023-07-18 | Monthly Report No 10 - Jul'23 |  |  | 112330560.37 | 93913586.15 | 13721765.22 | 4695209
20 | BUDGET TRANSFERS (INCOMING) |  | Approved Additional Budget | FF&E OSE - Budget Hold | 0 | 38306169 | 2023-07-18 | Monthly Report No 10 - Jul'23 |  |  | 33610960 | 38306169 | -4695209
Package under Procurement
21 | Transfer budget to Hard and Soft Landscaping |  | CN - Budget Hold | Hard and Soft Landscaping | -25857018 | 25857018 |  | Monthly Report No 10 - Jul'23
22 | Transfer budget to Interior Fitout (Approved Revised Budget) |  | CN - Budget Hold | Interior Fitout | -62092796 | 62092796 |  | Monthly Report No 10 - Jul'23 | -69715144.7768 | 75969227 | 13876431
23 | Tranfer budget to Loose FF&E Items (FOH) |  | FF&E OSE - Budget Hold | Loose FF&E items (FOH) | -25558750 | 25558750 |  | Monthly Report No 10 - Jul'23
24 | Transfer budget to Loose FF&E Items (BOH) |  | FF&E OSE - Budget Hold | Loose FF&E items (BOH) | -470000 | 470000 |  | Monthly Report No 10 - Jul'23
25 | Transfer budget to OS&E |  | FF&E OSE - Budget Hold | OS&E Items | -3543829 | 3543829 |  | Monthly Report No 10 - Jul'23
26 | Transfer budget to Art Works |  | FF&E OSE - Budget Hold | Art Work | -2874723 | 2874723 |  | Monthly Report No 10 - Jul'23
PS Variations to be funded under CN Budget Hold
27 | Dewan DVO 007 not yet entered in ACC - Transfer budget to PS Budget Hold from CN Budget Hold | AMA01003-RBTR-000059 | CN - Budget Hold | PS - Budget Hold | -413183 | 413183 |  | Monthly Report No 10 - Jul'23
28 | DEWAN DVO 009 - Transfer budget to PS Budget Hold from CN Budget Hold |  | CN - Budget Hold | PS - Budget Hold | -248219 | 248219 |  | Monthly Report No 10 - Jul'23
29 | DEWAN DVO 008 - Transfer budget to PS Budget Hold from CN Budget Hold |  | CN - Budget Hold | PS - Budget Hold | -194800 | 194800 |  | Monthly Report No 10 - Jul'23
30 | INTER PACKAGE TRANSFER - CN Budget Hold to GBC LEED Review | AMA01003-RBTR-000046 | CN - Budget Hold | GBC - Sustainability Accreditation | -13500.11 | 13500.11 | 2023-03-08 | Monthly Report No 11 - Aug'23
31 | INTER PACKAGE TRANSFER - NSC to CN Budget Hold | AMA01003-RBTR-000062 | NSCC - Piling | CN - Budget Hold | -3801279.3 | 3801279.3 | 2023-08-08 | Monthly Report No 11 - Aug'23
32 | INTER PACKAGE TRANSFER - CN Budget Hold to SAB (DVO 001) | AMA01003-RBTR-000061 | CN - Budget Hold | SAB - Civil and Arch Works, MEPD & ICT/ELV | -343524.99 | 343524.99 | 2023-08-07 | Monthly Report No 11 - Aug'23
33 | INTER PACKAGE TRANSFER - CN Budget Hold to NSC (DVO 007) | AMA01003-RBTR-000060 | CN - Budget Hold | NSCC - Piling | -70027.76 | 70027.76 | 2023-08-08 | Monthly Report No 11 - Aug'23
34 | INTER PACKAGE TRANSFER - CN Budget Hold to GBC LEED Review (future invoice) | AMA01003-RBTR-000074 | CN - Budget Hold | GBC - Sustainability Accreditation | -5737.5 | 5737.5 | 2023-09-11 | Monthly Report No 12 - Sep'23
35 | INTER PROJECT TRANSFER - AYC PS Budget Hold to Marina Village Wide MS Budget Hold (for Award of WSP Sustainability Accreditation LEED Consultancy Services) | AMA01100-WTRAN-003600 | CN - Budget Hold | Marina Village Wide MS Budget Hold | -302028 | 0 | 2023-09-16 | Monthly Report No 12 - Sep'23
| INTER PROJECT TRANSFER - CN Budget Hold to TB-Program 3 (Environmental Compliance Certificate) |  | CN - Budget Hold | TB - Program 3 - Medical Wellness Project (1.TB.03.008)) | 0 | 0 | 2023-08-16 | Monthly Report No 11 - Aug'23 | TB - Program 3 - Medical Wellness Project (not yet processed in ACC)
Contract Award for Interior Fitout (DEPA)
36 | Transfer budget to Interior Fitout (per Contract Award to DEPA). |  | FF&E OSE - Budget Hold | Interior Fitout | -5858867 | 5858867 |  | Monthly Report No 13 - Oct'23
37 | Transfer budget to Interior Fitout (per Contract Award to DEPA). |  | CN - Budget Hold | Interior Fitout | -393576.6032 | 393576.6032 |  | Monthly Report No 13 - Oct'23
38 | Transfer budget to Interior Fitout (per Contract Award to DEPA). |  | PS - Budget Hold | Interior Fitout | -1638.62 | 1638.62 |  | Monthly Report No 13 - Oct'23
39 | Transfer budget to Interior Fitout (per Contract Award to DEPA). |  | Hard and Soft Landscaping | Interior Fitout | -7622348.7768 | 7622348.7768 |  | Monthly Report No 13 - Oct'23
Contract Award to SALCO - AYC Landscape Works
40 | Balancing - Contract Award to SALCO |  | CN - Budget Hold | Hard and Soft Landscaping | -1511591.4168 | 1511591.4168 |  | Monthly Report No 18 - Mar'24 | -18234669.2232 | -16723077.8064
41 | Contract Award to Alutec |  | CN - Budget Hold | Façade & Glazing Works | -29899670.55 | 29899670.55 |  | Monthly Report No 18 - Mar'24
42 | Landscaping Budget Transfer to CN Hold (Fund the Alutec Award) |  | Hard and Soft Landscaping | CN - Budget Hold | -19746260.64 | 19746260.64 |  | Monthly Report No 15 - May'24
43 | Contract Award to Areen Design Ltd |  | Loose FF&E items (FOH) | FF&E and OSE Procurement Agent | -1107465.88 | 1107465.88 |  | Monthly Report No 16 - Jun'24
44 | Contract Award to Euro Consult for Engineering Consultancy |  | MS - Budget Hold | ECC-Mgt Fees | -182184.38 | 182184.38 |  | Monthly Report No 16 - Jun'24
Adjustments to Align with ACC
45 | Transfer of Kitchen funds from CN-Budget Hold to FF&E Budget Hold |  | CN - Budget Hold | FF&E OSE - Budget Hold | -6244811.44 | 6244811.44 |  | Monthly Report No 23 - Aug'24
47 | Seed Fund Transfer for FOH FF&E |  | Loose FF&E items (FOH) | OS&E Items | -1452636.56 | 1452636.56 |  | Monthly Report No 23 - Aug'24
48 | Seed Fund Transfer for OS&E |  | FF&E OSE - Budget Hold | OS&E Items | -6244811.44 | 6244811.44 |  | Monthly Report No 23 - Aug'24
49 | Seed Fund Transfer for for OS&E (Money transfer from Art Package) |  | Art Work | OS&E Items | -2874723 | 2874723 |  | Monthly Report No 23 - Aug'24
50 | Seed Fund Transfer for OS&E (Money transfer from FF&E BOH) |  | Loose FF&E items (BOH) | OS&E Items | -470000 | 470000 |  | Monthly Report No 23 - Aug'24
51 | Contract Award to CML (Independent Commissioning Agent) |  | CN - Budget Hold | CML-Mgt Fees | -1611661.58 | 1611661.58 |  | Monthly Report No 24 - Sep'24
51 | Contract Award to CML (Independent Commissioning Agent) |  | MS - Budget Hold | CML-Mgt Fees | -794838.42 | 794838.42 |  | Monthly Report No 24 - Sep'24
52 | Adjustment to GBC per actual commitment |  | GBC - Sustainability Accreditation | CN - Budget Hold | -643.12 | 643.12 |  | Monthly Report No 24 - Sep'24
53 | Contract Award to MAS (Wet Works) |  | CN - Budget Hold | MAS - Labour Supply - Wet Works | -4004000 | 4004000 |  | Monthly Report No 26 - Nov'24
54 | Contract Award to MAS (Amphitheatre) |  | CN - Budget Hold | MAS - Amphitheatre | -1078892.27 | 1078892.27 |  | Monthly Report No 26 - Nov'24
55 | Contract Award to Al Fanar (Labour Supply) |  | CN - Budget Hold | Al Fanar - MEP Labour Supply | -23125000 | 23125000 |  | Monthly Report No 26 - Nov'24
56 | Contract Award to ARMETAL |  | CN - Budget Hold | ARMETAL - Reflective ceiling | -7129950 | 7129950 |  | Monthly Report No 28 - Jan'25
57 | Owner Controlled Insurance Program |  | CN - Budget Hold | Al Rahji Takaful - Owner Controlled Insurance Program | -63223 | 63223 |  | Monthly Report No 28 - Jan'25
58 | Contract Award to Euro Consulta (Accom & Transpo) |  | MS - Budget Hold | ECC-Mgt Fees (Accom & Transpo) | -54000 | 54000 |  | Monthly Report No 29 - Feb'25
59 | INTER PROGRAM TRANSFER |  | IDC98998.98 (20-Jan-2025) | CN - Budget Hold | 0 | 26351961 |  | Monthly Report No 29 - Feb'25
60 | INTER PROGRAM TRANSFER |  | IDC98998.98 (20-Jan-2025) | FF&E OSE - Budget Hold | 0 | 429156 |  | Monthly Report No 29 - Feb'25
1511591.4168
61 | INTER PROGRAM TRANSFER |  | IDC98998.98 (20-Jan-2025) | CN - Budget Hold | 0 | 40000000 |  | Monthly Report No 30 - March'25
| TOTALS |  |  |  | -522951148.9468 | 729172467.2968
206221318.35
|  |  |  | 794838.42 | -522951148.9468 | 689172467.2968
[6 empty] | 166221318.35 |  |  | 7522474.2
|  |  |  | -1611661.58 | -342565351.38 | 95425177.5668 | -247140173.8132
[5 empty] | -63297718 | 38306169 | -24991549
2406500
12 | ADDITIONAL BUDGET - Inline with adapted Level 5 Cost Report - Revised Asset Budget Allocation - Civil and Arch Works Package |  | External - Approved - Revised Asset Budget Allocation (02/02/2023) | Civil and Arch Works |  | Refer to budget value in Item 3 above | 2023-02-02 | Monthly Report No 5 - Feb'23
13 | ADDITIONAL BUDGET - Inline with adapted Level 5 Cost Report - Revised Asset Budget Allocation - MEPD Works Package |  | External - Approved - Revised Asset Budget Allocation (02/02/2023) | MEPD |  | Refer to budget value in Item 4 above | 2023-02-02 | Monthly Report No 5 - Feb'23
14 | ADDITIONAL BUDGET - Inline with adapted Level 5 Cost Report - Revised Asset Budget Allocation - ICT / ELV Works Package |  | External - Approved - Revised Asset Budget Allocation (02/02/2023) | ICT / ELV |  | Refer to budget value in Item 5 above | 2023-02-02 | Monthly Report No 5 - Feb'23
15 | ADDITIONAL BUDGET - Inline with adapted Level 5 Cost Report - Revised Asset Budget Allocation - Lifts / Vertical Transport Works Package |  | External - Approved - Revised Asset Budget Allocation (02/02/2023) | Vertical Transport |  | 4445483.92 | 2023-02-02 | Monthly Report No 5 - Feb'23
16 | ADDITIONAL BUDGET - Inline with adapted Level 5 Cost Report - Revised Asset Budget Allocation - Hard and Soft Landscaping Works Package |  | External - Approved - Revised Asset Budget Allocation (02/02/2023) | Hard and Soft Landscaping |  | 25277152.84 | 2023-02-02 | Monthly Report No 5 - Feb'23
17 | ADDITIONAL BUDGET - Inline with adapted Level 5 Cost Report - Revised Asset Budget Allocation - Interior Fit-out Works Package |  | External - Approved - Revised Asset Budget Allocation (02/02/2023) | Interior Fitout |  | 16518492.02 | 2023-02-02 | Monthly Report No 5 - Feb'23
18 | BUDGET ALIGNMENT - Inline with adapted Level 5 Cost Report - Revised Asset Budget Allocation - Loose FF&E items (BOH) Package (reported as Early Warning No. 08) |  | External - Approved - Revised Asset Budget Allocation (02/02/2023) | Loose FF&E items (BOH) |  | 130000 | 2023-02-02 | Monthly Report No 5 - Feb'23
19 | BUDGET ALIGNMENT - Inline with adapted Level 5 Cost Report - Revised Asset Budget Allocation - Special Kitchen Package (reported as Early Warning No. 07) |  | External - Approved - Revised Asset Budget Allocation (02/02/2023) | Loose FF&E items (BOH) |  | -522340 | 2023-02-02 | Monthly Report No 5 - Feb'23
20 | BUDGET ALIGNMENT - Inline with adapted Level 5 Cost Report - Revised Asset Budget Allocation - Zeroing the Remaining budget - Construction Works (Item 2 and 8 above). |  | External - Approved - Revised Asset Budget Allocation (02/02/2023) | Loose FF&E items (BOH) | 17803624.85 | -17803624.85 | 2023-02-02 | Monthly Report No 5 - Feb'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to DEWAN Variations (DVO 05 & DVO 06) (PS - AYC) |  | Marina Hotel 3 - PS Hold | DAE -Prf Fees | -367150 | 367150 | 2023-03-27 | Monthly Report No 6 - Mar'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to DEWAN Variations (DVO 05 & DVO 06) (PS - AYC) |  | Marina Hotel 3 - PS Hold | DAE -Prf Fees | -367150 | 367150 | 2023-03-27 | Monthly Report No 6 - Mar'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to ESCCO - VT Package ( AYC) |  | Marina Hotel 3 - PS Hold | Vertical Transport | -2675473 | 2675473 | 2023-04-27 | Monthly Report No 7 - Apr'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to Jensen (PS - AYC) |  | Marina Hotel 3 - PS Hold | Jensen Hughes-Prf Fees | -127291.9 | 127291.9 | 2023-03-27 | Monthly Report No 7 - Apr'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to Kitchen Package (CN - AYC) |  | Marina Hotel 3 - PS Hold | DAE -Prf Fees | -4695209 | 4695209 |  | Monthly Report No 8 - May'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to Boundary Visualiztion Limited (Rosewood Team) |  | Marina Hotel 3 - PS Hold |  | -760489 | 760489 |  | Monthly Report No 8 - May'23 | To Rosewood PS Budget Hold.
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to Zuhair Fayez Partnership Contract Award (PS - AYC) |  | Marina Hotel 3 - PS Hold | ZFP-Prf Fees | -106231.5 | 106231.5 | 2022-01-26 | Monthly Report No 4 - Jan'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to Khatib & Alami Contract Award (MS - AYC) |  | Marina Hotel 3 - PS Hold | KAA-Mgt Fees | -4870433.67 | 4870433.67 | 2022-01-26 | Monthly Report No 4 - Jan'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to DEWAN Variations (DVO 05 & DVO 06) (PS - AYC) |  | Marina Hotel 3 - PS Hold | DAE -Prf Fees | -367150 | 367150 | 2023-03-27 | Monthly Report No 6 - Mar'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to DEWAN Variations (DVO 05 & DVO 06) (PS - AYC) |  | Marina Hotel 3 - PS Hold | DAE -Prf Fees | -367150 | 367150 | 2023-03-27 | Monthly Report No 6 - Mar'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to ESCCO - VT Package ( AYC) |  | Marina Hotel 3 - PS Hold | Vertical Transport | -2675473 | 2675473 | 2023-04-27 | Monthly Report No 7 - Apr'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to Jensen (PS - AYC) |  | Marina Hotel 3 - PS Hold | Jensen Hughes-Prf Fees | -127291.9 | 127291.9 | 2023-03-27 | Monthly Report No 7 - Apr'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to Kitchen Package (CN - AYC) |  | Marina Hotel 3 - PS Hold | DAE -Prf Fees | -4695209 | 4695209 |  | Monthly Report No 8 - May'23
| INTER PROJECT TRANSFER - MH3 PS Budget Hold to Boundary Visualiztion Limited (Rosewood Team) |  | Marina Hotel 3 - PS Hold |  | -760489 | 760489 |  | Monthly Report No 8 - May'23 | To Rosewood PS Budget Hold.

## Schedule E(ss)
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
SCHEDULE E - CLAIMS AND DISPUTES - | [14 empty] | Period to Settle Claim
Claims Summary | [5 empty] | Reference Documents | [17 empty] | Instruction Documents |  |  | Claim Amounts (SAR) |  |  | Extension of Time (days) |  |  | Actionee | Date | Remarks | Action Before Next Month | Don’t Delete
Claim No. |  | Description of Claim |  |  |  | Date on which Contractor became aware of the issue | Contractor's notification with COC clause reference |  |  | Period between aware & notification | Is period complying with the Contract | Acknowledgement of Contractor's notification by Engineer & advise to submit substantiation |  | Detailed substantiation due date | Final Detailed substantiation by Contractor |  | Is period complying with the Contract | Engineer's recommendation to Client's representative |  | Change Request Form confirmation from Client |  | Engineers Response to Contractor |  | Period between Final Substantiation from the Contractor to Determination | Variation Order |  | Contractor's Claim (SAR) | Engineer's Recommendation (SAR) | Client Representative's approval (SAR) | Contractors Claim (Days) | Engineer's Recommendation (Days) | Client Representative's Approval (Days)
AMAALA | CONTRACTOR | PROJECT | CODE | CONTRACTOR'S NAME | DESCRIPTION | (A) In Date | (B) Date | Aconex Ref | COC Clause Ref | C = (B-A) In Days | YES / NO | Date | Aconex Ref | D = A + 84 (old Contract) or 30 (new Contract) In Date | (E) Date | Aconex Ref | YES / NO | Date | Aconex Ref | Date | Aconex Ref | (F) Date | Aconex Ref | G = (F - E) DAYS | Date | Aconex Ref | SAR | SAR | SAR | DAYS | DAYS | DAYS
AMA - CLAIM NO. | CONT - CLAIM NO. | PROJECT | CODE | CONTRACTOR'S NAME | DESCRIPTION | 1 | DATE OF NOTIFICATION | 2 | 3 | DAYS | 4 | 5 | 6 | 84 DAYS | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
[11 empty] | C = <=28 DAYS (old Contract) or <=20 DAYS (new Contract) | [5 empty] | (E-A)= <84 DAYS (old Contract) or <30 DAYS (new Contract)
9 | 1 | AMAALA YACHT CLUB | 1.TB.01.003 | NSCC | Delay in Issuance of IFC drawings for piling | 2022-06-07 | 2022-06-08 | NSC-LTR-000029 | 10.1 | 1 | YES |  |  | 2022-08-30 | [12 empty] | 197807.1 |  |  | 44 |  |  | CONTRACTOR |  |  | See the Claim No.15
1 | 1 | AMAALA YACHT CLUB | 1.TB.01.003 | SIC | Change In Ground Condition | 2021-11-24 | 2022-01-17 | YAM.-LTR-000004 | 8.5 | 54 | NO | 2022-01-18 | 1TB00004-007C02-SAP-LTR-0043 | 2022-02-16 | 2022-03-09 | YAM.-LTR-000009 | NO | 2022-03-29 | 1TB04004-004D01-SAP-LTR-0008 | [7 empty] | 0 |  |  | 93 | 30 |  | CLIENT |  | No Cost Impact / CLOSED.
11 | 5 | AMAALA YACHT CLUB | 1.TB.01.003 | NSCC | Variance In Soil Layers | 2022-08-03 | 2022-08-03 | NSC-LTR-000061 |  | 0 | YES | 2022-08-21 | WSP-GENCORR-000078 | 2022-10-26 | [12 empty] | 6359633.48 |  |  | 190 |  |  | ENGINEER |  | Revised EOT via 1TB04400-005C13-NSC-LTR-0229 Dt: 19th Jan- 23
12 | 7 | AMAALA YACHT CLUB | 1.TB.01.003 | NSCC | Revised Co-ordinate System - SANSRS | 2022-06-06 | 2022-08-03 | NSC-LTR-000075 |  | 58 | NO |  |  | 2022-08-29 | [12 empty] | 5648747.98 |  |  | 190 |  |  | ENGINEER |  | NOD via 1TB04400-005C13-NSC-LTR-0241 Dt: 24th Jan-23 | See the Claim No.15
13 | 10 | AMAALA YACHT CLUB | 1.TB.01.003 | NSCC | Delay In Benchmarks & Control Points | 2022-08-28 | 2022-08-28 | NSC-LTR-000093 |  | 0 | YES |  |  | 2022-11-20 | [18 empty] | CONTRACTOR |  | Rejection by Engg Rep via WSP-LTR-000030
14 | 15 | AMAALA YACHT CLUB | 1.TB.01.003 | NSCC | Consolidated Claim (Item 1 & 7) - Upto 20th October 2022 | 2022-10-29 | 2022-10-29 | 1TB04400-005C13-NSC-LTR-0145 |  | 0 | YES |  |  | 2023-01-21 | [12 empty] | 3065470.23 |  |  | 152 |  |  | ENGINEER |  | Responded via 1TB04400-005C13-NSC-LTR-0204 Dt: 22nd Dec- 22
15 | 20 | AMAALA YACHT CLUB | 1.TB.01.003 | NSCC | Delay to Dewatering and Excavation Works | 2023-02-18 | 2023-02-23 | 1TB04400-005C13-NSC-LTR-0267 |  | 5 | YES |  |  | 2023-05-13 | 2023-03-16 | 1TB04400-005C13-NSC-LTR-0287 | YES | [9 empty] | 41556.12 |  |  | 12 |  |  | ENGINEER
2 | Consolidated | AMAALA YACHT CLUB | 1.TB.01.003 | NSCC | Updated Consolidation of the Contractor’s Claim up to 14 April 2023 (AYC Section) | 2022-10-29 | 2022-10-29 | 1TB04400-005C13-NSC-LTR-0145 |  | 0 | YES |  |  | 2023-01-21 | 2023-04-29 | 1TB04400-005C13-NSC-LTR-326 | NO | [9 empty] | 6874965.4328 |  |  | 122 |  |  | ENGINEER |  |  |  | 1436
8 | 1 | AMAALA YACHT CLUB | 1.TB.01.003 | Baytur | Extension of Time Claim Accordance to Approved Variation Order # 002 (Changes from IFT to IFC) | 2023-05-17 | 2023-05-18 | 1TB01003-003C03-SAB-LTR-0006 |  | 1 | YES |  |  | 2023-06-16 | 2023-09-17 | 1TB01003-003C03-SAB-LTR-0027 | NO | [5 empty] | 1TB01003-003C03-AMA-LTR-0026 |  |  |  | 0 | N/a | 0 | 42 | N/a | 0 | CONTRACTOR
23
24
25
26
27
28
29
CLAIM TRACKER
Note on G19: Vaseef Shaikh: Date of aware TBC
Note on G21: Vaseef Shaikh: Date of aware TBC
Note on G22: Vaseef Shaikh: Date of Awarness TBC
Note on G25: Vaseef Shaikh: Date of Awarness TBC

## Schedule L
PROGRAMME: - MARINA VILLAGE (PROGRAMME 1_TRIPLE BAY)
PROGRAMME CODE: - 1TB01003
ASSET NAME: - AMAALA YACHT CLUB
ASSET CODE: - 1TB01003.01
REPORT NO: - MONTHLY REPORT NO. 49
REPORTING PERIOD: - OCTOBER 2026
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 39 | 40 | TOTAL
|  |  |  | 41638 | 41668 | 41698 | 41728 | 41758 | 41788 | 41818 | 41848 | 41878 | 41908 | 41938 | 41968 | 41998 | 42028 | 42058 | 42088 | 42118 | 42148 | 42178 | 42208 | 42238 | 42268 | 42298 | 42328 | 42358 | 42388 | 42418 | 42448 | 42478 | 42508 | 42538 | 42568 | 42598 | 42628 | 42658 | 42688 | 42718 | 42748 | 42778 | 42808 | 42838 | 42868 | 42898 | 42928 | 42958 | 42988 | 43018 | 43048 | 42778 | 42808
AMAALA YACHT CLUB
PROJECT CASH FLOW
Project Render
Financial Status
Contract Award value
0
0
0
|  | Current Budget as of Report Date | 0
|  |  | CONTRACT | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 39 | 40 | TOTAL
|  |  | SUM | 2017-10-30 | 2017-11-29 | 2017-12-29 | 2018-01-28 | 2018-02-27 | 2018-03-29 | 2018-04-28 | 2018-05-28 | 2018-06-27 | 2018-07-27 | 2018-08-26 | 2018-09-25 | 2018-10-25 | 2018-11-24 | 2018-12-24 | 2019-01-23 | 2019-02-22 | 2019-03-24 | 2019-04-23 | 2019-05-23 | 2019-06-22 | 2019-07-22 | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18 | 2020-04-17 | 2020-05-17 | 2020-06-16 | 2020-07-16 | 2020-08-15 | 2020-09-14 | 2020-10-14 | 2020-11-13 | 2020-12-13 | 2021-01-12 | 2021-02-11 | 2021-03-13 | 2021-04-12 | 2021-05-12 | 2021-06-11 | 2021-07-11 | 2021-08-10 | 2021-09-09 | 2021-10-09 | 2021-11-08
|  | BASELINE - Cum. | 0 | 252931 | 788138 | 1368156 | 2407058 | 4174455 | 6076104 | 9344763 | 13455269 | 16843056 | 25355592 | 33041302 | 39218241 | 47423550 | 55608019 | 63560706 | 70540091 | 76980429 | 84273786 | 91584611 | 98582713 | 106645474 | 115777011 | 125345957 | 136828665 | 150811073 | 165222041 | 178337593 | 190708725 | 202369002 | 215633829 | 229349657 | 242352591 | 255855903 | 268279095 | 280034764 | 291478861 | 301924601 | 311973970 | 322235866 | 330337917 | 337714866 | 344585699 | 349868606 | 353035831 | 354816856 | 0 | 0 | 0 | 0 | 0
|  | BASELINE - Net |  | 252931 | 535207 | 580018 | 1038902 | 1767397 | 1901649 | 3268659 | 4110506 | 3387787 | 8512536 | 7685710 | 6176939 | 8205309 | 8184469 | 7952687 | 6979385 | 6440338 | 7293357 | 7310825 | 6998102 | 8062761 | 9131537 | 9568946 | 11482708 | 13982408 | 14410968 | 13115552 | 12371132 | 11660277 | 13264827 | 13715828 | 13002934 | 13503312 | 12423192 | 11755669 | 11444097 | 10445740 | 10049369 | 10261896 | 8102051 | 7376949 | 6870833 | 5282907 | 3167225 | 1781025 | -354816856 | 0 | 0 | -311973970 | 0
| 100 | MAIN CONSTRUCTION WORKS | CUM. | 252931 | 788138 | 1368156 | 2407058 | 4174455 | 6076104 | 9344763 | 13455269 | 16843056 | 25355592 | 33041302 | 39218241 | 47423550 | 55608019 | 63560706 | 70540091 | 76980429 | 84273786 | 91584611 | 98582713 | 106645474 | 115777011 | 125345957 | 136828665 | 150811073 | 165222041 | 178337593 | 190708725 | 202369002 | 215633829 | 229349657 | 242352591 | 255855903 | 268279095 | 280034764 | 291478861 | 301924601 | 311973970 | 322235866 | 330337917 | 337714866 | 344585699 | 349868606 | 353035831 | 354816856 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 252931 | 535207 | 580018 | 1038902 | 1767397 | 1901649 | 3268659 | 4110506 | 3387787 | 8512536 | 7685710 | 6176939 | 8205309 | 8184469 | 7952687 | 6979385 | 6440338 | 7293357 | 7310825 | 6998102 | 8062761 | 9131537 | 9568946 | 11482708 | 13982408 | 14410968 | 13115552 | 12371132 | 11660277 | 13264827 | 13715828 | 13002934 | 13503312 | 12423192 | 11755669 | 11444097 | 10445740 | 10049369 | 10261896 | 8102051 | 7376949 | 6870833 | 5282907 | 3167225 | 1781025 | -354816856 | 0 | 0 | -311973970 | 0
| 100.1 | 0 | 0
|  | Work Done To Date | i | 252931 | 788138 | 1368156 | 2407058 | 4174455 | 6076104 | 9344763 | 13455269 | 16843056 | 25355592 | 33041302 | 39218241 | 47423550 | 55608019 | 63560706 | 70540091 | 76980429 | 84273786 | 91584611 | 98582713 | 106645474 | 115777011 | 125345957 | 136828665 | 150811073 | 165222041 | 178337593 | 190708725 | 202369002 | 215633829 | 229349657 | 242352591 | 255855903 | 268279095 | 280034764 | 291478861 | 301924601 | 311973970 | 322235866 | 330337917 | 337714866 | 344585699 | 349868606 | 353035831 | 354816856 |  |  | 0 | 0 | 0
|  | Provisional Sum spread |  | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 252931 | 788138 | 1368156 | 2407058 | 4174455 | 6076104 | 9344763 | 13455269 | 16843056 | 25355592 | 33041302 | 39218241 | 47423550 | 55608019 | 63560706 | 70540091 | 76980429 | 84273786 | 91584611 | 98582713 | 106645474 | 115777011 | 125345957 | 136828665 | 150811073 | 165222041 | 178337593 | 190708725 | 202369002 | 215633829 | 229349657 | 242352591 | 255855903 | 268279095 | 280034764 | 291478861 | 301924601 | 311973970 | 322235866 | 330337917 | 337714866 | 344585699 | 349868606 | 353035831 | 354816856 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 252931 | 788138 | 1368156 | 2407058 | 4174455 | 6076104 | 9344763 | 13455269 | 16843056 | 25355592 | 33041302 | 39218241 | 47423550 | 55608019 | 63560706 | 70540091 | 76980429 | 84273786 | 91584611 | 98582713 | 106645474 | 115777011 | 125345957 | 136828665 | 150811073 | 165222041 | 178337593 | 190708725 | 202369002 | 215633829 | 229349657 | 242352591 | 255855903 | 268279095 | 280034764 | 291478861 | 301924601 | 311973970 | 322235866 | 330337917 | 337714866 | 344585699 | 349868606 | 353035831 | 354816856 | 0 | 0 | 0 | 0 | 0
|  | Retention 5% cash 5% bond | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | Sub-total | x=vii+viii+ix | 252931 | 788138 | 1368156 | 2407058 | 4174455 | 6076104 | 9344763 | 13455269 | 16843056 | 25355592 | 33041302 | 39218241 | 47423550 | 55608019 | 63560706 | 70540091 | 76980429 | 84273786 | 91584611 | 98582713 | 106645474 | 115777011 | 125345957 | 136828665 | 150811073 | 165222041 | 178337593 | 190708725 | 202369002 | 215633829 | 229349657 | 242352591 | 255855903 | 268279095 | 280034764 | 291478861 | 301924601 | 311973970 | 322235866 | 330337917 | 337714866 | 344585699 | 349868606 | 353035831 | 354816856 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 252931 | 788138 | 1368156 | 2407058 | 4174455 | 6076104 | 9344763 | 13455269 | 16843056 | 25355592 | 33041302 | 39218241 | 47423550 | 55608019 | 63560706 | 70540091 | 76980429 | 84273786 | 91584611 | 98582713 | 106645474 | 115777011 | 125345957 | 136828665 | 150811073 | 165222041 | 178337593 | 190708725 | 202369002 | 215633829 | 229349657 | 242352591 | 255855903 | 268279095 | 280034764 | 291478861 | 301924601 | 311973970 | 322235866 | 330337917 | 337714866 | 344585699 | 349868606 | 353035831 | 354816856 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 252931 | 535207 | 580018 | 1038902 | 1767397 | 1901649 | 3268659 | 4110506 | 3387787 | 8512536 | 7685710 | 6176939 | 8205309 | 8184469 | 7952687 | 6979385 | 6440338 | 7293357 | 7310825 | 6998102 | 8062761 | 9131537 | 9568946 | 11482708 | 13982408 | 14410968 | 13115552 | 12371132 | 11660277 | 13264827 | 13715828 | 13002934 | 13503312 | 12423192 | 11755669 | 11444097 | 10445740 | 10049369 | 10261896 | 8102051 | 7376949 | 6870833 | 5282907 | 3167225 | 1781025 | -354816856 | 0 | 0 | -311973970 | 0
| 200 | FIXTURES, FITTINGS & EQUIPMENT | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 200.1 | Vendor - None
|  | Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 300 | LOCAL AUTHORITIES | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 300.1 | 0 | 0
|  | Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 400 | CONTINGENCY | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 400.1 | Contingency Spend | 0
|  | Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 500 | MISCELLANEOUS ITEMS | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 500.1 | Vendor - NA
|  | Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[33 empty] | 5% | 10% | 20% | 30% | 45% | 60% | 70% | 80% | 90% |  | 5% | 10% | 20% | 30% | 45% | 60% | 70% | 80% | 90% | 95% | 100%
|  |  | CONTRACT | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 39 | 40 | TOTAL
|  |  | SUM | 2017-10-30 | 2017-11-29 | 2017-12-29 | 2018-01-28 | 2018-02-27 | 2018-03-29 | 2018-04-28 | 2018-05-28 | 2018-06-27 | 2018-07-27 | 2018-08-26 | 2018-09-25 | 2018-10-25 | 2018-11-24 | 2018-12-24 | 2019-01-23 | 2019-02-22 | 2019-03-24 | 2019-04-23 | 2019-05-23 | 2019-06-22 | 2019-07-22 | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18 | 2020-04-17 | 2020-05-17 | 2020-06-16 | 2020-07-16 | 2020-08-15 | 2020-09-14 | 2020-10-14 | 2020-11-13 | 2020-12-13 | 2021-01-12 | 2021-02-11 | 2021-03-13 | 2021-04-12 | 2021-05-12 | 2021-06-11 | 2021-07-11 | 2021-08-10 | 2021-09-09 | 2021-10-09 | 2021-11-08
|  | ACTUAL/FORECAST - Cum. | 0 | 252931 | 788517 | 1368533.82 | 2407436.82 | 4036135.1 | 6076103.82 | 9385869.82 | 12971852.76 | 14526575.17 | 24389411.91 | 28088742.47 | 30455903.82 | 34141754.18 | 38326488.94 | 41604487.87 | 45771266.12 | 52661081.4 | 58458574.05 | 63354535.66 | 68652105.98 | 75153981.91 | 82227931.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ACTUAL/FORECAST - Net |  | 252931 | 535586 | 580016.82 | 1038903 | 1628698.28 | 2039968.72 | 3309766 | 3585982.94 | 1554722.41 | 9862836.74 | 3699330.56 | 2367161.35 | 3685850.36 | 4184734.76 | 3277998.93 | 4166778.25 | 6889815.28 | 5797492.65 | 4895961.61 | 5297570.32 | 6501875.93 | 7073949.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 100 | MAIN CONSTRUCTION WORKS | CUM. | 252931 | 788517 | 1368533.82 | 2407436.82 | 4036135.1 | 6076103.82 | 9385869.82 | 12971852.76 | 14526575.17 | 24389411.91 | 28088742.47 | 30455903.82 | 34141754.18 | 38326488.94 | 41604487.87 | 45771266.12 | 52661081.4 | 58458574.05 | 63354535.66 | 68652105.98 | 75153981.91 | 82227931.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 252931 | 535586 | 580016.82 | 1038903 | 1628698.28 | 2039968.72 | 3309766 | 3585982.94 | 1554722.41 | 9862836.74 | 3699330.56 | 2367161.35 | 3685850.36 | 4184734.76 | 3277998.93 | 4166778.25 | 6889815.28 | 5797492.65 | 4895961.61 | 5297570.32 | 6501875.93 | 7073949.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 100.1 | 0 | 0
|  | Work Done To Date | i | 252931 | 788517 | 1368533.82 | 2407436.82 | 4036135.1 | 6076103.82 | 9385869.82 | 12971852.76 | 14526575.17 | 24389411.91 | 28088742.47 | 30455903.82 | 34141754.18 | 38326488.94 | 41604487.87 | 45771266.12 | 52661081.4 | 58458574.05 | 63354535.66 | 68652105.98 | 75153981.91 | 82227931.37 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 252931 | 788517 | 1368533.82 | 2407436.82 | 4036135.1 | 6076103.82 | 9385869.82 | 12971852.76 | 14526575.17 | 24389411.91 | 28088742.47 | 30455903.82 | 34141754.18 | 38326488.94 | 41604487.87 | 45771266.12 | 52661081.4 | 58458574.05 | 63354535.66 | 68652105.98 | 75153981.91 | 82227931.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [27 empty] | 0 | [9 empty] | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 252931 | 788517 | 1368533.82 | 2407436.82 | 4036135.1 | 6076103.82 | 9385869.82 | 12971852.76 | 14526575.17 | 24389411.91 | 28088742.47 | 30455903.82 | 34141754.18 | 38326488.94 | 41604487.87 | 45771266.12 | 52661081.4 | 58458574.05 | 63354535.66 | 68652105.98 | 75153981.91 | 82227931.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 5% Cash 5% Bond | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 252931 | 788517 | 1368533.82 | 2407436.82 | 4036135.1 | 6076103.82 | 9385869.82 | 12971852.76 | 14526575.17 | 24389411.91 | 28088742.47 | 30455903.82 | 34141754.18 | 38326488.94 | 41604487.87 | 45771266.12 | 52661081.4 | 58458574.05 | 63354535.66 | 68652105.98 | 75153981.91 | 82227931.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 252931 | 788517 | 1368533.82 | 2407436.82 | 4036135.1 | 6076103.82 | 9385869.82 | 12971852.76 | 14526575.17 | 24389411.91 | 28088742.47 | 30455903.82 | 34141754.18 | 38326488.94 | 41604487.87 | 45771266.12 | 52661081.4 | 58458574.05 | 63354535.66 | 68652105.98 | 75153981.91 | 82227931.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 252931 | 535586 | 580016.82 | 1038903 | 1628698.28 | 2039968.72 | 3309766 | 3585982.94 | 1554722.41 | 9862836.74 | 3699330.56 | 2367161.35 | 3685850.36 | 4184734.76 | 3277998.93 | 4166778.25 | 6889815.28 | 5797492.65 | 4895961.61 | 5297570.32 | 6501875.93 | 7073949.46 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 200 | FIXTURES, FITTINGS & EQUIPMENT | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [29 empty] | 0
| 200.1 | Vendor - N/A
|  | Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 300 | LOCAL AUTHORITIES | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 300.1 | Local Authorities Fees | 0
|  | Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 400 | CONTINGENCY | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 400.1 | 0 | 0
|  | Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 500 | MISCELLANEOUS ITEMS | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 500.1 | Proposed Vendor XXX
|  | Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | CONTRACT | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 39 | 40 | TOTAL
|  |  | VALUE | 2017-10-30 | 2017-11-29 | 2017-12-29 | 2018-01-28 | 2018-02-27 | 2018-03-29 | 2018-04-28 | 2018-05-28 | 2018-06-27 | 2018-07-27 | 2018-08-26 | 2018-09-25 | 2018-10-25 | 2018-11-24 | 2018-12-24 | 2019-01-23 | 2019-02-22 | 2019-03-24 | 2019-04-23 | 2019-05-23 | 2019-06-22 | 2019-07-22 | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18 | 2020-04-17 | 2020-05-17 | 2020-06-16 | 2020-07-16 | 2020-08-15 | 2020-09-14 | 2020-10-14 | 2020-11-13 | 2020-12-13 | 2021-01-12 | 2021-02-11 | 2021-03-13 | 2021-04-12 | 2021-05-12 | 2021-06-11 | 2021-07-11 | 2021-08-10 | 2021-09-09 | 2021-10-09 | 2021-11-08
|  | MPX -UPDATED FORECAST - Cum. | 340254842 | 252931 | 788517 | 1368354 | 2407437 | 4036135 | 6076104 | 9385870 | 12971853 | 14526575 | 24389412 | 28088741 | 30455904 | 34141752 | 38326487 | 41604486 | 45771264 | 52661083 | 58458576 | 63354541 | 69951821 | 78915068 | 89038178 | 96941258 | 109754198 | 123157738 | 137058937 | 149330446 | 160478869 | 174860365 | 191142014 | 206678181 | 224766961 | 240086514 | 255365398 | 269471295 | 282195252 | 295675731 | 307407170 | 316387357 | 323624009 | 330876746 | 335752727 | 338805988 | 340156015 | 340254842 | 340254842 | 0 | 0 | 0 | 0
|  | MPX -UPDATED FORECAST - Net |  | 252931 | 535586 | 579837 | 1039083 | 1628698 | 2039969 | 3309766 | 3585983 | 1554722 | 9862837 | 3699329 | 2367163 | 3685848 | 4184735 | 3277999 | 4166778 | 6889819 | 5797493 | 4895965 | 6597280 | 8963247 | 10123110 | 7903080 | 12812940 | 13403540 | 13901199 | 12271509 | 11148423 | 14381496 | 16281649 | 15536167 | 18088780 | 15319553 | 15278884 | 14105897 | 12723957 | 13480479 | 11731439 | 8980187 | 7236652 | 7252737 | 4875981 | 3053261 | 1350027 | 98827 | 0 | -340254842 | 0 | -307407170 | 0
| 100 | MAIN CONSTRUCTION WORKS | CUM. | 252931 | 788517 | 1368354 | 2407437 | 4036135 | 6076104 | 9385870 | 12971853 | 14526575 | 24389412 | 28088741 | 30455904 | 34141752 | 38326487 | 41604486 | 45771264 | 52661083 | 58458576 | 63354541 | 69951821 | 78915068 | 89038178 | 96941258 | 109754198 | 123157738 | 137058937 | 149330446 | 160478869 | 174860365 | 191142014 | 206678181 | 224766961 | 240086514 | 255365398 | 269471295 | 282195252 | 295675731 | 307407170 | 316387357 | 323624009 | 330876746 | 335752727 | 338805988 | 340156015 | 340254842 | 340254842 | 0 | 0 | 0 | 0
|  |  | NET. | 252931 | 535586 | 579837 | 1039083 | 1628698 | 2039969 | 3309766 | 3585983 | 1554722 | 9862837 | 3699329 | 2367163 | 3685848 | 4184735 | 3277999 | 4166778 | 6889819 | 5797493 | 4895965 | 6597280 | 8963247 | 10123110 | 7903080 | 12812940 | 13403540 | 13901199 | 12271509 | 11148423 | 14381496 | 16281649 | 15536167 | 18088780 | 15319553 | 15278884 | 14105897 | 12723957 | 13480479 | 11731439 | 8980187 | 7236652 | 7252737 | 4875981 | 3053261 | 1350027 | 98827 | 0 | -340254842 | 0 | -307407170 | 0
| 100.1 | 0 | 0
|  | Work Done To Date | i | 252931 | 788517 | 1368354 | 2407437 | 4036135 | 6076104 | 9385870 | 12971853 | 14526575 | 24389412 | 28088741 | 30455904 | 34141752 | 38326487 | 41604486 | 45771264 | 52661083 | 58458576 | 63354541 | 69951821 | 78915068 | 89038178 | 96941258 | 109754198 | 123157738 | 137058937 | 149330446 | 160478869 | 174860365 | 191142014 | 206678181 | 224766961 | 240086514 | 255365398 | 269471295 | 282195252 | 295675731 | 307407170 | 316387357 | 323624009 | 330876746 | 335752727 | 338805988 | 340156015 | 340254842 | 340254842 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 252931 | 788517 | 1368354 | 2407437 | 4036135 | 6076104 | 9385870 | 12971853 | 14526575 | 24389412 | 28088741 | 30455904 | 34141752 | 38326487 | 41604486 | 45771264 | 52661083 | 58458576 | 63354541 | 69951821 | 78915068 | 89038178 | 96941258 | 109754198 | 123157738 | 137058937 | 149330446 | 160478869 | 174860365 | 191142014 | 206678181 | 224766961 | 240086514 | 255365398 | 269471295 | 282195252 | 295675731 | 307407170 | 316387357 | 323624009 | 330876746 | 335752727 | 338805988 | 340156015 | 340254842 | 340254842 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 252931 | 788517 | 1368354 | 2407437 | 4036135 | 6076104 | 9385870 | 12971853 | 14526575 | 24389412 | 28088741 | 30455904 | 34141752 | 38326487 | 41604486 | 45771264 | 52661083 | 58458576 | 63354541 | 69951821 | 78915068 | 89038178 | 96941258 | 109754198 | 123157738 | 137058937 | 149330446 | 160478869 | 174860365 | 191142014 | 206678181 | 224766961 | 240086514 | 255365398 | 269471295 | 282195252 | 295675731 | 307407170 | 316387357 | 323624009 | 330876746 | 335752727 | 338805988 | 340156015 | 340254842 | 340254842 | 0 | 0 | 0 | 0
|  | Retention 5% Cash 5% Bond | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 252931 | 788517 | 1368354 | 2407437 | 4036135 | 6076104 | 9385870 | 12971853 | 14526575 | 24389412 | 28088741 | 30455904 | 34141752 | 38326487 | 41604486 | 45771264 | 52661083 | 58458576 | 63354541 | 69951821 | 78915068 | 89038178 | 96941258 | 109754198 | 123157738 | 137058937 | 149330446 | 160478869 | 174860365 | 191142014 | 206678181 | 224766961 | 240086514 | 255365398 | 269471295 | 282195252 | 295675731 | 307407170 | 316387357 | 323624009 | 330876746 | 335752727 | 338805988 | 340156015 | 340254842 | 340254842 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 252931 | 788517 | 1368354 | 2407437 | 4036135 | 6076104 | 9385870 | 12971853 | 14526575 | 24389412 | 28088741 | 30455904 | 34141752 | 38326487 | 41604486 | 45771264 | 52661083 | 58458576 | 63354541 | 69951821 | 78915068 | 89038178 | 96941258 | 109754198 | 123157738 | 137058937 | 149330446 | 160478869 | 174860365 | 191142014 | 206678181 | 224766961 | 240086514 | 255365398 | 269471295 | 282195252 | 295675731 | 307407170 | 316387357 | 323624009 | 330876746 | 335752727 | 338805988 | 340156015 | 340254842 | 340254842 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 252931 | 535586 | 579837 | 1039083 | 1628698 | 2039969 | 3309766 | 3585983 | 1554722 | 9862837 | 3699329 | 2367163 | 3685848 | 4184735 | 3277999 | 4166778 | 6889819 | 5797493 | 4895965 | 6597280 | 8963247 | 10123110 | 7903080 | 12812940 | 13403540 | 13901199 | 12271509 | 11148423 | 14381496 | 16281649 | 15536167 | 18088780 | 15319553 | 15278884 | 14105897 | 12723957 | 13480479 | 11731439 | 8980187 | 7236652 | 7252737 | 4875981 | 3053261 | 1350027 | 98827 |  | -340254842 | 0 | -307407170 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 14260023
| 200 | FIXTURES, FITTINGS & EQUIPMENT | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [29 empty] | 0
| 200.1 | Vendor - N/A
|  | Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 300 | LOCAL AUTHORITIES | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 300.1 | Local Authorities Fees | 0
|  | Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 400 | CONTINGENCY | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 400.1 | 0 | 0
|  | Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 500 | MISCELLANEOUS ITEMS | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 500.1 | Proposed Vendor XXX
|  | Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2017-10-30 | 2017-11-29 | 2017-12-29 | 2018-01-28 | 2018-02-27 | 2018-03-29 | 2018-04-28 | 2018-05-28 | 2018-06-27 | 2018-07-27 | 2018-08-26 | 2018-09-25 | 2018-10-25 | 2018-11-24 | 2018-12-24 | 2019-01-23 | 2019-02-22 | 2019-03-24 | 2019-04-23 | 2019-05-23 | 2019-06-22 | 2019-07-22 | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18 | 2020-04-17 | 2020-05-17 | 2020-06-16 | 2020-07-16 | 2020-08-15 | 2020-09-14 | 2020-10-14 | 44118 | 2020-12-13 | 2021-01-12 | 2021-02-11 | 2021-03-13 | 2021-04-12 | 2021-05-12 | 2021-06-11 | 2021-07-11 | 2021-08-10 | 44418 | 44118
|  | DIFFERENCE - BASELINE & ACTUAL |  | 0 | -379 | -377.82 | -378.82 | 138319.9 | 0.18 | -41106.82 | 483416.24 | 2316480.83 | 966180.09 | 4952559.53 | 8762337.18 | 13281795.82 | 17281530.06 | 21956218.13 | 24768824.88 | 24319347.6 | 25815211.95 | 28230075.34 | 29930607.02 | 31491492.09 | 33549079.63 | [15 empty] | 0 | [9 empty] | 0 | 0
|  |  |  | 0% | -0.04809% | -0.02762% | -0.01574% | 3.313% | 2.962e-06% | -0.4399% | 3.593% | 13.75% | 3.811% | 14.99% | 22.34% | 28.01% | 31.08% | 34.54% | 35.11% | 31.59% | 30.63% | 30.82% | 30.36% | 29.53% | 28.98%
[20 empty] | -1.6 | -1.95 | -5.34 | -1299715.02 | -3761086.09 | -6810246.63
[14 empty] | 1.47 | 0.18 |  | 1.94 | 1.87 | 2.12
252931.2502
788516.9702
788516.9702
2277623.0925
4036135.1
6076103.2725
9385869.2725
12971852.8325
14526575.2625
20915077.2586
24421339.657
29209181.1171
36616260.5973
42510856.607
48020387.5919
53766977.5307
60445052.0302
66342450.3892
75960822.2498
84832751.5677
94982360.6799
105519178.2136
116536895.5889
129001325.9487
144166583.8714
159387817.864
173157267.4261
186266325.9705
199576551.2288
213928409.6324
228842447.7776
243617547.7848
256918028.6369
269439194.731
281286430.8702
292253424.1677
303529689.3823
314016521.7792
324132215.0356
331302918.5644
338210251.7549
344901568.3207
350048492.9904
353112131.1484
354816856.117

## Cash Flow - Future
#REF! | #REF! | [51 empty] | #REF!
#REF! | #REF! | [51 empty] | #REF!
SCHEDULE I - CASH FLOW -
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 39 | 40 | TOTAL
|  |  | 41638 | 41668 | 41698 | 41728 | 41758 | 41788 | 41818 | 41848 | 41878 | 41908 | 41938 | 41968 | 41998 | 42028 | 42058 | 42088 | 42118 | 42148 | 42178 | 42208 | 42238 | 42268 | 42298 | 42328 | 42358 | 42388 | 42418 | 42448 | 42478 | 42508 | 42538 | 42568 | 42598 | 42628 | 42658 | 42688 | 42718 | 42748 | 42778 | 42808 | 42838 | 42868 | 42898 | 42928 | 42958 | 42988 | 43018 | 43048 | 42778 | 42808
AMAALA YACHT CLUB
PROJECT CASH FLOW
Project Render
Financial Status
| Contract Award value | 479457540.54
0
0
0
| Current Budget as of Report Date | 479457540.54
|  | CONTRACT | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 39 | 40 | TOTAL
|  | SUM | 2017-10-30 | 2017-11-29 | 2017-12-29 | 2018-01-28 | 2018-02-27 | 2018-03-29 | 2018-04-28 | 2018-05-28 | 2018-06-27 | 2018-07-27 | 2018-08-26 | 2018-09-25 | 2018-10-25 | 2018-11-24 | 2018-12-24 | 2019-01-23 | 2019-02-22 | 2019-03-24 | 2019-04-23 | 2019-05-23 | 2019-06-22 | 2019-07-22 | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18 | 2020-04-17 | 2020-05-17 | 2020-06-16 | 2020-07-16 | 2020-08-15 | 2020-09-14 | 2020-10-14 | 2020-11-13 | 2020-12-13 | 2021-01-12 | 2021-02-11 | 2021-03-13 | 2021-04-12 | 2021-05-12 | 2021-06-11 | 2021-07-11 | 2021-08-10 | 2021-09-09 | 2021-10-09 | 2021-11-08
| BASELINE - Cum. | 481705006.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BASELINE - Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | MAIN CONSTRUCTION WORKS | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.003C20 | #REF! | 481682421.01
| Work Done To Date | i
| Provisional Sum spread |  | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 5% cash 5% bond | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN - EW | EARLY WORKS | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.003C20 | Green Business Certification Inc.2220038 | 22585.01
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF!
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MS | MANAGEMENT SUPERVISION | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300.1 | 0 | 0
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | CONTINGENCY | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400.1 | Contingency Spend | 0
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | MISCELLANEOUS ITEMS | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500.1 | Vendor - NA
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[32 empty] | 5% | 10% | 20% | 30% | 45% | 60% | 70% | 80% | 90% |  | 5% | 10% | 20% | 30% | 45% | 60% | 70% | 80% | 90% | 95% | 100%
|  | CONTRACT | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 39 | 40 | TOTAL
|  | SUM | 2017-10-30 | 2017-11-29 | 2017-12-29 | 2018-01-28 | 2018-02-27 | 2018-03-29 | 2018-04-28 | 2018-05-28 | 2018-06-27 | 2018-07-27 | 2018-08-26 | 2018-09-25 | 2018-10-25 | 2018-11-24 | 2018-12-24 | 2019-01-23 | 2019-02-22 | 2019-03-24 | 2019-04-23 | 2019-05-23 | 2019-06-22 | 2019-07-22 | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18 | 2020-04-17 | 2020-05-17 | 2020-06-16 | 2020-07-16 | 2020-08-15 | 2020-09-14 | 2020-10-14 | 2020-11-13 | 2020-12-13 | 2021-01-12 | 2021-02-11 | 2021-03-13 | 2021-04-12 | 2021-05-12 | 2021-06-11 | 2021-07-11 | 2021-08-10 | 2021-09-09 | 2021-10-09 | 2021-11-08
| ACTUAL/FORECAST - Cum. | 479457540.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ACTUAL/FORECAST - Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | MAIN CONSTRUCTION WORKS | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.1 | 0 | 479457540.54
| Work Done To Date | i
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [27 empty] | 0 | [9 empty] | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 5% Cash 5% Bond | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | FIXTURES, FITTINGS & EQUIPMENT | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [29 empty] | 0
200.1 | Vendor - N/A
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | LOCAL AUTHORITIES | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300.1 | Local Authorities Fees | 0
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | CONTINGENCY | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400.1 | 0 | 0
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | MISCELLANEOUS ITEMS | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500.1 | Proposed Vendor XXX
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CONTRACT | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 39 | 40 | TOTAL
|  | VALUE | 2017-10-30 | 2017-11-29 | 2017-12-29 | 2018-01-28 | 2018-02-27 | 2018-03-29 | 2018-04-28 | 2018-05-28 | 2018-06-27 | 2018-07-27 | 2018-08-26 | 2018-09-25 | 2018-10-25 | 2018-11-24 | 2018-12-24 | 2019-01-23 | 2019-02-22 | 2019-03-24 | 2019-04-23 | 2019-05-23 | 2019-06-22 | 2019-07-22 | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18 | 2020-04-17 | 2020-05-17 | 2020-06-16 | 2020-07-16 | 2020-08-15 | 2020-09-14 | 2020-10-14 | 2020-11-13 | 2020-12-13 | 2021-01-12 | 2021-02-11 | 2021-03-13 | 2021-04-12 | 2021-05-12 | 2021-06-11 | 2021-07-11 | 2021-08-10 | 2021-09-09 | 2021-10-09 | 2021-11-08
| MPX -UPDATED FORECAST - Cum. | 340254842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MPX -UPDATED FORECAST - Net |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | MAIN CONSTRUCTION WORKS | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.1 | 0 | 479457540.54
| Work Done To Date | i
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 5% Cash 5% Bond | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 14260023
200 | FIXTURES, FITTINGS & EQUIPMENT | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [29 empty] | 0
200.1 | Vendor - N/A
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | LOCAL AUTHORITIES | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300.1 | Local Authorities Fees | 0
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | CONTINGENCY | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400.1 | 0 | 0
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | MISCELLANEOUS ITEMS | CUM. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NET. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500.1 | Proposed Vendor XXX
| Work Done To Date | i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material on Site | ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variations | iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Value of Works Done | iv=i+ii+iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment Recovery | v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Advance Payment | vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gross Amount Certified | vii=iv+v+vi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention 10% | viii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Retention Released | ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-total | x=vii+viii+ix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fluctuations | xi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Penalties | xii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contra charges | xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Cumulative | xiv=x+xi+xii+xiii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net Amount Certified Monthly | xv=xiv- prev xiv | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2017-10-30 | 2017-11-29 | 2017-12-29 | 2018-01-28 | 2018-02-27 | 2018-03-29 | 2018-04-28 | 2018-05-28 | 2018-06-27 | 2018-07-27 | 2018-08-26 | 2018-09-25 | 2018-10-25 | 2018-11-24 | 2018-12-24 | 2019-01-23 | 2019-02-22 | 2019-03-24 | 2019-04-23 | 2019-05-23 | 2019-06-22 | 2019-07-22 | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18 | 2020-04-17 | 2020-05-17 | 2020-06-16 | 2020-07-16 | 2020-08-15 | 2020-09-14 | 2020-10-14 | 44118 | 2020-12-13 | 2021-01-12 | 2021-02-11 | 2021-03-13 | 2021-04-12 | 2021-05-12 | 2021-06-11 | 2021-07-11 | 2021-08-10 | 44418 | 44118
| DIFFERENCE - BASELINE & ACTUAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | [9 empty] | 0 | 0
|  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 |  | 0 | 0 | 0
252931.2502
788516.9702
788516.9702
2277623.0925
4036135.1
6076103.2725
9385869.2725
12971852.8325
14526575.2625
20915077.2586
24421339.657
29209181.1171
36616260.5973
42510856.607
48020387.5919
53766977.5307
60445052.0302
66342450.3892
75960822.2498
84832751.5677
94982360.6799
105519178.2136
116536895.5889
129001325.9487
144166583.8714
159387817.864
173157267.4261
186266325.9705
199576551.2288
213928409.6324
228842447.7776
243617547.7848
256918028.6369
269439194.731
281286430.8702
292253424.1677
303529689.3823
314016521.7792
324132215.0356
331302918.5644
338210251.7549
344901568.3207
350048492.9904
353112131.1484
354816856.117